## عملكرد كلي
رديف | شرح | (هزار ريال)
(هزار دلار)
1 | هزينه هاي در تعهد كارفرما | 67888993
2 | هزينه انجام شده تاكنون طراحي و مهندسي | 39621943
3 | جمع هزينه شده | 107510936
4 | برآورد اعتبار بخش ريالي زير پروژه 002 | 51783851590
5 | برآورد اعتبار بخش ارزي زير پروژه 002 | 23392
6 | پیش بینی تعديل معادل 40 درصد برآورد بخش ريالي زيرپروژه 002 | 20713540636
7 | پيش بيني اضافه­كاري در سقف 25 درصد برآورد بخش ريالي زير پروژه 002 | 12945962897
8 | پيش بيني اضافه­كاري در سقف 25 درصد برآورد بخش ارزي زير پروژه 002 | 5848
9 | جمع كل درخواست بخش ريالي | 85550866059
10 | جمع كل درخواست بخش ارزي | 29240
11 | اعتبار مصوب بخش ريالي | 268700000
12 | اعتبار مصوب بخش ارزي | 18000
13 | مبلغ افزايش اعتبار بخش ريالي | 85282166059
14 | مبلغ افزايش اعتبار بخش ارزي | 11240

## EPC Summary
| برآورد هزينه هاي مستقيم |  |  |  |  | برآورد با اعمال بالاسري
بخش |  | بخش ريالي | بخش ارزي (دلار) | مجموع (ريال) | درصد از كل پروژه | بخش ريالي با اعمال سربار | بخش ارزي(دلار) با اعمال سربار | مجموع (ريال با اعمال سربار) | درصد از كل پروژه
E | مهندسي | 994810000000 |  | 994810000000 | 2.055% | 1264727000000 |  | 1264727000000 | 2.055%
P | كالا | 24007580000000 | 23392000 | 33832220000000 | 69.88% | 33187108000000 | 23392000 | 43011748000000 | 69.88%
C | اجرا | 13111410000000 |  | 13111410000000 | 27.08% | 16668864000000 |  | 16668864000000 | 27.08%
Development | توسعه فناوري | 479390000000 |  | 479390000000 | 0.9901% | 609461000000 |  | 609461000000 | 0.9901%
| جمع | 38593190000000 | 23392000 | 48417830000000 | 100% | 51730160000000 | 23392000 | 61554800000000 | 100%
| FR(EPC Initial Capex) | ریال | ارز - دلار | مجموع (ريال + ارز تسعير شده) |  | Adjustment | Over Work | Elevated Price | 89205005
2.14% | مهندسي -E | 1318418590000 |  | 1318418590000 |  | 527367436000 | 329604647000 | 2175390673000 | 53691590000
69.81% | کالا- P | 33187108000000 | 23392000 | 43011748000000 |  | 13274843200000 | 8296777000000 | 54758728200000 | Expenditure
27.06% | اجرا- C | 16668864000000 |  | 16668864000000 |  | 6667545600000 | 4167216000000 | 28509236250000 | 107510936000
0.9892% | توسعه - De | 609461000000 |  | 609461000000 |  | 243784400000 | 152365250000 |  | Request
61608491590000 | مجموع | 51783851590000 | 23392000 | 61608491590000 |  | 20713540636000 | 12945962897000 | 85443355123000 | 85550866059000
|  |  |  | Bpd_Cost_rate |  |  | 5848000 | 85443355123000 | 29240000
فناوري سخت | 549461000000 |  |  | 1333.5171 |  |  |  |  | Approved Finance
توسعه مديريت | 30000000000 | [7 empty] | 268700000000
سهم داخل | 30000000000 | RFCS | [6 empty] | 18000000
|  | 51783851590000 | [6 empty] | Finance Increment
|  | 21266000 | [6 empty] | 85282166059000
نيروگاه خورشيدي | 100000000000 | [7 empty] | 11240000
تصفيه پساب | 449461000000

## PEP
ردیف | شرح |  |  | ريال | یورو
1 | خدمات مهندسی | الف | بازنگری و تائید مهندسی مقدماتی | 45441000000 | 0
|  | ب | انجام خدمات مهندسی تفصیلی | 748916000000 | 0
|  | ج | مطالعات ارزیابی اثرات زیست محیطی، پيوست سلامت، هزاپ، ژئوتكنيك تكميلي، و نقشه برداري تكميلي | 34650000000 | 0
|  | د | مديريت مهندسي | 165802000000
|  |  | جمع خدمات مهندسی | 994809000000 | 0
2 | 2-1 تهیه و تامین کالا و تجهیزات خارجی بر مبنای DAP (تحويل در محل پروژه) | الف | هزینه تهیه و تامین کالا و تجهیزات خارجی | 0 | 20672776.5042
|  |  | هزینه تهیه و تامین قطعات یدکی برای دوران راه اندازی و 2 ساله تعمیر و نگهداری | 0 | 2719000
|  | ب | هزینه حمل خارجی | 0 | در آيتم الف از 1-2 در نظر گرفته شده است
|  | ج | هزینه بیمه کالا و تجهیزات خارجی |  | در آيتم الف از 1-2 و ج از 2-2 در نظر گرفته شده است
|  | د | هزینه ترخیص شامل عوارض گمرکی و سود بازرگانی کالا و تجهیزات خارجی | 1813192000000 | 0
|  | ه‍ | هزینه حمل داخلی کالا و تجهیزات خرید خارج و هزينه حمل كالاي داخلي | 512751000000 | 0
|  | و | هزینه خدمات فنی سازندگان در دوران نصب و راه اندازی | 832917000000 | 0
|  | ز | هزینه بازرسی کالا و تجهیزات خارجی | 300719000000 | 0
| 2-2 تهیه و تامین کالا و تجهیزات داخلی برمبنای تحويل در محل پروژه | الف | هزینه تهیه و تامین کالا و تجهیزات داخلی | 19081325000000 | 0
|  |  | هزینه تهیه و تامین قطعات یدکی برای دوران راه اندازی و 2 ساله تعمیر و نگهداری | 1165951000000 | 0
|  | ب | هزینه حمل داخلی | در آيتم ه از 1-2 در نظر گرفته شده است | 0
|  | ج | هزینه بیمه کالا و تجهیزات داخلی و هزينه هاي داخلي بيمه كالا و تجهيزات خريد خارج | 300719000000 | 0
|  | د | هزینه خدمات فنی سازندگان در دوران نصب و راه اندازی | در آيتم و از 1-2 در نظر گرفته شده است | 0
|  | ه‍ | هزینه بازرسی کالا و تجهیزات داخلی | در آيتم ز از 1-2 در نظر گرفته شده است | 0
|  |  | جمع خدمات تهیه و تامین کالا و تجهیزات | 24007574000000 | 23391776.5042
3 | عملیات ساختمانی و اجرا | الف | تجهیز و برچیدن | 287281000000 | 0
|  | ب | ساخت و نصب و راه اندازی | 11352175000000 | 0
|  | ج | تسهیلات مورد نیاز کارفرما | 1284816000000 | 0
|  | د | الزامات HSE (مقررات ایمنی، بهداشت و محیط زیست شرکت ملی نفت ایران) | 115133000000 | 0
|  | ه‍ | ه: هزینه دفتر فنی کارگاه | 72000000000
|  |  | جمع خدمات ساختمانی | 13111405000000 | 0
4 | توسعه فناوريهاي سخت، توسعه قابليتهاي مديريتي و توسعه سهم داخل | الف | يك درصد از كل برآورد | 479384000000
|  |  | جمع کل پروژه ( ردیف های 5 ، 4 ، 3 ، 2 ، 1) | 38593172000000 | 23391776.5042

## basic data
per Euro | 1.085 |  | Year | ME0 | ME | IN | EL | ME0 | ME | IN | EL | درصد تغيير شاخص قيمت توليد كننده در بخش صنعت - طبق آمار منتشر شده در بهمن ماه 1401 در مركز آمار ايران | Year | Ind. PPI | Ind. PPI Variation | 1395=100
per $ | 420000 | ريال | 94 | -12.6 | -0.62 | -2.3 | -1.6 | 0.874 | 0.9938 | 0.977 | 0.984 | ME0: ساخت فلزات پايه | 1395 |  | 4.7
overhead factor (E,G,D) | 1.2713 |  | 95 | 1.9 | 3.4 | 2.7 | 2 | 1.019 | 1.034 | 1.027 | 1.02 | ME: ساخت محصولات فلزي ساخته شده به جز ماشين آلات و تجهيزات | 1396 |  | 13.3
overhead factor (P) | 1.2713 |  | 96 | 31.8 | 6.7 | 0.8 | 11.5 | 1.318 | 1.067 | 1.008 | 1.115 | IN: ساخت محصولات رايانه اي، الكترونيكي و نوري | 1397 |  | 58.6
overhead factor (C) | 1.2713 |  | 97 | 67.9 | 66.7 | 58.8 | 68.1 | 1.679 | 1.667 | 1.588 | 1.681 | EL: ساخت تجهيزات برقي | 1398 | 246.2 | 37.1
سال مبنا | تورم ريالي | تورم ارزي | 98 | 32.7 | 49.2 | 43.1 | 43 | 1.327 | 1.492 | 1.431 | 1.43 |  | 1399 | 386.1 | 56.8
1392 | 37.3% | 2% | 99 | 105.6 | 62.9 | 37.3 | 71 | 2.056 | 1.629 | 1.373 | 1.71 |  | 1400 | 605 | 56.7
1393 | 15.6% | 2% | 1400 | 54.9 | 53.4 | 37.6 | 46.9 | 1.549 | 1.534 | 1.376 | 1.469 |  | 99.2 | 355.6 | 23.9
1394 | 11.9% | 2% | 1400.2 | 98.2 | 71.5 | 53.3 | 79.3 | 1 | 1 | 1 | 1 |  | 99.3 | 433.1 | 37.4
1395 | 9% | 2% | 1400.3 | 72.3 | 61.9 | 45 | 60.9 | 1 | 1 | 1 | 1 |  | 99.4 | 485.8 | 56.8
1396 | 9.6% | 2% | 1400.4 | 54.9 | 53.4 | 37.6 | 46.9 | 1 | 1 | 1 | 1 |  | 1400.1 | 525.6 | 78.5
1397 | 31.2% | 2% | 1401.1 | 36.5 | 46 | 27.3 | 38.2 | 1.365 | 1.46 | 1.273 | 1.382 |  | 1400.2 | 577 | 80.4
1398 | 41.2% | 2% | 1401.2 | 21.6 | 41.6 | 21.2 | 35.4 | 1 | 1 | 1 | 1 |  | 1400.3 | 633.9 | 69.7
1399 | 47.1% | 1.2% | [5 empty] | 11.3692 | 9.9492 | 5.5276 | 9.339 | ضريب تغيير قيمت نسبت به سال مبنا (1395) | 1400.4 | 683.6 | 56.7
1400 | 46.2% | 4.7% | [10 empty] | 1401.1 | 768.9 | 48
1401 | 46.5% | 8% | [10 empty] | 1401.2 | 750.9 | 40.4
1402 | 50% | 4%
| 18.576 | 1.3671

## Engineering
| لیست مدارک مهندسی تفصیلی پروژه احداث واحد نمکردایی گچساران-4 به روش EPC | [24 empty] | بهاي كل (ریال) | حق الزحمه (ریال به ازای یک نفرساعت) |  |  | نفرساعت نيروي انساني |  |  | شرح
[27 empty] | مهندس ارشد | مهندس طراح | نقشه کش | مهندس ارشد | مهندس طراح | نقشه کش
[26 empty] | 45441000000 | 9180000 |  |  | 4950 |  |  | بازنگری و صحه گذاری اسناد پایه
جدول نفر ساعت مهندسی مورد نیاز انجام مهندسی تفصیلی
[30 empty] | نفرساعت نيروي انساني |  |  | شرح | شرح | نفر ساعت مهندسی |  |  |  | حق الزحمه (ریال) نفر ساعت |  |  | بهای کل
[30 empty] | مهندس ارشد | مهندس طراح | نقشه کش |  |  | سال | نقشه کش | مهندس طراح | مهندس ارشد | نقشه کش | مهندس طراح | مهندس ارشد | (ریال)
| PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN |  |  |  |  | 1269 | 5210.65 | 624.75 | بخش فرآيند | بخش فرآيند | سال 1402 | 250 | 2084 | 508 | 5120000 | 6400000 | 8000000 | 18681600000
| Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | [5 empty] | 1171.6 | 4957.5 | 224.25 | بخش كارهاي مكانيكال |  | سال 1403 | 250 | 2084 | 508 | 7168000 | 8960000 | 11200000 | 26154240000
Endorsement | 0 | 600 | 0 | 600 | 0 | 400 | 0 | 500 | 0 | 400 | 0 | 400 | 0 | 500 | 0 | 400 | 0 | 400 | 0 | 400 | 0 | 350 | 0 | 0 | 0 |  |  |  |  | 292.4 | 1555.55 | 1380 | بخش كارهاي HVAC |  | سال 1404 | 125 | 1042 | 254 | 10035200 | 12544000 | 15680000 | 18307968000
Process | 4045.65 | 1109 | 161 | 23 | 0 | 1 | 5 | 2 | 425 | 73 | 162 | 109 | 77 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624.75 |  |  |  |  | 677.4 | 1665.55 | 368 | بخش ایمنی | بخش كارهاي مكانيكال | سال 1402 | 90 | 1983 | 469 | 5120000 | 6400000 | 8000000 | 16904000000
Mechanic | 604 | 77 | 4649 | 1070.6 | 0 | 0 | 6 | 1 | 62 | 0 | 562.5 | 74 | 193.5 | 37 | 0 | 0 | 0 | 0 | 95 | 5 | 0 | 0 | 0 | 0 | 224.25 |  |  |  |  | 2404.6 | 7970 | 4887.5 | بخش كارهاي لوله كشي و خطوط لوله |  | سال 1403 | 90 | 1983 | 469 | 7168000 | 8960000 | 11200000 | 23665600000
HVAC | 0 | 0 | 0 | 0 | 1543.55 | 287.4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 |  |  |  |  | 5246.7 | 7618.9 | 1075.25 | بخش كارهاي ابزار دقيق |  | سال 1404 | 45 | 992 | 234 | 10035200 | 12544000 | 15680000 | 16564352000
HSE | 7 | 1 | 20 | 0 | 0 | 0 | 1624.55 | 628.4 | 4 | 0 | 8 | 2 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 |  |  |  |  | 2437.8 | 7549.56 | 3772 | بخش كارهاي برقي | بخش كارهاي HVAC | سال 1402 | 552 | 622 | 117 | 5120000 | 6400000 | 8000000 | 7743040000
Piping&Pipeline | 65 | 49 | 0 | 45 | 0 | 0 | 0 | 17 | 7365 | 2302.6 | 0 | 6 | 0 | 34 | 66 | 33 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 4887.5 |  |  |  |  | 696.4 | 3485.8 | 598 | بخش كارهاي مخابرات |  | سال 1403 | 552 | 622 | 117 | 7168000 | 8960000 | 11200000 | 10840256000
Instrument | 476 | 29 | 0 | 8 | 0 | 0 | 13 | 10 | 0 | 4 | 6833.4 | 5031.7 | 8 | 8 | 9 | 9 | 4 | 0 | 0 | 0 | 80 | 15 | 0 | 0 | 1075.25 |  |  |  |  | 296.2 | 1763.35 | 1919.35 | بخش كارهاي سيويل |  | سال 1404 | 276 | 311 | 58 | 10035200 | 12544000 | 15680000 | 7580339200
Electrical | 5 | 0 | 79 | 8 | 0 | 0 | 0 | 0 | 11 | 0 | 6 | 0 | 7161.06 | 2304.8 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3772 |  |  |  |  | 1008.5 | 4983.95 | 3254.5 | بخش كارهاي معماری | بخش ایمنی | سال 1402 | 147 | 666 | 271 | 5120000 | 6400000 | 8000000 | 7183040000
Telecom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1186.5 | 291.8 | 0 | 0 | 598 |  |  |  |  | 306.8 | 1266.5 | 3914.6 | بخش كارهاي سازه |  | سال 1403 | 147 | 666 | 271 | 7168000 | 8960000 | 11200000 | 10056256000
Civil | 6 | 3 | 8 | 4 | 0 | 0 | 4 | 2 | 72 | 10 | 19 | 9 | 53 | 16 | 3369.8 | 650.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.35 |  |  |  |  | 230 | 860 | 0 | کنترل پروژه |  | سال 1404 | 74 | 333 | 135 | 10035200 | 12544000 | 15680000 | 7036556800
Architectural | 2 | 1 | 14 | 1 | 12 | 4 | 5 | 13 | 14 | 0 | 14 | 5 | 22 | 8 | 0 | 0 | 1710.35 | 296.2 | 0 | 0 | 0 | 0 | 0 | 0 | 3254.5 |  |  |  |  | 16037.4 | 48887.31 | 22018.2 | مجموع | بخش كارهاي لوله كشي و خطوط لوله | سال 1402 | 1955 | 3188 | 962 | 5120000 | 6400000 | 8000000 | 38108800000
[35 empty] | سال 1403 | 1955 | 3188 | 962 | 7168000 | 8960000 | 11200000 | 53352320000
Structural | 0 | 0 | 26.5 | 12 | 0 | 0 | 8 | 4 | 15 | 15 | 14 | 10 | 13 | 13 | 0 | 0 | 30 | 0 | 4888.95 | 992.5 | 0 | 0 | 0 | 0 | 3914.6 | [5 empty] | مطالعات زیست محیطی و غیره |  |  |  | سال 1404 | 978 | 1524 | 481 | 10035200 | 12544000 | 15680000 | 36473561600
Project Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860 | 230 | 0 | [5 empty] | حق الزحمه | شرح |  | بخش كارهاي ابزار دقيق | سال 1402 | 430 | 3048 | 2099 | 5120000 | 6400000 | 8000000 | 38500800000
Total | 5210.65 | 1869 | 4957.5 | 1771.6 | 1555.55 | 692.4 | 1665.55 | 1177.4 | 7970 | 2804.6 | 7618.9 | 5646.7 | 7549.56 | 2937.8 | 3485.8 | 1096.4 | 1763.35 | 696.2 | 4983.95 | 1408.5 | 1266.5 | 656.8 | 860 | 230 | 22018.2 | [5 empty] | 4000000000 | مطالعات FMEA, HAZID, HAZOP (فاز طرح و ساخت) |  |  | سال 1403 | 430 | 3048 | 2099 | 7168000 | 8960000 | 11200000 | 53901120000
[31 empty] | 1500000000 | مطالعات پیوست سلامت |  |  | سال 1404 | 215 | 1594 | 1049 | 10035200 | 12544000 | 15680000 | 38601024000
[31 empty] | 3500000000 | مطالعات ارزیابی اثرات زیست محیطی (فاز طرح و ساخت) |  | بخش كارهاي برقي | سال 1402 | 1509 | 3020 | 975 | 5120000 | 6400000 | 8000000 | 34854080000
[31 empty] | 9000000000 | مطالعات ژئوتکنیک تکمیلی مورد نیاز برای تهیه مدارک مهندسی |  |  | سال 1403 | 1509 | 3020 | 975 | 7168000 | 8960000 | 11200000 | 48795712000
[31 empty] | 3500000000 | مطالعات پدافند غیر عامل |  |  | سال 1404 | 754 | 1510 | 488 | 10035200 | 12544000 | 15680000 | 34159820800
[31 empty] | 4000000000 | عملیات نقشه برداری مورد نیاز برای تهیه مدارک مهندسی |  | بخش كارهاي مخابرات | سال 1402 | 239 | 1394 | 279 | 5120000 | 6400000 | 8000000 | 12377280000
[31 empty] | 4000000000 | عملیات مستند سازی و استقرار سیستم ارسال مدارک |  |  | سال 1403 | 239 | 1394 | 279 | 7168000 | 8960000 | 11200000 | 17328192000
[31 empty] | 3500000000 | مهندسی ارزش |  |  | سال 1404 | 120 | 697 | 139 | 10035200 | 12544000 | 15680000 | 12126912000
[31 empty] | 1650000000 | ماليات قرارداد شركتهاي ثالث بر عهده پيمانكار به ميزان 5 درصد |  | بخش كارهاي سيويل | سال 1402 | 768 | 705 | 118 | 5120000 | 6400000 | 8000000 | 9388160000
[31 empty] | 34650000000 | مجموع |  |  | سال 1403 | 768 | 705 | 118 | 7168000 | 8960000 | 11200000 | 13143424000
[35 empty] | سال 1404 | 384 | 353 | 59 | 10035200 | 12544000 | 15680000 | 9206668800
[34 empty] | بخش كارهاي معماری | سال 1402 | 1302 | 1994 | 403 | 5120000 | 6400000 | 8000000 | 22651840000
[31 empty] | مبلغ (ريال) | شرح |  |  | سال 1403 | 1302 | 1994 | 403 | 7168000 | 8960000 | 11200000 | 31712576000
[31 empty] | 45441000000 | بازنگری و صحه گذاری اسناد پایه |  |  | سال 1404 | 651 | 997 | 202 | 10035200 | 12544000 | 15680000 | 22206643200
[31 empty] | 748915072000 | مهندسی تفصیلی |  | بخش كارهاي سازه | سال 1402 | 1566 | 507 | 123 | 5120000 | 6400000 | 8000000 | 12246720000
[31 empty] | 34650000000 | مطالعات زیست محیطی و غیره |  |  | سال 1403 | 1566 | 507 | 123 | 7168000 | 8960000 | 11200000 | 17145408000
[31 empty] | 165801214400 | مديريت مهندسي |  |  | سال 1404 | 783 | 253 | 61 | 10035200 | 12544000 | 15680000 | 11987673600
[31 empty] | 994807286400 | مجموع |  | کنترل پروژه | سال 1402 | 0 | 344 | 92 | 5120000 | 6400000 | 8000000 | 2937600000
[35 empty] | سال 1403 | 0 | 344 | 92 | 7168000 | 8960000 | 11200000 | 4112640000
[35 empty] | سال 1404 | 0 | 172 | 46 | 10035200 | 12544000 | 15680000 | 2878848000
[35 empty] | مجموع | 22021 | 48888 | 16038 |  |  |  | 748915072000

## Procurement
جدول 2.1 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي مکانیک و لوله و اتصالات مورد نياز پروژه بر اساس پیوست 1،2 و3 |  |  |  | ارز مرجع | 420000
رديف | شرح فعاليت ها | دلار | ريال | ضريب تورم عمومي ريالي | 18.576
1 | الكترواستاتيك ها و ادوات مربوطه | 7594862.7657 | 0 | ضريب تورم ارزي دلار | 1.3671
2 | كوره ها و ادوات مربوطه | 6487000 | 0
3 | مبدل نفت / نفت و مبدل آب / آب | 0 | 625209000000
4 | تلمبه ها | 0 | 2082268000000
5 | شيرآلات و اتصالات ، رنگها و لوله های داخل سایت | 0 | 2452617000000
6 | خرید لوله های بیرون سایت | 0 | 2982846000000
7 | مخزن های اتمسفریک و تحت فشار | 0 | 797604000000
8 | سیستم پساب | 4773913.7384 | 0
9 | air compressor Packages | 0 | 418938000000
10 | Flare & Ignitor | 0 | 372764000000
| بسته های تزریق مواد شیمیایی | 0 | 337896000000
12 | Vacuum Deaerator Package | 0 | 134429070953.0233
13 | سیستم HVAC | 0 | 370840000000
14 | جرثقیلهای سقفی | 0 | 401940000000
15 | خرید اقلام ایمنی و آتش نشانی | 0 | 163763000000
16 | گیرنده و فرستنده توپک | 0 | 94500000000
17 | مواد شیمیایی مصرفی | 0 | 592670000000
| جمع كل | 18855776.5042 | 1.1828e+13
جدول 2.4 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي برق و مخابرات مورد نياز پروژه بر اساس پیوست 4
رديف | شرح فعاليت ها | دلار | ريال
1 | تابلوها | 0 | 806342000000
2 | اتصالات برق (شامل گلندها، شرودها، جعبه هاي اتصال، مفصلها و ...) | 0 | 305001000000
3 | كابلهاي قدرت | 0 | 627631000000
4 | ترانس ها و UPS دیزل ژنراتور | 1414000 | 575848000000
5 | وسايل و تجهيزات مخابرات، و پیجینگ | 197000 | 7581000000
6 | پایه ها و برجهاي روشنائي و سایر ملحقات و ادوات روشنایی | 0 | 169114000000
7 | خط انتقال برق شامل کابل ، پایه ها و یراق آلات | 0 | 532980000000
| جمع كل | 1611000 | 3024497000000
جدول 2.5 -جدول خلاصه مالی تفكيكي تهيه و خريدادوات و تجهیزات ابزاردقیق و تجهیزات آزمایشگاه مورد نياز پروژه بر اساس پیوست 5و6
رديف | شرح فعاليت ها | دلار | ريال
1 | ادوات ابزار دقیق شامل : ترانسمیترها ، سوئیچ ها ، گیج ها و ... | 206000 | 761483000000
2 | شیرآلات ابزار شامل : شیر ON/OFF ، شیرهای کنترلی ، PSV ، PCV | 0 | 1232422000000
3 | سيستم كنترل ( DCS,FGS )، ESD | 0 | 701447326000
4 | ادوات F&G و CO2 Total Flooding و ابزار خاص | 0 | 604298000000
5 | اقلام بالک ابزار دقیق | 0 | 78020000000
6 | کابلهای ابزار دقیق و ملحقات شامل : گلند سینی و ... | 0 | 229255000000
7 | تجهیزات آزمایشگاه | 0 | 436842000000
8 | CCTV | 0 | 184776000000
| جمع كل | 206000 | 4228543326000
جدول 1.7 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي پروژه
رديف | شرح فعاليت ها | دلار | ريال
1 | مجموع قیمت خرید تجهیزات مطابق جداول 2.1، 2.4 و 2.5 و اعمال فاكتور تورم ريال و دلار از سال 1395 تا 1402 | 20672776.5042 | 1.9081e+13
2 | لوازم يدكي (شامل لوازم يدكي براي راه اندازي و لوازم يدكي موردنياز براي كاركرد دو ساله) | 2719000 | 1165951000000 | ضريب
3 | ترخيص كالاي خارجي شامل هزينه هاي گمرك و بازرگاني ، عوارض موردنياز ماليات، هزينه‌هاي بانكي و ... |  | 1813192000000
4 | بیمه حمل کالاهای داخلی و خارجی، بیمه مسئولیت، تمام خطر نصب و سایر بیمه های مورد نیاز |  | 300719000000 | 1%
5 | هزينه هاي بارگيري ، حمل و تخليه كالاي خارجي، هزينه هاي بارگيري، حمل و تخليه كالاي داخلي |  | 512751000000 | 3%
6 | هزینه های بازرسی اشخاص ثالث |  | 300719000000 | 1%
7 | خدمات فنی سازندگان در دوران نصب و راه اندازی |  | 832917000000 | 3%
| جمع كل | 23391776.5042 | 2.4008e+13

## Construction
:خلاصه براورد ساخت و اجرا مطابق تفکیک نرخ پیمان- پیوست یک قرارداد
|  | 287280564151.0419 |  |  |  | الف:تجهیز و برچیدن مطابق جدول ب-1 |  |  | الف
|  | 1.1352e+13 |  |  |  | ب:ساخت و نصب و راه اندازی مطابق جدول ب-1 |  |  | ب
|  | 1.2848e+12 |  |  |  | ج:تسهیلات مورد نیاز کارفرما مطابق جدول ب-2 |  |  | ج
|  | 115132939491.663 |  |  |  | د: الزامات HSEمطابق جدول ب-3 |  |  | د
|  | 72000000000 |  |  |  | ه: هزینه دفتر فنی کارگاه |  |  | ه
|  | 1.3111e+13 |  |  |  | مجموع
شرح ردیف های الف و ب - برآورد هزینه ساخت و نصب و راه اندازی و تجهیز کارگاه - مطابق جداول
جمع کل | هزینه تجهیز کارگاه |  | هزینه اجرا پس از اعمال ضریب بروزرسانی | ضریب بروزرسانی به سه ماهه اول 1402 | هزینه اجرا پس از اعمال ضرایب فهرست بهای مربوطه |  | هزینه اجرامطابق فهرست بهای مربوطه | عنوان
464924940101.9019 | 174512901875.9019 |  | 290412038226 | 1.06 | 273973620968.068 |  | 175163935524 | اجرای فونداسیون تجهیزات
637828274396 | یک قلم در ردیف اول محاسبه گردید |  | 637828274396 | 1.06 | 601724787166.4387 |  | 380893730036 | اجرای جاده های داخلی و خارجی
719145156294 | یک قلم در ردیف اول محاسبه گردید |  | 719145156294 | 1.06 | 678438826692.4945 |  | 438710828644 | اجرای سایبانها
1709692715148 | یک قلم در ردیف اول محاسبه گردید |  | 1709692715148 | 1.06 | 1612917655800 |  | 1.0495e+12 | اجرای ساختمانها
2158472497849 | یک قلم در ردیف اول محاسبه گردید |  | 2158472497849 | 1.06 | 2.0363e+12 |  | 1239981269679 | اجرای ابنیه و اقلام متفرقه
1103852062935 | یک قلم در ردیف اول محاسبه گردید |  | 1103852062935 | 1.06 | 1041369870693 |  | 461314673320 | محوطه سازی واحدها
171750408507 | یک قلم در ردیف اول محاسبه گردید |  | 171750408507 | 1.062 | 161723548500 |  | 102421500000 | اجرای دیوار حایل و شیروانی دورواحد
200075296057 | یک قلم در ردیف اول محاسبه گردید |  | 200075296057 | 1.06 | 188750279299.4 |  | 113706706200 | دفن کابل و لوله های دفنی
992055090120 | یک قلم در ردیف اول محاسبه گردید |  | 992055090120 | 1.06 | 935901028415.3 |  | 607865879900 | نصب و اجرای سازه های فلزی متفرقه
8711234972 | یک قلم در ردیف اول محاسبه گردید |  | 8711234972 | 1.06 | 8218146200 |  | - | احداث فضای سبز
347262540861.44 | 19656370237.44 |  | 327606170624 | 1.061 | 308771131596.1379 |  | 150633619879 | اجرا و نصب تجهیزات مکانیک
296699441290.58 | 16794307997.58 |  | 279905133293 | 1.061 | 263812566723 |  | 109329700258 | اجرای خطوط لوله
925173456074.4 | 52368308834.4 |  | 872805147240 | 1.06 | 823401082302.3358 |  | 328965674112 | اجرای پایپینگ درون واحدها
213703558631.04 | 12096427847.04 |  | 201607130784 | 1.058 | 190554944030 |  | 162341006850 | اجرای برق
209389703336.68 | 11852247358.68 |  | 197537455978 | 1.058 | 186708370490 |  | 75559842024 | اجرای ابزاردقیق
1.0159e+13 | 287280564151.0419 |  | 9871455812423 |  | 9.3126e+12 |  | 5.3964e+12 | مجموع
شرح ردیف د - برآورد هزینه ایمنی کارگاه (HSE) | [6 empty] | شرح ردیف ج - برآورد تسهیلات کارفرما
80139507093.8472 | لوازم حفاظت فردی و تجهیزات | [5 empty] | 1.1748e+12 | تسهيلات رفاهي گروه نظارت
2858851458.1448 | سدجش و اندازه گیری 1 | [5 empty] | 110028826201.4986 | تسهیلات ماموریت داخل و خارج و آموزش
81900000 | سدجش و اندازه گیری 2
5052680939.6711 | آموزش | [5 empty] | 1.2848e+12 | مجموع
27000000000 | نیروی انسانی
شرح ردیف ه: هزینه دفتر فنی کارگاه
115132939491.663 | مجموع | [5 empty] | 4 نفر طی بیست و چهار ماه هزینه نفر ماه : 750،000،000 ریال | پرسنل دفتر فنی کارگاه (طبق توضیح بند 6 صفحه قبل (صفحه 4)
[7 empty] | 72000000000 | مجموع

## C.CONTENT
فهرست
الف) مبانی محاسبات براورد
ب) خلاصه برآورد مالی بخش اجرا
پیوست یک - برآورد هزینه اجرای پروژه بر اساس فهارس بها
جدول 1 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث فونداسیون تجهیزات وادوات (بر اساس ریز متره مندرج در جدول الف پیوست 2) |  |  | -
جدول 2 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث سایبان تجهیزات(بر اساس ریز متره مندرج در جدول ب پیوست 2) |  |  | -
جدول 3 - برآورد اجرا بر اساس فهرست بهای ابنیه 140 - احداث جاده های دسترسی، جاده های داخل واحدها و پاترول(بر اساس ریز متره مندرج در جدول ج پیوست 2) |  |  | -
جدول 4 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث ابنیه متفرقه (بر اساس ریز متره مندرج در جدول د پیوست 2) |  |  | -
جدول 5 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 -محوطه سازی واحدها (بر اساس ریز متره مندرج در جدول ه پیوست 2) |  |  | -
جدول 6 - برآورد اجرا فضای سبز - خارج از فهرست بها |  |  | -
جدول7 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - دفن لوله ها (داخل و خارج واحد) و کابل های زیر زمینی (بر اساس ریز متره مندرج در جدول و پیوست 2) |  |  | -
جدول 8 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - سازه های فلزی متفرقه (بر اساس ریز متره مندرج در جدول ط پیوست 2) |  |  | -
جدول10 - برآورد اجرا بر اساس فهرست بهای باند و راه 1402 -ساخت دیوار حایل مجاور تپه و سطوح کوهبری شده و شیروانی دورتادور کارخانه |  |  | -
جدول 11 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 -تجهیز و برچیدن کارگاه |  |  | -
جدول 12 - برآورد اجرای لوله کشی وپایپینگ بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401 |  |  | -
جدول 13 - برآورد اجراو نصب تجهیزات مکانیک بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401 |  |  | -
جدول 14 - برآورد اجرا ی خطوط لوله بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته خطوط لوله روزمینی جریانی نفت و گاز1401 - |  |  | -
جدول 15 - برآورد اجرای عملیات برق و مخابرات و کابل کشی بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401 |  |  | -
جدول 16 - برآورد اجرا و نصب تجهیزات ابزاردقیق بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401 |  |  | -
جدول 17-1: هزینه تسهیلات کارفرما جهت ماموریت داخل کشور |  |  | -
جدول 17 -2: هزینه تسهیلات کارفرما جهت ماموریت خارج کشور |  |  | -
جدول 17-3: - هزینه آموزشی عملیاتی (اپراتوری) به میزان 192 نفر-روز |  |  | -
جدول 17-4: هزینه تسهیلات کارفرما مربوط به احداث کمپهای دستگاه نظارت کلیه بندهای اشاره شده در ذیل مربوط به مدرک "مشخصات فنی کمپهای دستگاه نظارت به شماره M9003-BD-GN-OTH-26011میباشد |  |  | -
جدول 18-1: براورد هزینه ایمنی کارگاه : لوازم حفاظت فردی و تجهیزات |  |  | -
جدول 18 -2: براورد هزینه ایمنی کارگاه : نیروی انسانی |  |  | -
جدول 18-3 - براورد هزینه ایمنی کارگاه : سنجش و اندازه گیری (1) - اندازه گیری آلاینده های فیزیکی،شیمیایی و ارگونومی در محیط کار |  |  | -
جدول 18-4: براورد هزینه ایمنی کارگاه : سنجش و اندازه گیری (2) |  |  | -
جدول 18-5: براورد هزینه ایمنی کارگاه : آموزش |  |  | -
پیوست دو - ریز متره و برآورد احجام بخش سیویل وسازه
جدول الف : ریز برآورد متره فونداسیون تجهیزات |  |  | -
جدول ب-1 : ریز برآورد متره سایبانها - فونداسیون و کف سازی |  |  | -
جدول ب-2 : ریز برآورد متره سایبانها - لسکلت فلزی |  |  | -
جدول ج : ریز برآورد متره جاده ها |  |  | -
جدول د : ریز برآورد متره ابنیه متفرقه |  |  | -
جدول ه : ریز برآورد متره محوطه سازی |  |  | -
جدول و : ریز برآورد کانال های لوله ها و کابل های دفنی |  |  | -
جدول ط : ریز برآورد متره سازه های فلزی متفرقه |  |  | -

## C.Note
[9 empty] | مبانی محاسبات براورد : | الف)
[9 empty] | جهت براورد هزینه اجرای بخش سیویل و سازه از "فهرست بهای واحد پایه رشته ابنیه" سال 1402 استفاده شده است. | -1
با توجه به آنکه این پروژه در حد مهندسی مقدماتی و پایه بوده و نقشه معماری فاز یک آن اماده گردیده لیکن نقشه های فاز 2 معماری، نقشه های اجرایی فونداسیون، سازه بتی و فولادی و نیز نقشه های تاسیسات آن تهیه نگردیده و میبایست در مرحله مهندسی تفصیلی انجام شود، لذا امکان تهیه ریز برآورد اقلام و استفاده از فهرست احاد بهای ابنیه در این مرحله از پروژه میسر نمیباشد. لذا برای برآورد هزینه ساخت و اجرای ساختمانها از ابلاغیه شماره 47855/ش م مورخ 1401/12/16شورای مرکزی سازمان نظام مهندسی ساختمان که بر مبنای متراژ ساخت بنا میباشد، استفاده گردیده است | [9 empty] | -2
جهت برآورد هزینه اجرای سایر بخشها از "فهرست بهای اختصاصی تاسیسات نفت و گاز - رشته نصب واحدهای بهره برداری نفت و گاز ایستگاه تراکم گاز" و "فهرست بهای اختصاصی تاسیسات نفت و گاز - رشته خطوط لوله روزمینی جریانی نفت و گاز" سال 1401 استفاده شده است. | [9 empty] | -3
[9 empty] | ضریب بالاسری بخش اجرا بر اساس فهرست بهای اختصاصی نصب واحدهای بهره برداری که در محاسبه هزینه پروژه منظور شده است معادل است با : | -4
[7 empty] | گروه لوله کشی |  | 1-4-
هزینه بالاسری برای کارهایی که از طریق مناقصات انجام میشود : 48%
ضریب هزینه تفاوت بیمه های تامین اجتماعی به میزان 1
ضریب منطقه ای : 1.12
ضریب بروزرسانی به سه ماهه چهارم 1401 : 1.51
| 2.503 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : =1.12*1.51 * 1.48 = | -
|  | 6% | [6 empty] | ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = | -
[7 empty] | گروه نصب تجهیزات |  | 2-4-
هزینه بالاسری برای کارهایی که از طریق مناقصات انجام میشود : 48%
ضریب هزینه تفاوت بیمه های تامین اجتماعی به میزان 1
ضریب منطقه ای : 1.12
ضریب بروزرسانی به سه ماهه چهارم 1401 : 1.515
| 2.5113 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : =1.12*1.515 * 1.48 = | -
|  | 6% | [6 empty] | ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = | -
[5 empty] | گروه نصب کارهای برقی و ابزار دقیق |  |  |  | 3-4-
هزینه بالاسری برای کارهایی که از طریق مناقصات انجام میشود : 48%
ضریب هزینه تفاوت بیمه های تامین اجتماعی به میزان 1
ضریب منطقه ای : 1.12
ضریب بروزرسانی به سه ماهه چهارم 1401 : 1.491
| 2.4715 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : =1.12*1.491 * 1.48 = | -
|  | 6% | [6 empty] | ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = | -
[9 empty] | ضریب بالاسری بخش اجرا بر اساس فهرست بهای اختصاصی خطوط لوله روزمینی که در محاسبه هزینه پروژه منظور شده است معادل است با : | -5
هزینه بالاسری برای کارهایی که از طریق مناقصات انجام میشود : 48%
ضریب هزینه تفاوت بیمه های تامین اجتماعی به میزان 1
ضریب منطقه ای : 1.11
ضریب بروزرسانی به سه ماهه چهارم 1401 : 1.469
| 2.4133 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : =1.11*1.469 * 1.48 = | -
|  | 6% | [6 empty] | ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = | -
[9 empty] | ضریب بالاسری بخش اجرا بر اساس فهرست رشته ابنیه که در محاسبه هزینه پروژه منظور شده است معادل است با | -5
|  |  | 1.41 | [5 empty] | ضریب بالاسری برای کارهایی که از طریق مناقصات انجام میشود :
[9 empty] | ضریب منطقه ای : 1.09 | -
[9 empty] | ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = 4% | -
| 1.5369 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : 1.09 * 1.41 = | -
[9 empty] | برای دفتر فنی کارگاه 4 نفر به شرح زیر برای مدت 20 ماه در نظر گرفته شده است: | -6
سرپرست دفتر فنی ، کنترل پروژه، دو نفر کارشناس فنی بر حسب نیاز
حقوق هر کارشناس سایت بر اساس تجربه این مشاور 50 ملیون تومان در نظر گرفته شده است که با احتساب مالیات و بیمه 75 ملیون تومان هزینه در نظر گرفته شده است.
[9 empty] | ضریب بالاسری بخش اجرا بر اساس فهرست رشته راه و باند که در محاسبه هزینه پروژه منظور شده است معادل است با | 7-
|  |  | 1.41 | [5 empty] | ضریب بالاسری برای کارهایی که از طریق مناقصات انجام میشود :
ضریب منطقه ای : 1.12
ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = 4%
| 1.5792 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : 1.12 * 141 = | -
[8 empty] | با توجه به اینکه نرخ فهارس بها براساس 1402 براساس نرخ سه ماهه چهارم 1401 میباشد لذا جهت بروزرسانی مبالغ به سه ماهه اول 1402 از ضرایب بروزرسانی زیر استفاده شده است : | توضیحات
|  |  |  | 1.06 |  | 1- فهرست ابنیه
|  |  |  | 1.062 |  | 2- فهرست راه و باند
|  |  |  | 1.061 |  | 3- فهرست خطوط لوله روزمینی
|  |  |  | 1.061 | گروه نصب | 4- فهرست نصب واحدهای بهره برداری
|  |  |  | 1.06 | گروه لوله کشی
|  |  |  | 1.058 | گروه برق

## C.foundation-2
جدول 1 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث فونداسیون تجهیزات وادوات (بر اساس ریز متره مندرج در جدول الف پیوست 2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح | ردیف
[5 empty] | * | خاکبرداری و پی کنی با ماشین | * | 1.537
26335376064 | 17134272000 | 9664 | 2725101 | 1773000 | m3 | کندن زمین در صورت لزوم استفاده از چکش هیدرولیکی در زمین های سنگی و حمل و تخلیه مواد کنده شده تا فاصله ٢٠ متر از مرکز ثقل برداشت | 30504 | منطقه ای گچساران. | 1.09
| 0 |  |  |  | * | قالب بندی فلزی | * | بالاسری | 1.41
10024235613 | 6521949000 | 4501 | 2227113 | 1449000 | m2 | تهیه مصالح و قالب بندی فلزی در پی ها | 60101 | تجهیزکارگاه | 1
| 0 |  |  |  | * | تهیه مصالح و اجرای پی | * | بروزرسانی | 1
145592263520 | 94724960000 | 376640 | 386555.5 | 251500 | Kg | تهیه، بریدن، خم کردن و کار گذاشتن میلگرد آج دار به قطر ١٢ تا ١٨ میلی متر، برای بتن مسلح با سیم پیچی لازم. | 70202
63865785195 | 41552235000 | 4149 | 15393055 | 10015000 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با عیار 350 کیلو سیمان | 80106
512711845.2 | 333579600 | 4149 | 123574.8 | 80400 | m3 | اضافه بهایه ردیفهای بتنه ریزی در بتن مسلح | 80310
256670546.5 | 166994500 | 500 | 513341.093 | 333989 | kg | نهیه و نصب انکربولت، میل مهار با مهره مربوطه | 70606
| 0 |  |  |  | * | تهیه خاک مناسب از فاصله 15 کیلومتری | *
1323293036.208 | 860958384 | 4472 | 295906.314 | 192522 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری | 31002
1670251752 | 108669600 | 4472 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 30703
680472936 | 88545600 | 4472 | 152163 | 19800 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر | 30704
| 0 |  |  |  | * | خاکریزی و آبپاشی و کوبیدن با ماشین | *
961823860 | 625780000 | 2680 | 358889.5 | 233500 | m3 | پخش و کوبیدن خاکریزیها با 100% تراکم | 30904
| 0 |  |  |  | * | آبپاشی و کوبیدن سطوح با دست | *
129452288 | 84224000 | 1792 | 72239 | 47000 | m2 | آبپاشی و کوبیدن سطوح با تراکم 95 درصد | 20601
| 0 |  |  |  | * | تهیه مصالح و اجرای بتن با عیار 150 کیلو سیمان | *
10945921025.4 | 7121614200 | 795.8 | 13754613 | 8949000 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با 150 کیلو سیمان | 80102
207323009.7 | 134888100 | 795.8 | 260521.5 | 169500 | m3 | اضافه بها برای بتن به ضخامت 15 سانتیمتر و کمتر | 80304
| 0 |  |  |  | * | حمل خاک تا km10 با ماشین | *
1826988864 | 1188672000 | 9664 | 189051 | 123000 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری | 30701
352772240 | 45904000 | 9664 | 36503.75 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایه ر 100 متر مازاد | 30702
3609417024 | 234835200 | 9664 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 30703
905916069.06 | 589405380 | 1410 | 642493.666 | 418018 | مترمربع | تهیه و اجرای بتن آسفالتی با سنگ شکسته از مصالح رودخانه ای برای قشر رویه ( توپکا ) ، هر گاه دانه بندی مصالح صفر تا 12/5 میلی متر باشد ، به ازای هر سانتی متر ضخامت آسفالت | 270306
| 0 |  |  |  |  | اجرای لایه نفوذ ناپذیر زیر فونداسیون مخازن | *
3224257120 | 2097760000 | 2240 | 1439400.5 | 936500 | m2 | تهیه و اجرای ژئوممبرین (زمین غشا) از جنس پلی اتیلن سنگین (High Density Poly Ethylene) به ضخامت یک میلی متر | 231206 | چهارم 91 | 481.9
1548688960 | 1548688960 | 2240 | 691379 | - | m2 | تهیه مصالح و اجرای ژئو تکستایل بافته | 231207* | چهارم 1401 | 5125.778
273973620968.068 | 175163935524 |  |  |  |  | مجموع |  | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366

## C.Shelters-2
جدول 2 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث سایبان تجهیزات(بر اساس ریز متره مندرج در جدول ب پیوست 2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح | ردیف
[5 empty] | * | خاکبرداری و پی کنی با ماشین | * | 1.537
16926964861.5 | 11012989500 | 6211.5 | 2725101 | 1773000 | m3 | کندن زمین در صورت لزوم استفاده از چکش هیدرولیکی در زمین های سنگی و حمل و تخلیه مواد کنده شده تا فاصله ٢٠ متر از مرکز ثقل برداشت | 30504 | منطقه ای گچساران. | 1.09
226743043.125 | 29504625 | 6211.5 | 36503.75 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد | 30702 | بالاسری | 1.41
2319939346.5 | 150939450 | 6211.5 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 30703 | تجهیزکارگاه | 1
| 0 |  |  |  | * | قالب بندی فلزی | * | بروزرسانی | 1
3287218788 | 2138724000 | 1476 | 2227113 | 1449000 | m2 | تهیه مصالح و قالب بندی فلزی در پی ها | 60101
151089559.2 | 98301600 | 4428 | 34121.4 | 22200 | dm3 | تعبیه انواع درز در مقطع عرضی قطعات بتنی بدون پر کرد آن بر حسب حجم درز. | 60912
| 0 |  |  |  | * | تهیه مصالح و اجرای پی | *
8617682340 | 5606820000 | 17305 | 497988 | 324000 | Kg | تهيه، بريدن، خم كردن و كار گذاشتن ميل گرد ساده به قطر تا 10 ميلي‌متر، براي بتن مسلح | 70101
15452556112.5 | 10053712500 | 39975 | 386555.5 | 251500 | Kg | تهیه، بریدن، خم کردن و کار گذاشتن میلگرد آج دار به قطر ١٢ تا ١٨ میلی متر، برای بتن مسلح با سیم پیچی لازم. | 70202
21244724858.25 | 13822202250 | 1380.15 | 15393055 | 10015000 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با عیار 350 کیلو سیمان | 80106
170551760.22 | 110964060 | 1380.15 | 123574.8 | 80400 | m3 | اضافه بهایه ردیفهای بتنه ریزی در بتن مسلح | 80310
19011564.7623 | 12369268 | 519.15 | 36620.562 | 23826 | m4 | اضافه بها براي بتن كف‌سازي‌ها با هر وسيله و به هر ضخامت | 80306
789261930.4875 | 513508088 | 1537.5 | 513341.093 | 333989 | kg | نهیه و نصب انکربولت، میل مهار با مهره مربوطه | 70606
| 0 |  |  |  | * | تهیه خاک مناسب از فاصله 15 کیلومتری | *
1091894298.66 | 710406180 | 3690 | 295906.314 | 192522 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری | 31002
1378181790 | 89667000 | 3690 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 30703
561481470 | 73062000 | 3690 | 152163 | 19800 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر | 30704
| 0 |  |  |  | * | خاکریزی و آبپاشی و کوبیدن با ماشین | * | چهارم 91 | 481.9
662151127.5 | 430807500 | 1845 | 358889.5 | 233500 | m3 | پخش و کوبیدن خاکریزیها با 100% تراکم | 30904 | چهارم 1401 | 5125.778
| 0 |  |  |  | * | آبپاشی و کوبیدن سطوح با دست | * | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
133280955 | 86715000 | 1845 | 72239 | 47000 | m2 | آبپاشی و کوبیدن سطوح با تراکم 95 درصد | 20601
| 0 |  |  |  | * | تهیه مصالح و اجرای بتن با عیار 150 کیلو سیمان | *
9993414075.15 | 6501895950 | 726.55 | 13754613 | 8949000 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با 150 کیلو سیمان | 80102
189281895.825 | 123150225 | 726.55 | 260521.5 | 169500 | m3 | اضافه بها برای بتن به ضخامت 15 سانتیمتر و کمتر | 80304
| 0 |  |  |  | * | حمل خاک تا km10 با ماشین | *
1174290286.5 | 764014500 | 6211.5 | 189051 | 123000 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری | 30701
226743043.125 | 29504625 | 6211.5 | 36503.75 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایه ر 100 متر مازاد | 30702
231993934.65 | 150939450 | 6211.5 | 37349.1 | 24300 | m3 | حمل از 500 متر تا 10 کیلومتر | 30703
| 0 |  |  |  |  | عملیات بنایی | *
8702263296.3 | 5661849900 | 1038.3 | 8381261 | 5453000 | m3 | سنگ چيني دركف ساختمان (بلوكاژ) با سنگ لاشه. | 40102
| 0 |  |  |  |  | ساخت سازه فلزی | *
60924141583.02 | 39638348460 | 118677.69 | 513358 | 334000 | Kg | تهیه ، ساخت و نصب ستون از یک تیرآهن | 90101
55913668026.8891 | 36378443739 | 136259.57 | 410346.723 | 266979 | Kg | تهیه و نصب تیرحمال با جوشکاریهای لازم در محل اتصال | 90210
74841166606.42 | 48693016660 | 254937.26 | 293567 | 191000 | Kg | اضافه بها در صورت مصرف تیراهن پهن | 90605
19660702855.6302 | 12791608885 | 52745.64 | 372745.555 | 242515 | Kg | تهیه و نصب پرلین روی سطح شیبدار اسکلت فلزی از پروفیلZ | 90203
21990250704.45 | 14307254850 | 43954.7 | 500293.5 | 325500 | Kg | تهیه ونصب بادبندبا تمام قطعات اتصال | 90402
32767838092.717 | 21319348141 | 87909.4 | 372745.555 | 242515 | Kg | تهیه و نصب پرلین روی سطح شیبدار اسکلت فلزی با قطعات اتصال | 90204
1839614521.297 | 1196886481 | 87909.4 | 20926.255 | 13615 | Kg | اضافه بها به ردیف 90204 برای پرلین افقی | 90217
42250581472.5 | 27488992500 | 51915 | 813841.5 | 529500 | Kg | تهیه مصالح و پوشش سقف با ورق گالوانیزه با وسایل و لوازم نصب | 160302
| 0 |  |  |  |  | زنگ زدایی و رنگ آمیزی اسکلت فلزی | *
262802074471 | 170983783000 | 439547 | 597893 | 389000 | Kg | زنگ زدايي اسكلت‌هاي فلزي، به روش ساچمه پاشي (شات بلاست). | 250104
11898068021.3164 | 7741098257 | 9690.8 | 1227769.433 | 798809 | m2 | تهيه مصالح و اجراي رنگ اپوكسي برايساير كارهاي فلزي، شامل دوقشر ضد زنگ براي اپوكسي، يك قشرآستر و يك قشر رويه. | 250303
678438826692.4945 | 438710828644 |  |  |  |  | جمع :

## C.ROAD-2
جدول 3 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث جاده های دسترسی، جاده های داخل واحدها و پاترول(بر اساس ریز متره مندرج در جدول ج پیوست2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح | ردیف
36577852458.8 | 23798212400 | 8260.4 | 4428097 | 2881000 | m3 | تهیه مصالح زیر اساس از مصالح رودخانه ای با دانه بندی صفر تا 50 میلی متر | 260101 | 1.537
45338254470.8 | 29497888400 | 8260.4 | 5488627 | 3571000 | m3 | تهیه مصالح اساس از مصالح رودخانه ای با دانه بندی صفر تا 38 میلی متر ، وقتی که حداقل 50 درصد مصالح مانده روی الک نمره 4 در یک وجه شکسته باشد | 260302 | منطقه ای گچساران. | 1.09
1904130510.3648 | 1238861750 | 8260.4 | 230513.112 | 149976 | m3 | پخش ، آب پاشی ، تسطیح و کوبیدن قشرهای زیر اساس به ضخامت تا 15 سانتی متر ، با حداقل 95 درصد تراکم به روش آشو اصلاحی | 260602 | بالاسری | 1.41
5243544972.4 | 3411545200 | 8260.4 | 634781 | 413000 | m3 | پخش ، آب پاشی ، تسطیح و کوبیدن قشرهای اساس به ضخامت بیش از 10 سانتی متر تا 15، با حداقل 100 درصد تراکم به روش آشو اصلاحی | 260605 | تجهیزکارگاه | 1
16732846833.6 | 10886692800 | 55262.4 | 302789 | 197000 | kg | تهیه مصالح و اجرای اندود نفوذی ( پریمکت ) با قیر محلول | 270101 | بروزرسانی | 1
6806261032.758 | 4428276534 | 18585.9 | 366205.62 | 238260 | kg | تهیه مصالح و اجرای اندود سطحی ( تک کت ) با قیر محلول | 270201
336277553406.72 | 218788258560 | 6608.32 | 50886996 | 33108000 | مترمربع | تهیه و اجرای بتن آسفالتی با سنگ شکسته از مصالح رودخانه ای برای قشر آستر ( بیندر ) ، هرگاه دانه بندی مصالح صفر تا 19 میلی متر باشد ، به ازای هر سانتی متر ضخامت آسفالت | 270304
3550574196.7958 | 2310067792 | 5526.24 | 642493.666 | 418018 | مترمربع | تهیه و اجرای بتن آسفالتی با سنگ شکسته از مصالح رودخانه ای برای قشر رویه ( توپکا ) ، هر گاه دانه بندی مصالح صفر تا 12/5 میلی متر باشد ، به ازای هر سانتی متر ضخامت آسفالت | 270306
3761346400 | 2447200000 | 950 | 3959312 | 2576000 | m2 | هيه مصالح رودخانه‌اي (تونان) براي تحكيم بستر راه و محوطه، يا اجراي قشر تقويتي در زير سازي راه و محوطه | 260701
| 0 |  |  |  | * | تهیه خاک مناسب از فاصله 15 کیلومتری | *
3728419556.4 | 2425777200 | 12600 | 295906.314 | 192522 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری | 31002
4705986600 | 306180000 | 12600 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 30703
1917253800 | 249480000 | 12600 | 152163 | 19800 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر | 30704
| 0 |  |  |  | * | خاکریزی و آبپاشی و کوبیدن با ماشین | *
340945025 | 221825000 | 950 | 358889.5 | 233500 | m3 | پخش و کوبیدن خاکریزیها و تونان با 100% تراکم | 30904
2992077900 | 1946700000 | 12600 | 237466.5 | 154500 |  | پخش و کوبیدن خاکریزیها و تونان با 90% تراکم | 30902 | چهارم 91 | 481.9
0 | 0 |  |  |  | * | حمل خاک تا km10 با ماشین | * | چهارم 1401 | 5125.778
2019618000 | 1314000000 | 7200 | 280502.5 | 182500 | m3 | کانال کنی در زمینهای نرم تا عمق 2 متر | 30501 | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
7044881306.4 | 4583527200 | 25200 | 279558.782 | 181886 | m3 | کانال کنی در زمینهای سخت با وسیله مکانیکی تا عمق 2 متر | 30502
104348920107.6 | 67891294800 | 3600 | 28985811.141 | 18858693 | m3 | کانال کنی در زمینهایسنگی با چکش هیدرولیکی تا عمق 2 متر | 30504
1181802988.8 | 768902400 | 28800 | 41034.826 | 26698 | m3 | اضافه بها برای فاصله حمل بیش از 20 متر و حداکثر 50متر | 30404
5444668800 | 3542400000 | 28800 | 189051 | 123000 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری | 30701
1051308000 | 136800000 | 28800 | 36503.75 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد | 30702
10756540800 | 699840000 | 28800 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 30703
601724787166.4387 | 380893730036 |  |  |  |  | جمع :

## C.OTHERS-2
جدول 4 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث ابنیه متفرقه (بر اساس ریز متره مندرج در جدول د پیوست 2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح |  | ردیف
[5 empty] | * | خاکبرداری و پی کنی با ماشین |  | * | 1.537 | ضریب =
939154391735.0399 | 611030833920 | 344631.04 | 2725101 | 1773000 | m3 | کندن زمین در صورت لزوم استفاده از چکش هیدرولیکی در زمین های سنگی و حمل و تخلیه مواد کنده شده تا فاصله ٢٠ متر از مرکز ثقل برداشت |  | 30504 | منطقه ای گچساران. | 1.09
0 |  |  |  |  | * | حمل خاک تا km10 با ماشین |  | * | بالاسری | 1.41
65152842743.04 | 42389617920 | 344631.04 | 189051 | 123000 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری |  | 30701 | تجهیزکارگاه | 1
12580325326.4 | 1636997440 | 344631.04 | 36503.75 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد |  | 30702 | بروزرسانی | 1
128716591760.64 | 8374534272 | 344631.04 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول |  | 30703
[5 empty] | * | قالب بندی فلزی |  | *
81556878060 | 53062380000 | 36620 | 2227113 | 1449000 | m2 | تهیه مصالح و قالب بندی فلزی در پی ها |  | 60101
[5 empty] | * | تهیه مصالح و اجرای پی |  | *
278700883943.0049 | 181327836007 | 720985.4314 | 386555.5 | 251500 | Kg | تهیه، بریدن، خم کردن و کار گذاشتن میلگرد آج دار به قطر ١٢ تا ١٨ میلی متر، برای بتن مسلح با سیم پیچی لازم. |  | 70202
242078879457.5 | 157500897500 | 15726.5 | 15393055 | 10015000 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با عیار 350 کیلو سیمان |  | 80106
1943399092.2 | 1264410600 | 15726.5 | 123574.8 | 80400 | m3 | اضافه بهایه ردیفهای بتنه ریزی در بتن مسلح |  | 80310
[5 empty] | * | تهیه خاک مناسب از فاصله 15 کیلومتری |  | *
10877516102.64 | 7077108720 | 36760 | 295906.314 | 192522 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری |  | 31002
13729529160 | 893268000 | 36760 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول |  | 30703
5593511880 | 727848000 | 36760 | 152163 | 19800 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر |  | 30704
0 |  |  |  |  | * | خاکریزی و آبپاشی و کوبیدن با ماشین |  | *
36079161435 | 23473755000 | 100530 | 358889.5 | 233500 | m3 | پخش و کوبیدن خاکریزیها با 100% تراکم |  | 30904
0 |  |  |  |  | * | آبپاشی و کوبیدن سطوح با دست |  | *
2655505640 | 1727720000 | 36760 | 72239 | 47000 | m2 | آبپاشی و کوبیدن سطوح با تراکم 95 درصد |  | 20601
0 |  |  |  |  | * | تهیه مصالح و اجرای بتن با عیار 150 کیلو سیمان |  | *
31427640151.44 | 20447391120 | 2284.88 | 13754613 | 8949000 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با 150 کیلو سیمان |  | 80102
595260364.92 | 387287160 | 2284.88 | 260521.5 | 169500 | m3 | اضافه بها برای بتن به ضخامت 15 سانتیمتر و کمتر |  | 80304
0 | [6 empty] | فنس | *
90700076070 | 59011110000 | 100530 | 902219 | 587000 | Kg | تهیه و ساخت و کارگذاری پایه با دستک فلزی از لوله گالوانیزه برای نصب تور یا مشابه |  | 160208
34060304250 | 22160250000 | 60300 | 564847.5 | 367500 | Kg | تهیه و نصب تور سیمی گالوانیزه حصاری با لوازم اتصال |  | 160401
0 | [5 empty] | اجرای لایه نفوذ ناپذیر |  | *
23318288100 | 10114200000 | 10800 | 2159100.75 | 936500 | m2 | تهیه و اجرای ژئوممبرین (زمین غشا) از جنس پلی اتیلن سنگین (High Density Poly Ethylene) به ضخامت یک میلی متر |  | 231206 | چهارم 91 | 481.9
7591341420 | 7591341420 | 10980 | 691379 | - | m2 | تهیه مصالح و اجرای ژئو تکستایل بافته |  | 231207* | چهارم 1401 | 5125.778
29782482600 | 29782482600 | 200 | 148912413 | خارج فهرست بها | m2 | تهیه و اجرای آجر نسوز برای گودال های سوزا |  | * | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
2.0363e+12 | 1239981269679 |  |  |  |  | جمع :

## C.SITE-2
جدول 5 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 -محوطه سازی واحدها (بر اساس ریز متره مندرج در جدول ه پیوست2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح |  | ردیف
[5 empty] | * |  | خاکبرداری و پی کنی با ماشین و حمل تا فاصله 10 کیلومتری | * | 1.537 | ضریب =
67590789722 | 43975790320 | 534160 | 126536.599 | 82327 | m3 | خاکبرداری در زمین های سخت با هر وسیله مکانیکی و حمل تا فاصله 20 متری |  | 30104 | منطقه ای گچساران. | 1.09
127442445320 | 82916360000 | 152560 | 835359.5 | 543500 | m3 | خاکبرداری در زمین های سنگی با هر وسیله مکانیکی و حمل تا فاصله 20 متری |  | 30105 | بالاسری | 1.41
48948685300 | 31846900000 | 76280 | 641697.5 | 417500 | m3 | خاکبرداری در زمین های سنگی با استفاده از چکش هیدرولیکی و حمل تا فاصله 20 متری |  | 30202 | تجهیزکارگاه | 1
44915597300 | 29222900000 | 763000 | 58867.1 | 38300 | m3 | اضافه بها برای فاصله حمل بیش از 20 متر و حداکثر 50متر |  | 30404 | بروزرسانی | 1
144245913000 | 93849000000 | 763000 | 189051 | 123000 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری |  | 30701
27852361250 | 3624250000 | 763000 | 36503.75 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد |  | 30702 |  | چهارم 91 | 481.9
284973633000 | 18540900000 | 763000 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول |  | 30703 |  | چهارم 1401 | 5125.778
0 |  |  |  |  | * | تهیه خاک مناسب از فاصله 15 کیلومتری |  | * |  | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
34621038738 | 22525074000 | 117000 | 295906.314 | 192522 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری |  | 31002
43698447000 | 2843100000 | 117000 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول |  | 30703
17803071000 | 2316600000 | 117000 | 152163 | 19800 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر |  | 30704
0 |  |  |  |  | * |  | خاکریزی و آبپاشی و کوبیدن با ماشین | *
27783580500 | 18076500000 | 117000 | 237466.5 | 154500 | m3 |  | پخش و کوبیدن خاکریزیها با 90% تراکم | 30902
0 |  |  |  |  | * |  | حمل خاک تا km10 با ماشین | *
19950395256 | 12980088000 | 534160 | 37349.1 | 24300 | m3 |  | حمل از 500 متر تا 10 کیلومتر | 30703
0 | [6 empty] | محوطه سازی | *
10573654707 | 6879411000 | 346.5 | 30515598 | 19854000 | m3 |  | تهيه و نصب جدول هاي بتني پيش ساخته با سطح مقطع بيش از 0/05 تا 0/1 مترمربع با بتن به عيار250 كيلو گرم سيمان در مترمكعب | 120102
140970258600 | 91717800000 | 21300 | 6618322 | 4306000 | m3 |  | تهيه، حمل و ريختن شن طبيعي در داخل كانال‌ها، اطراف پي‌ها و لوله‌ها، كف ساختمان‌ها، معابر محوطه‌ها يا هر محل ديگري كه لازم باشد، به‌انضمام پخش و تسطيح آن‌ها در ضخامت‌هاي لازم. | 40504
1041369870693 | 461314673320 |  |  |  |  | جمع :
|  |  |  | 120102 | تهيه و نصب جدول هاي بتني پيش ساخته با سطح مقطع بيش از 0/05 تا 0/1 مترمربع با بتن به عيار250 كيلو گرم سيمان در مترمكعب و ملات ماسه سيمان 1:5. | مترمكعب | 1517000

## C.SITE-3
جدول 6 - برآورد اجرا فضای سبز - خارج از فهرست بها
توضیحات | هزینه نهایی | مقدار | هزینه واحد | واحد | شرح | ردیف
| - | - | 95733 | متر مربع | اختصاص حداقل 10 درصد از محدوده تعیین شده کارخانه و تاسیسات به فضای سبز | * |  |  | چهارم 91 | 481.9
%60 سطح فضای سبز برای کاشت چمن و مابقی برای کاشت گیاهان در نظر گرفته شده است. | 430798500 | 4500 | 95733 | متر مکعب | تهیه خاک مناسب مخلوط رسی-شنی با PH مناسب | 1 | 45000 | 191466 | چهارم 1401 | 5125.778
| 861597000 | 9000 | 95733 | مترمربع | خاکریزی به میزان تقریبی 40سانتی متر | 2 |  | 191466 | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.637
| 86159700 | 900 | 95733 | متر مکعب | خاک رس سرندی به میزان 10 سانتی متری | 3 |  | 191466
| 861597000 | 9000 | 95733 | متر مکعب | تسطیح و رگلاژ | 4 |  | 191466
| 861597000 | 9000 | 95733 | مترمربع | کودپاشی | 5 |  | 191466
| 670131000 | 7000 | 95733 | مترمربع | بذر پاشی چمن | 6 |  | 191466
| 670131000 | 7000 | 95733 | مترمربع | اجرت کاشت چمن | 7 |  | 191466
| 670131000 | 7000 | 95733 | مترمربع | نگهداری چمن به مدت یک ماه | 8 |  | 191466
در هر متربع دو عدد | 382932000 | 4000 | 95733 | عدد | تهیه گیاهان پوششی | 9 |  | 191466
| 191466000 | 2000 | 95733 | متر مربع | کندوکوهی و کود دهی گیاهان پوششی | 10 |  | 191466
| 191466000 | 2000 | 95733 | مترمربع | نگهداری گیاهان پوششی به مدت یک ماه | 11 |  | 191466
| 2127400000 | مطابق مشخصات فنی فضای سبز پروژه | یک قلم | یک قلم | احداث سیستم آبیاری پروژه به صورت مکانیزه و تحت فشار ( بارانی- قطره ای ) | *
| 212740000 |  | یک قلم | یک قلم | تهیه لوازم کشاورزی | *
| 8218146200 |  |  |  | مجموع

## C.UG CIVIL-2
جدول7 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - دفن لوله ها (داخل و خارج واحد) و کابل های زیر زمینی (بر اساس ریز متره مندرج در جدول و پیوست2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح | ردیف
[5 empty] | * | کانال کنس با ماشین | * | 1.537 | ضریب =
61042262400 | 39715200000 | 22400 | 2725101 | 1773000 | m3 | کندن زمین در صورت لزوم استفاده از چکش هیدرولیکی در زمین های سنگی و حمل و تخلیه مواد کنده شده تا فاصله ٢٠ متر از مرکز ثقل برداشت | 30504
[5 empty] | * | حمل خاک تا km10 با ماشین | *
4234742400 | 2755200000 | 22400 | 189051 | 123000 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری | 30701 | منطقه ای گچساران. | 1.09
817684000 | 106400000 | 22400 | 36503.75 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد | 30702 | بالاسری | 1.41
8366198400 | 544320000 | 22400 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 30703 | تجهیزکارگاه | 1
[5 empty] | * | قالب بندی فلزی | * | بروزرسانی | 1
3117958200 | 2028600000 | 1400 | 2227113 | 1449000 | m2 | تهیه مصالح و قالب بندی فلزی در پی ها | 60101
15354630 | 9990000 | 450 | 34121.4 | 22200 | dm3 | تعبیه انواع درز در مقطع عرضی قطعات بتنی بدون پر کرد آن بر حسب حجم درز. | 60912
[5 empty] | * | تهیه مصالح و اجرای پی | *
14147931300 | 9204900000 | 36600 | 386555.5 | 251500 | Kg | تهیه، بریدن، خم کردن و کار گذاشتن میلگرد آج دار به قطر ١٢ تا ١٨ میلی متر، برای بتن مسلح با سیم پیچی لازم. | 70202
15177552230 | 9874790000 | 986 | 15393055 | 10015000 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با عیار 350 کیلو سیمان | 80106
65917011.6 | 42886800 | 1800 | 36620.562 | 23826 | m4 | اضافه بها براي بتن كف‌سازي‌ها با هر وسيله و به هر ضخامت | 80306
[5 empty] | * | تهیه خاک مناسب از فاصله 15 کیلومتری | * |  | چهارم 91 | 481.9
3166197559.8 | 2059985400 | 10700 | 295906.314 | 192522 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری | 31002 |  | چهارم 1401 | 5125.778
3996353700 | 260010000 | 10700 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 30703 |  | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
1628144100 | 211860000 | 10700 | 152163 | 19800 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر | 30704
[5 empty] | * | تهیه مصالح و اجرای بتن با عیار 150 کیلو سیمان | *
2145719628 | 1396044000 | 156 | 13754613 | 8949000 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با 150 کیلو سیمان | 80102
[6 empty] | ماسه/خاک نرم ریزی در کانال | *
52226337800 | 33979400000 | 9100 | 5739158 | 3734000 | m3 | تهیه، حمل و ریختن ماسه کفی خاکدار در داخل کانال | 40503
[6 empty] | عملیات بنایی | *
4525880940 | 2944620000 | 540 | 8381261 | 5453000 | m3 | سنگ چيني دركف ساختمان (بلوكاژ) با سنگ لاشه. | 40102
[5 empty] | * | کانال کنی با ماشین | * | 1.642 | ضریب =
11075290000 | 6745000000 | 1000 | 11075290 | 6745000 | مترمكعب | بنايي با سنـگ لاشه و ملات ماسه سيمان 1:3 در پي. | 60203 | منطقه ای گچساران. | 1.12
2755276000 | 1678000000 | 1000 | 2755276 | 1678000 | مترمكعب | اضافه بها به رديف‌هاي بنايي با سنـگ لاشه در پي، براي بنايي در ديوار. | 60301 | بالاسری | 1.41
245479000 | 149500000 | 1000 | 245479 | 149500 | مترمربع | اضافه بها به رديف‌هاي خشکه‌چيني و بنايي با سنـگ لاشه، براي سطوح شيب‌دار. | 60403 | تجهیزکارگاه | 1.04
188750279299.4 | 113706706200 |  |  |  |  | مجموع |  | بروزرسانی | 1

## C.STEEL STRUCTURE (2)
جدول 8 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - سازه های فلزی متفرقه (بر اساس ریز متره مندرج در جدول ط پیوست 2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح |  | ردیف
[5 empty] | * | خاکبرداری و پی کنی با ماشین |  | * | 1.537 | ضریب =
12017695410 | 7818930000 | 4410 | 2725101 | 1773000 | m3 | پکندن زمین در صورت لزوم استفاده از چکش هیدرولیکی در زمین های سنگی و حمل و تخلیه مواد کنده شده تا فاصله ٢٠ متر از مرکز ثقل برداشت |  | 30504
0 |  |  |  |  | * | حمل خاک تا km10 با ماشین |  | * |  | منطقه ای گچساران. | 1.09
833714910 | 542430000 | 4410 | 189051 | 123000 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری |  | 30701 |  | بالاسری | 1.41
160981537.5 | 20947500 | 4410 | 36503.75 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد |  | 30702 |  | تجهیزکارگاه | 1
1647095310 | 107163000 | 4410 | 373491 | 24300 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول |  | 30703 |  | بروزرسانی | 1
[5 empty] | * | قالب بندی فلزی |  | *
29981395206 | 19506438000 | 13462 | 2227113 | 1449000 | m2 | تهیه مصالح و قالب بندی فلزی در پی ها |  | 60101
[5 empty] | * | تهیه مصالح و اجرای پی |  | *
152426564760 | 99171480000 | 394320 | 386555.5 | 251500 | Kg | تهیه، بریدن، خم کردن و کار گذاشتن میلگرد آج دار به قطر ١٢ تا ١٨ میلی متر، برای بتن مسلح با سیم پیچی لازم. |  | 70202
46764101090 | 30425570000 | 3038 | 15393055 | 10015000 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با عیار 350 کیلو سیمان |  | 80106
375420242.4 | 244255200 | 3038 | 123574.8 | 80400 | m3 | اضافه بهایه ردیفهای بتنه ریزی در بتن مسلح |  | 80310
0 |  |  |  |  | * | تهیه مصالح و اجرای بتن با عیار 150 کیلو سیمان |  | *
14893494956.4 | 9689977200 | 1082.8 | 13754613 | 8949000 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با 150 کیلو سیمان |  | 80102
282092680.2 | 183534600 | 1082.8 | 260521.5 | 169500 | m3 | اضافه بها برای بتن به ضخامت 15 سانتیمتر و کمتر |  | 80304
[7 empty] | نصب برجها و پایه های روشنایی | *
76579488 | 49824000 | 144 | 531802 | 346000 | Kg | (تهیه ، ساخت و) نصب ستون از یک قوطی و یا لوله(توضیح : با توجه به انکه پایه ها و برجها جداگانه خرید میگردندو در براورد اجرا فقط نصب آن منظور میگردد، از هزینه فهرست بها10،000 ریال /کیلوگرم بابت تامین مواد پایه ها کم شده است) |  | *90102
[6 empty] | تهیه ونصب استند پایپ مخازن |  | *
44726700000 | 29100000000 | 60000 | 745445 | 485000 | Kg | تهیه و ساخت . نصب برجهای فلزی مرتفع (آب) (توضیح : با توجه به مشخصات مشابه استند پایپها با سازه فلزی مخازن مرتفع آب ، از این بند استفاده گردید) |  | 90501
[6 empty] | نصب دکلهای انتقال برق 66 کیلوولت |  | *
248625120000 | 161760000000 | 480000 | 517969 | 337000 | Kg | تهیه، ساخت و نصب ستون های خرپایی به اشکال مختلف ا ز تیرآهن ، ناودانی ، نبش ی و مانن د آن، ب ا اتصا ل اعضای خرپا بدون استفاده از ورق. |  | 90305
[6 empty] | ساخت و نصب پلترمها و سایر سازه های فلزی |  | *
165756228000 | 107844000000 | 264000 | 627864.5 | 408500 | Kg | تهیه ، ساخت و نصب قاب ها (تا دهانه 30 متر) |  | 90401
[6 empty] | زنگ زدایی و رنگ آمیزی اسکلت فلزی |  | *
210458336000 | 136928000000 | 352000 | 597893 | 389000 | Kg | زنگ زدايي اسكلت‌هاي فلزي، به روش ساچمه پاشي (شات بلاست). |  | 250104 |  | چهارم 91 | 481.9
6875508824.8 | 4473330400 | 5600 | 1227769.433 | 798809 | m2 | تهيه مصالح و اجراي رنگ اپوكسي برايساير كارهاي فلزي، شامل دوقشر ضد زنگ براي اپوكسي، يك قشرآستر و يك قشر رويه. |  | 250303 |  | چهارم 1401 | 5125.778
935901028415.3 | 607865879900 |  |  |  |  | جمع : |  |  |  | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366

## C.Buildings
جدول 9- برآورد اجرا بر اساس ابلاغیه شماره 47855 مورخ 1401/12/16 شورای مرکزی سازمان نظام مهندسی ساختمان -احداث ساختمانها
|  |  | هزینه اجرا |  | متراژ بر حسب متر |  | ردیف
|  | 294344107200 |  |  | 936 | احداث اتاق کنترل و مخابرات | 1 | 93000000
|  | 647808612000 |  | 790+ | 480 | احداث پست برق | 2 | 3.3814
|  | 17610331200 |  |  | 56 | احداث نگهبانی | 3
|  | 73271556600 |  |  | 233 | احداث کارگاه مهندسی | 4
|  | 81762252000 |  |  | 260 | احداث ساختمان کمپرسور و دیزل ژنراتور | 5 | منطقه ای گچساران. | 1.09
|  | 7861755000 |  |  | 25 | توسعه پست برق بهره برداری | 6 | بالاسری | 1.41
|  | 20755033200 |  |  | 66 | ساختمان رفاهی بهره برداری | 7 | تجهیزکارگاه | 1
|  | 41824536600 |  |  | 133 | توسعه اتاق کنترل بهره برداری | 8 | بروزرسانی | 1
|  | 61950629400 |  |  | 197 | احداث ساختمان کمپرسور واحد بهره برداری | 9 | ضريب تطبيق | 2
|  | 133649835000 |  |  | 425 | ایستگاه برق 33 کیلو ولت | 10 | چهارم 91 | 481.9
|  | 93397649400 |  |  | 297 | پست برق 3.45/33 کیلوولت | 11 | چهارم 1401 | 5125.778
|  | 15094569600 |  |  | 48 | احداث دیزل ژنراتور پست برق | 12 | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
|  | 9119635800 |  |  | 29 | احداث نگهبانی پست برق | 13
|  | 71699205600 |  |  | 228 | احداث آزمایشگاه مرکزی | 14
|  | 21383973600 |  |  | 68 | احداث انبار فوم | 15
|  | 21383973600 |  |  | 68 | ساختمان انبار مصرفی | 16
1612917655800
نحوه محاسبه اجرای ساختمانها با توجه به آنکه این پروژه در حد مهندسی مقدماتی و پایه بوده و نقشه معماری فاز یک آن اماده گردیده لیکن نقشه های فاز 2 معماری، نقشه های اجرایی فونداسیون، سازه بتی و فولادی و نیز نقشه های تاسیسات آن تهیه نگردیده و میبایست در مرحله مهندسی تفصیلی انجام شود، لذا امکان تهیه ریز برآورد اقلام و استفاده از فهرست احاد بهای اببنیه در این مرحله از پروژه میسر نمیباشد. لذا برای برآورد هزینه ساخت و اجرای ساختمانها از ابلاغیه شماره 47855/ش م مورخ 1401/12/16شورای مرکزی سازمان نظام مهندسی ساختمان که بر مبنای متراژ ساخت بنا میباشد، استفاده گردیده است که در ذیل ابلاغیه مذکور درج گردیده است:

## C.RETAINING WAL
جدول10 - برآورد اجرا بر اساس فهرست بهای باند و راه 1402 -ساخت دیوار حایل مجاور تپه و سطوح کوهبری شده و شیروانی دورتادور کارخانه
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست راه و باند 1402 | واحـد | شــــــــرح | ردیف
[5 empty] | * | کانال کنی با ماشین | * | 1.579 | ضریب =
127804260000 | 80940000000 | 12000 | 10650355 | 6745000 | مترمكعب | بنايي با سنـگ لاشه و ملات ماسه سيمان 1:3 در پي. | 60203 |  |  | منطقه ای گچساران. | 1.12
31794744000 | 20136000000 | 12000 | 2649562 | 1678000 | مترمكعب | اضافه بها به رديف‌هاي بنايي با سنـگ لاشه در پي، براي بنايي در ديوار. | 60301 |  |  | بالاسری | 1.41
2124544500 | 1345500000 | 9000 | 236060.5 | 149500 | مترمربع | اضافه بها به رديف‌هاي خشکه‌چيني و بنايي با سنـگ لاشه، براي سطوح شيب‌دار. | 60403 |  |  | تجهیزکارگاه | 1
161723548500 | 102421500000 |  |  |  |  | مجموع |  |  |  | بروزرسانی | 1
جدول 11 - برآورد اجرا بر اساس فهرست بهای راه و باند 1402 -تجهیز و برچیدن کارگاه
توضیحات (ارقام بر اساس اطلاعات برداشت شده از پروژه مشابه درج شده است) |  |  |  | مبلغ | واحد | شرح | ردیف |  |  | 4/91 | 469.7
اجاره 400مترمربع مسکونی |  |  |  | 7167099567.0996 | مقطوع | تامين و تجهيز محل سكونت كارمندان و افراد متخصص پيمانكار. | 420101 |  |  | 4/1401 | 5610.6444
احداث 200 متر مربع و تجهیز |  |  |  | 9556132756.1328 | مقطوع | تامين و تجهيز ساختمان‌هاي اداري و دفاتر كار پيمانكار. | 420103 |  |  |  | 11.9452
طبخ روزانه 100 وعده غذا |  |  |  | 107506493506.4935 | مقطوع | تامين كمك هزينه يا تسهيلات لازم براي تهيه غذاي كارگران. | 420201
|  |  |  | 5972582.9726 | مقطوع | تامين وتجهيزساختمانهاي اداري و دفاتركاركارفرما،مهندس مشاورو .آزمايشگاه | 420302
احداث 500 متر انبار سرپوشیده |  |  |  | 14931457431.4574 | مقطوع | تامين ساختمان‌هاي پشتيباني و هزينه تجهيز انبارهاي سرپوشيده، آزمايشگاه پيمانكار و موارد مشابه. | 420401
|  |  |  | 3583549783.5498 | مقطوع | تامين و تجهيز ساختمان‌هاي عمومي، بجز ساختمان‌هاي مسکوني و اداري و دفاتر کار. | 420403
2000 متر مربع |  |  |  | 2389033189.0332 | مقطوع | محوطه سازي. | 420404
ماهیانه 2،000،000 ریال |  |  |  | 107506493.5065 | مقطوع | تامين آب كارگاه و شبكه آب رساني داخل كارگاه. | 420601
ماهیانه 30،000،000 ریال |  |  |  | 10750649350.6494 | مقطوع | تامين برق كارگاه و شبكه برق رساني داخل كارگاه. | 420602
|  |  |  | 597258297.2583 | مقطوع | تامين سيستم‌هاي مخابراتي داخل كارگاه. | 420603
ماهیانه 30،000،000 ریال |  |  |  | 10750649350.6494 | مقطوع | تامين سيستم سوخت رساني كارگاه. | 420605
[5 empty] | مقطوع | تامين راه دسترسي. | 420701
[5 empty] | مقطوع | بيمه تجهيز كارگاه. | 421301
|  |  |  | 7167099567.0996 | مقطوع | برچيدن کارگاه. | 421302
|  |  |  | 174512901875.9019 |  | جمع :

## C.PIPING
جدول 12 - برآورد اجرای لوله کشی وپایپینگ بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | فصل | شرح عمليات
21563274290.25 | 8614971750 | 3733900.31 | 1491770 | 1.01 | 590101101 | 5775 | تن | فصل اول-لوله کشی-حمل و جابجایی مصالح | حمل و جابجايي مصالح در محدوده سايت |  |  |  | 8662.5
12233985687 | 4887729000 | 2118439.08 | 846360 | 1.02 | 590111101 | 5775 | تن | فصل اول-لوله کشی-حمل و جابجایی مصالح | بخشی که در محل ساخته و نصب می شود | 2.503 | منطقه ای گچساران. | 1.12 | 8662.5
41196251250 | 16458750000 | 23778.5 | 9500 | 1.03 | 590142101 | 1732500 | تن/کیلومتر | فصل اول-لوله کشی-حمل و جابجایی مصالح | اضافه بهای حمل بیش از 5 کیلومتر |  | بالاسری | 1.48 | 2598750
101993467729.215 | 40748488905 | 14657392.79 | 5855930 | 3.01 | 590301101 | 6958.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 2 اينچ با ضخامت كوچكتر يا مساوي 375/0 اينچ |  | تجهیزکارگاه | 1 | 10437.75
34083235586.67 | 13616953890 | 18353923.31 | 7332770 | 3.02 | 590301102 | 1857 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 3 اينچ با ضخامت كوچكتر يامساوي 375/. اينچ |  | بروزرسانی | 1.51 | 2785.5
26619702957.12 | 10635119040 | 21329890.19 | 8521730 | 3.03 | 590301103 | 1248 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 4 اينچ با ضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 1872
37122439510.17 | 14831178390 | 27682654.37 | 11059790 | 3.04 | 590301105 | 1341 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 6 اينچ با ضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 2011.5
28336381477.29 | 11320967430 | 34409692.14 | 13747380 | 3.05 | 590301106 | 823.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 8 اينچ با ضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 1235.25
44400741779.7 | 17739009900 | 42899267.42 | 17139140 | 3.06 | 590301107 | 1035 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 10 اينچ با ضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 1552.5
43514433559.59 | 17384911530 | 50804942.86 | 20297620 | 3.07 | 590301108 | 856.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 12 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 1284.75
711205623.84 | 284141280 | 59267135.32 | 23678440 | 3.08 | 590301109 | 12 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 14 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 18
24887957853.72 | 9943251240 | 66903112.51 | 26729170 | 3.09 | 590301110 | 372 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 16 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 558
894858342.96 | 357514320 | 74571528.58 | 29792860 | 3.1 | 590301111 | 12 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 18 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 18
52165665094.59 | 20841256530 | 82215390.22 | 32846740 | 3.11 | 590301112 | 634.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 20 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ | 1.529 |  |  | 951.75
315590129.25 | 126084750 | 105196709.75 | 42028250 | 3.12 | 590301114 | 3 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 26 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 4.5
72910587.84 | 29129280 | 759485.29 | 303430 | 3.13 | 590326101 | 96 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 1 اینچ |  |  |  | 144
50126029.14 | 20026380 | 1518970.58 | 606860 | 3.14 | 590326103 | 33 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 2 اینچ |  |  |  | 49.5
243979048.95 | 97474650 | 2198009.45 | 878150 | 3.15 | 590326105 | 111 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 3 اینچ |  |  |  | 166.5
2083612638.36 | 832446120 | 2869989.86 | 1146620 | 3.16 | 590326106 | 726 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 4 اینچ |  |  |  | 1089
174912843.84 | 69881280 | 3644017.58 | 1455860 | 3.17 | 590326107 | 48 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 5 اینچ |  |  |  | 72
984047541.72 | 393147240 | 4315997.99 | 1724330 | 3.18 | 590326108 | 228 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 6 اینچ |  |  |  | 342
1326082041.18 | 529797060 | 5667017.27 | 2264090 | 3.19 | 590326109 | 234 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 8 اینچ |  |  |  | 351
2084356855.35 | 832743450 | 7018036.55 | 2803850 | 3.2 | 590326110 | 297 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 10 اینچ |  |  |  | 445.5
281403229.14 | 112426380 | 8527370.58 | 3406860 | 3.21 | 590326111 | 33 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 12 اینچ |  |  |  | 49.5
255722148.78 | 102166260 | 358154.27 | 143090 | 3.22 | 590303101 | 714 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 2 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 1071
298363356.9 | 119202300 | 536142.6 | 214200 | 3.23 | 590303102 | 556.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 3 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 834.75
316002936.525 | 126249675 | 714130.93 | 285310 | 3.24 | 590303103 | 442.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 4 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 663.75
42715997.76 | 17065920 | 889916.62 | 355540 | 3.25 | 590303104 | 48 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 5 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 72
293737662.72 | 117354240 | 1070082.56 | 427520 | 3.26 | 590303105 | 274.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 6 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 411.75
280648537.095 | 112124865 | 1428236.83 | 570610 | 3.27 | 590303106 | 196.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 8 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 294.75
675255835.8 | 269778600 | 1786391.1 | 713700 | 3.28 | 590303107 | 378 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 10 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 567
491673400.92 | 196433640 | 2142367.76 | 855920 | 3.29 | 590303108 | 229.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 12 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 344.25
14989916.34 | 5988780 | 2498319.39 | 998130 | 3.3 | 590303109 | 6 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 14 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 9
111317545.95 | 44473650 | 2854296.05 | 1140350 | 3.31 | 590303110 | 39 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 16 اينچ با كلاس كوچكتر يا مساوي600 |  |  |  | 58.5
19274701.92 | 7700640 | 3212450.32 | 1283440 | 3.32 | 590303111 | 6 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 18 اينچ با كلاس كوچكتر يا مساوي600 |  |  |  | 9
181988499.45 | 72708150 | 3568401.95 | 1425650 | 3.33 | 590303112 | 51 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 20 اينچ با كلاس كوچكتر يا مساوي600 |  |  |  | 76.5
6961030.725 | 2781075 | 4640687.15 | 1854050 | 3.34 | 590303114 | 1.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 26 اينچ با كلاس كوچكتر يا مساوي600 |  |  |  | 2.25
520937438.175 | 208125225 | 564701.83 | 225610 | 3.35 | 590331101 | 922.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 2 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 1383.75
185266102.86 | 74017620 | 845963.94 | 337980 | 3.36 | 590331102 | 219 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 3 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 328.5
200816678.685 | 80230395 | 1125023.41 | 449470 | 3.37 | 590331103 | 178.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 4 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 267.75
25312688.82 | 10112940 | 1406260.49 | 561830 | 3.38 | 590331104 | 18 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 5 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 27
129263980.86 | 51643620 | 1689725.24 | 675080 | 3.39 | 590331105 | 76.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 6 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 114.75
207542602.62 | 82917540 | 3843381.53 | 1535510 | 3.4 | 590331106 | 54 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 8 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 81
670413995.055 | 267844185 | 4805835.09 | 1920030 | 3.41 | 590331107 | 139.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 10 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 209.25
449926514.7 | 179754900 | 5768288.65 | 2304550 | 3.42 | 590331108 | 78 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 12 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 117
10096113.315 | 4033605 | 6730742.21 | 2689070 | 3.43 | 590331109 | 1.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 14 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 2.25
103858142.895 | 41493465 | 7693195.77 | 3073590 | 3.44 | 590331110 | 13.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 16 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 20.25
12983473.995 | 5187165 | 8655649.33 | 3458110 | 3.45 | 590331111 | 1.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 18 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 2.25
187553006.355 | 74931285 | 9618102.89 | 3842630 | 3.46 | 590331112 | 19.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 20 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 29.25
59568146.1 | 23798700 | 661868.29 | 264430 | 4.01 | 590404101 | 90 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 40 میلیمتر |  |  |  | 135
560745913.59 | 224029530 | 843861.42 | 337140 | 4.02 | 590404104 | 664.5 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 63 میلیمتر |  |  |  | 996.75
552487590.48 | 220730160 | 868691.18 | 347060 | 4.03 | 590404106 | 636 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 90 میلیمتر |  |  |  | 954
778555496.82 | 311048940 | 1085851.46 | 433820 | 4.04 | 590404107 | 717 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 110 میلیمتر |  |  |  | 1075.5
129336517.8 | 51672600 | 1197560.35 | 478450 | 4.05 | 590404108 | 108 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 125 میلیمتر |  |  |  | 162
260197174.875 | 103954125 | 1196308.85 | 477950 | 4.06 | 590404109 | 217.5 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 160 میلیمتر |  |  |  | 326.25
82873453.95 | 33109650 | 1315451.65 | 525550 | 4.07 | 590404110 | 63 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 200 میلیمتر |  |  |  | 94.5
1618154508.06 | 646486020 | 1494140.82 | 596940 | 4.08 | 590404111 | 1083 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 250 میلیمتر |  |  |  | 1624.5
217793288.7 | 87012900 | 1613283.62 | 644540 | 4.09 | 590404112 | 135 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 315 میلیمتر |  |  |  | 202.5
19323683127 | 7720209000 | 1484153.85 | 592950 | 5.01 | 590501101 | 13020 | اينچ-قطر | فصل پنجم-گروه لوله كشي- عمليات تكميلي لوله كشي | عمليات تكميلي لوله كشي ، آزمايشات پرتو نگاری |  |  |  | 19530
49956835000.38 | 19958783460 | 196335.32 | 78440 | 5.02 | 590541101 | 254446.5 | اينچ-متر | فصل پنجم-گروه لوله كشي- عمليات تكميلي لوله كشي | عمليات تكميلي لوله كشي ، آزمايشات هیدرو استاتیک |  |  |  | 381669.75
18730628727.195 | 7483271565 | 73613.23 | 29410 | 6.01 | 590641101 | 254446.5 | اینچ-متر | فصل ششم– گروه لوله کشی- عملیات پیش ساخت راه اندازی لوله کشی | پیش راه اندازی خطوط لوله کشی در همه سایزها |  |  |  | 381669.75
2907514836 | 1161612000 | 157588.88 | 62960 | 15.01 | 591501101 | 18450 | کیلوگرم | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-ساخت قطعات-10 تا 50 کیلوگرم |  |  |  | 27675
3324140437.5 | 1328062500 | 118191.66 | 47220 | 15.02 | 591501102 | 28125 | کیلوگرم | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-ساخت قطعات-سنگینتر از 50 کیلوگرم |  |  |  | 42187.5
3192909399 | 1275633000 | 173057.42 | 69140 | 15.03 | 591511101 | 18450 | کیلوگرم | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-نصب قطعات-10 تا 50 کیلوگرم |  |  |  | 27675
3607839843.75 | 1441406250 | 128278.75 | 51250 | 15.04 | 591511102 | 28125 | کیلوگرم | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-نصب قطعات-سنگینتر از 50 کیلوگرم |  |  |  | 42187.5
1300389096.6 | 519532200 | 1520922.92 | 607640 | 15.05 | 591531101 | 855 | عدد | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-ساخت و نصب تکیه گاه های سبکتر از 5 کیلوگرم |  |  |  | 1282.5
2810012348.25 | 1122657750 | 3286564.15 | 1313050 | 15.06 | 591531102 | 855 | عدد | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-ساخت و نصب تکیه گاه های 5 تا 10 کیلوگرم |  |  |  | 1282.5
49796529339.15 | 19894738050 | 1156310.91 | 461970 | 17.01 | 591701101 | 43065 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | رنگ آميزي، كارهاي لوله كشي، سند بلاست |  |  |  | 64597.5
12114425887.2 | 4839962400 | 349018.32 | 139440 | 17.02 | 591702101 | 34710 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | رنگ آميزي، كارهاي لوله كشي، رنگ در کارگاه |  |  |  | 52065
2869390141.2 | 1146380400 | 724593.47 | 289490 | 17.03 | 591703101 | 3960 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | رنگ آميزي، كارهاي لوله كشي، رنگ در محل نصب- قطر زیر 2اينچ |  |  |  | 5940
29598309400.8 | 11825133600 | 623647.48 | 249160 | 17.04 | 591704101 | 47460 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | رنگ آميزي، كارهاي لوله كشي، رنگ در محل نصب قطر بزرگتر يا مساوي 2 اينچ |  |  |  | 71190
33593742423.9 | 13421391300 | 871094.06 | 348020 | 17.05 | 591731103 | 38565 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | مصالح رنگ آمیزی |  |  |  | 57847.5
93136194227.7 | 37209825900 | 1207522.29 | 482430 | 17.06 | 591731112 | 77130 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | مصالح رنگ آمیزی |  |  |  | 115695
75415800.492 | 30130164 | 1107427.32 | 442440 | 18.01 | 591801102 | 68.1 | متر | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم لوله های راسته-2 تا 6 اینچ |  |  |  | 102.15
990456593.364 | 395707788 | 1360330.44 | 543480 | 18.02 | 591801103 | 728.1 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم لوله های راسته-8 تا 12 اینچ |  |  |  | 1092.15
172176113.7 | 68787900 | 1275378.62 | 509540 | 18.03 | 591802101 | 135 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم شیرآلات و فیتینگ ها-زیر 2 اینچ |  |  |  | 202.5
213296448.96 | 85216320 | 2539243.44 | 1014480 | 18.04 | 591802102 | 84 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم شیرآلات و فیتینگ ها- 2 تا 6 اینچ |  |  |  | 126
1197979101.9 | 478617300 | 3803108.26 | 1519420 | 18.05 | 591802103 | 315 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم شیرآلات و فیتینگ ها-8 تا 12 اینچ |  |  |  | 472.5
30672763.2 | 12254400 | 639015.9 | 255300 | 18.06 | 591803101 | 48 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم فلنجها-زیر 2 اینچ |  |  |  | 72
41897516.76 | 16738920 | 1269621.72 | 507240 | 18.07 | 591803102 | 33 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم فلنجها-2 تا 6 اینچ |  |  |  | 49.5
468108657.12 | 187019040 | 1902880.72 | 760240 | 18.08 | 591803103 | 246 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم فلنجها-8 تا 12 اینچ |  |  |  | 369
2910203058 | 1162686000 | 357628.64 | 142880 | 18.09 | 591861101 | 8137.5 | اینچ/متر | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | مصالح عایقکاری گرم لوله های راسته |  |  |  | 12206.25
3193751420.715 | 1275969405 | 863059.43 | 344810 | 18.1 | 591862101 | 3700.5 | اینچ/قطر | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | مصالح عایقکاری گرم شیرآلات و فیتینگ ها |  |  |  | 5550.75
551624506.02 | 220385340 | 208474.87 | 83290 | 18.11 | 591863101 | 2646 | اینچ/قطر | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | مصالح عایقکاری گرم فلنجها |  |  |  | 3969
823401082302.3358 | 328965674112 | [7 empty] | مجموع

## C.mECHANICAL
جدول 13 - برآورد اجراو نصب تجهیزات مکانیک بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | شماره تجهیز |  | شرح | ردیف |  |  |  | وزن واحد
[9 empty] | نصب دیسالترها و هیترها | 1
6172791300 | 2458300000 | 47483.01 | 18910 | کد 591111 ردیف 4 | 130000 | Kg | DE | -001-A/B | 1at TRAIN DESALTER | 1.1 |  |  |  | 65000
6172791300 | 2458300000 | 47483.01 | 18910 | کد 591111 ردیف 4 | 130000 | Kg | DE | -002-A/B | 2nd TRAIN DESALTER | 1.2 |  |  |  | 65000
4902205212 | 1952292000 | 40851710.1 | 16269100 | کد 591231 ردیف2 | 120 | TON | H | -001-A1/A2 | CRUDE OIL INDIRECT FIRED HEATER | 1.3 |  |  |  | 60
4902205212 | 1952292000 | 40851710.1 | 16269100 | کد 591231 ردیف 2 | 120 | TON | H | -001-B1/B2 | CRUDE OIL INDIRECT FIRED HEATER | 1.4 |  |  |  | 60
| 0 | [7 empty] | نصب مبدلهای حرارتی | 2 |  |  |  |  | منطقه ای گچساران. | 1.12
205525350 | 81850000 | 41105.07 | 16370 | کد 591111 ردیف 1 | 5000 | Kg | E | -001-A/B | SALTY CRUDE / DESALTED CRUDE HEAT EXCHANGER | 2.1 |  |  |  | 2500 | بالاسری | 1.48
164420280 | 65480000 | 41105.07 | 16370 | کد 591111 ردیف 1 | 4000 | Kg | E | -002-A/B | WATER / WATER HEAT EXCHANGER | 2.2 |  |  |  | 2000 | تجهیزکارگاه | 1
| 0 | [7 empty] | نصب پمپ ها | 3 |  |  |  |  | بروزرسانی | 1.515
540768960 | 215360000 | 67596.12 | 26920 | کد 591001 ردیف 04 | 8000 | Kg | P | -001-A/B | MAIN TRANSFER PUMPS | 3.1 |  |  |  | 4000
378538272 | 150752000 | 67596.12 | 26920 | کد 591001 ردیف 04 | 5600 | Kg | P | -002-A/B | AUXILLIARY TRANSFER PUMPS | 3.2 |  |  |  | 2800
270058050 | 107550000 | 90019.35 | 35850 | کد 591001 ردیف 03 | 3000 | Kg | P | -003-A/B | OFF-SPEC PUMPS | 3.3 |  |  |  | 1500
159699600 | 63600000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 1000 | Kg | P | -005-A/B | DEGASSING WATER PUMPS | 3.4 |  |  |  | 500
125298900 | 49900000 | 125298.9 | 49900 | کد 591001 ردیف 02 | 1000 | Kg | P | -103 | DILUTION WATER PUMPS | 3.5 |  |  |  | 1000
187948350 | 74850000 | 125298.9 | 49900 | کد 591001 ردیف 02 | 1500 | Kg | P | -106-A1/A2 | DILUTION WATER PUMPS | 3.6 |  | ضریب | 2.511 | 750
79849800 | 31800000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 500 | Kg | P | -601-A/B | FLARE K.O DRUM LIQUID PUMPS | 3.7 |  |  |  | 250
95819760 | 38160000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 600 | Kg | P | -102-A/B | DEAERATED WATER PUMPS | 3.8 |  |  |  | 300
63879840 | 25440000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 400 | Kg | P | -105 | DEAERATED WATER PUMPS | 3.9 |  |  |  | 400
47909880 | 19080000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 300 | Kg | P | -104 | POTABLE WATER FILLING PUMP | 3.10 |  |  |  | 300
378081270 | 150570000 | 90019.35 | 35850 | کد 591001 ردیف 03 | 4200 | Kg | P | -201-A/B | WATER INJECTION MAIN PUMPS | 3.11 |  |  |  | 2100
252054180 | 100380000 | 90019.35 | 35850 | کد 591001 ردیف 03 | 2800 | Kg | P | -206-A/B/C | WATER INJECTION BOOSTER PUMPS | 3.12 |  |  |  | 1400
79849800 | 31800000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 500 | Kg | P | -501-A/B/C | CHEMICAL INJECTION PORTABLE PUMPS | 3.13 |  |  |  | 250
143729640 | 57240000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 900 | Kg | P | -701-A/B | HC CLOSED DRAIN TRANSFER PUMPS | 3.14 |  |  |  | 450
39924900 | 15900000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 250 | Kg | P | -702 | HC CLOSED DRAIN DRUM SUMP PUMP | 3.15 |  |  |  | 250
79849800 | 31800000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 500 | Kg | P | -703-A/B | CLEAN WATER PUMPS | 3.16 |  |  |  | 250
95819760 | 38160000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 600 | Kg | P | -704-A/B | RECOVERED WASTE OIL PUMPS | 3.17 |  |  |  | 300
39924900 | 15900000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 250 | Kg | P | -750 | OILY WATER SEPARATOR PUMP | 3.18 |  |  |  | 250
79849800 | 31800000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 500 | Kg | P | -705-A/B | DIRTY OIL PUMPS | 3.19 |  |  |  | 250
95819760 | 38160000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 600 | Kg | P | -706-A/B | RECOVERED WASTE WATER PUMPS | 3.2 |  |  |  | 300
39924900 | 15900000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 250 | Kg | P | -801 | DIESEL OIL PUMP | 3.21 |  |  |  | 250
360077400 | 143400000 | 90019.35 | 35850 | کد 591001 ردیف 03 | 4000 | Kg | P | -901 | FIRE WATER MAIN ELECTRICAL PUMP | 3.22 |  |  |  | 2000
288915660 | 115060000 | 52530.12 | 20920 | کد 591001 ردیف 05 | 5500 | Kg | P | 902 | FIRE WATER MAIN DESEL PUMP | 3.23 |  |  |  | 5500
127759680 | 50880000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 800 | Kg | P | -903-A/B | FIRE WATER JOCKEY PUMPS | 3.24 |  |  |  | 400
127759680 | 50880000 | 159699.6 | 63600 | کد 591001 ردیف 01 | 800 | Kg | P | -904 | FIRE WATER LOADING PUMP | 3.25 |  |  |  | 400
| 0 | [7 empty] | نصب بسته های فرایندی | 4
1453241250 | 578750000 | 58129.65 | 23150 | کد 591101 -ردیف 3 | 25000 | No. | PK | -101 | VACUUM DEAERATOR PACKAGE | 4.1 |  |  |  | 25000
2906482500 | 1157500000 | 58129.65 | 23150 | کد 591101 -ردیف 3 | 50000 | Kg | PK | -201-A/B | IGF PACKAGE | 4.2 |  |  |  | 50000
1453241250 | 578750000 | 58129.65 | 23150 | کد 591101 -ردیف 3 | 25000 | Kg | PK | -202 | NUTSHELL FILTER PACKAGE | 4.3 |  |  |  | 25000
846141714 | 336974000 | 79824.69 | 31790 | کد 591011 ردیف 02 | 10600 | Kg | PK | -401-A/B | AIR COMPRESSOR PACKAGE | 4.4 |  |  |  | 5300
77037480 | 30680000 | 77037.48 | 30680 | کد 591101 ردیف 01 | 1000 | Kg | PK | -402 | AIR DRYER PACKAGE | 4.5 |  |  |  | 1000
894639168 | 356288000 | 117715.68 | 46880 | کد 591011 ردیف 01 | 7600 | Kg | PK | -002-A/B | AIR COMPRESSOR PACKAGE | 4.6 |  |  |  | 3800
77037480 | 30680000 | 77037.48 | 30680 | کد 591101 ردیف 01 | 1000 | Kg | PK | -003 | AIR DRYER PACKAGE | 4.7 |  |  |  | 1000
201959730 | 80430000 | 67319.91 | 26810 | کد 591101 -ردیف 2 | 3000 | Kg | PK | -501 | DEMULSIFIER INJECTION PACKAGE | 4.8 |  |  |  | 3000
403919460 | 160860000 | 67319.91 | 26810 | کد 591101 -ردیف 2 | 6000 | Kg | PK | -502-A/B | DEMULSIFIER INJECTION PACKAGE | 4.9 |  |  |  | 3000
154074960 | 61360000 | 77037.48 | 30680 | کد 591101 ردیف 01 | 2000 | Kg | PK | -503 | OXYGEN SCAVENGER INJECTION PACKAGE | 4.10 |  |  |  | 2000
201959730 | 80430000 | 67319.91 | 26810 | کد 591101 -ردیف 2 | 3000 | Kg | PK | -504 | CORROSION INHIBITOR INJECTION PACKAGE | 4.11 |  |  |  | 3000
201959730 | 80430000 | 67319.91 | 26810 | کد 591101 -ردیف 2 | 3000 | Kg | PK | -505 | REVERSE DEMULSIFIER INJECTION PACKAGE | 4.12 |  |  |  | 3000
348777900 | 138900000 | 58129.65 | 23150 | کد 591101 -ردیف 3 | 6000 | Kg | PK | -506-A | BIOCIDE INJECTION PACKAGE (TYPE A) | 4.13 |  |  |  | 3000
348777900 | 138900000 | 58129.65 | 23150 | کد 591101 -ردیف 3 | 6000 | Kg | PK | -506-B | BIOCIDE INJECTION PACKAGE (TYPE B) | 4.14 |  |  |  | 3000
201959730 | 80430000 | 67319.91 | 26810 | کد 591101 -ردیف 2 | 3000 | Kg | PK | -507 | ANTI SCALE INJECTION PACKAGE | 4.15 |  |  |  | 3000
| 0 | [7 empty] | نصب مخازن تحت فشار | 5
250740927 | 99857000 | 41105.07 | 16370 | کد 591111 ردیف 1 | 6100 | Kg | V | -601 | FLARE K.O. DRUM | 5.1 |  |  |  | 6100
49391370 | 19670000 | 49391.37 | 19670 | کد 591112 ردیف 1 | 1000 | Kg | V | -301 | FUEL GAS K.O. DRUM | 5.2 |  |  |  | 1000
702904230 | 279930000 | 54488.7 | 21700 | کد 591112 ردیف 2 | 12900 | Kg | V | -401 | AIR RECIEVER | 5.3 |  |  |  | 12900
11680820460 | 4651860000 | 47483.01 | 18910 | کد 591111 ردیف 4 | 246000 | Kg | V | -001-A/B | FREE WATER K.O DRUM | 5.4 |  |  |  | 246000
1091843064 | 434824000 | 36886.59 | 14690 | کد 591111 ردیف 2 | 29600 | Kg | V | -701 | HC CLOSED DRAIN DRUM | 5.5 |  |  |  | 29600
171704691 | 68381000 | 28148.31 | 11210 | کد 581113 ردیف 1 | 6100 | Kg | V | -801 | DIESEL STORAGE TANK | 5.6 |  |  |  | 6100
811504980 | 323180000 | 36886.59 | 14690 | کد 591111 ردیف 2 | 22000 | Kg |  |  | LUNCHER AND RECEIVER | 5.7
| 0 | [7 empty] | نصب فلرها | 6
275779288.17 | 109828470 | 91926429.39 | 36609490 | کد 591241 ردیف 01 | 3 | Kg | PK | -602 | FLARE PACKAGE | 6.1 |  |  |  | 3000
229816073.475 | 91523725 | 91926429.39 | 36609490 | کد 591241 ردیف 01 | 2.5 | Kg | PK | -603 | COLD FLARE PACKAGE | 6.2 |  |  |  | 2500
| 0 | [7 empty] | نصب جرثقیلهای سقفی | 7
3737274973.2 | 1488361200 | 62287916.22 | 24806020 | کد 591401 - ردیف 1 | 12x5 تن | TON | CR | 001~0012 | CRANES | 7.1 |  |  |  | 40
| 0 | [7 empty] | نصب مخازن اتمسفریک | 8
| 0 | [5 empty] | TK | -003 | OFF-SPEC TANK : نصب و اجرای مخزن | 8.1 | ID= | 25 | 216500
842009085.09 | 335328190 | 3889187.46 | 1548860 | کد 591301 - ردیف 2 | 216.5 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.1.1 | HEIGHT= | 15
5492428728.652 | 2187347164 | 142540304.85 | 56766350 | کد 591302 - ردیف 2 | 38.5325 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.1.2 |  |  | 38532.4609
25098407927.6982 | 9995383484 | 215778516.3 | 85933300 | کد 591303 - ردیف 2 | 116.3156 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.1.3 |  |  | 116315.6016
5560994166.0732 | 2214653192 | 180399656.25 | 71843750 | کد 591304 - ردیف 2 | 30.826 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.1.4 |  |  | 30825.9688
7493481969.1003 | 2984262035 | 243089.91 | 96810 | کد 591308 | 30825.9688 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.1.5 |  |  | 30825.9688
865466370 | 344670000 | 288488.79 | 114890 | کد 591307 | 3000 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.1.6
683188970.2945 | 272078443 | 1391822.19 | 554290 | کد 591741 - ردیف 1 | 490.8594 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.1.7
2951385226.0172 | 1175382408 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 1767.0938 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.1.8 |  |  | 0
163958450.6025 | 65296078 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 785.375 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.1.9
2787419380.1273 | 1110083385 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 1668.9219 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.1.10 |  |  | 0
163958450.6025 | 65296078 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 785.375 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.1.11 |  |  | 0
1175850687.6562 | 468279844 | 299436.75 | 119250 | کد 591742 - ردیف 2 | 3926.875 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.1.12 |  |  | 0
56243625.345 | 22398895 | 35806.86 | 14260 | کد 591742 - ردیف 3 | 1570.75 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.1.13 |  |  | 0
1544224740.8231 | 614983967 | 873878.22 | 348020 | کد 591731- ردیف 3 | 1767.0938 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.1.14
4281250167.8944 | 1704998076 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 3534.1875 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.1.15
6065104404.517 | 2415413940 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 5006.7656 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (سه لایه پرایمر،میانی و نهایی) | 8.1.16
1482939994.6055 | 590577457 | 201407.31 | 80210 | کد591901ردیف 2 | 7362.8906 | M3 |  |  | تست هیدرواستاتیک | 8.1.17
39632949.1688 | 15783731 | 53233.2 | 21200 | کد591921 | 744.5156 | CM |  |  | آزمایش پرتو نگاری | 8.1.18
0 | 0 | [5 empty] | TK | -101 | DILUTION WATER TANK : نصب و اجرای مخزن | 8.2 |  | 12.5 | 62000
305430958.98 | 121637180 | 4926305.79 | 1961890 | کد 591301 - ردیف 1 | 62 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.2.1 |  | 12
1487241084.4805 | 592290356 | 154388383.02 | 61484820 | کد 591302 - ردیف 1 | 9.6331 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.2.2 |  |  | 9633.1152
8547584202.8775 | 3404055835 | 231303979.08 | 92116280 | کد 591303 - ردیف 1 | 36.9539 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.2.3 |  |  | 36953.9004
1508333773.2878 | 600690471 | 195722481.33 | 77946030 | کد 591304 - ردیف 1 | 7.7065 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.2.4 |  |  | 7706.4922
1873370492.2751 | 746065509 | 243089.91 | 96810 | کد 591308 | 7706.4922 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.2.5 |  |  | 7706.4922
721221975 | 287225000 | 288488.79 | 114890 | کد 591307 | 2500 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.2.6
170797242.5736 | 68019611 | 1391822.19 | 554290 | کد 591741 - ردیف 1 | 122.7148 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.2.7
1032984829.106 | 411383843 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 618.4828 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.2.8 |  |  | 0
57385457.7109 | 22853627 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 274.8813 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.2.9
991993367.6336 | 395059087 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 593.9398 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.2.10 |  |  | 0
57385457.7109 | 22853627 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 274.8813 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.2.11 |  |  | 0
399789233.8031 | 159215147 | 299436.75 | 119250 | کد 591742 - ردیف 2 | 1335.1375 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.2.12 |  |  | 0
19685268.8708 | 7839613 | 35806.86 | 14260 | کد 591742 - ردیف 3 | 549.7625 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.2.13 |  |  | 0
540478659.2881 | 215244388 | 873878.22 | 348020 | کد 591731- ردیف 3 | 618.4828 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.2.14
1498437558.763 | 596749326 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 1236.9656 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.2.15
2158463626.3134 | 859603196 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 1781.8195 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (سه لایه پرایمر،میانی و نهایی) | 8.2.16
419571627.4477 | 167093440 | 284923.17 | 113470 | کد591901ردیف 1 | 1472.5781 | M3 |  |  | تست هیدرواستاتیک | 8.2.17
27002956.5844 | 10753866 | 53233.2 | 21200 | کد591921 | 507.2578 | CM |  |  | آزمایش پرتو نگاری | 8.2.18
0 | 0 | [5 empty] | TK | -102 | POTABLE WATER TANK : نصب و اجرای مخزن | 8.3 |  | 4 | 25500
125620797.645 | 50028195 | 4926305.79 | 1961890 | کد 591301 - ردیف 1 | 25.5 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.3.1 |  | 2.6
152293487.0508 | 60650532 | 154388383.02 | 61484820 | کد 591302 - ردیف 1 | 0.98643 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.3.2 |  |  | 986.431
1324082095.4018 | 527312662 | 231303979.08 | 92116280 | کد 591303 - ردیف 1 | 5.7244 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.3.3 |  |  | 5724.4242
154453378.3847 | 61510704 | 195722481.33 | 77946030 | کد 591304 - ردیف 1 | 0.78914 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.3.4 |  |  | 789.1448
1487014200 | 592200000 | 82611.9 | 32900 | کد 90501 فهرست ابنیه | 18000 | Kg |  |  | نصب و جوشکاری سازه نگهدارنده مخزن مخزن | 8.3.5 |  |  | 18000
330447600 | 131600000 | 82611.9 | 32900 | کد 90501 فهرست ابنیه | 4000 | Kg |  |  | نصب و جوشکاری پله بدنه و سایر متعلقات | 8.3.6
17489637.6395 | 6965208 | 1391822.19 | 554290 | کد 591741 - ردیف 1 | 12.566 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.3.7
79752987.4408 | 31761445 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 47.7508 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.3.8 |  |  | 0
0 | 0 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 0 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.3.9
75555461.786 | 30089790 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 45.2376 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.3.10 |  |  | 0
0 | 0 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 0 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.3.11 |  |  | 0
31606866.4842 | 12587362 | 299436.75 | 119250 | کد 591742 - ردیف 2 | 105.5544 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.3.12 |  |  | 0
0 | 0 | 35806.86 | 14260 | کد 591742 - ردیف 3 | 0 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.3.13 |  |  | 0
41728384.1076 | 16618233 | 873878.22 | 348020 | کد 591731- ردیف 3 | 47.7508 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.3.14
115688893.4258 | 46072837 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 95.5016 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.3.15
164400006.4471 | 65471926 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 135.7128 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (سه لایه پرایمر،میانی و نهایی) | 8.3.16
9308895.841 | 3707246 | 284923.17 | 113470 | کد591901ردیف 1 | 32.6716 | M3 |  |  | تست هیدرواستاتیک | 8.3.17
6660671.067 | 2652597 | 53233.2 | 21200 | کد591921 | 125.1225 | CM |  |  | آزمایش پرتو نگاری | 8.3.18
0 | 0 | [5 empty] | TK | -201 | DISPOSAL TANK : نصب و اجرای مخزن | 8.4 |  | 10 | 40000
197052231.6 | 78475600 | 4926305.79 | 1961890 | کد 591301 - ردیف 1 | 40 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.4.1 |  | 12
951834294.0675 | 379065828 | 154388383.02 | 61484820 | کد 591302 - ردیف 1 | 6.1652 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.4.2 |  |  | 6165.1938
5544471163.1472 | 2208072944 | 231303979.08 | 92116280 | کد 591303 - ردیف 1 | 23.9705 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.4.3 |  |  | 23970.4963
965333614.9042 | 384441902 | 195722481.33 | 77946030 | کد 591304 - ردیف 1 | 4.9322 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.4.4 |  |  | 4932.155
1198957115.0561 | 477481926 | 243089.91 | 96810 | کد 591308 | 4932.155 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.4.5 |  |  | 4932.155
721221975 | 287225000 | 288488.79 | 114890 | کد 591307 | 2500 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.4.6
109310235.2471 | 43532551 | 1391822.19 | 554290 | کد 591741 - ردیف 1 | 78.5375 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.4.7
787036060.2713 | 313435309 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 471.225 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.4.8 |  |  | 0
45908366.1687 | 18282902 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 219.905 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.4.9
760801524.9289 | 302987465 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 455.5175 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.4.10 |  |  | 0
45908366.1687 | 18282902 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 219.905 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.4.11 |  |  | 0
301017776.04 | 119879640 | 299436.75 | 119250 | کد 591742 - ردیف 2 | 1005.28 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.4.12 |  |  | 0
15748215.0966 | 6271691 | 35806.86 | 14260 | کد 591742 - ردیف 3 | 439.81 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.4.13 |  |  | 0
411793264.2195 | 163995725 | 873878.22 | 348020 | کد 591731- ردیف 3 | 471.225 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.4.14
1141666711.4385 | 454666154 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 942.45 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.4.15
1417173704.2575 | 564386183 | 1037043 | 413000 | خارج از فهرست بها | 1366.5525 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (EPOXY GLASS FLAKE) | 8.4.16
268525841.5665 | 106939802 | 284923.17 | 113470 | کد591901ردیف 1 | 942.45 | M3 |  |  | تست هیدرواستاتیک | 8.4.17
25435155.6675 | 10129493 | 53233.2 | 21200 | کد591921 | 477.8063 | CM |  |  | آزمایش پرتو نگاری | 8.4.18
0 | 0 | [5 empty] | OS | -201 | OIL SKIMMER TANK : نصب و اجرای مخزن | 8.5 |  | 10 | 45900
226117435.761 | 90050751 | 4926305.79 | 1961890 | کد 591301 - ردیف 1 | 45.9 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.5.1 |  | 12
951834294.0675 | 379065828 | 154388383.02 | 61484820 | کد 591302 - ردیف 1 | 6.1652 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.5.2 |  |  | 6165.1938
6909164639.7192 | 2751558996 | 231303979.08 | 92116280 | کد 591303 - ردیف 1 | 29.8705 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.5.3 |  |  | 29870.4963
965333614.9042 | 384441902 | 195722481.33 | 77946030 | کد 591304 - ردیف 1 | 4.9322 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.5.4 |  |  | 4932.155
1198957115.0561 | 477481926 | 243089.91 | 96810 | کد 591308 | 4932.155 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.5.5 |  |  | 4932.155
721221975 | 287225000 | 288488.79 | 114890 | کد 591307 | 2500 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.5.6
109310235.2471 | 43532551 | 1391822.19 | 554290 | کد 591741 - ردیف 1 | 78.5375 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.5.7
787036060.2713 | 313435309 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 471.225 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.5.8 |  |  | 0
45908366.1687 | 18282902 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 219.905 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.5.9
760801524.9289 | 302987465 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 455.5175 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.5.10 |  |  | 0
45908366.1687 | 18282902 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 219.905 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.5.11 |  |  | 0
301017776.04 | 119879640 | 299436.75 | 119250 | کد 591742 - ردیف 2 | 1005.28 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.5.12 |  |  | 0
15748215.0966 | 6271691 | 35806.86 | 14260 | کد 591742 - ردیف 3 | 439.81 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.5.13 |  |  | 0
411793264.2195 | 163995725 | 873878.22 | 348020 | کد 591731- ردیف 3 | 471.225 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.5.14
1141666711.4385 | 454666154 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 942.45 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.5.15
564386182.5 | 564386183 | 413000 | - | خارج از فهرست بها | 1366.5525 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (EPOXY GLASS FLAKE) | 8.5.16
268525841.5665 | 106939802 | 284923.17 | 113470 | کد591901ردیف 1 | 942.45 | M3 |  |  | تست هیدرواستاتیک | 8.5.17
25435155.6675 | 10129493 | 53233.2 | 21200 | کد591921 | 477.8063 | CM |  |  | آزمایش پرتو نگاری | 8.5.18
1982400000 | 1982400000 | 330400 | - | خارج از فهرست بها | 6000 | Kg |  |  | نصب اجزا داخلی اسکیمر | 8.5.19
0 | 0 | [5 empty] | TK | -701 | DIRTY OILTANK : نصب و اجرای مخزن | 8.6 |  | 3 | 3600
17734700.844 | 7062804 | 4926305.79 | 1961890 | کد 591301 - ردیف 1 | 3.6 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.6.1 |  | 3
85665086.4661 | 34115925 | 154388383.02 | 61484820 | کد 591302 - ردیف 1 | 0.55487 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.6.2 |  |  | 554.8674
499002404.6832 | 198726565 | 231303979.08 | 92116280 | کد 591303 - ردیف 1 | 2.1573 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.6.3 |  |  | 2157.3447
86880025.3414 | 34599771 | 195722481.33 | 77946030 | کد 591304 - ردیف 1 | 0.44389 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.6.4 |  |  | 443.894
107906140.355 | 42973373 | 243089.91 | 96810 | کد 591308 | 443.894 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.6.5 |  |  | 443.894
86546.637 | 34467 | 288488.79 | 114890 | کد 591307 | 0.3 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.6.6
9837921.1722 | 3917930 | 1391822.19 | 554290 | کد 591741 - ردیف 1 | 7.0684 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.6.7
61388812.7012 | 24447954 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 36.7555 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.6.8 |  |  | 0
0 | 0 | 208764.54 | 83140 | کد 591741 - ردیف 4 |  | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.6.9
59027704.5203 | 23507648 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 35.3419 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.6.10 |  |  | 0
0 | 0 | 208764.54 | 83140 | کد 591741 - ردیف 4 |  | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.6.11 |  |  | 0
23705149.8632 | 9440522 | 299436.75 | 119250 | کد 591742 - ردیف 2 | 79.1658 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.6.12 |  |  | 0
0 | 0 | 35806.86 | 14260 | کد 591742 - ردیف 3 | 0 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.6.13 |  |  | 0
32119874.6091 | 12791667 | 873878.22 | 348020 | کد 591731- ردیف 3 | 36.7555 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.6.14
89050003.4922 | 35463960 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 73.5111 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.6.15
109953132.2269 | 43788583 | 1037043 | 413000 | خارج از فهرست بها | 106.0256 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (EPOXY GLASS FLAKE) | 8.6.16
6041831.4352 | 2406146 | 284923.17 | 113470 | کد591901ردیف 1 | 21.2051 | M3 |  |  | تست هیدرواستاتیک | 8.6.17
6672349.1003 | 2657248 | 53233.2 | 21200 | کد591921 | 125.3419 | CM |  |  | آزمایش پرتو نگاری | 8.6.18
0 | [6 empty] | TK | -902-A/B | FIRE WATER STORAGE: نصب و اجرای مخزن | 8.7 |  | 11 | 144600
712343817.234 | 283689294 | 4926305.79 | 1961890 | کد 591301 - ردیف 1 | 144.6 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.7.1 |  | 12
2303438991.6434 | 917339304 | 154388383.02 | 61484820 | کد 591302 - ردیف 1 | 14.9198 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.7.2 |  |  | 14919.7689
55159704263.6151 | 21967225911 | 231303979.08 | 92116280 | کد 591303 - ردیف 1 | 238.4728 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.7.3 |  |  | 238472.7858
2336107348.0681 | 930349402 | 195722481.33 | 77946030 | کد 591304 - ردیف 1 | 11.9358 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.7.4 |  |  | 11935.8151
5802952436.8713 | 2311012520 | 243089.91 | 96810 | کد 591308 | 23871.6302 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.7.5 |  |  | 23871.6302
721221975 | 287225000 | 288488.79 | 114890 | کد 591307 | 2500 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.7.6
132265384.649 | 52674387 | 1391822.19 | 554290 | کد 591741 - ردیف 1 | 95.0304 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.7.7
883054459.6243 | 351674416 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 528.7144 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.7.8
50499202.7856 | 20111192 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 241.8955 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.7.9
851310671.8601 | 339032526 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 509.7084 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.7.10
50499202.7856 | 20111192 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 241.8955 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.7.11
339397542.4851 | 135164294 | 299436.75 | 119250 | کد 591742 - ردیف 2 | 1133.4532 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.7.12
17323036.6063 | 6898860 | 35806.86 | 14260 | کد 591742 - ردیف 3 | 483.791 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.7.13
462032042.4543 | 184003203 | 873878.22 | 348020 | کد 591731- ردیف 3 | 528.7144 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.7.14
1280950050.234 | 510135424 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 1057.4289 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.7.15
1852354239.309 | 737695834 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 1529.1251 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (سه لایه پرایمر،میانی و نهایی) | 8.7.16
324916268.2955 | 129397160 | 284923.17 | 113470 | کد591901ردیف 1 | 1140.3645 | M3 |  |  | تست هیدرواستاتیک | 8.7.17
26062276.0343 | 10379242 | 53233.2 | 21200 | کد591921 | 489.5869 | CM |  |  | آزمایش پرتو نگاری | 8.7.18
[7 empty] | TK | 104 | SUPPLY WATER TANK : نصب و اجرای مخزن | 8.8 |  | 8 | 32000
157641785.28 | 62780480 | 4926305.79 | 1961890 | کد 591301 - ردیف 1 | 32 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.8.1 |  | 10
609173948.2032 | 242602130 | 154388383.02 | 61484820 | کد 591302 - ردیف 1 | 3.9457 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.8.2 |  |  | 3945.724
5028807010.5262 | 2002710876 | 231303979.08 | 92116280 | کد 591303 - ردیف 1 | 21.7411 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.8.3 |  |  | 21741.1176
617813513.5387 | 246042817 | 195722481.33 | 77946030 | کد 591304 - ردیف 1 | 3.1566 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.8.4 |  |  | 3156.5792
767332553.6359 | 305588432 | 243089.91 | 96810 | کد 591308 | 3156.5792 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.8.5 |  |  | 3156.5792
| 287225000 | 288488.79 | 114890 | کد 591307 | 2500 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.8.6
69958550.5582 | 27860833 | 1391822.19 | 554290 | کد 591741 - ردیف 1 | 50.264 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.8.7
520493181.1927 | 207285218 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 311.6368 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.8.8 |  |  | 0
26233352.0964 | 10447372 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 125.66 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.8.9
503703078.5736 | 200598598 | 1670191.65 | 665150 | کد 591741 - ردیف 3 | 301.584 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.8.10 |  |  | 0
26233352.0964 | 10447372 | 208764.54 | 83140 | کد 591741 - ردیف 4 | 125.66 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.8.11 |  |  | 0
198671732.1864 | 79120562 | 299436.75 | 119250 | کد 591742 - ردیف 2 | 663.4848 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.8.12 |  |  | 0
8998980.0552 | 3583823 | 35806.86 | 14260 | کد 591742 - ردیف 3 | 251.32 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.8.13 |  |  | 0
272332612.0705 | 108455839 | 873878.22 | 348020 | کد 591731- ردیف 3 | 311.6368 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.8.14 | [5 empty] | 4/1400 | 3296.3 | 5257 | 3323.285
755022251.8313 | 300685883 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 623.2736 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.8.15 | [5 empty] | 4/1391 | 429.7 | 597 | 402.315
1096000042.981 | 436479507 | 1211381.73 | 482430 | کد 591731- ردیف 12 | 904.752 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (سه لایه پرایمر،میانی و نهایی) | 8.8.16
143213782.1688 | 57034561 | 284923.17 | 113470 | کد591901ردیف 1 | 502.64 | M3 |  |  | تست هیدرواستاتیک | 8.8.17 | [7 empty] | 8.26
20986922.934 | 8357994 | 53233.2 | 21200 | کد591921 | 394.245 | CM |  |  | آزمایش پرتو نگاری | 8.8.18
24780000000 | 24780000000 | 0 |  | خارج از فهرست بها |  | No. |  |  | نصب سیستم HVAC ساختمانها | 9 |  |  |  | 1
16520000000 | 16520000000 | 0 |  | خارج از فهرست بها |  | No. |  |  | نصب تجهیزات سیستم CO2 | 10
1652000000 | 1652000000 | 0 |  | خارج از فهرست بها |  | No. |  |  | نصب تجهیزات اطفا حریق | 11 |  |  |  | 13
[6 empty] | No. |  |  | WATER HYDRANT WITH MONITOR | 65.3
[6 empty] | No. |  |  | DELUGE VALVE | 65.4
[6 empty] | No. |  |  | DRY POWDER PORTABLE FIRE EXTINGUISHER | 65.5
[6 empty] | No. |  |  | DRY POWDER WHELEED FIRE EXTINGUISHER | 65.6
[6 empty] | No. |  |  | CO2 PORTABLE FIRE EXTINGUISHER | 65.7
[6 empty] | No. |  |  | CO2 WHEELD FIRE EXTINGUISHER | 65.8
[6 empty] | No. |  |  | SAFETY SHOWER & EYE WASH | 65.9
[6 empty] | No. |  |  | FIRST AID KIT | 65.10
[6 empty] | No. |  |  | CO2 TOTAL FLOODING SYSTEM | 65.11
[6 empty] | No. |  |  | FIRE SHED EQUIPMENT. 100 lit foam drums, 3% FP (5 NOS.), Fire Hose, 25 m (10 NOS.) Foam Nozzle 10X (2 NOS.) Water Nozzle, 450 lpm (Fog/Jet/Stop) (5 NOS.)) 12 kg portable powder fire extinguisher (6 NOS.) 75 kg Wheeled powder fire extinguisher (2 NOS.) 5 kg portable CO2 fire extinguisher (2 NOS.) In Line Inductor, 450 lpm with pick up tube (2 NOS.) Drum Wrench (1 NO.) Hose Bridge (1 NO.) | 65.12
[6 empty] | No. |  |  | FIRE DOSE SYSTEM | 65.13
[6 empty] | No. |  |  | 9 LIT WATER EXTINGUISHER | 65.14
[9 empty] | نصب تجهیزات مکانیک (غیر از مخازن ذخیره) | 67
308771131596.1379 | 150633619879 | [7 empty] | مجموع

## C.PIPELINE
جدول 14 - برآورد اجرا ی خطوط لوله بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته خطوط لوله روزمینی جریانی نفت و گاز 1401 -
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | شرح |  | ردیف
[10 empty] | 2.413 | ضریب
[5 empty] | 400 | متر | احداث خط لوله انتقال نفت نمکی 20 اینچ روزمینی با جنسAPI 5L GR.X52/SCH.30/NACE از واحد بهره برداری گچساران 4 به واحد نمک زدایی گچساران 4 به طول تقریبی 1500 متر و شامل الکترود و تست هیدرواستاتیک |  | 1 | منطقه ای گچساران. | 1.11
[5 empty] | 400 | متر | احداث خط لوله انتقال نفت نمک زدایی شده 20 اینچ روزمینی با جنس API 5L GR.X52/SCH.30/NACE از واحد نمک زدایی گچساران 4 به واحد بهره برداری گچساران 4 به طول تقریبی 1500 متر. |  | 2 | بالاسری | 1.48
343340944 | 142288000 | 429176.18 | 177860 | 560101009 | 800 | متر |  | عملیات ریسه کردن | 2.1 | تجهیزکارگاه | 1
4092367062 | 1695966458 | 30313830.0885 | 12562714.5 | 560209008 | 135 | سرجوش |  | عملیات خم زدن و جوشکاری لوله 20" با ضخامت 0.5" | 2.2 | بروزرسانی | 1.469
1411473612 | 584945550 | 10455360.09 | 4332930 | 56301009 | 135 | سرجوش |  | پرتو نگاری از جوش لوله، شیر واتصالات فولادی 20" | 2.3
1789307064 | 741528000 | 2236633.83 | 926910 | 560401009 | 800 | متر |  | زنگ زدایی و پرایمر زنی لوله 20" با ماسه پاشی در کارگاه پابت | 2.4
1445271176 | 598952000 | 1806588.97 | 748690 | 560404009 | 800 | متر |  | اجرای یک لایه ضد زنگ و دولایه رنگ روی قطر 20" | 2.5
292786760 | 121337240 | 73196690.03 | 30334310 | 560501012 | 4 | عدد |  | نصب شیر 20" تا کلاس 600در هر نقطه از طول خط لوله | 2.6
74280248 | 30783360 | 18570061.92 | 7695840 | 560502012 | 4 | جفت |  | اتصال یک جفت فلنج 20" تا کلاس 600 در هر نقطه از خط | 2.7
1102331900 | 456830460 | 551165949.99 | 228415230 | 560504009 | 2 | عدد |  | اتصال گرم خط لوله به قطر 20" به لوله اصلی | 2.8
551129200 | 228400000 | 688911.5 | 285500 | 560701008 | 800 | متر |  | آزمایش هیدرواستیتک خط لوله به قطر 20" | 2.9
| 0 |  |  |  | 17000 | m |  | تعویض خط لوله انتقال نفت از واحد بهره برداری پازنان به واحد بهره برداری گچساران 3 با سایز 12 اینچ | 3
4766229990 | 1975230000 | 280366.47 | 116190 | 560101005 | 17000 | متر |  | عملیات ریسه کردن | 3.1
48240250078 | 19991815200 | 16926403.536 | 7014672 | 560205009 | 2850 | سرجوش |  | عملیات خم زدن و جوشکاری لوله 12" تا ضخامت 0.5" | 3.2
19158911136 | 7939872000 | 6722424.96 | 2785920 | 560301005 | 2850 | سرجوش |  | پرتو نگاری از جوش لوله، شیر واتصالات فولادی 12" | 3.3
22535296560 | 9339120000 | 1325605.68 | 549360 | 560401005 | 17000 | متر |  | زنگ زدایی و پرایمر زنی لوله 12" با ماسه پاشی در کارگاه پابت | 3.4
18466013360 | 7652720000 | 1086236.08 | 450160 | 560404005 | 17000 | متر |  | اجرای یک لایه ضد زنگ و دولایه رنگ روی قطر 12" | 3.5
175672095 | 72802360 | 43918023.67 | 18200590 | 560501008 | 4 | عدد |  | نصب شیر 12" تا کلاس 600در هر نقطه از طول خط لوله | 3.6
44568110 | 18470000 | 11142027.5 | 4617500 | 560502008 | 4 | جفت |  | اتصال یک جفت فلنج 12" تا کلاس 600 در هر نقطه از خط | 3.7
822392965 | 340817640 | 411196482.66 | 170408820 | 560504005 | 2 | عدد |  | اتصال گرم خط لوله به قطر 12" به لوله اصلی | 3.8
6780047400 | 2809800000 | 565003.95 | 234150 | 560701005 | 12000 | متر |  | آزمایش هیدرواستیتک خط لوله به قطر 12" | 3.9
| 0 |  |  |  | 1000 | m | جابجایی حدود 1900 متر از خط لوله 4 اینچ فشار بالای گاز موجود در سمت شرق سایت و احداث مجدد آن در فاصله حداقل 200 متر از حصار تسهیلات بیرون واحد. لازم به ذکر است در این زمینه حریمهای مجاز فاصله از خطوط لوله و تاسیسات مطابق با ضوابط اغلام شده در آیین نامه مناطق نفتخیز جنوب باید مد نظر قرار گیرد. |  | 4
388232396 | 160892000 | 204332.84 | 84680 | 560101001 | 1900 | متر |  | عملیات ریسه کردن | 4.1
3315483717 | 1374009000 | 9472810.62 | 3925740 | 560201009 | 350 | سرجوش |  | عملیات خم زدن و جوشکاری لوله 4" تا ضخامت0.674" | 4.2
1232308242 | 510695500 | 3520880.69 | 1459130 | 560301001 | 350 | سرجوش |  | پرتو نگاری از جوش لوله، شیر واتصالات فولادی 4" | 4.3
942293391 | 390507000 | 495943.89 | 205530 | 560401001 | 1900 | متر |  | زنگ زدایی و پرایمر زنی لوله 4" با ماسه پاشی در کارگاه پابت | 4.4
695178061 | 288097000 | 365883.19 | 151630 | 560404001 | 1900 | متر |  | اجرای یک لایه ضد زنگ و دولایه رنگ روی قطر 4" | 4.5
31365284 | 12998460 | 15682641.99 | 6499230 | 560501004 | 2 | عدد |  | نصب شیر 4" تا کلاس 600در هر نقطه از طول خط لوله | 4.6
21710533 | 8997320 | 5427633.29 | 2249330 | 560502004 | 4 | جفت |  | اتصال یک جفت فلنج 4" تا کلاس 600 در هر نقطه از خط | 4.7
342499772 | 141939400 | 171249886.1 | 70969700 | 560504001 | 2 | عدد |  | اتصال گرم خط لوله به قطر 4" به لوله اصلی | 4.8
424929300 | 176100000 | 424929.3 | 176100 | 560701001 | 1000 | متر |  | آزمایش هیدرواستیتک خط لوله به قطر 4" | 4.9
| 0 |  |  |  | 500 | m | احداث خط لوله انتقال گاز 6 اینچ فلزی با جنس API5L GR.X52/SCH.80/NACE به صورت روزمینی از واحد بهره برداری گچساران 4 به واحد نمک زدایی گچساران 4 |  | 5
| 0 |  |  |  | 500 |  | ·احداث خط انتقال آب 6 اینچ فلزی با جنس API 5L0 به صورت رو زمینی از تصفیه خانه خیر آباد به واحدنمکزدایی گچساران-4 |  | 6
217218260 | 90020000 | 217218.26 | 90020 | 560101002 | 1000 | متر |  | عملیات ریسه کردن | 6.1
2358691333 | 977493300 | 11793456.6645 | 4887466.5 | 560202009 | 200 | سرجوش |  | عملیات خم زدن و جوشکاری لوله 6"تاا ضخامت 0.5" | 6.2
871918246 | 361342000 | 4359591.23 | 1806710 | 560301002 | 200 | سرجوش |  | پرتو نگاری از جوش لوله، شیر واتصالات فولادی 6" | 6.3
713017370 | 295490000 | 713017.37 | 295490 | 560401002 | 1000 | متر |  | زنگ زدایی و پرایمر زنی لوله 6" با ماسه پاشی در کارگاه پابت | 6.4
537399230 | 222710000 | 537399.23 | 222710 | 560404002 | 1000 | متر |  | اجرای یک لایه ضد زنگ و دولایه رنگ روی قطر 6" | 6.5
0 | 0 | 19603308.52 | 8124040 | 560501005 |  | عدد |  | نصب شیر 6" تا کلاس 600در هر نقطه از طول خط لوله | 6.6
0 | 0 | 6383374.33 | 2645410 | 560502005 |  | جفت |  | اتصال یک جفت فلنج 6" تا کلاس 600 در هر نقطه از خط | 6.7
218819310 | 90683510 | 218819309.63 | 90683510 | 560504002 | 1 | عدد |  | اتصال گرم خط لوله به قطر 6" به لوله اصلی | 6.8
463899250 | 192250000 | 463899.25 | 192250 | 560701002 | 1000 | متر |  | آزمایش هیدرواستیتک خط لوله به قطر 6" | 6.9
47935789320 | 19865640000 | 7989298.22 | 3310940 | خارج از فهرست بها | 6000 | m | احداث دو خط لوله انتقال پساب غیر فلزی با جنس RTP زیر زمینی از واحدنمکزدایی گچساران-4 به چاههای تزریق در فاصله تقریبی 3 کیلومتر برای هر خط لوله. |  | 7 |  | 4/1400 | 4356.5
3994649110 | 1655470000 | 7989298.22 | 3310940 | خارج از فهرست بها | 500 | m | احداث خط لوله انتقال آب ازاد غیر فلزی با جنس RTP زیر زمینی از واحد بهره برداری گچساران-4 به واحدنمکزدایی گچساران-4 |  | 8 |  | 4/1391 | 500 | 8.713
26806197975 | 11109075000 | 3153670.35 | 1306950 | خارج از فهرست بها | 8500 | m | خط لوله آب "6 از چاههای لیشتر با جنس PE-100 به طول تقریبی |  | 9
40209296963 | 16663612500 | 4730505.525 | 1960425 | خارج از فهرست بها | 8500 | m | خط لوله "10 آب آتش نشانی اتصال بین دو واحد با جنس PE-100 به طول تقریبی 500متر |  | 10
263812566723 | 109329700258 | [5 empty] | مجموع |  | 11
133432596703.5

## C.ELECTRICAL
جدول 15 - برآورد اجرای عملیات برق و مخابرات و کابل کشی بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | شرح | ردیف
716960650 | 290150000 | 143392.13 | 58030 | کد 592401 - ردیف 04 | 5000 | Kg | نصب پنل برق MV Switchgear, 33KV, 630A, 3 (with approximately 15 cell)/Location:33KV station | 1 |  |  |  |  | 1 | SET
370761195 | 150045000 | 105931.77 | 42870 | کد 592401 - ردیف 06 | 3500 | Kg | نصب پنل برق MV Switchgear, 3.3KV, 1250A,(with approximately 9 cell) /Location: DE4 Outdoor station | 2 | ضریب = | 2.471 |  |  | 1 | SET
423727080 | 171480000 | 105931.77 | 42870 | کد 592401 - ردیف 06 | 4000 | Kg | نصب پنل برق MV Switchgear, 3.3KV, 630A, 3 phase +E, (with approximately 12 cell)/Location:DE4 | 3 |  |  |  |  | 1 | SET
788656715 | 319165000 | 143392.13 | 58030 | کد 592401 - ردیف 04 | 5500 | Kg | LV Switchgear, 400V, 4000A/Location: DE4 | 4 | منطقه ای گچساران. | 1.12 |  |  | 1 | SET
317795310 | 128610000 | 105931.77 | 42870 | کد 592401 - ردیف 06 | 3000 | Kg | نصب پنل برق 33 KV transformer bay,(2 SET) | 5 | بالاسری | 1.48 |  |  | 2 | SET
370761195 | 150045000 | 105931.77 | 42870 | کد 592401 - ردیف 06 | 3500 | Kg | نصب پنل برق MV Switchgear, 3.3KV, 630A, (with approximately 9 cell). /Location:Production un | 6 | تجهیزکارگاه | 1 |  |  | 1 | SET
286784260 | 116060000 | 143392.13 | 58030 | کد 592401 - ردیف 04 | 2000 | Kg | نصب پنل برق GACHSARAN 4-DESALTING UNIT EDP,400V SWITCHGEAR (EDP) | 7 | بروزرسانی | 1.491 |  |  | 2 | SET
0 |  | 0 |  |  | 1 | Kg | MV Switchgear, 3.3KV, 1000A, نصب تابلو | 8 |  | 33 KV transformer bay, withdrawable, outdoor type with OCB and all protection and metering devises in accordance to Dwg no. M9003-EB-EL-SLD-21026
212382450 | 85950000 | 84952.98 | 34380 | کد 592411 - ردیف 01 | 2500 | Kg | نصب تابلو روشنایی 37 عدد | 8
1869407869 | 756539000 | 2670582.67 | 1080770 | کد 592841 ردیف 1 | 700 | Kg | NGRنصب | 9
2071765472 | 838432000 | 10358827.36 | 4192160 | کد 592451 ستون 1 | 200 | Kg | نصب 62 عدد تابلوی محلی | 10
1736910378 | 702918000 | 8684551.89 | 3514590 | کد 592451 ستون 2 | 200 |  | نصب 62 عدد تابلوی محلی ضد انفجار
84631750 | 34250000 | 16926.35 | 6850 | کد 592801 - ردیف 01 - ستون 2 | 5000 | Kg | پیش راه اندازی و راه اندازی پنل برق MV Switchgear, 33KV, 630A, 3 (with approximately 15 cell)/Location:33KV station | 11
54831490 | 22190000 | 15666.14 | 6340 | کد 592801 - ردیف 01 - ستون 1 | 3500 | Kg | پیش راه اندازی و راه اندازی پنل برق MV Switchgear, 3.3KV, 1250A,(with approximately 9 cell) /Location: DE4 Outdoor station | 12
62664560 | 25360000 | 15666.14 | 6340 | کد 592801 - ردیف 01 - ستون 1 | 4000 | Kg | پیش راه اندازی و راه اندازی پنل برق MV Switchgear, 3.3KV, 630A, 3 phase +E, (with approximately 12 cell)/Location:DE4 | 13
705485326 | 285506000 | 3527426.63 | 1427530 | کد 592812 | 200 | OUTGOING | LV Switchgear, 400V, 4000A/Location: DE4 | 14
50779050 | 20550000 | 16926.35 | 6850 | کد 592801 - ردیف 01 - ستون 2 | 3000 | Kg | پیش راه اندازی و راه اندازی پنل برق 33 KV transformer bay,(2 SET) | 15
54831490 | 22190000 | 15666.14 | 6340 | کد 592801 - ردیف 01 - ستون 1 | 3500 | Kg | پیش راه اندازی و راه اندازی پنل برق MV Switchgear, 3.3KV, 630A, (with approximately 9 cell). /Location:Production un | 16
105822799 | 42825900 | 3527426.63 | 1427530 | کد 592812 | 30 | OUTGOING | پیش راه اندازی و راه اندازی پنل برق GACHSARAN 4-DESALTING UNIT EDP,400V SWITCHGEAR (EDP) | 17
205834300 | 83300000 | 82333.72 | 33320 | کد 592813 | 2500 | Kg | پیش راه اندازی و راه اندازی تابلو روشنایی 37 عدد | 18
1979271 | 801000 | 6597.57 | 2670 | کد 592801 - ردیف 03 - ستون 1 | 300 | Kg | پیش راه اندازی و راه اندازی 62 عدد تابلوی محلی | 19
262123680 | 106080000 | 43687.28 | 17680 | کد 592411 - ردیف 04 | 6000 | Kg | TR1 : Power Transformer 2500 KVA, 3.3 / 0.42 Kv - TR1 نصب تارنسفورماتور | 20
262123680 | 106080000 | 43687.28 | 17680 | کد 592411 - ردیف 04 | 6000 | Kg | 2500 KVA, 3.3 / 0.42 kV - TR2 نصب ترانسفورماتور | 21
349498240 | 141440000 | 43687.28 | 17680 | کد 592411 - ردیف 04 | 8000 | Kg | 6000 KVA, 33 / 3.45kV- PTR1 نصب ترانسفورماتور | 22
349498240 | 141440000 | 43687.28 | 17680 | کد 592411 - ردیف 04 | 8000 | Kg | 6000 KVA, 33 / 3.45kV - PRT2 نصب ترانسفورماتور | 23
47443200 | 19200000 | 7907.2 | 3200 | کد 592821 - ردیف 02- ستون 1 | 6000 | Kg | TR1 : Power Transformer 2500 KVA, 3.3 / 0.42 Kv - TR1 پیش راه اندازی و راه اندازی تارنسفورماتور | 24
47443200 | 19200000 | 7907.2 | 3200 | کد 592821 - ردیف 02- ستون 1 | 6000 | Kg | 2500 KVA, 3.3 / 0.42 kV - TR2 پیش راه اندازی و راه اندازی ترانسفورماتور | 25
56734160 | 22960000 | 7091.77 | 2870 | کد 592821 - ردیف 03- ستون 03 | 8000 | Kg | 6000 KVA, 33 / 3.45kV- PTR1 پیش راه اندازی و راه اندازی ترانسفورماتور | 26
56734160 | 22960000 | 7091.77 | 2870 | کد 592821 - ردیف 03- ستون 03 | 8000 | Kg | 6000 KVA, 33 / 3.45kV - PRT2 پیش راه اندازی و راه اندازی ترانسفورماتور | 27
255402560 | 103360000 | 63850.64 | 25840 | کد 591034 - ردیف 01 | 4000 | Kg | 0.4 kv, 550 KVA- نصب ژنراتور دیزل | 28
127701280 | 51680000 | 63850.64 | 25840 | کد 591034 - ردیف 01 | 2000 | Kg | 0.4 kv, 180 KVA- نصب ژنراتور دیزل | 29
127701280 | 51680000 | 63850.64 | 25840 | کد 591034 - ردیف 01 | 2000 | Kg | 0.4 kv, 180 KVA- نصب ژنراتور دیزل | 30
0 |  | 0 |  |  | 1 |  | UNINTERRUPTIBLE POWER SUPPLY (UPS) | 32
5880980 | 2380000 | 11761.96 | 4760 | کد 592821 - ردیف 01- ستون 1 | 500 | Kg | UPS-1, 110V AC UPS, 80KW - نصب پکیج برق | 31
3528588 | 1428000 | 11761.96 | 4760 | کد 592821 - ردیف 01- ستون 1 | 300 | Kg | DC-01, 110V DC UPS,13 KW - نصب پکیج برق | 32
3528588 | 1428000 | 11761.96 | 4760 | کد 592821 - ردیف 01- ستون 1 | 300 | Kg | DC-02, 24V DC UPS, 18KW - نصب پکیج برق | 33
3528588 | 1428000 | 11761.96 | 4760 | کد 592821 - ردیف 01- ستون 1 | 300 | Kg | DC-03, 110V DC UPS, 9 KW - نصب پکیج برق | 34
3528588 | 1428000 | 11761.96 | 4760 | کد 592821 - ردیف 01- ستون 1 | 300 | Kg | DC-04, 110V DC UPS, 7.5 KW - نصب پکیج برق | 35
3528588 | 1428000 | 11761.96 | 4760 | کد 592821 - ردیف 01- ستون 1 | 300 | Kg | DC-05, 110V DC UPS, 13 KW - نصب پکیج برق | 36
849529800 | 343800000 | 84952.98 | 34380 | کد 592411 - ردیف 01 | 10000 | Kg | نصب باتری | 37
42476490 | 17190000 | 84952.98 | 34380 | کد 592411 - ردیف 01 | 500 | Kg | UPS-1, 110V AC UPS, 80KW - پیش راه اندازی و راه اندازی پکیج برق | 38
25485894 | 10314000 | 84952.98 | 34380 | کد 592411 - ردیف 01 | 300 | Kg | DC-01, 110V DC UPS,13 KW - پیش راه اندازی و راه اندازی پکیج برق | 39
25485894 | 10314000 | 84952.98 | 34380 | کد 592411 - ردیف 01 | 300 | Kg | DC-02, 24V DC UPS, 18KW - پیش راه اندازی و راه اندازی پکیج برق | 40
25485894 | 10314000 | 84952.98 | 34380 | کد 592411 - ردیف 01 | 300 | Kg | DC-03, 110V DC UPS, 9 KW - پیش راه اندازی و راه اندازی پکیج برق | 41
25485894 | 10314000 | 84952.98 | 34380 | کد 592411 - ردیف 01 | 300 | Kg | DC-04, 110V DC UPS, 7.5 KW - پیش راه اندازی و راه اندازی پکیج برق | 42
25485894 | 10314000 | 84952.98 | 34380 | کد 592411 - ردیف 01 | 300 | Kg | DC-05, 110V DC UPS, 13 KW - پیش راه اندازی و راه اندازی پکیج برق | 43
590225655 | 238861050 | 39348376.97 | 15924070 | کد 592421 - ردیف 03- ستون 1 | 15 | متر | نصب باسداکت | 44
0 |  | 0 |  |  | 1 |  | Earting | 45
141222592 | 57152000 | 15023.68 | 6080 | کد 592101 ردیف 1 | 9400 | متر | نصب اتصال زمین -سیم کشی | 45
0 |  | 0 |  |  | 500 |  | نصب اتصال زمین -سیم کشی | 49
0 |  | 0 |  |  |  |  | 70 mm2 BARE STRANDED COPPER CONDUCTOR | 50
0 |  | 0 |  |  | 2850 |  | 70 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 51
0 |  | 0 |  |  | 350 |  | 35 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 52
0 |  | 0 |  |  | 400 |  | 16 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 53
17180566 | 6952880 | 780934.84 | 316040 | کد 592615 ردیف 1 | 22 | عدد | نصب اتصال زمین تسمه مسی | 46
245006816 | 99152900 | 3101352.1 | 1255100 | کد 592612 ردیف 3 | 79 | عدد | نصب اتصال زمین کدولد مسی | 47
727172799 | 294282800 | 2597045.71 | 1051010 | کد 592612 ردیف 2 | 280 | عدد | نصب اتصال زمین کدولد مسی | 48
0 |  | 0 |  |  | 160 | عدد | CADWELD,CARTRIDGE, FOR CROSS CONNECTION OF 70x70 mm2 | 57
0 |  | 0 |  |  | 40 | عدد | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 70x35 mm2 | 58
0 |  | 0 |  |  | 40 | عدد | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 70x16 mm2 | 59
0 |  | 0 |  |  | 40 | عدد | CADWELD,CARTRIDGE, FOR CONNECTION OF 70 mm2 COPPER CONDUCTOR TO COPPER EARTH PLATE | 60
0 |  | 0 |  |  | 68 | عدد | 10-WAY COPPER EARTH BAR,6mm THICKNESS,50 mm WIDE,700 mm LENGTH AND TWO WASHERS AND ONE NUT FOR EACH HOLE | 61
2444970189 | 989465880 | 15672885.83 | 6342730 | کد 592613 | 156 | عدد | نصب اتصال زمین- الکنرود (میله) زمین | 49
0 |  | 0 |  |  | 64 | NO | "U" bolt rod to cable clamp for nominal rod dia. 20 mm | 63
0 |  | 0 |  |  | 24 | NO | TINNED COPPER COMPRESSION CABLE LUG FOR CABLE SIZE 120 mm2 | 64
64121709 | 25949700 | 916024.41 | 370710 | کد 592614 ردیف 1 | 70 | عدد | نصب اتصال زمین- اتصال به تجهیزات | 50
249648713 | 101031450 | 1280249.81 | 518110 | کد 592614 ردیف 2 | 195 | عدد | نصب اتصال زمین- اتصال به تجهیزات | 51
0 |  | 0 |  |  | 121 | عدد | نصب اتصال زمین- اتصال به تجهیزات | 67
0 |  | 0 |  |  | 49 | عدد | CONDUIT , HEAVY GUAGE HOT DIP GALVANIZED ,RIGID STEEL,DOUBLE SIDE ISO THREADED, LENGTH 3000mm, size: M50 | 68
0 |  | 0 |  |  | 147 | عدد | Conduit clamp, m50 | 69
0 |  | 0 |  |  | 1 | عدد | Spark gap | 70
94243940 | 38140000 | 235609.85 | 95350 | کد 592616 | 400 | Kg | نصب اتصال زمین- مخلوط ذغال
48438889 | 19602950 | 9687777.89 | 3920590 | کد 592621 ردیف 1 | 5 | عدد | نصب صاعقه گیر | 52
0 |  | 0 |  |  |  | 1 | cable | 64.3333
0 |  | 0 |  |  |  |  | 0.6/1 KV, Stranded Annealed Copper Conductor, PVC Insulated, Lead Sheath, Extruded PVC Bedding, Galvanized Steel Wire Armored, PVC Sheathed, Cu-PVC-Lsh-Bd-SWA-PVC Power Cable | 64.7619
8506686839 | 3442609000 | 203363.3 | 82300 | کد 592103 - ستون 1- ردیف 1 | 41830 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی -زره دار باغلاف سربی-0.6/1 KV | 53
1249767060 | 505773800 | 232298.71 | 94010 | کد 592103 - ستون 1- ردیف 2 | 5380 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی -زره دار باغلاف سربی-0.6/1 KV | 54
217960733 | 88207500 | 290614.31 | 117610 | کد 592103 - ستون 1- ردیف 3 | 750 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی -زره دار باغلاف سربی-0.6/1 KV | 55
0 |  | 0 |  |  | 8200 | M | 3C4 | 56
0 |  | 0 |  |  |  | M | 3C6 | 57
0 |  | 0 |  |  | 2100 | M | 3C10 | 58
0 |  | 0 |  |  | 4100 | M | 3C16 | 59
0 |  | 0 |  |  | 550 | M | 3C25 | 60
0 |  | 0 |  |  | 250 | M | 3C95 | 61
0 |  | 0 |  |  |  | M | 3C150 | 62
0 |  | 0 |  |  |  | M | 3C25+16 | 63
0 |  | 0 |  |  | 200 | M | 3C150+70 | 64
0 |  | 0 |  |  | 750 | M | 3C240+120 | 65
0 |  | 0 |  |  | 280 | M | 3C95+50 | 66
0 |  | 0 |  |  | 3900 | M | 3C70 | 67
0 |  | 0 |  |  | 750 | M | 3C50 | 68
0 |  | 0 |  |  | 1100 | M | 4C4 | 69
0 |  | 0 |  |  | 1500 | M | 4C10 | 70
0 |  | 0 |  |  | 300 | M | 4C16 | 71
0 |  | 0 |  |  |  |  | 0.6/1 KV, Stranded Annealed Copper Conductor, PVC Insulated, Galvanized Steel Wire Armored, PVC Sheathed, Cu-PVC-SWA-PVC Power Cable | 72
6093862828 | 2466152500 | 183274.07 | 74170 | کد 592102 - ستون 1- ردیف 1 | 33250 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی - زره دار-0.6/1 KV | 56
282780005 | 114439500 | 209466.67 | 84770 | کد 592102 - ستون 1- ردیف 2 | 1350 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی - زره دار-0.6/1 KV | 57
3979219328 | 1610368000 | 216261.92 | 87520 | کد 592102 - ستون2 - ردیف 2 | 18400 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی - زره دار-3/6 KV | 58
938016310 | 379610000 | 268004.66 | 108460 | کد 592102 - ستون2 - ردیف 3 | 3500 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی - زره دار-3/6 KV | 59
0 |  | 0 |  |  | 2000 | M | 1C300 | 60
0 |  | 0 |  |  | 150 | M | 3C4 | 61
0 |  | 0 |  |  | 250 | M | 3C6 | 62
0 |  | 0 |  |  | 300 | M | 3C16 | 63
0 |  | 0 |  |  | 650 | M | 3C25 | 64
0 |  | 0 |  |  | 500 | M | 3C25+16 | 65
0 |  | 0 |  |  | 100 | M | 3C150+70 | 66
0 |  | 0 |  |  | 400 | M | 4C4 | 67
0 |  | 0 |  |  | 600 | M | 4C16 | 68
0 |  | 0 |  |  | 150 | M | 4C10 | 69
0 |  | 0 |  |  | 50 | M | 3C95+50 | 70
0 |  | 0 |  |  | 100 | M | 3C50+25 | 71
0 |  | 0 |  |  | 1100 | M | 3C50 | 72
0 |  | 0 |  |  |  | M | 3/6 KV, Stranded Annealed Copper Conductor, XLPE Insulated, Galvanized Steel Wire Armored, PVC Sheathed, Cu-XLPE-SWA-PVC Power Cable | 73
0 |  | 0 |  |  | 15000 | M | 1C95 | 74
0 |  | 0 |  |  | 2000 | M | 3C70 | 75
0 |  | 0 |  |  | 1400 | M | 3C95 | 76
0 |  | 0 |  |  | 2500 | M | 3C300 | 77
0 |  | 0 |  |  | 1000 | M | 3C240+120 | 78
606081938 | 245278000 | 550983.58 | 222980 | کد 592141 ردیف 1 | 1100 | M2 | ماسه ریزی داخل ترانشه | 60
862317225 | 348975000 | 783924.75 | 317250 | کد 592141 ردیف 2 | 1100 | M2 | آجر چینی داخل ترانشه | 61
492149070 | 199170000 | 820248.45 | 331950 | کد 592201 ردیف 2 - ستون 2 | 600 | سر | سر سیم بندی کابل های کنترل- 5 تا 12 CORE | 62
290767512 | 117672000 | 363459.39 | 147090 | کد 592213 ردیف 2 - ستون 3 | 800 | سر | سر سیم بندی کابل فشار ضعیف - زره داربا غلاف سربی-3 CORE | 63
109025462 | 44122000 | 545127.31 | 220610 | کد 592213 ردیف 3 - ستون 3 | 200 | سر | سر سیم بندی کابل فشار ضعیف - زره داربا غلاف سربی-3 CORE | 64
251814668 | 101908000 | 1259073.34 | 509540 | کد 592213 ردیف 4 - ستون 4 | 200 | سر | سر سیم بندی کابل فشار ضعیف - زره داربا غلاف سربی-3 CORE | 65
136863748 | 55388000 | 342159.37 | 138470 | کد 592212 ردیف 2 - ستون 3 | 400 | سر | سر سیم بندی کابل فشار ضعیف - زره دار-3 CORE | 66
307936020 | 124620000 | 513226.7 | 207700 | کد 592212 ردیف 3 - ستون 3 | 600 | سر | سر سیم بندی کابل فشار ضعیف - زره دار-3 CORE | 67
123809455 | 50105000 | 1238094.55 | 501050 | کد 592212 ردیف 4 - ستون 4 | 100 | سر | سر سیم بندی کابل فشار ضعیف - زره دار-4.5 CORE | 68
835999592 | 338324400 | 6966663.27 | 2819370 | کد 592222 ردیف 1 - ستون 3 | 120 | سر | سر سیم بندی کابل فشارمتوسط - 3 CORE - تا 6KV | 69
334554620 | 135392400 | 11151820.68 | 4513080 | کد 592222 ردیف 2 - ستون 3 | 30 | سر | سر سیم بندی کابل فشار متوسط - 3 CORE - تا 6KV | 70
250946359 | 101556600 | 16729757.24 | 6770440 | کد 592224 ردیف 3 - ستون 3 | 15 | سر | سر سیم بندی کابل فشار متوسط - تا 33KV | 71
8429817 | 3411500 | 168596.33 | 68230 | کد 592231 ردیف 6 | 50 | عدد | نصب گلند ضد گردوغبارM20 | 72
65184980 | 26380000 | 325924.9 | 131900 | کد 592231 ردیف 7 | 200 | عدد | نصب گلند ضد گردوغبارM25 | 73
54090190 | 21890000 | 540901.9 | 218900 | کد 592231 ردیف 8 | 100 | عدد | نصب گلند ضد گردوغبارM33 | 74
30843146 | 12482050 | 881232.73 | 356630 | کد 592231 ردیف 9 | 35 | عدد | نصب گلند ضد گردوغبارM40 | 75
18427235 | 7457400 | 921361.77 | 372870 | کد 592231 ردیف 10 | 20 | عدد | نصب گلند ضد گردوغبارM50 | 76
219094922 | 88666500 | 1460632.81 | 591110 | کد 592231 ردیف 11 | 150 | عدد | نصب گلند ضد گردوغبارM63 | 77
489811010 | 198223800 | 16327033.66 | 6607460 | کد 592232 ردیف 12 | 30 | عدد | نصب گلند ضد گردوغبارM75 | 78
1104043 | 446800 | 220808.56 | 89360 | کد 592231 ردیف 6 | 5 | عدد | نصب گلند ضدانفجارM20 | 79
4264699 | 1725900 | 426469.89 | 172590 | کد 592231 ردیف 7 | 10 | عدد | نصب گلند ضدانفجارM25 | 80
35318003 | 14293000 | 706360.06 | 285860 | کد 592231 ردیف 8 | 50 | عدد | نصب گلند ضدانفجارM33 | 81
45803444 | 18536400 | 1145086.11 | 463410 | کد 592231 ردیف 9 | 40 | عدد | نصب گلند ضدانفجارM40 | 82
7649351 | 3095650 | 1529870.23 | 619130 | کد 592231 ردیف 10 | 5 | عدد | نصب گلند ضدانفجارM50 | 83
9561782 | 3869600 | 1912356.32 | 773920 | کد 592231 ردیف 11 | 5 | عدد | نصب گلند ضدانفجارM63 | 84
0 |  | 0 |  |  | 31 | SET | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator.(L4-T12,L2-T12 Schematic code). | 73
0 |  | 0 |  |  | 8 | SET | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be explosion proof type, IP55, EExd, IIB, T3 and supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator.(L4-T12,L2-T12 Schematic code). | 74
0 |  | 0 |  |  | 13 | SET | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch and remote position indicator.(L1-T12 Schematic code). | 75
0 |  | 0 |  |  | 9 | SET | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be explosion proof type, IP55, EExd, IIB,T3 and supplied with stop push Button, start push button, Local / Remote Selector Switch and remote position indicator.(L1-T12 Schematic code). | 76
0 |  | 0 |  |  | 1 | SET | Local Control Stations for remote operation of the fire water pump.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator. | 77
423303551 | 171308600 | 9202251.1 | 3724100 | کد 592501 ردیف 1 ستون 2 | 46 | عدد | 1x250W HIGH PRESSURE MERCURY نصب نورافکن و چراغ های صنعتی محوطه | 85
736180088 | 297928000 | 9202251.1 | 3724100 | کد 592501 ردیف 1 ستون 2 | 80 | عدد | نصب نورافکن و چراغ های صنعتی محوطه CORROSION RESISTANT OUTDOOR AREA FLOOD LIGHT,1x400W METAL HALIDE LAMP | 87
165576126 | 67007740 | 2670582.67 | 1080770 | کد 592831 ردیف 1 | 62 | دستگاه | پیش راه اندازی و راه اندازی موتورها تا یک KV - زیر 50 KW | 88
42729520 | 17292400 | 4272952.04 | 1729240 | کد 592831 ردیف 2 | 10 | دستگاه | پیش راه اندازی و راه اندازی موتورها تا یک KV -بالای 50 KW | 89
57137452 | 23123210 | 5194313.81 | 2102110 | کد 5ردیف82832 ردیف 1 | 11 | دستگاه | پیش راه اندازی و راه اندازی موتورها بیش از یک KV -زیر 500 KW | 90
[7 empty] | Power Transition Line | 79
126732600000 | 126732600000 | 1173450000 |  | خارج از فهرست بها | 108 | km | Cable ACSR -33KV –LYNX | 91 |  | 4/1400 | 3296.3 | 5257 | 3492.37
7040700000 | 7040700000 | 1173450000 |  | خارج از فهرست بها | 6 | m | Cable ACSR -66KV –HORSE | 92 |  | 4/1391 | 429.7 | 597 | 446.43
800116966 | 323802900 | 26670565.53 | 10793430 | کد 592721 ردیف 1 | 30 | دستگاه | نصب دوربین مدار بسته | 93
156983421 | 63530320 | 39245855.18 | 15882580 | کد 592721 ردیف 2 | 4 | دستگاه | نصب مونیتور های سیتم تلویزیون مدار بسته | 94 |  |  |  | 7.823
51507674 | 20844870 | 51507673.77 | 20844870 | کد 592721 ردیف 3 | 1 | دستگاه | نصب سیستم کنترل تلویزیون مدار بسته | 95
3911500000 | 3911500000 | - | یک قلم | خارج از فهرست بها | - | - | نصب سیستم محافظت پیرامونی ، مخابرات و فراخوان (غیر از داخل ساختمانها و کابل) | 96
3911500000 | 3911500000 | - | یک قلم | خارج از فهرست بها | 34 | عدد | نصب کلیه سوکتهای صنعتی محوطه
1564600000 | 1564600000 | - | یک قلم | خارج از فهرست بها | - | - | نصب کلیه سوییچهای روشنایی
190554944030 | 162341006850 | [5 empty] | مجموع | 97

## C.INSTRUMENT
جدول 16 - برآورد اجرا و نصب تجهیزات ابزاردقیق بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401 | [10 empty] | منطقه ای گچساران. | 1.12
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | شرح | ردیف |  | وزن واحد | بالاسری | 1.48
[11 empty] | تجهیزکارگاه | 1
[11 empty] | بروزرسانی | 1.491
6846661800 | 2770806000 | 11411103 | 4618010 | کد 593133 ردیف 02 | 600 | کیلوگرم | نصب سیستم های آنالایزر- بیشتر از 10 کیلوگرم | 1 | 2.471
1686748000 | 682617600 | 6024100 | 2437920 | کد 593133 ردیف 01 | 280 | کیلوگرم | نصب سیستم های آنالایزر-تا 10 کیلوگرم | 2 | 2.471
548465097 | 221960780 | 14823381 | 5998940 | کد 593101 ردیف 02 | 37 | دستگاه | نصب انتقال دهنده جریان | 3 | 2.471
182458444 | 73839920 | 13032746 | 5274280 | کد 593102 ردیف 04 | 14 | دستگاه | نصب سوییچ جریان | 4 | 2.471
253015972 | 102394160 | 11500726 | 4654280 | کد 593111 ردیف 09 | 22 | دستگاه | نصب نمایشگر جریان | 5 | 2.471
146618670 | 59335760 | 6664485 | 2697080 | کد 593119 ردیف 01 | 22 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات جریان سنجهای در طول خط سایز تا 4" | 6 | 2.471
54851953 | 22198280 | 4219381 | 1707560 | کد 593118 ردیف 01 | 13 | عدد | نصب/ کنترل مشخصات صفحه اوریفیس سایز تا 4" | 7 | 2.471
72894630 | 29500050 | 4859642 | 1966670 | کد 593118 ردیف 02 | 15 | عدد | نصب/ کنترل مشخصات صفحه اوریفیس سایز از 4" تا 8" | 8 | 2.471
94077609 | 38072690 | 5533977 | 2239570 | کد 593118 ردیف 03 | 17 | عدد | نصب/ کنترل مشخصات صفحه اوریفیس سایز از 8" تا 12" | 9 | 2.471
18880392 | 7640790 | 6293464 | 2546930 | کد 593118 ردیف 04 | 3 | عدد | نصب/ کنترل مشخصات صفحه اوریفیس سایز از 12" تا 20" | 10 | 2.471
225718934 | 91347200 | 16122781 | 6524800 | کد 593111 ردیف01 | 14 | دستگاه | نصب نمایشگر سطح مغناطیسی | 11 | 2.471
71257610 | 28837560 | 35628805 | 14418780 | کد 593111 ردیف02 | 2 | دستگاه | (FLOAT-CABLE) نصب نمایشگر سطح | 12 | 2.471
786352500 | 318232500 | 26211750 | 10607750 | کد 593102 ردیف 01 | 30 | دستگاه | نصب سوییچ سطح EXTERNAL | 13 | 2.471
157894282 | 63898940 | 22556326 | 9128420 | کد 593102 ردیف 02 | 7 | دستگاه | نصب سوییچ سطح INTERNAL | 14 | 2.471
32897486 | 13313430 | 32897486 | 13313430 | کد 593101 ردیف 06 | 1 | دستگاه | نصب انتقال دهنده سطح EXT. DIS. TYPE تا 32 اینچ | 15 | 2.471
141114856 | 57108400 | 35278714 | 14277100 | کد 593101 ردیف 07 | 4 | دستگاه | نصب انتقال دهنده سطح EXT. DIS. TYPE از 32 تا 72 اینچ | 16 | 2.471
117075954 | 47379990 | 39025318 | 15793330 | کد 593101 ردیف 08 | 3 | دستگاه | نصب انتقال دهنده سطح EXT. DIS. TYPE بزرگتر از 72 اینچ | 17 | 2.471
88940286 | 35993640 | 14823381 | 5998940 | کد 593101 ردیف 02 | 6 | دستگاه | DIFF. PRESSURE TYPE نصب انتقال دهنده سطح | 18 | 2.471
1204711848 | 487540200 | 8729796 | 3532900 | کد 593111 ردیف 03 | 138 | دستگاه | نصب نمایشگر فشار | 19 | 2.471
261893880 | 105987000 | 8729796 | 3532900 | کد 593111 ردیف 03 | 30 | دستگاه | نصب نمایشگر اختلاف فشار | 20 | 2.471
1225078124 | 495782320 | 13032746 | 5274280 | کد 593102 ردیف 04 | 94 | دستگاه | نصب سوییچ فشار | 21 | 2.471
1141400337 | 461918380 | 14823381 | 5998940 | کد 593101 ردیف 02 | 77 | دستگاه | نصب انتقال دهنده فشار | 22 | 2.471
251997477 | 101981980 | 14823381 | 5998940 | کد 593101 ردیف 02 | 17 | دستگاه | نصب انتقال دهنده اختلاف فشار | 23 | 2.471
548465097 | 221960780 | 14823381 | 5998940 | کد 593101 ردیف 02 | 37 | دستگاه | نصب انتقال دهنده دما | 24 | 2.471
104261968 | 42194240 | 13032746 | 5274280 | کد 593102 ردیف 04 | 8 | دستگاه | نصب سوییچ دما | 25 | 2.471
514973417 | 208406880 | 8728363 | 3532320 | کد 593111 ردیف 07 | 59 | دستگاه | نصب نمایشگر دما (BIMETAL) | 26 | 2.471
559415584 | 226392400 | 5378996 | 2176850 | کد 593104 ردیف 06 | 104 | دستگاه | نصب THERMOWELL - طول بیشتر از 60 سانتی متر | 27 | 2.471
382495674 | 154793880 | 13189506 | 5337720 | کد 593114 ردیف 1 | 29 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر کنترل سایز تا 4" | 28 | 2.471
132903153 | 53785170 | 14767017 | 5976130 | کد 593114 ردیف 2 | 9 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر کنترل سایز از 4" تا 8" | 29 | 2.471
47691165 | 19300350 | 15897055 | 6433450 | کد 593114 ردیف 3 | 3 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر کنترل سایز از 4" تا 8" | 30 | 2.471
43104272 | 17444060 | 21552136 | 8722030 | کد 593114 ردیف 4 | 2 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر کنترل سایز از 12" تا 20" | 31 | 2.471
115394710 | 46699600 | 11539471 | 4669960 | کد 593116 ردیف 1 | 10 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر قطع و وصل سایز تا 4" | 32 | 2.471
104936056 | 42467040 | 13117007 | 5308380 | کد 593116 ردیف 2 | 8 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر قطع و وصل سایز از 4" تا 8" | 33 | 2.471
341928480 | 138376560 | 14247020 | 5765690 | کد 593116 ردیف 3 | 24 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر قطع و وصل سایز از 8" تا 12" | 34 | 2.471
79608504 | 32217120 | 19902126 | 8054280 | کد 593116 ردیف 4 | 4 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر قطع و وصل سایز از 12" تا 20" | 35 | 2.471
321117580 | 129954510 | 11073020 | 4481190 | کد 593117 ردیف 1 | 29 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیراطمینان سایز تا 4" | 36 | 2.471
131930640 | 53391600 | 13193064 | 5339160 | کد 593117 ردیف 2 | 10 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیراطمینان سایز از 4" تا 8" | 37 | 2.471
1423366650 | 576028000 | 194715 | 78800 | کد 593171- ردیف 1-ستون 1 | 7310 | متر | کابل کشی و اتصالات- خواباندن کابلها-زیر زمینی و ...-کابل سیگنال-2~10 core | 38 | 2.471
3571745220 | 1445462400 | 205983 | 83360 | کد 593171- ردیف 2-ستون 1 | 17340 | متر | کابل کشی و اتصالات- خواباندن کابلها-زیر زمینی و ...-کابل سیگنال-12~20 core | 39 | 2.471
226207440 | 91545000 | 221772 | 89750 | کد 593171- ردیف 3-ستون 1 | 1020 | متر | کابل کشی و اتصالات- خواباندن کابلها-زیر زمینی و ...-کابل سیگنال-22~30 core | 40 | 2.471
2080387920 | 841921600 | 235338 | 95240 | کد 593171- ردیف 4-ستون 1 | 8840 | متر | کابل کشی و اتصالات- خواباندن کابلها-زیر زمینی و ...-کابل سیگنال-32~40 core | 41 | 2.471
2171060820 | 878614400 | 205983 | 83360 | کد 593173- ردیف 1-ستون 1 | 10540 | متر | کابل کشی و اتصالات- خواباندن کابلها-زیر زمینی و ...-کابل سیستم اعلان خطر-S<16 mm2 | 42 | 2.471
5502857670 | 2226976200 | 211567 | 85620 | کد 593174- ردیف 1-ستون 1 | 26010 | متر | کابل کشی و اتصالات- خواباندن کابلها-سینی و ...-کابل سیگنال-2~10 core | 43 | 2.471
3308523000 | 1338938700 | 223700 | 90530 | کد 593176- ردیف 1-ستون 1 | 14790 | متر | کابل کشی و اتصالات- خواباندن کابلها-سینی و ...-کابل سیستم اعلان خطر-S<16 mm2 | 44 | 2.471
521803440 | 211170600 | 170524 | 69010 | کد 593176- ردیف 1-ستون 2 | 3060 | متر | کابل کشی و اتصالات- خواباندن کابلها-سینی و ...-کابل سیستم اعلان خطر-S<16 mm2 | 45 | 2.471
1158387310 | 468793700 | 234967 | 95090 | کد 593183- ردیف 1-ستون 1 | 4930 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیگنال-2~4 core | 46 | 2.471
1401084580 | 567011200 | 588691 | 238240 | کد 593183- ردیف 2-ستون 1 | 2380 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیگنال-5~10 core | 47 | 2.471
14752698600 | 5970335400 | 850790 | 344310 | کد 593183- ردیف 3-ستون 1 | 17340 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیگنال-12~20 core | 48 | 2.471
1149462480 | 465181200 | 1126924 | 456060 | کد 593183- ردیف 4-ستون 1 | 1020 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیگنال-22~30 core | 49 | 2.471
12952403360 | 5241766400 | 1465204 | 592960 | کد 593183- ردیف 5-ستون 1 | 8840 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیگنال-32~40 core | 50 | 2.471
1116483160 | 451834500 | 505196 | 204450 | کد 593183- ردیف 1-ستون 3 | 2210 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیستم اعلان خطر-2~4 core | 51 | 2.471
6482370300 | 2623378800 | 1815790 | 734840 | کد 593183- ردیف 3-ستون 3 | 3570 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیستم اعلان خطر-12~20 core | 52 | 2.471
11439093960 | 4629338000 | 2403171 | 972550 | کد 593183- ردیف 4-ستون 3 | 4760 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیستم اعلان خطر-22~30 core | 53 | 2.471
5736791610 | 2321652600 | 220561 | 89260 | کد 593184- ردیف 1-ستون 1 | 26010 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار-سیگنال-2~4 core | 54 | 2.471
7009543020 | 2836722000 | 473938 | 191800 | کد 593184- ردیف 1-ستون 3 | 14790 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار-سیستم اعلان خطر-2~4 core | 55 | 2.471
1215168840 | 491772600 | 397114 | 160710 | کد 593185- ردیف 1-ستون 3 | 3060 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-بدون زره-سیستم اعلان خطر-2~4 core | 56 | 2.471
3962780325 | 1603715400 | 740015 | 299480 | کد 593191- ردیف 1-ستون 1 | 5355 | متر | مسیرهای عبور کابل-سینی ها-W<=10cm-STRAIGHT | 57 | 2.471
1068940416 | 432594240 | 1964964 | 795210 | کد 593191- ردیف 1-ستون 2 | 544 | متر | مسیرهای عبور کابل-سینی ها-W<=10cm-TEE | 58 | 2.471
1131711352 | 457998360 | 191848 | 77640 | کد 593191- ردیف 1-ستون 3 | 5899 | متر | مسیرهای عبور کابل-سینی ها-W<=10cm-COVER | 59 | 2.471
2009581560 | 813266400 | 985089 | 398660 | کد 593191- ردیف 2-ستون 1 | 2040 | متر | مسیرهای عبور کابل-سینی ها-W<=30cm , W>10-STRAIGHT | 60 | 2.471
601770420 | 243533160 | 2949855 | 1193790 | کد 593191- ردیف 2-ستون 2 | 204 | متر | مسیرهای عبور کابل-سینی ها-W<=30cm , W>10-TEE | 61 | 2.471
539520432 | 218341200 | 240428 | 97300 | کد 593191- ردیف 2-ستون 3 | 2244 | متر | مسیرهای عبور کابل-سینی ها-W<=30cm , W>10-COVER | 62 | 2.471
1035722875 | 419151150 | 1107725 | 448290 | کد 593191- ردیف 3-ستون 1 | 935 | متر | مسیرهای عبور کابل-سینی ها-W<=60cm , W>30-STRAIGHT | 63 | 2.471
376518006 | 152374740 | 3691353 | 1493870 | کد 593191- ردیف 3-ستون 2 | 102 | متر | مسیرهای عبور کابل-سینی ها-W<=60cm , W>30-TEE | 64 | 2.471
323557481 | 130941990 | 312013 | 126270 | کد 593191- ردیف 3-ستون 3 | 1037 | متر | مسیرهای عبور کابل-سینی ها-W<=60cm , W>30-COVER | 65 | 2.471
101438490 | 41051600 | 596697 | 241480 | کد 593194- ردیف 12 | 170 | متر | مسیرهای عبور کابل-کاندویت ها-پی وی سی | 66 | 2.471
4663691974 | 1887370260 | 1515662 | 613380 | کد 593182- ردیف 6 | 3077 | عدد | کابل کشی و اتصالات-نصب گلندها-ضد انفجار-فلزی-M20 | 67 | 2.471
412101250 | 166775100 | 4848250 | 1962060 | کد 593182- ردیف 8 | 85 | عدد | کابل کشی و اتصالات-نصب گلندها-ضد انفجار-فلزی-M32 | 68 | 2.471
401796513 | 162604830 | 7878363 | 3188330 | کد 593182- ردیف 9 | 51 | عدد | کابل کشی و اتصالات-نصب گلندها-ضد انفجار-فلزی-M40 | 69 | 2.471
446493440 | 180693425 | 10505728 | 4251610 | کد 593182- ردیف 10 | 42.5 | عدد | کابل کشی و اتصالات-نصب گلندها-ضد انفجار-فلزی-M50 | 70 | 2.471
517709163 | 209513746 | 282238 | 114220 | کد 593125- ردیف 1 | 1834.3 | کیلوگرم | جعبه تقسیم - وزن تا 25 کیلوگرم | 71 | 2.471
7108698852 | 2876851010 | 56507940 | 22868450 | کد 593141- ردیف 2 | 125.8 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-لوله کشی (هوک آپ) ادوات PD - جنس SS | 72 | 2.471
11657107500 | 4717566810 | 40100129 | 16228300 | کد 593142- ردیف 2 | 290.7 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-لوله کشی (هوک آپ) ادوات P - جنس SS | 73 | 2.471
6181493270 | 2501616096 | 21643884 | 8759160 | کد 593143- ردیف 2 | 285.6 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-لوله کشی (هوک آپ) فشار سنج ها - جنس SS | 74 | 2.471
2219736723 | 898315156 | 17644966 | 7140820 | کد 593144- ردیف 1 | 125.8 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-تیوبینگ ها (هوک آپ) ادوات PD - جنس SS | 75 | 2.471
2948810218 | 1193367105 | 10143826 | 4105150 | کد 593145- ردیف 1 | 290.7 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-تیوبینگ ها (هوک آپ) ادوات P - جنس SS | 76 | 2.471
492123327 | 199159590 | 9649477 | 3905090 | کد 593146- ردیف 1 | 51 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-تیوبینگ ها (هوک آپ) فشار سنج ها - جنس SS | 77 | 2.471
11237316356 | 4547679690 | 21392188 | 8657300 | کد 593147- ردیف 2 | 525.3 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-دو راهه-جنس SS | 78 | 2.471
5991286662 | 2424640504 | 33887368 | 13714030 | کد 593148- ردیف 2 | 176.8 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-پنج راهه-جنس SS | 79 | 2.471
1292363392 | 523012480 | 1187834 | 480710 | کد 593153- ردیف 1 | 1088 | متر | شبکه هوای ابزار دقیق-نصب تیوبهای فولاد زنگ نزن | 80 | 2.471
1656611580 | 670422200 | 286611 | 115990 | کد 593201- ردیف 2 | 5780 | کیلوگرم | تجهیزات اتاق کنترل- پنلها - وزن 101 تا 250 کیلو گرم | 81 | 2.471
54699668 | 22136652 | 10725425 | 4340520 | کد 593211- ردیف 1 | 5.1 | دستگاه | تجهیزات اتاق کنترل- سایر ادوات نصب شده | 82 | 2.471
176353784 | 71369400 | 10373752 | 4198200 | کد 593221- ردیف 1 | 17 | دستگاه | تجهیزات جانبی سیستم کنترل | 83 | 2.471
899871060 | 364172820 | 13634410 | 5517770 | کد 593103- ردیف 2 | 66 | دستگاه | ادوات F&G واقع در محوطه - GAS DETECTOR | 84 | 2.471
1519169498 | 614799480 | 12452209 | 5039340 | کد 593103- ردیف 3 | 122 | دستگاه | ادوات F&G واقع در محوطه - HEAT DETECTOR | 85 | 2.471
343990464 | 139211040 | 7166468 | 2900230 | کد 593103- ردیف 5 | 48 | دستگاه | ادوات F&G واقع در محوطه - FLAME DETECTOR (UV/IR) | 86 | 2.471
66517740 | 26919360 | 22172580 | 8973120 | کد 593103- ردیف 7 | 3 | دستگاه | ادوات F&G واقع در محوطه - LINEAR HEAT DETECTOR | 87 | 2.471
409588473 | 165758180 | 5610801 | 2270660 | کد 593103- ردیف 8 | 73 | دستگاه | ادوات F&G واقع در محوطه - MANUAL CALL POINT | 88 | 2.471
334838376 | 135507240 | 9301066 | 3764090 | کد 593103- ردیف 9 | 36 | دستگاه | ادوات F&G واقع در محوطه - BEACON | 89 | 2.471
270738699 | 109566450 | 12892319 | 5217450 | کد 593103- ردیف 10 | 21 | دستگاه | ادوات F&G واقع در محوطه - SIREN | 90 | 2.471
1578874080 | 638961600 | 19735926 | 7987020 | کد 593301- ردیف 1 | 80 | لوپ | عملیات لوپ چک-لوپ حلقه بسته | 91 | 2.471
10416175250 | 4215368500 | 10964395 | 4437230 | کد 593301- ردیف 2 | 950 | لوپ | عملیات لوپ چک-لوپ حلقه باز | 92 | 2.471
186708370490 | 75559842024 | [5 empty] | مجموع

## C.tashilat
جدول 17-1: هزینه تسهیلات کارفرما جهت ماموریت داخل کشور
| هزینه | تعداد | هزینه واحد | شرح
| 12260181691.8489 | 300 | 40867272.3062 | بلیط رفت و برگشت داخلی (با محوریت اهواز)
| 1671842957.9794 | 300 | 5572809.8599 | ترانسفر فرودگاهی
| 16068268429.4686 | 865 | 18576032.8664 | ایاب و ذهاب در سطح شهر واسطه و مقصد
| 24102402644.203 | 865 | 27864049.2997 | اقامت در هتل پنج ستاره در اتاق تک تخته به ازای هر نفر- شب
| 11677500000 | 865 | 13500000 | خورد و خوراک 3 وعده در روز
| 65780195723.4999 |  |  | مجموع
توضیح جدول 1-17 : تعداد تقریبی ماموریتهای داخل کشورپرسنل کارفرما معادل 865 نفر-روز مطابق مدرک شرح خدمات و تسهیلات کارفرما به شرح ذیل: 250 نفر -روز جهت شرکت در جلسات و 255 نفر-روز جهت دوره اموزشی و360 نفر روز برای بازدید از مراحل ساخت کالا در تهران یا سایر نقاط کشور (مبدا : اهواز). هر ماموریت بطور متوسط 3 روز منظور شده است. لذا جمعا 300 سفر و به مدت 865 شب اقامت منظور شده است.
جدول 17 -2: هزینه تسهیلات کارفرما جهت ماموریت خارج کشور
| هزینه | تعداد | هزینه واحد | شرح
| 24000 | 40 | 600 | بلیط رفت و برگشت خارجی و بیمه (متوسط قیمت)
| 2000 | 40 | 50 | ترانسفر فرودگاهی
| 16000 | 160 | 100 | ایاب و ذهاب در سطح شهر واسطه و مقصد
| 19200 | 160 | 120 | اقامت در هتل پنج ستاره در اتاق تک تخته به ازای هر نفر- شب
| 12800 | 160 | 80 | خورد و خوراک 3 وعده در روز
| 6000 | 40 | 150 | هزینه امور کنسولی و ویزا
| 80000 |  | 1100 | مجموع
| 36455341275.3962 |  |  | معادل ریالی
توضیح جدول 2-17 : تعداد تقریبی ماموریتهای خارج کشورپرسنل کارفرما مطابق مدرک شرح خدمات و تسهیلات کارفرما معادل است با: 120 نفر شرکت در مراحل ساخت و 40 نفر-روز جهت حضور احتمالی در آزمایشات هر ماموریت بطور متوسط 4 روز منظور شده است. لذا جمعا 40 سفر و به مدت 160 شب اقامت منظور شده است.
جدول 17-3: - هزینه آموزشی عملیاتی (اپراتوری) به میزان 192 نفر-روز
| هزینه | تعداد | هزینه واحد | شرح
| 2592000000 | 192 | 13500000 | خورد و خوراک 3 وعده در روز در سایت
| 1857603286.6438 | - | یک قلم | امکانات سخت افزاری و نرم افزاری
| 557280985.9931 | - | یک قلم | تدارک مواد آموزشی شامل تکثیر جزوه و کتاب
| 2786404929.9657 | - | یک قلم | برگزاری دوره نقشه برداری
| 7793289202.6026 |  |  | مجموع
مرجع : مدرک شرح خدمات و تسهیلات مورد نیاز کارفرما به شماره M9003-BD-GN-OTH-26010

## C.tashilat (2)
جدول 17-4: هزینه تسهیلات کارفرما مربوط به احداث کمپهای دستگاه نظارت کلیه بندهای اشاره شده در ذیل مربوط به مدرک "مشخصات فنی کمپهای دستگاه نظارت به شماره M9003-BD-GN-OTH-26011میباشد
هزینه (ریال) | توضیحات | شرح
283023180000 | به مساحت 900 متر با هزینه محاسبه شده برای احداث ساختمان | کمپ اصلی استقرار کارفرما مطابق مشخصات منرج در بند 4
190080000000 | توضیح : طبق استعلام مشخصات درخواستی | کمپ فرعی استقرار کارفرمامندرج در بند 5.1
189241272000 | حراست فيزيكي و سيستم دوربين مدار بسته، روشنايي، فضاي سبز | محوطه سازی کمپ اصلی و فرعی مطابق مشخصات منرج در بند 4.2و5.2
20062115495.7528 | یک نفر آبدارچی به صورت شبانه‌روزی. یک نفر آشپز بصورت روزانه. یک نفر نظافتچی به صورت روزانه. یک نفر نگهبان به صورت شبانه روزی | تامین نیروی خدماتی برای طول مدت پروژه مطابق بند 6.1
291600000000 | سه وعده غذاي گرم، میوه فصل، دسر ، آب معدنی ، نوشیدنی و غیره در روز به طور ميانگين براي 20 نفر نمایندگان کارفرما در طي زمان قرارداد در تمام روزها | تهيه و تأمين و سرو خورد و خوراک کادر نظارت کارفرما مطابق بند6.3
18576032866.4377 | پذیرایی سرد/گرم | پذیرایی از شرکت کنندگان جلسات کارفرما
14860826293.1502 | تجهيزات لازم و متعارف براي پرسنل کادر نظارت | تجهیز دفاتر کار، سالنها و اتاقهاي خواب مطابق بند 6.5
3715206573.2875 |  | سيستم اعلان حريق خودكار
4644008216.6094 | شامل كپسول آبي و پودري و گازي و غيره | تجهیزات ایمنی و آتش‌نشانی به تعداد كافي
2229123943.9725 |  | جعبه كمكهاي اوليه .
7653325540.9723 | (کولرهاي گازي نو تركيبي از پنجره اي و دو تكه، بخاري از نوع رادياتور روغني برقي. سه دستگاه آبگرمكن برقي با مخزن 200 ليتري ) | تجهيزات سرمايشي و گرمايشي در كليه فضاها مطابق بند 7.4
7801933803.9038 | ( مبلمان دفتری و مبلمان پذيرايي، کابینت نگهداری نقشه ها و مدارک پروژه، کابینت پرونده و كابينت بايگاني به تعداد كافي، نوشت‌افزار و غيره.) | لوازم و تجهيزات اداري مطابق بند5، 6 و 7.6
10402578405.2051 | (تلويزيون رنگي 48 اينچ از نوع LEDبه تعداد 2 دستگاه، تلويزيون رنگي 32 اينچ از نوع LED به تعداد 8 دستگاه، يخچال كوچك در هر اتاق خواب، مبلمان نشيمن، خواب و راحتي و مطالعه.) | لوازم و تجهيزات رفاهي: مطابق بند 7.7 | 2 | 0
6315851174.5888 | يخچال، اجاق و فر گاز، مايكروفر، ماشين لباسشويي، میز و لوازم غذاخوري،تجهيزات آبدارخانه، كابينت‌بندي و تجهيزات و ظروف آشپزخانه، فريزر، كباب‌پز، هود، اگزوزفن، دستگاه تصفيه آب جهت آشپزخانه و غيره | . لوازم و تجهيزات آشپزخانه مطابق بند 7.8:
46440082166.0943 | هفت دستگاه كامپيوتر روميزي كامل با لوازم جانبي؛ چهار دستگاه چاپگر ليزري، سه دستگاه چاپگر ليزري رنگي؛ چهار دستگاه نمابر؛ چهار دستگاه كپي؛ چهار دستگاه اسكنر؛ پنج دستگاه كامپيوتر لپ‌تاپ؛ سه خط تلفن ثابت؛ گوشي تلفن سيار | . لوازم و تجهيزات كامپيوتري مطابق بند 7.9
6687371831.9176 | كمپ اصلي و كمپ فرعي | 7.10. لوازم و تجهيزات ورزشي متناسب با فضاهاي پيش‌بيني‌شده
54000000000 | سه دستگاه خودرو شاسي استيشن | وسيله اياب و ذهاب
9094825691.4079 | آب و برق و گاز و خطوط تلفن و اشتراك اينترنت در كمپهاي كارفرما | تأمين و پرداخت كليه هزينه‌هاي انشعاب و هزينه جاري
928801643.3219 | به تعداد مورد نیاز کارفرما | تکثیر نسخ نرم و سخت و اسکن اسناد قرارداد
7430413146.5751 | به ظرفيت 5 متر مكعب در روز | بسته تصفيه فاضلاب بهداشتي
1.1748e+12 |  | مجموع

## C.HSE(1)
جدول 18-1: براورد هزینه ایمنی کارگاه : لوازم حفاظت فردی و تجهیزات
بهای کل (ریال) |  | تعداد کل | بهای واحد (ریال) |  | زمان کل پروژه(ماه) | زمان استفاده در هر دوره (ماه) | تعداد | شرح | ردیف |  | بهای واحد (ریال)Min | بهای واحد (ریال)Max | فاکتور
13374743663.8352 |  | 2400 | 5572809.8599 |  | 36 | 3 | 200 | لباس کار | 1 | 12 | 220000 | 380000 | 4900000
3450000000 |  | 300 | 11500000 |  | 36 | 6 | 50 | لباس جوشکار و تجهیزات مربوطه | 2 | 6 | 500000 | 500000 | 11500000
380000000 |  | 40 | 9500000 |  | 36 | 42 | 40 | لباس سند بلاست کار و تجهیزات مربوطه | 3 | 1 | 4800000 | 31500000 | 9500000
9055816022.3884 |  | 1500 | 6037210.6816 |  | 36 | 6 | 250 | کفش ایمنی | 4 | 6 | 270000 | 380000 | 4500000
438858776.4696 |  | 35 | 12538822.1848 |  | 36 | 42 | 35 | کمربند ایمنی | 5 | 1 | 200000 | 1150000 | 9000000
1597538826.5136 |  | 400 | 3993847.0663 |  | 36 | 21 | 200 | کلاه ایمنی | 6 | 2 | 50000 | 380000 | 1500000
12037269297.4517 |  | 14400 | 835921.479 |  | 36 | 0.5 | 200 | دستکش کارگر ساده | 7 | 72 | 30000 | 60000 | 390000
1203726929.7452 |  | 1080 | 1114561.972 |  | 36 | 1 | 30 | دستکش ورق کار | 8 | 36 | 60000 | 60000 | 9500000
1755435105.8784 |  | 540 | 3250805.7516 |  | 36 | 2 | 30 | دستکش مواد شیمیایی | 9 | 18 | 130000 | 220000 | 2500000
11368532114.2599 |  | 360 | 31579255.8729 |  | 36 | 3 | 30 | دستکش برق کار | 10 | 12 | 1100000 | 2300000 | 1800000
6419876958.6409 |  | 14400 | 445824.7888 |  | 36 | 0.5 | 200 | ماسک گرد و غبار استاندارد فیلتر دار | 11 | 72 | 10000 | 38000 | 1800000
2061939648.1746 |  | 300 | 6873132.1606 |  | 36 | 6 | 50 | ماسک فیلتردار جهت رنگ آمیزی مخازن | 12 | 6 | 90000 | 650000 | 8000000
23127160.9187 |  | 3 | 7709053.6396 |  | 36 | 42 | 3 | زنگ اعلام شرایط اضطراری | 13 | 1 | 280000 | 550000
3260093768.0598 |  | 3600 | 905581.6022 |  | 36 | 1 | 100 | علائم و تابلوهای هشدار دهنده ایمنی و آموزشی | 14 | 36 | 2500 | 95000
777406975.4604 |  | 90 | 8637855.2829 |  | 36 | 6 | 15 | لباس کار،کلاه و چکمه برای کارکنان آشپزخانه و آبدارخانه ها | 15 | 6 | 380000 | 550000
4988779386.6105 |  | 288 | 17322150.648 |  | 36 | 1 | 8 | جعبه کمکهای اولیه با تجهیزات کامل | 16 | 36 | 65000 | 1800000
16254028.7581 |  | مقطوع | 1625402.8758 |  | 36 | 1 |  | نوار محدوده خطر | 17 | 36 | 75000 | 100000
3371549965.2584 |  | 60 | 56192499.421 |  | 36 | 42 | 60 | کپسول اطفاء حریق 12Kg (نوعC) (مربوط به دوران شروع تا پایان پروژه) | 18 | 1 | 2750000 | 3300000
157896279.3647 |  | 10 | 15789627.9365 |  | 36 | 42 | 10 | کپسول اطفاء حریق 12Kg (نوعB) (مربوط به دوران شروع تا پایان پروژه) | 19 | 1 | 850000 | 850000
26006446.013 |  | 2 | 13003223.0065 |  | 36 | 42 | برای کلیه ی اتاقها و اماکن سرپوشیده | سیستم دودیاب و حسگرهای آن (مربوط به دوران شروع تا پایان پروژه) | 20 | 1 | 700000 | 700000
1588250810.0804 |  | 3 | 529416936.6935 |  | 36 | 42 | برای تمام ساختمانها و کانکس ها | سیتم ارتینگ (مربوط به دوران شروع تا پایان پروژه) زمین شن زار | 21 | 1 | 28500000 | 28500000
2786404929.9657 |  | 6 | 464400821.6609 |  | 36 | 42 | برای 6 ساختمان | صاعقه گیر (مربوط به دوران شروع تا پایان پروژه) | 22 | 1 | 25000000 | 25000000
80139507093.8472 | [7 empty] | مجموع | 23
جدول 18 -2: براورد هزینه ایمنی کارگاه : نیروی انسانی
| جمع (ریال) |  | زمان کل پروژه(ماه) | مقدار حقوق ماهیانه(ریال) |  |  | واحد / نفر | عنوان | ردیف
| 13500000000 |  | 30 | 450000000 |  |  | 1 | کارشناس HSE جهت سایت ویزیتو نظارت برانجام ایمن کارها | 1
| 13500000000 |  | 30 | 450000000 |  |  | 1 | کارشناس IMS جهت مستندسازی فرآیندهای مربوطه و کارهای داکیومنتی | 2
| 27000000000 | [6 empty] | مجموع | 3

## C.HSE(2)
جدول 18-3 - براورد هزینه ایمنی کارگاه : سنجش و اندازه گیری (1) - اندازه گیری آلاینده های فیزیکی،شیمیایی و ارگونومی در محیط کار
بهای کل ریال | تعداد دفعات اندازه گیری در هر سال | کل زمان پروژه |  | بهای اندازه گیری در هر دوره |  |  | عنوان | ردیف
16718429.5798 | 30 | 36ماه |  | 185760.3287 |  |  | نور | 1
208980369.7474 | 30 | 36ماه |  | 2322004.1083 |  |  | صدا(اکتاو،دزیمتری،محیط کار) | 2
417960739.4948 | 10 | 36ماه |  | 13932024.6498 |  |  | هوا | 3
167184295.7979 | 10 | 36ماه |  | 5572809.8599 |  |  | سنجش غبار زیست محیطی | 4
178329915.5178 | 10 | 36ماه |  | 5944330.5173 |  |  | سنجش گازهای محیط کار | 5
167184295.7979 | 30 | 36ماه |  | 1857603.2866 |  |  | ارتعاش | 6
25077644.3697 | 10 | 36ماه |  | 835921.479 |  |  | استرس گرمایی | 7
75232933.1091 | 30 | 36ماه |  | 835921.479 |  |  | اشعهX,UV,IR | 8
334368591.5959 | 20 | 36ماه |  | 5572809.8599 |  |  | گرد و غبار | 9
585145035.2928 | 30 | 36ماه |  | 6501611.5033 |  |  | فیوم جوشکاری | 10
334368591.5959 | 30 | 36ماه |  | 3715206.5733 |  |  | گازهای خروجی ماشین آلات | 11
317650162.0161 | 3 | 36ماه |  | 35294462.4462 |  |  | آب آشامیدنی | 12
30650454.2296 | 3 | 36ماه |  | 10216818.0765 |  |  | کارشناسی | 13
2858851458.1448 | [6 empty] | مجموع | 14
جدول 18-4: براورد هزینه ایمنی کارگاه : سنجش و اندازه گیری (2)
بهای کل(ریال) | دفعات انجام آزمایش در کل پروژه | کل زمان پروژه | بهای انجام آزمایشات برای هر نفر(ریال) |  |  | تعداد نفرات | عنوان | ردیف
81900000 | 3 | 36 | 9100000 |  |  | 3 | انجام آزمایشات دوره ای طب صنعتی برای پرسنل آبدارخانه و آشپزخانه | 1
جدول 18-5: براورد هزینه ایمنی کارگاه : آموزش
بهای کل (ریال) | بهای دوره (ریال) | زمان دوره(روز) | تعداد دوره در کل زمان پروژه | زمان کل پروژه (سال) | زمان استفاده در هر دوره (ماه) | تعداد دوره در سال | سرفصل دوره ها | ردیف
445824788.7945 | 222912394.3973 | 1 | 2 | 3 | 18 | 2 | MSDS کار با مواد شیمیایی و | 1
668737183.1918 | 222912394.3973 | 1 | 3 | 3 | 12 | 2 | ایمنی داربستها،کار در ارتفاع،بالابرها،جرثقیل و لیفتراکها | 2
222912394.3973 | 222912394.3973 | 1 | 1 | 3 | 36 | 2 | ایمنی برق و برق صنعتی،صاعقه و رعد و برق و سیستمهای ارتینگ | 3
668737183.1918 | 222912394.3973 | 1 | 3 | 3 | 12 | 3 | آتش نشانی و اطفاء حریق | 4
185760328.6644 | 185760328.6644 | 1 | 1 | 3 | 36 | 1 | آشنایی با استانداردهای Iso9001و TS29001 | 5
185760328.6644 | 185760328.6644 | 1 | 1 | 3 | 36 | 1 | آشنایی با استانداردهای Iso 14001 | 6
185760328.6644 | 185760328.6644 | 1 | 1 | 3 | 36 | 2 | آشنایی باOHSAS18001 | 7
371520657.3288 | 185760328.6644 | 1 | 2 | 3 | 18 | 2 | کنترل عملیاتHSE،IMS و پرمیتها | 8
668737183.1918 | 222912394.3973 | 1 | 3 | 3 | 12 | 1 | ایمنی کار با پرتوها و اشعه ها | 9
557280985.9931 | 185760328.6644 | 1 | 3 | 3 | 12 | 3 | اورژانس ،کمکهای اولیه و ارگونومی و مدیریت بحران | 10
668737183.1918 | 222912394.3973 | 1 | 3 | 3 | 12 | 2 | ایمنی جوشکاری، برشکاری و عملیات سند بلاست | 11
222912394.3973 | 222912394.3973 | 1 | 1 | 3 | 36 | 2 | انبارداری و رعایت اصول مربوطه | 12
5052680939.6711 | [6 empty] | مجموع | 13
ردیف
1

## C.Foundation-1
جدول الف : ریز برآورد متره فونداسیون تجهیزات
| حجم خاکبرداري | حجم خاکریزی | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد | کوبیدن خاک | ASPHALT | Geotextile | Geomembrane
فونداسیون های تجهیزات | متر مکعب | متر مکعب | متر مربع | متر مکعب | متر مکعب | کيلو گرم | متر مکعب | متر مربع | متر مربع | متر مربع
FOUNDATION OF OFF-SPEC TANK | 1960 | 1480 | 340 | 100 | 320 | 50000 | 1480 | 1000 | 1340 | 1340
FOUNDATION OF DILUTION WATER TANK | 480 | 100 | 100 | 40 | 240 | 18000 |  | 160 | 280 | 280
FOUNDATION OF POTABLE WATER TANK | 90 | 40 | 100 | 5 | 80 | 5800
FOUNDATION OF DISPOSAL TANK | 360 | 300 | 260 | 20 | 240 | 20000 | 200 | 20 | 280 | 280
FOUNDATION OF DIRTY OILTANK | 90 |  | 50 | 120 | 20 | 3600 |  | 20 | 60 | 60
FOUNDATION OF FIRE WATER STORAGE TANK | 1080 | 200 | 240 | 80 | 500 | 52400 | 180 | 50
FOUNDATION OF SKIMMER TANK | 720 | 560 | 480 | 40 | 480 | 40000 | 400 | 160 | 280 | 280
FOUNDATION OF FREE WATER K.O DRUM | 1500 | 700 | 900 | 100 | 0 | 76000 | 60
FOUNDATION OF FUEL GAS K.O. DRUM | 64 | 8 |  | 2 | 50 | 600
FOUNDATION OF AIR RECIEVER | 30 | 16 | 15 | 3 | 20 | 1500
FOUNDATION OF FLARE K.O. DRUM | 28 |  | 44 | 3 | 20 | 2600
FOUNDATION OF HC CLOSED DRAIN DRUM | 16 |  | 26 | 2 | 12 | 1800
FOUNDATION OF DIESEL oil STORAGE TANK | 80 | 34 | 30 | 30 | 5 | 3600
FOUNDATION OF DESALTER FOUNDATION | 900 | 500 | 400 | 40 | 500 | 38000 | 100
FOUNDATION OF HEATERS FOUNDATION | 380 | 160 | 280 | 32 | 280 | 18000 | 100
FOUNDATION OF EXCHANGER FOUNDATION | 24 |  | 36 | 4 | 24 | 2400
FOUNDATION OF DEARATOR FOUNDATION | 38 | 18 | 70 | 26 | 42 | 2140 | 20
FOUNDATION OF IGF FOUNDATION | 240 | 120 | 840 | 30 | 80 | 5600 | 40
FOUNDATION OF NUTSHELL FILTER | 110 | 20 | 84 | 12 | 60 | 5200 | 20
FOUNDATION OF COLD FLARE | 32 | 4 |  | 2 | 30 | 500
FOUNDATION OF HOT FLARE | 28 | 4 |  | 2 | 30 | 440
FOUNDATION OF COMPRESSOR (4no.) | 12 |  | 20 | 4 | 20 | 800
FOUNDATION OF PROCESS PUMPS (~ 40NO.) | 960 | 120 |  | 60 | 900 | 15000 | 80
FOUNDATION OF FIREWATER PUMP(5 no.) | 50 |  | 80 | 12 | 36 | 3400
FOUNDATION OF AIR DRYER | 64 | 8 |  | 2 | 50 | 600
FOUNDATION OF DIESEL GENERATOR | 288 | 80 | 46 | 4.8 | 40 | 3500
FOUNDATION OF INJECTION PACKAGE (9 NO.) | 40 |  | 60 | 20 | 70 | 5160
TOTAL : | 9664 | 4472 | 4501 | 795.8 | 4149 | 376640 | 2680 | 1410 | 2240 | 2240

## C.Shelters-1
جدول ب-1 : ریز برآورد متره سایبانها - فونداسیون و کف سازی
مشخصات سایبان |  | فونداسیون | [7 empty] | کف سازی
شرح سایبان | متراژ | حجم خاکبرداري | حجم خاکریزی | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد | کوبیدن خاک | انکربولت | بلوکاژ (30سانتیمتر) | بتن با عيار150 | بتن با عيار300 | ميلگرد | درزبندی کف
| متر مربع | متر مکعب | متر مکعب | متر مربع | متر مکعب | متر مکعب | کيلو گرم | متر مکعب | کیلو گرم | متر مکعب | متر مکعب | متر مکعب | کيلو گرم | دسی متر مکعب
احداث سایبان پمپ 1 نمکزدایی (ناحیه 8) | 600 | 1010 | 600 | 240 | 90 | 140 | 6500 | 300 | 250 | 180 | 30 | 90 | 3000 | 720 | 10
احداث سایبان پمپ 2 نمکزدایی (ناحیه 9) | 180 | 303 | 180 | 72 | 27 | 42 | 1950 | 90 | 75 | 54 | 9 | 27 | 900 | 216 | 3
احداث سایبان پمپ 3 نمکزدایی (ناحیه 5) | 90 | 151.5 | 90 | 36 | 13.5 | 21 | 975 | 45 | 37.5 | 27 | 4.5 | 13.5 | 450 | 108 | 1.5
احداث سایبان پمپ 4 نمکزدایی (ناحیه 4) | 240 | 404 | 240 | 96 | 36 | 56 | 2600 | 120 | 100 | 72 | 12 | 36 | 1200 | 288 | 4
احداث سایبان پمپ 5 نمکزدایی (ناحیه 1) | 60 | 101 | 60 | 24 | 9 | 14 | 650 | 30 | 25 | 18 | 3 | 9 | 300 | 72 | 1
احداث سایبان پمپ آب آتش نشانی | 420 | 707 | 420 | 168 | 63 | 98 | 4550 | 210 | 175 | 126 | 21 | 63 | 2100 | 504 | 7
احداث سایبان پمپ بهره برداری | 425 | 808 | 480 | 192 | 72 | 112 | 5200 | 240 | 200 | 127.5 | 21.25 | 63.75 | 2125 | 576 | 8
احداث سایبان پکیج تزریق 1 نمکزدایی | 240 | 505 | 300 | 120 | 45 | 70 | 3250 | 150 | 125 | 72 | 12 | 36 | 1200 | 360 | 5
احداث سایبان پکیج تزریق 2 نمکزدایی | 180 | 303 | 180 | 72 | 27 | 42 | 1950 | 90 | 75 | 54 | 9 | 27 | 900 | 216 | 3
احداث انبار مواد1 شیمیایی | 250 | 505 | 300 | 120 | 45 | 70 | 3250 | 150 | 125 | 75 | 12.5 | 37.5 | 1250 | 360 | 5
احداث انبار مواد2 شیمیایی | 150 | 303 | 180 | 72 | 27 | 42 | 1950 | 90 | 75 | 45 | 7.5 | 22.5 | 750 | 216 | 3
توسعه سایبان پکیج تزریق بهره داری | 36 | 101 | 60 | 24 | 9 | 14 | 650 | 30 | 25 | 10.8 | 1.8 | 5.4 | 180 | 72 | 1
احداث انبار مواد شیمیایی بهره برداری گچساران-4 | 90 | 101 | 60 | 24 | 9 | 14 | 650 | 30 | 25 | 27 | 4.5 | 13.5 | 450 | 72 | 1
احداث پارکینگ | 310 | 505 | 300 | 120 | 45 | 70 | 3250 | 150 | 125 | 93 | 15.5 | 46.5 | 1550 | 360 | 5
احداث پارکینگ پست برق 33 کیلولت | 70 | 202 | 120 | 48 | 18 | 28 | 1300 | 60 | 50 | 21 | 3.5 | 10.5 | 350 | 144 | 2
احداث سایبان آتش نشانی (13 عدد) | 120 | 202 | 120 | 48 | 18 | 28 | 1300 | 60 | 50 | 36 | 6 | 18 | 600 | 144 | 2
مجموع |  | 6211.5 | 3690 | 1476 | 553.5 | 861 | 39975 | 1845 | 1537.5 | 1038.3 | 173.05 | 519.15 | 17305 | 4428
میزان واحد |  | 101 | 60 | 24 | 9 | 14 | 650 | 30 | 25 | 0.3 | 0.5 | 0.15 | 5 | 72

## C.Shelters-1 (2)
جدول ب-2 : ریز برآورد متره سایبانها - لسکلت فلزی
مشخصات سایبان |  | سازه فلزی
شرح سایبان | متراژ | ستون | سازه سقف | Girt | Strut | Purlin | پوشش سقف | سطح رنگ خور
| متر مربع | کیلو گرم | کیلو گرم | کیلو گرم | کیلو گرم | کیلو گرم | کیلو گرم | متر مربع
احداث سایبان پمپ 1 نمکزدایی (ناحیه 8) | 600 | 20574 | 23622 | 15240 | 7620 | 9144 | 9000 | 1680
احداث سایبان پمپ 2 نمکزدایی (ناحیه 9) | 180 | 6172.2 | 7086.6 | 4572 | 2286 | 2743.2 | 2700 | 504
احداث سایبان پمپ 3 نمکزدایی (ناحیه 5) | 90 | 3086.1 | 3543.3 | 2286 | 1143 | 1371.6 | 1350 | 252
احداث سایبان پمپ 4 نمکزدایی (ناحیه 4) | 240 | 8229.6 | 9448.8 | 6096 | 3048 | 3657.6 | 3600 | 672
احداث سایبان پمپ 5 نمکزدایی (ناحیه 1) | 60 | 2057.4 | 2362.2 | 1524 | 762 | 914.4 | 900 | 168
احداث سایبان پمپ آب آتش نشانی | 420 | 14401.8 | 16535.4 | 10668 | 5334 | 6400.8 | 6300 | 1176
احداث سایبان پمپ بهره برداری | 425 | 14573.25 | 16732.25 | 10795 | 5397.5 | 6477 | 6375 | 1190
احداث سایبان پکیج تزریق 1 نمکزدایی | 240 | 8229.6 | 9448.8 | 6096 | 3048 | 3657.6 | 3600 | 672
احداث سایبان پکیج تزریق 2 نمکزدایی | 180 | 6172.2 | 7086.6 | 4572 | 2286 | 2743.2 | 2700 | 504
احداث انبار مواد1 شیمیایی | 250 | 8572.5 | 9842.5 | 6350 | 3175 | 3810 | 3750 | 700
احداث انبار مواد2 شیمیایی | 150 | 5143.5 | 5905.5 | 3810 | 1905 | 2286 | 2250 | 420
توسعه سایبان پکیج تزریق بهره داری | 36 | 1234.44 | 1417.32 | 914.4 | 457.2 | 548.64 | 540 | 100.8
احداث انبار مواد شیمیایی بهره برداری گچساران-4 | 90 | 3086.1 | 3543.3 | 2286 | 1143 | 1371.6 | 1350 | 252
احداث پارکینگ | 310 | 10629.9 | 12204.7 | 7874 | 3937 | 4724.4 | 4650 | 868
احداث پارکینگ پست برق 33 کیلولت | 70 | 2400.3 | 2755.9 | 1778 | 889 | 1066.8 | 1050 | 196
احداث سایبان آتش نشانی (13 عدد) | 120 | 4114.8 | 4724.4 | 3048 | 1524 | 1828.8 | 1800 | 336
مجموع |  | 118677.69 | 136259.57 | 87909.4 | 43954.7 | 52745.64 | 51915 | 9690.8
میزان واحد |  | 34.29 | 39.37 | 25.4 | 12.7 | 15.24 | 15 | 2.8
|  | 0.27 | 0.31 | 0.2 | 0.1 | 0.12

## C.ROAD-1
جدول ج : ریز برآورد متره جاده ها
|  | مساحت | خاکبرداری | زیر اساس | اساس | پریمکت | تک کت | بیندر با لایه 4 cm | توپکا با لایه 4 cm | خاکریزی با تراکم 100% | خاکریزی با تراکم 95% | تونان
ردیف | شرح | متر مربع |  | متر مکعب | متر مکعب | متر مکعب | کیلو گرم | متر مربع | متر مربع | متر مکعب | متر مکعب | متر مکعب
1 | جاده های داخل واحد نمکزدایی | 1900 x 7.5 |  | 3300 | 3300 | 19800 | 7425 | 660 | 495 |  |  |  | 2200 | 7.5 | 16500
2 | جاده های داخل واحد بهره برداری | 210x6 |  | 300 | 300 | 1800 | 675 | 60 | 45 |  |  |  | 250 | 6 | 1500
3 | حاده و محوطه اسفالته پست برق گچساران-3 | 1300 |  | 230 | 230 | 1380 | 517.5 | 46 | 34.5 | [5 empty] | 1150
4 | حاده و محوطه اسفالته پست برق گچساران-4 | 1050 |  | 196 | 196 | 1176 | 441 | 39.2 | 29.4 | [5 empty] | 980
5 | جاده های دسترسی بین واحدهای جانبی | 400x6 |  | 720 | 720 | 4320 | 1620 | 144 | 108 |  |  |  | 600 | 6 | 3600
6 | جاده های دسترسی اصلی به واحد نمکزدایی | 500x6 |  | 986.4 | 986.4 | 5918.4 | 2219.4 | 197.28 | 147.96 |  |  |  | 822 | 6 | 4932
7 | جاده های پاترول | 1500x6 |  | 2400 | 2400 | 14400 | 5400 | 480 | 360 |  |  |  | 2000 | 6 | 12000
8 | جاده های داخلی حوضچه تبخیر | 500x6 |  |  |  | 5040 |  |  | 126 | 840 | 1680 | 840 | 700 | 6 | 4200
9 | جاده های داخلی فلرها | 450 |  |  |  | 360 |  |  | 9 | 60 | 120 | 60 |  |  | 300
10 | جاده های داخلی گودال های سوزا | 300 |  |  |  | 300 |  |  | 7.5 | 50 | 100 | 50 |  |  | 250
11 | احداث جاده خطوط لوله نفت 12" | 12000x6 | 30000 | [7 empty] | 7500 |  | 15000 | 6 | 90000
12 | احداث جاده خطوط لوله پساب | 3200x6 | 6000 | [7 empty] | 2250 |  | 4500 | 6 | 27000
13 | پارکینگ واحد نمکزدایی | 600 |  | 88 | 88 | 528 | 198 | 17.6 | 13.2 | [5 empty] | 440
14 | پارکینگ پست برق گچساران-3 | 200 |  | 40 | 40 | 240 | 90 | 8 | 6 | [5 empty] | 200
15 | مجموع |  | 36000 | 8260.4 | 8260.4 | 55262.4 | 18585.9 | 1652.08 | 1381.56 | 950 | 11650 | 950
توضیح : برای میزان خاکبرداریجاده های خطوط لوله با نظر مشاور ژئوتکنیک، 70% زمین از نوع سخت، 20% از نوع نرم و 10% سنگی در نظر گرفته شده است.
فنس ها
[14 empty] | متراژ بر حسب متر |  | عنوان | ردیف
[13 empty] | 1160 |  |  | فنس واحد نمکزدایی | 1
[13 empty] | 500 |  |  | فنس واحد بهره برداری | 2
[13 empty] | 170 |  |  | فنس پست برق گچساران-3 | 3
[13 empty] | 150 |  |  | فنس پست برق گچساران-4 | 4
[13 empty] | 200 |  |  | فنس واحدهای جانبی | 5
[13 empty] | 700 |  |  | فنس حوضچه تبخیر | 5

## C.OTHERS-1
جدول د : ریز برآورد متره ابنیه متفرقه
| حجم خاکبرداري | حجم خاکریزی | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد | پایه گالوانیزه برای نصب فنس | فنس گالوانیزه برای نصب فنس | Geotextile | Geomembrane (1.5mm) | آجر نسوز
فونداسیون ها | متر مکعب | متر مکعب | متر مربع | متر مکعب | متر مکعب | کیلو گرم | کیلو گرم | کیلو گرم | متر مربع | متر مربع | تن | M2 | M2 | M2
Cable Trench
Culvert
Sump Pit (H/C Drain & KNOCK Out Drain) | 8400 | 500 | 2800 | 100 | 1900 | 86000
Sump Pit (IGF) | 2600 | 900 | 2200 | 200 | 2000 | 64000
Bound Wall | 800 | 300 | 2200 | 320 | 800 | 94000
PIPEWAY | 11400 | 3000 | 0 | 240 | 0 | 0
هزینه ساخت پل دسترسی داخل واحد (6 عدد در نمکزدایی و 1 عدد درحوضچه تبخیر) | 5600 | 0 | 6000 | 140 | 2100 | 159600
هزینه ساخت پل دسترسی خارج واحد (4 عدد) | 3200 | 0 | 3600 | 80 | 1300 | 99000
هزینه ساخت پل ورودی واحد با دهانه حداقل 40 متر | 2200 | 0 | 2800 | 60 | 1000 | 77000
API SEPARATOR | 2400 | 60 | 500 | 16 | 280 | 10400 | 30 |  |  | 180
احداث حوضچه تبخیربا در نظر گرفتن خاکریزهای میانی وپیرامونی وحوضچه آرامش | 290400 | 25000 | 440 | 10 | 220 | 17000 |  |  | 7800 | 7800 |  | 8900 | 1200
BURN PIT | 1200 | 0 | 0 | 120 | 0 | 1600 |  |  | 750 | 750 | 50 |  |  | 240
احداث سه گودال سوزا چاههای 58 و 58 الف | 1800 | 0 | 0 | 360 | 0 | 4800 |  |  | 2250 | 2250 | 150 |  |  | 240
برچیدن سه گودال سوزا چاههای 58 و 58 الف | 4000 | 7000 | 0 | 0 | 0 | 0
فنس واحد نمکزدایی (طول تقریبی 1150متر) | 1290.24 | 0 | 4480 | 161.28 | 1484 | 13257.6326 | 28000 | 16800 |  |  |  | 1120
فنس محوطه فلرها، گودالهای سوز(4 منطقه با طول تقریبی 800 متر) | 921.6 | 0 | 3200 | 115.2 | 1060 | 9469.7376 | 20000 | 12000 |  |  |  | 800
فنس محوطه حوضچه تبخیر(طول تقریبی 700متر) | 806.4 | 0 | 2800 | 100.8 | 927.5 | 8286.0204 | 17500 | 10500 |  |  |  | 700
فنس پیرامونی منطقه نمکزدایی (طول تقریب 960 متر) | 1105.92 | 0 | 3840 | 138.24 | 1272 | 11363.6851 | 24000 | 14400 |  |  |  | 960
فنس محوطه پست های برق 33 کیلو ولت گچساران-3 و 3.45 گچساران-4(جمعاطول تقریبی220 2x متر) | 506.88 | 0 | 1760 | 63.36 | 583 | 5208.3557 | 11000 | 6600 |  |  |  | 440
کارهای متفرقه : کالورتها ، منهولها، چاله شیرها، و غیره | 6000 | 0 | 0 | 60 | 800 | 60000
مجموع | 344631.04 | 36760 | 36620 | 2284.88 | 15726.5 | 720985.4314 | 100530 | 60300 | 10800 | 10980 | 200

## C.SITE-1
جدول ه : ریز برآورد متره محوطه سازی
| حجم خاکبرداری | [6 empty] | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد
| زمین سخت | زمین سنگی | زمین سنگی (با پیکور) | حجم خاکریزی | جدول بندی | شن ریزی
[8 empty] | متر مربع | متر مکعب | متر مکعب | کيلو گرم
فونداسیون ها | متر مکعب | متر مکعب | متر مکعب | متر مکعب | متر مکعب | متر مربع
محوطه سازی واحد نمکزدایی | 498400 | 142400 | 71200 | 110000 | 285 | 20000 | [5 empty] | 712000 | 1424000
محوطه سازی واحد بهره برداری | 0 | 0 | 0 |  | 31.5 | 500 | [5 empty] | 0 | 0
محوطه سازی پست برق گچساران-3 | 17500 | 5000 | 2500 | 2300 | 15 | 400 | [5 empty] | 25000 | 50000
محوطه سازی پست برق گچساران-4 | 3500 | 1000 | 500 | 1200 | 15 | 400 | [5 empty] | 5000 | 10000
محوطه سازی حوضچه تبخیر | 560 | 160 | 80 | [5 empty] | Cut (m3) | Fill (m3) |  | 800 | 1600
محوطه سازی محدوده فلرها | 7000 | 2000 | 1000 | 2000 |  |  |  | Flare-1 | 3940 | 3963 |  | 10000 | 20000
محوطه سازی محدوده گودالهای سوزا | 7000 | 2000 | 1000 | 1500 |  |  |  | Flare-2 | 3496 | 2781 |  | 10000 | 20000
ترانشه تپه مجاور | [7 empty] | Burn pit | 37730 | 0 |  | 0 | 0
کارهای متفرقه : منهولها، چاله شیرها، و غیره | 200 | [6 empty] | Evaporation pond | 175919 | 11 |  | 400 | 800
مجموع | 534160 | 152560 | 76280 | 117000 | 346.5 | 21300 | [5 empty] | 763200
توضیح : با توجه به مشخصات مندرج در مدرک مکانیک خاک و استعلام از مشاور ژئو تکنینک، 30% زمین ، از نوع سنگی و 70% آن از نوع سخت
در نظر گرفته شده است.

## C.UG CIVIL-1
جدول و : ریز برآورد کانال های لوله ها و کابل های دفنی
| حجم خاکبرداری | حجم خاکریزی | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد | ماسه ریزی | بلوکاژ (30سانتیمتر) | درزبندی کف | سنگچین کانال
فونداسیون ها | متر مکعب | متر مکعب | متر مربع | متر مکعب | متر مکعب | کیلو گرم | متر مکعب | متر مکعب | دسی متر مکعب
کانال کابلهای برق و ابزاردقیق | 4600 | 2500 | 500 | 50 | 440 | 13000 | 2100
کانال کابلهای برق ارتباط واحدها دفنی | 2000 | 1200 | 180 | 6 | 40 | 3600 | 800
کانال لوله های زیر زمینی آتش نشانی | 4400 | 2440 | 300 | 12 | 96 | 6000 | 1960
کانال خط لوله زیرزمینی پساب | 800 | 360 | 100 | 6 | 40 | 1600 | 440
کانال کنی خط لوله پساب | 8000 | 3800 | 320 | 12 | 100 | 7000 | 3800 | [5 empty] | 8900 | 1200
روسازی پیاده روهای بتونی |  |  |  | 70 | 270 | 5400 |  | 540 | 450 | [5 empty] | 240
کانال جمع آوری سیلاب بیرون محوطه (طول تقریبی 1000متر و عرض متوسط و عمق یک متر) | 2600 | 400 | [7 empty] | 1000
مجموع | 22400 | 10700 | 1400 | 156 | 986 | 36600 | 9100 | 540 | 450 | 1000 |  | 900
1120
800
700
960

## C.STEEL STRUCTURE-1
جدول ط : ریز برآورد متره سازه های فلزی متفرقه
| حجم خاکبرداري | حجم خاکریزی | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد | ساخت سازه فلزی | نصب سازه فلزی | سطح رنگ خور
فونداسیون ها | متر مکعب | متر مکعب | متر مربع | متر مکعب | متر مکعب | کیلو گرم | تن | تن | متر مربع
STANDPIPES (7 NO.) | 200 | 5 | 250 | 10 | 180 | 3520 | 60 | 60 | 336
ACCESS PLATFORMS(ABOUT 30 NO.) | 80 |  | 320 | 80 | 8 | 10000 | 200 | 200 | 448
ساخت سازه گنتری درایستگاه های برق | 50 |  | 80 | 6 | 44 | 1600 | 4 | 4 | 280
اجرای فونداسیون و نصب پایه های انتقال برق 66 کیلوولت(80 عدد) | 1900 |  | 4400 | 2400 | 80 | 240000 | هزینه ساخت در خرید دیده شده است | 480
اجرای فونداسیون و نصب برجهای روشنایی | 240 |  | 640 | 160 | 8 | 8000 |  | 64
اجرای فونداسیون و نصب پایه های روشنایی | 320 |  | 512 | 256 | 12.8 | 12800 |  | 80
نصب واجرای پلکان دسترسی چاله | 20 |  | 60 | 6 | 30 | 1400 | 4 | 4 | 56
ساپورت خطوط لوله و لوله کشی | 1600 |  | 7200 | 120 | 720 | 117000 | 84 | 84 | 4480
مجموع | 4410 | 5 | 13462 | 3038 | 1082.8 | 394320 | 352 | 976 | 5600

## P.ME
ITEM | TAG. NO. |  | SERVICE | SPECIFICATION | UNIT | Quantity | هزینه واحد بدون ضریب |  |  | هزینه کل بدون ضریب
[7 empty] | خرید |  |  | خرید |  | ترخیص | حمل
[7 empty] | Rls | Dollar | Euro | Rls | Euro | Rls
1 | DE | -001-A/B | 1at TRAIN DESALTER | 536 m3/hr , 19.5 bar D.P. T/T=18000 mm , ID=5300 mm | SET | 1 |  |  | 3500000 |  | 3500000 | 159492118079.8582 | 5572809859.9313
2 | DE | -002-A/B | 2nd TRAIN DESALTER | 537 m3/hr , 19.5 bar D.P. T/T=18000 mm , ID=5300 mm | SET | 1 |  |  | 3500000 |  | 3500000 | 159492118079.8582 | 5572809859.9313
3 | E | -001-A/B | SALTY CRUDE / DESALTED CRUDE HEAT EXCHANGER | COLD = 527 m³/h, HOT = 421 m³/h , D.P.=19.5barg, 5275 kw | No. | 2 | 270680909000 |  | 0 | 541361818000 | 0 | 0 | 2229123943.9725
4 | E | -002-A/B | WATER / WATER HEAT EXCHANGER | COLD = 21 m³/h, HOT = 136.5 m³/h , D.P.=19.5barg, 1250 kw | No. | 2 | 13215061000 |  | 0 | 26430122000 | 0 | 0 | 1486082629.315
5 | H | -001-A1/A2 | CRUDE OIL INDIRECT FIRED HEATER | 245.4 m³/h (each) , D.P.=19.5barg 7155 kw | No. | 2 |  |  | 1494506 |  | 2989012 | 136206815670.318 | 5572809859.9313
6 | H | -001-B1/B2 | CRUDE OIL INDIRECT FIRED HEATER | 245.4 m³/h (each) , D.P.=19.5barg 7155 kw | No. | 2 |  |  | 1494506 |  | 2989012 | 136206815670.318 | 5572809859.9313
7 | TK | -003 | OFF-SPEC TANK | 7363 m³,H=15000mm.D=25000mm | Kg | 216500 | 660000 |  |  | 142890000000 |  |  | 3622326408.9554
8 | P | -001-A/B | MAIN TRANSFER PUMPS | 500m3/hr, 15.2 bar, 216.3 kw | No. | 2 | 175441330000 |  | 0 | 350882660000 | 0 | 0 | 3715206573.2875
9 | P | -002-A/B | AUXILLIARY TRANSFER PUMPS | 250m3/hr, 15.2 bar, 108.1 kw | No. | 2 | 61518388000 |  | 0 | 123036776000 | 0 | 0 | 3715206573.2875
10 | P | -003-A/B | OFF-SPEC PUMPS | 100 m3/hr , 15.5 bar,44.2 kw | No. | 2 | 63796847231.9433 |  | 0 | 127593694463.8866 | 0 | 0 | 3715206573.2875
11 | P | -005-A/B | DEGASSING WATER PUMPS | 30m3/hr, 3bar, 2.7 kw | No. | 2 | 15493520000 |  | 0 | 30987040000 | 0 | 0 | 3715206573.2875
12 | V | -001-A/B | FREE WATER K.O DRUM | 340 m³, L=21250mm, ID=4250mm | Kg | 246000 | 1260000 |  |  | 309960000000 |  |  | 120744213.6318
13 | TK | -101 | DILUTION WATER TANK | 1472 m³,H=12000mm, ID=12500mm | Kg | 62000 | 660000 |  |  | 40920000000 |  |  | 1207442136.3185
14 | P | -103 | DILUTION WATER PUMPS | 40m3/hr , 10.4 bar, 12 kw | No. | 1 | 13215061212.3311 |  | 0 | 13215061212.3311 | 0 | 0 | 1857603286.6438
15 | P | -106-A1/A2 | DILUTION WATER PUMPS | 20 m3/hr, 10.4 bar, 6 kw | No. | 2 | 12531523563.4174 |  | 0 | 25063047126.8349 | 0 | 0 | 1857603286.6438
16 | PK | -101 | VACUUM DEAERATOR PACKAGE | 41 m³/h | No. | 1 | 134429070953.0233 |  | 0 | 134429070953.0233 | 0 | 0 | 362232640.8955
17 | P | -102-A/B | DEAERATED WATER PUMPS | 20m3/hr, 2.4 bar, 1.35 kw | No. | 2 | 6835376489.1368 |  | 0 | 13670752978.2736 | 0 | 0 | 1857603286.6438
18 | P | -105 | DEAERATED WATER PUMPS | 40m3/hr, 2.4 bar, 2.7 kw | No. | 1 | 7746760021.0217 |  | 0 | 7746760021.0217 | 0 | 0 | 1857603286.6438
19 | TK | -102 | POTABLE WATER TANK | 32.6 m³,H=2600mm, D=4000mm | Kg | 25500 | 660000 |  |  | 16830000000 |  |  | 362232640.8955
20 | P | -104 | POTABLE WATER FILLING PUMP | 20m3/hr, 2.5 bar, 1.4 kw | No. | 1 | 5012609000 |  | 0 | 5012609000 | 0 | 0 | 1857603286.6438
21 | P | -201-A/B/C | WATER INJECTION MAIN PUMPS | 73m3/hr (each),36.3 bar, 73.6 kw | No. | 3 | 195947459000 |  | 0 | 587842377000 | 0 | 0 | 3715206573.2875
22 | P | -206-A/B/C | WATER INJECTION BOOSTER PUMPS | 36.5m3/hr (each),36.3 bar, 36.5 kw | No. | 3 | 129872153000 |  | 0 | 389616459000 | 0 | 0 | 3715206573.2875
23 | OS | -201 | OIL SKIMMER TANK | 392.5 m³,H=5000mm, D=10000mm | Kg | 45900 | 660000 |  |  | 30294000000 |  |  | 2414884272.6369
24 | PK | -201-A/B | IGF PACKAGE | 18105 SBPD (each) | SET | 1 |  |  | 3000000 |  | 3000000 | 136707529782.7356 | 5572809859.9313
25 | PK | -202 | NUTSHELL FILTER PACKAGE | 36100 SBPD | SET | 1 |  |  | 1400000 |  | 1400000 | 63796847231.9433 | 5572809859.9313
26 | TK | -201 | DISPOSAL TANK | 942 m³,H=12000mm,D=10000mm | Kg | 40000 | 660000 |  |  | 26400000000 |  |  | 1811163204.4777
27 | V | -301 | FUEL GAS K.O. DRUM | 1.5 m³ , T/T=2810 mm, D=860 mm | Kg | 1000 | 2940000 |  |  | 2940000000 |  |  | 120744213.6318
28 | V | -401 | AIR RECIEVER | 30 m³, T/T=7000mm, ID=2335mm | Kg | 12900 | 906031.4348 |  |  | 11687805508.6895 |  |  | 120744213.6318
29 | PK | -401-A/B | AIR COMPRESSOR PACKAGE | 553 N m³/h, 10barg | No. | 2 | 114467980000 |  | 0 | 228935960000 | 0 |  | 5572809859.9313
30 | PK | -402 | AIR DRYER PACKAGE | 453 N m³/h | No. | 1 | 4485276000 |  | 0 | 4485276000 | 0 |  | 5572809859.9313
31 | PK | -002-A/B | AIR COMPRESSOR PACKAGE | 300 N m³/h, 10barg | No. | 2 | 91107168000 |  | 0 | 182214336000 | 0 |  | 5572809859.9313
32 | PK | -003 | AIR DRYER PACKAGE | 525 N m³/h | No. | 1 | 3301661000 |  | 0 | 3301661000 | 0 |  | 5572809859.9313
33 | P | -501-A/B/C | CHEMICAL INJECTION PORTABLE PUMPS | .8m³/h, 2bar, 0.45 kw | No. | 3 | 4101226000 |  | 0 | 12303678000 | 0 | 0 | 1857603286.6438
34 | PK | -501 | DEMULSIFIER INJECTION PACKAGE | 10-20 LIT/HR Injection Pressure = 5 barg | No. | 1 | 37822417000 |  | 0 | 37822417000 | 0 |  | 120744213.6318
35 | PK | -502-A/B | DEMULSIFIER INJECTION PACKAGE | 10-20 LIT/HR Injection Pressure = 15 bar | No. | 2 | 38505954000 |  | 0 | 77011908000 | 0 |  | 120744213.6318
36 | PK | -503 | OXYGEN SCAVENGER INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 4.5 bar | No. | 1 | 32126269000 |  | 0 | 32126269000 | 0 |  | 120744213.6318
37 | PK | -504 | CORROSION INHIBITOR INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 3 bar | No. | 1 | 37822417000 |  | 0 | 37822417000 | 0 |  | 120744213.6318
38 | PK | -505 | REVERSE DEMULSIFIER INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 3 bar | No. | 1 | 37822417000 |  | 0 | 37822417000 | 0 |  | 120744213.6318
39 | PK | -506-A | BIOCIDE INJECTION PACKAGE (TYPE A) | 20-70 LIT/HR Injection Pressure = 3 bar | No. | 1 | 38733800000 |  | 0 | 38733800000 | 0 |  | 120744213.6318
40 | PK | -506-B | BIOCIDE INJECTION PACKAGE (TYPE B) | 20-70 LIT/HR Injection Pressure = 3 bar | No. | 1 | 38278108000 |  | 0 | 38278108000 | 0 |  | 120744213.6318
41 | PK | -507 | ANTI SCALE INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 9 bar | No. | 1 | 38278108000 |  | 0 | 38278108000 | 0 |  | 120744213.6318
42 | V | -601 | FLARE K.O. DRUM | 17.0 m³, T/T=7400 mm, ID=1600 mm | Kg | 6100 | 2940000 |  |  | 17934000000 |  |  | 120744213.6318
43 | P | -601-A/B | FLARE K.O DRUM LIQUID PUMPS | 15m3/hr, 0.8 bar, 0.33 kw | No. | 2 | 12759369000 |  | 0 | 25518738000 | 0 | 0 | 1857603286.6438
44 | PK | -602 | FLARE PACKAGE |  | No. | 1 | 295903623000 |  | 0 | 295903623000 | 0 |  | 120744213.6318
45 | PK | -603 | COLD FLARE PACKAGE |  | No. | 1 | 76860000000 |  |  | 76860000000 |  |  | 120744213.6318
46 | PK | -701 | BURN PIT IGNITION PACKAGE |  | No. | 1 |  |  | 0 |  | ردیف 44 |  | 120744213.6318
47 | P | -701-A/B | HC CLOSED DRAIN TRANSFER PUMPS | 27.5m3/hr, 4.3 bar, 3.3 kw | No. | 2 | 24151664000 |  | 0 | 48303328000 | 0 | 0 | 1857603286.6438
48 | P | -702A/B | HC CLOSED DRAIN DRUM SUMP PUMP | 5.5m3/hr, 7 bar. 0.11 kw | No. | 2 | 24151664000 |  | 0 | 48303328000 | 0 | 0 | 1857603286.6438
49 | V | -701 | HC CLOSED DRAIN DRUM | 96.2 m³,T/T=10000 mm ID=3500 mm | Kg | 29600 | 2520000 |  |  | 74592000000 |  |  | 120744213.6318
50 | P | -703-A/B | CLEAN WATER PUMPS | 11m3/hr, 1.8 bar, 0.54 kw | No. | 2 | 13215061000 |  | 0 | 26430122000 | 0 | 0 | 1857603286.6438
51 | P | -704-A/B | RECOVERED WASTE OIL PUMPS | 11 m3/hr, 2.7 bar, 0.8 kw | No. | 2 | 15949212000 |  | 0 | 31898424000 | 0 | 0 | 1857603286.6438
52 | P | -750 | OILY WATER SEPARATOR PUMP | 1m3/hr, 0.84 bar, 0.02kw | No. | 1 | 6083485000 |  | 0 | 6083485000 | 0 | 0 | 1857603286.6438
53 | TK | -701 | DIRTY OILTANK | 21 m³,T/T=3000 mm, ID=3000 mm | Kg | 3600 | 660000 |  |  | 2376000000 |  |  | 120744213.6318
54 | P | -705-A/B | DIRTY OIL PUMPS | 5m3/hr, 2bar, 0.3 kw | No. | 2 | 14126445000 |  | 0 | 28252890000 | 0 | 0 | 1857603286.6438
55 | P | -706-A/B | RECOVERED WASTE WATER PUMPS | 33m3/hr, 1.5 bar, 1.35 kw | No. | 2 | 12759369000 |  | 0 | 25518738000 | 0 | 0 | 371520657.3288
56 | V | -801 | DIESEL STORAGE TANK | 14.9 m³, T/T=4750mm ID=2000mm | Kg | 6100 | 660000 |  |  | 4026000000 |  |  | 120744213.6318
57 | P | -801 | DIESEL OIL PUMP | 10m3/hr, 0.6 bar, 0.16 kw | No. | 1 | 6151839000 |  | 0 | 6151839000 | 0 | 0 | 1857603286.6438
58 | P | -901A/B | FIRE WATER MAIN ELECTRICAL PUMP | 480m3/hr, 10 barg,133kw | No. | 2 | 37500000000 |  |  | 75000000000 |  |  | 148608262.9315
59 | P | 902 | FIRE WATER MAIN DESEL PUMP | 480m3/hr, 10 barg,133kw | No. | 1 | 45000000000 |  |  | 45000000000 |  |  | 371520657.3288
60 | P | -903-A/B | FIRE WATER JOCKEY PUMPS | 15m3/hr, 6 barg, 2.5 kw | No. | 2 | 2000000000 |  |  | 4000000000 |  |  | 185760328.6644
60 | P | 108A/B | UNIT SUPPLY WATER PUMP | 15m3/hr, 6 barg, 2.5 kw | No. | 2 | 7974606000 |  | 0 | 15949212000 | 0 |  | 185760328.6644
61 | TK | -901 | DISEL FUEL DAILY TANK | 2 m³ | Kg | 300 | 660000 |  |  | 198000000 |  |  | 3622326408.9554
62 | TK | -902-A/B | FIRE WATER STORAGE TANK |  | Kg | 144600 | 660000 |  |  | 95436000000 |  |  | 120744213.6318
63 | TK | -104 | SUPPLY WATER STORAGE TANK | 1717.2 m³, T/T=14000mm, ID=12500mm | Kg | 32000 | 660000 |  |  | 21120000000 |  |  | 120744213.6318
64 | P | -904 | FIRE WATER LOADING PUMP | 30m3/hr, 3 bar, 2.5 kw | No. | 1 | 8885989000 |  | 0 | 8885989000 | 0 |  | 185760328.6644
65 |  |  | CRANES | [6 empty] | طبق لیست زیر |  |  | 2414884272.6369
65.1 | CR | 001 | AIR COMPRESSOR ROOM CRANE |  | No. | 1 | 16380000000 |  |  | 16380000000
65.2 | CR | 002 | CHEMICAL STORAGE SHELTER CRANE (ex) |  | No. | 1 | 32760000000 |  |  | 32760000000
65.3 | CR | 003 | CHEMICAL STORAGE SHELTER CRANE (ex) |  | No. | 1 | 32760000000 |  |  | 32760000000
65.4 | CR | 004 | CHEMICAL INJECTION PACKAGE SHELTER CRANE (ex) |  | No. | 1 | 40320000000 |  |  | 40320000000
65.5 | CR | 005 | CHEMICAL INJECTION PACKAGE SHELTER CRANE (ex) |  | No. | 1 | 40320000000 |  |  | 40320000000
65.6 | CR | 006 | WORK SHOP CRANE |  | No. | 1 | 16380000000 |  |  | 16380000000
65.7 | CR | 007 | PUMP SHELTER CRANE (ex) |  | No. | 1 | 40320000000 |  |  | 40320000000
65.8 | CR | 008 | FIRE WATER SHELTER CRANE |  | No. | 1 | 15120000000 |  |  | 15120000000
65.9 | CR | 009 | PROCESS PUMP SHELTER CRANE (ex) |  | No. | 1 | 46200000000 |  |  | 46200000000
65.10 | CR | 010 | DILUTION WATER PUMP SHELTER CRANE |  | No. | 1 | 15540000000 |  |  | 15540000000
65.11 | CR | 011 | DEARATOR WATER PUMP SHELTER CRANE |  | No. | 1 | 15540000000 |  |  | 15540000000
65.12 | CR | 012 | PU4 COMPRESSOR STATION CRANE |  | No. | 1 | 50400000000 |  |  | 50400000000
65.13 | CR | 013 | CHEMICAL STORAGE SHELTER CRANE(ex) |  | No. | 1 | 39900000000 |  |  | 39900000000
66 |  |  | HVAC | [6 empty] | طبق لیست زیر |  |  | 1207442136.3185
66.1 |  |  | HVAC FOR ACCOMMODATION |  | SET | 1 | 1300000000 |  |  | 1300000000
66.2 |  |  | HVAC FOR DE4 SWITCHGERA ROOM |  | SET | 1 | 115920000000 |  |  | 115920000000
66.3 |  |  | HVAC FOR DE4 CONTROL ROOM |  | SET | 1 | 141120000000 |  |  | 141120000000
66.4 |  |  | HVAC FOR 33 KV STATION |  | SET | 1 | 92400000000 |  |  | 92400000000
66.5 |  |  | HVAC FOR 33/3.45 STATION |  | SET | 1 | 3700000000 |  |  | 3700000000
66.6 |  |  | HVAC FOR GUARD HOUSE |  | SET | 1 | 1300000000 |  |  | 1300000000
66.7 |  |  | HVAC FOR LABORATORY |  | SET | 1 | 3000000000 |  |  | 3000000000
66.8 |  |  | HVAC BULK |  | No. | 1 | 6000000000 |  |  | 6000000000 |  |  | 603721068.1592
66.9 |  |  | Waste water treatment package |  | SET | 1 | 3600000000 |  |  | 3600000000 |  |  | 120744213.6318
66.10 |  |  | Water treatment package |  | SET | 1 | 2500000000 |  |  | 2500000000 |  |  | 120744213.6318
67 |  |  | SAFETY EQUIPMENT | طبق لیست زیر | No. |  |  |  |  | طبق لیست زیر
67.1 |  |  | WATER HYDRANT | 6" | No. | 13 | 373071767.2632 |  |  | 4849932974.422
67.2 |  |  | WATER HYDRANT WITH MONITOR | 6" | No. | 27 | 906031434.7821 |  |  | 24462848739.1175
67.3 |  |  | DELUGE VALVE | 4" | No. | 2 | 6300000000 |  |  | 12600000000
67.4 |  |  | DRY POWDER PORTABLE FIRE EXTINGUISHER | 12 KG | No. | 32 | 47966370.0767 |  |  | 1534923842.4544
67.5 |  |  | DRY POWDER WHELEED FIRE EXTINGUISHER | 75 KG | No. | 12 | 319775800.5113 |  |  | 3837309606.1361
67.6 |  |  | CO2 PORTABLE FIRE EXTINGUISHER | 5 KG | No. | 42 | 37307176.7263 |  |  | 1566901422.5056
67.7 |  |  | CO2 WHEELD FIRE EXTINGUISHER | 30 KG | No. | 24 | 266479833.7595 |  |  | 6395516010.2268
67.8 |  |  | SAFETY SHOWER & EYE WASH | - | No. | 7 | 1260000000 |  |  | 8820000000
67.9 |  |  | FIRST AID KIT | - | No. | 4 | 138569513.5549 |  |  | 554278054.2197
67.11 |  |  | OS&Y GATE VALVE-ISOLATING VALVE, 12" |  | No. | 2 | 1680000000 |  |  | 3360000000
67.12 |  |  | OS&Y GATE VALVE-ISOLATING VALVE, 6" |  | No. | 19 | 840000000 |  |  | 15960000000
67.13 |  |  | 9 LIT WATER EXTINGUISHER | - | No. | 8 | 37307176.7263 |  |  | 298457413.8106
67.14 |  |  | EMERGANCY BREATHING APPARATUS WITH MASK |  | No. | 2 | 532959667.5189 |  |  | 1065919335.0378
67.15 |  |  | FIRE MAN CABINET |  | No. | 2 | 5329596675.189 |  |  | 10659193350.378
67.16 |  |  | FIRE SHED EQUIPMENT. 100 lit foam drums, 3% FP (5 NOS.), Fire Hose, 25 m (10 NOS.) Foam Nozzle 10X (2 NOS.) Water Nozzle, 450 lpm (Fog/Jet/Stop) (5 NOS.)) 12 kg portable powder fire extinguisher (6 NOS.) 75 kg Wheeled powder fire extinguisher (2 NOS.) 5 kg portable CO2 fire extinguisher (2 NOS.) In Line Inductor, 450 lpm with pick up tube (2 NOS.) Drum Wrench (1 NO.) Hose Bridge (1 NO.) | - | No. | 10 | 6300000000 |  |  | 63000000000
67.17 |  |  | WATER SPRAY SYSTEM |  | No. | 40 | 4263677.3402 |  |  | 170547093.606
67.18 |  |  | SAFETY SIGN |  | No. | 200 | 2131838.6701 |  |  | 426367734.0151
67.19 |  |  | Bulks OS&Y GATE VALVE-ISOLATING VALVE;OS&Y GATE VALVE-ISOLATING VALVE; WIND SOCK; HOSE REEL; EMERGENCY EQUIPMENT BOX;EMERGENCY BREATING APPARATUS WITH MASK; FIRE MAN CABINET;STRETCHER; FIRE DOSE SYSTEM;WATER SPRAY SYSTEM;SAFETY SIGN;AXE;RECHARGEABLE FLASHLIGHT (EXPLOSION PROOF);EMERGENCY BREATHING APPARATUS WITH AIR MASTER;BREATHING RECOVERY DEVICE |  | a lot | 1 | 4200000000 |  |  | 4200000000 |  |  | 1207442136.3185
68 |  |  | Pig Launcher & Receiver |  | SET | 1 | 94500000000 |  |  | 94500000000 |  |  | 241488427.2637
69 |  |  | CLEANING IN PLATE FOR EXCHANGER |  | SET | 2 | 28708122189.3149 |  |  | 57416244378.6297 |  |  | 241488427.2637
[5 empty] | 580014656421.8619 | 1737802.4 | 5.8001e+12 | 17378024 | 910687581192.2859 | 321268343167.9406
[5 empty] | IRR | Euro | Rls | Euro | Rls | Rls
[5 empty] | لوازم یدکی |  | خرید |  | ترخیص | حمل
هزینه کل بدون ضریب
جدول 2.1 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي مکانیک و لوله و اتصالات مورد نياز پروژه بر اساس پیوست 1،2 و3
[6 empty] | رديف | شرح فعاليت ها | دلار | یورو | ريال
[6 empty] | 1 | الكترواستاتيك ها و ادوات مربوطه | 7594862.7657 | 7000000 | 0
[6 empty] | 2 | كوره ها و ادوات مربوطه | 6487000 | 5979000 | 0
[6 empty] | 3 | مبدل نفت / نفت و مبدل آب / آب | 0 | 0 | 625209000000
[6 empty] | 4 | تلمبه ها | 0 | 0 | 2082268000000
[6 empty] | 5 | شيرآلات و اتصالات ، رنگها و لوله های داخل سایت | 0 | 0 | 2452617000000
[6 empty] | 6 | خرید لوله های بیرون سایت | 0 | 0 | 2982846000000
[6 empty] | 7 | مخزن های اتمسفریک و تحت فشار | 0 |  | 797604000000
[6 empty] | 8 | سیستم پساب | 4773913.7384 | 4400000 | 0
[6 empty] | 9 | کمپرسور و خشک کن هوا | 0 | 0 | 418938000000
[6 empty] | 10 | Flare & Ignitor | 0 | 0 | 372764000000
[7 empty] | بسته های تزریق مواد شیمیایی | 0 | 0 | 337896000000
[6 empty] | 12 | Vacuum Deaerator Package | 0 | 0 | 134429070953.0233
[6 empty] | 13 | سیستم HVAC | 0 |  | 370840000000
[6 empty] | 14 | جرثقیلهای سقفی | 0 |  | 401940000000
[6 empty] | 15 | خرید اقلام ایمنی و آتش نشانی | 0 |  | 163763000000
[6 empty] | 16 | گیرنده و فرستنده توپک | 0 |  | 94500000000
[6 empty] | 17 | مواد شیمیایی مصرفی | 0 |  | 592670000000
[6 empty] | 18 | جمع كل | 18855776.5042 | 17379000 | 1.1828e+13

## P.EL
ITEM | DESCRIPTION | QUANTITY |  | هزینه واحد بدون ضریب |  |  | هزینه کل بدون ضریب
|  | QTY | UNIT | خرید |  |  | خرید |  | حمل
|  |  |  | Rls | Euro | Dollar | Rls | Euro | Rls
1 | SWITCHGEAR
1.1 | MV Switchgear, 33KV, 630A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 15 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010/Location:33KV station/DWG no. EL-SLD-21028 | 1 | SET | 198750000000 |  |  | 198750000000 | 0 | 1161002054.1524
1.2 | MV Switchgear, 3.3KV, 1250A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 9 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010. /Location: DE4 Outdoor station/ DWG no. M9003-EB-EL-SLD-21026 : OUT-SWG-01 | 1 | SET | 104940000000 |  |  | 104940000000 | 0 | یک قلم در ردیف 1.1
1.3 | MV Switchgear, 3.3KV, 630A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 12 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010./Location:DE4/ DWG no. M9003-EB-EL-SLD-21026 : DE4-SWG-01 | 1 | SET | 139920000000 |  |  | 139920000000 | 0 | یک قلم در ردیف 1.1
1.4 | LV Switchgear, 400V, 4000A, 3 phase + N+E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 50KA, 1Sec., in accordance with attached Specification No.: M9003-EB-EL-SPC-21008./Location: DE4 / / DWG no. M9003-EB-EL-SLD-21025 : (DE-MCC-001 | 1 | SET | 84800000000 |  |  | 84800000000 | 0 | یک قلم در ردیف 1.1
1.5 | 33 KV transformer bay, withdrawable, outdoor type with OCB and all protection and metering devises in accordance to Dwg no. M9003-EB-EL-SLD-21026 | 2 | SET | 61586000000 |  |  | 123172000000 | 0 | یک قلم در ردیف 1.1
1.6 | MV Switchgear, 3.3KV, 630A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 9 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010./Location:Production uni/ DWG no. M9003-EB-EL-SLD-21026 : PU4-SWG-01 | 1 | SET | 104940000000 |  |  | 104940000000 | 0 | یک قلم در ردیف 1
1.7 | GACHSARAN 4-DESALTING UNIT EDP,400V SWITCHGEAR (EDP) / DWG no. M9003-EB-EL-SLD-21024 | 2 | SET | 15900000000 |  |  | 31800000000 | 0 | یک قلم در ردیف 2
1.8 | Capacitor Bank Set 400/230 V AC, 50Hz, 3Phase, 3-wires + N + PE , 425KVAR with min 5 Steps Regulator (50KVAR fixed step+375KVAR as variable steps), rapid discharge on contactor, free standing type, supplying from L V Switchgear, for indoor use, IP42. | 2 |  | 9010000000 |  |  | 18020000000 | 0
2 | TRANSFORMERS
2.1 | TR1 : Power Transformer 2500 KVA, 3.3 / 0.42 Kv 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral solidly earthed Complete with accessories. | 1 | SET | 28896400000 |  |  | 28896400000 |  | 232200410.8305
2.2 | TR2 : Power Transformer 2500 KVA, 3.3 / 0.42 kV 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase, 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral solidly earthed Complete with accessories. | 1 | SET | 28896400000 |  |  | 28896400000 |  | 232200410.8305
2.3 | PTR1 : Power Transformer6000 KVA, 33 / 3.45kV 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase, 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral earthed with NGR. | 1 | SET | 55291600000 |  |  | 55291600000 |  | 232200410.8305
2.4 | PTR2 : Power Transformer 6000 KVA, 33 / 3.45kV 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase, 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral earthed with NGR. | 1 | SET | 55291600000 |  |  | 55291600000 |  | 232200410.8305
3 | DIESEL GENERATOR EDG-1
3.1 | DIESEL GENERATOR EDG-1 0.4 kv, 550kva, 50Hz, 1500rpm | 1 |  | 36296000000 |  |  | 36296000000 |  | 696601232.4914
3.2 | emergency diesel generator, 0.4 kv, 180KVA, 50Hz, 1500rpm,with automatic control panel | 1 |  | 16536000000 |  |  | 16536000000 |  | یک قلم در ردیف فوق
4 | UNINTERRUPTIBLE POWER SUPPLY (UPS)
4.1 | UPS-001/ 110V AC | 2 | [6 empty] | 232200410.8305
4..1.1 | INVERTER: 20 KVA inverter with all metering and protective devices. | 2 |  | 28600000000 |  |  | 57200000000
4.1.2 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (100%) with respective rack, Battery Back Up Duration : 2 Hours capacity, with fuse box EXD -IIC ,automatic switch 200 A | 2 |  |  | 91592.5803 |  |  | 183185.1606
4.2 | DC-001/110V DC | 2 | [6 empty] | یک قلم در ردیف 4.1
4.2.1 | CHARGERS :Suitable to feed 13KW UPS load and charge batteries simultaneity, as per manufacturer standard battery chargers with all metering and protective devices. | 2 |  | 14040000000 |  |  | 28080000000
4.2.2 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (50%) with respective rack, Battery Back Up Duration : 8Hours capacity, with fuse box EXD -IIC ,automatic switch 160 A | 2 |  |  | 76900 |  |  | 153800
4.3 | DC-002/24V DC | 2 | [6 empty] | 232200410.8305
4.3.1 | CHARGERS :Suitable to feed 18KW UPS load and charge batteries simultaneity, as per manufacturer standard battery chargers with all metering and protective devices. | 2 |  | 93600000000 |  |  | 187200000000
4.3.3 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (50%) with respective rack, Battery Back Up Duration :24Hours capacity, with fuse box EXD -IIC ,automatic switch400 A | 2 |  |  | 276100 |  |  | 552200
4.4 | DC-003/110V DC | 2 | [6 empty] | یک قلم در ردیف 4.3
4.4.1 | CHARGERS :Suitable to feed 11KW UPS load and charge batteries simultaneity, as per manufacturer standard battery chargers with all metering and protective devices. | 2 |  | 13520000000 |  |  | 27040000000
4.4.2 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (50%) with respective rack, Battery Back Up Duration : 8Hours capacity , with fuse box EXD -IIC ,automatic switch160 A | 2 |  |  | 65000 |  |  | 130000
4.5 | DC-004/ 110V DC | 2 | [6 empty] | 232200410.8305
4.5.1 | CHARGERS :Suitable to feed 11KW UPS load and charge batteries simultaneity, as per manufacturer standard battery chargers with all metering and protective devices. | 2 |  | 13520000000 |  |  | 27040000000
4.5.2 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (50%) with respective rack, Battery Back Up Duration : 8Hours capacity ,with fuse box EXD -IIC ,automatic switch160 A | 2 |  |  | 65000 |  |  | 130000
4.6 | DC-005/ 110V DC | 2 | [6 empty] | یک قلم در ردیف 4.5
4.6.1 | CHARGERS :Suitable to feed 13KW UPS load and charge batteries simultaneity, as per manufacturer standard battery chargers with all metering and protective devices. | 2 |  | 14040000000 |  |  | 28080000000
4.6.2 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (50%) with respective rack, Battery Back Up Duration : 8Hours capacity ,with fuse box EXD -IIC ,automatic switch 160 A | 2 |  |  | 76900 |  |  | 153800
5 | Earthing
5.1 | 120 mm2 BARE STRANDED COPPER CONDUCTOR | 1200 | m | 7031700 |  |  | 8438040000 |  | 696601232.4914
5.2 | 120 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 500 | m | 7423000 |  |  | 3711500000 |  | یک قلم در ردیف 5.1
5.3 | 70 mm2 BARE STRANDED COPPER CONDUCTOR | 4630 | m | 4108000 |  |  | 19020040000 |  | یک قلم در ردیف 5.1
5.4 | 70 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 2850 | m | 4355000 |  |  | 12411750000 |  | یک قلم در ردیف 5.1
5.5 | 35 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 350 | m | 2210000 |  |  | 773500000 |  | یک قلم در ردیف 5.1
5.6 | 16 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 400 | m | 1053000 |  |  | 421200000 |  | یک قلم در ردیف 5.1
5.7 | FLEXIBLE COPPER BRAID STRIP, 20x3 mm, HOLE=11mm,HOLE CENTERS= 250 mm | 22 | NO | 2730000 |  |  | 60060000 |  | یک قلم در ردیف 5.1
5.8 | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 120x120 mm2 | 72 | NO | 1560000 |  |  | 112320000 |  | یک قلم در ردیف 5.1
5.9 | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 120x70 mm2 | 7 | NO | 1053000 |  |  | 7371000 |  | یک قلم در ردیف 5.1
5.10 | CADWELD,CARTRIDGE, FOR CROSS CONNECTION OF 70x70 mm2 | 160 | NO | 1261000 |  |  | 201760000 |  | یک قلم در ردیف 5.1
5.11 | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 70x35 mm2 | 40 | NO | 780000 |  |  | 31200000 |  | یک قلم در ردیف 5.1
5.12 | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 70x16 mm2 | 40 | NO | 780000 |  |  | 31200000 |  | یک قلم در ردیف 5.1
5.13 | CADWELD,CARTRIDGE, FOR CONNECTION OF 70 mm2 COPPER CONDUCTOR TO COPPER EARTH PLATE | 40 | NO | 1261000 |  |  | 50440000 |  | یک قلم در ردیف 5.1
5.14 | 10-WAY COPPER EARTH BAR,6mm THICKNESS,50 mm WIDE,700 mm LENGTH AND TWO WASHERS AND ONE NUT FOR EACH HOLE | 68 | NO | 32500000 |  |  | 2210000000 |  | یک قلم در ردیف 5.1
5.15 | EARTHING ROD, SOLID COPPER, 3000mm LONG x 20 mm DIA. WITH ALL FITTINGS & ACC. | 64 | NO | 50700000 |  |  | 3244800000 |  | یک قلم در ردیف 5.1
5.16 | "U" bolt rod to cable clamp for nominal rod dia. 20 mm | 64 | NO | 273000 |  |  | 17472000 |  | یک قلم در ردیف 5.1
5.17 | TINNED COPPER COMPRESSION CABLE LUG FOR CABLE SIZE 120 mm2 | 24 | NO | 1105000 |  |  | 26520000 |  | یک قلم در ردیف 5.1
5.18 | TINNED COPPER COMPRESSION CABLE LUG FOR CABLE SIZE 70 mm2 | 46 | NO | 585000 |  |  | 26910000 |  | یک قلم در ردیف 5.1
5.19 | TINNED COPPER COMPRESSION CABLE LUG FOR CABLE SIZE 35 mm2 | 74 | NO | 455000 |  |  | 33670000 |  | یک قلم در ردیف 5.1
5.20 | TINNED COPPER COMPRESSION CABLE LUG FOR CABLE SIZE 16 mm2 | 121 | NO | 234000 |  |  | 28314000 |  | یک قلم در ردیف 5.1
5.21 | CONDUIT , HEAVY GUAGE HOT DIP GALVANIZED ,RIGID STEEL,DOUBLE SIDE ISO THREADED, LENGTH 3000mm, size: M50 | 49 | NO | 432000 |  |  | 21168000 |  | یک قلم در ردیف 5.1
5.22 | Conduit clamp, m50 | 147 | NO | 25200 |  |  | 3704400 |  | یک قلم در ردیف 5.1
5.23 | Spark gap | 1 | NO | 84500000 |  |  | یک قلم در ردیف 5 |  | یک قلم در ردیف 5.1
6 | CABLE
6.1 | 0.6/1 KV, Stranded Annealed Copper Conductor, PVC Insulated, Lead Sheath, Extruded PVC Bedding, Galvanized Steel Wire Armored, PVC Sheathed, Cu-PVC-Lsh-Bd-SWA-PVC Power Cable
6.2 | 3C4 | 8200 | m | 2148800 |  |  | 17620160000 |  | 5108409038.2704
6.3 | 3C10 | 2100 | m | 3091700 |  |  | 6492570000 |  | یک قلم در ردیف 6.2
6.4 | 3C16 | 4100 | m | 4051700 |  |  | 16611970000 |  | یک قلم در ردیف 6.2
6.5 | 3C25 | 550 | m | 5876100 |  |  | 3231855000 |  | یک قلم در ردیف 6.2
6.6 | 3C95 | 250 | m | 16995700 |  |  | 4248925000 |  | یک قلم در ردیف 6.2
6.7 | 3C240+120 | 750 | m | 46158700 |  |  | 34619025000 |  | یک قلم در ردیف 6.2
6.8 | 4C4 | 1100 | m | 2309300 |  |  | 2540230000 |  | یک قلم در ردیف 6.2
6.9 | 4C6 | 4100 | m | 2796200 |  |  | 11464420000 |  | یک قلم در ردیف 6.2
6.10 | 4C10 | 1500 | m | 3715900 |  |  | 5573850000 |  | یک قلم در ردیف 6.2
6.11 | 4C16 | 300 | m | 4986700 |  |  | 1496010000 |  | یک قلم در ردیف 6.2
6.12 | 3C95+50 | 280 | m | 19778400 |  |  | 5537952000 |  | یک قلم در ردیف 6.2
6.13 | 3C70 | 3900 | m | 12690900 |  |  | 49494510000 |  | یک قلم در ردیف 6.2
6.14 | 3C50 | 750 | m | 9358000 |  |  | 7018500000 |  | یک قلم در ردیف 6.2
6.15 | 3C120+70 | 200 | m | 25095700 |  |  | 5019140000 |  | یک قلم در ردیف 6.2
6.16 | 4C25 | 300 | m | 7424100 |  |  | 2227230000 |  | یک قلم در ردیف 6.2
6.17 | 3C240 | 1000 | m | 40044000 |  |  | 40044000000 |  | یک قلم در ردیف 6.2
6.18 | 0.6/1 KV, Stranded Annealed Copper Conductor, PVC Insulated, Galvanized Steel Wire Armored, PVC Sheathed, Cu-PVC-SWA-PVC Power Cable
6.19 | 1C300 | 2000 | m | 13768500 |  |  | 27537000000 |  | یک قلم در ردیف 6.2
6.20 | 3C4 | 150 | m | 877400 |  |  | 131610000 |  | یک قلم در ردیف 6.2
6.21 | 3C6 | 250 | m | 1171900 |  |  | 292975000 |  | یک قلم در ردیف 6.2
6.22 | 3C16 | 300 | m | 2605900 |  |  | 781770000 |  | یک قلم در ردیف 6.2
6.23 | 3C25 | 650 | m | 3864100 |  |  | 2511665000 |  | یک قلم در ردیف 6.2
6.24 | 3C25+16 | 500 | m | 4571500 |  |  | 2285750000 |  | یک قلم در ردیف 6.2
6.25 | 3C150+70 | 100 | m | 23917300 |  |  | 2391730000 |  | یک قلم در ردیف 6.2
6.26 | 4C4 | 500 | m | 1061400 |  |  | 530700000 |  | یک قلم در ردیف 6.2
6.27 | 4C16 | 600 | m | 3292200 |  |  | 1975320000 |  | یک قلم در ردیف 6.2
6.28 | 4C10 | 150 | m | 2302600 |  |  | 345390000 |  | یک قلم در ردیف 6.2
6.29 | 3C95+50 | 500 | m | 15674200 |  |  | 7837100000 |  | یک قلم در ردیف 6.2
6.30 | 3C50+25 | 100 | m | 8183600 |  |  | 818360000 |  | یک قلم در ردیف 6.2
6.31 | 3C50 | 1100 | m | 6919800 |  |  | 7611780000 |  | یک قلم در ردیف 6.2
6.32 | 4C6 | 200 | m | 1435700 |  |  | 287140000 |  | یک قلم در ردیف 6.3
6.33 | 3/6 KV, Stranded Annealed Copper Conductor, XLPE Insulated, Galvanized Steel Wire Armored, PVC Sheathed, Cu-XLPE-SWA-PVC Power Cable
6.34 | 3C50 | 600 | m | 9770700 |  |  | 5862420000 |  | یک قلم در ردیف 6.2
6.35 | 3C70 | 1800 | m | 12871400 |  |  | 23168520000 |  | یک قلم در ردیف 6.2
6.36 | 3C95 | 400 | m | 16488900 |  |  | 6595560000 |  | یک قلم در ردیف 6.2
6.37 | 3C240 | 3800 | m | 36963500 |  |  | 140461300000 |  | یک قلم در ردیف 6.2
6.38 | 3C240+120 | 1000 | m | 46158700 |  |  | 46158700000 |  | یک قلم در ردیف 6.2
6.39 | 33 KV, Stranded Annealed Copper Conductor, XLPE Insulated, Galvanized Steel Wire Armored, PVC Sheathed, Cu-XLPE-SWA-PVC Power Cable
6.35 | 1C95 | 14500 | m | 6775600 |  |  | 98246200000 |  | یک قلم در ردیف 6.2
6.36 | CONTROL CABLE | 17000 | m | 2268204 |  |  | 38559468000 |  | یک قلم در ردیف 6.2
7 | LOCAL CONTROL STATION
7.1 | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator.(L4-T12,L2-T12 Schematic code). | 31 | SET | 156000000 |  |  | 5077800000 |  | 2322004238.3369
7.2 | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be explosion proof type, IP55, EExd, IIB, T3 and supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator.(L4-T12,L2-T12 Schematic code). | 8 | SET | 504400000 |  |  | 4035200000 |  | یک قلم در ردیف 7.1
7.3 | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch and remote position indicator.(L1-T12 Schematic code). | 13 | SET | 156000000 |  |  | 2028000000 |  | یک قلم در ردیف 7.1
7.4 | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be explosion proof type, IP55, EExd, IIB,T3 and supplied with stop push Button, start push button, Local / Remote Selector Switch and remote position indicator.(L1-T12 Schematic code). | 9 | SET | 341120000 |  |  | 3070080000 |  | یک قلم در ردیف 7.1
7.5 | Local Control Stations for remote operation of the fire water pump.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator. | 1 | SET | 156000000 |  |  | 156000000 |  | یک قلم در ردیف 7.1
8 | Power Transition Line
8.1 | Cable ACSR -33KV –LYNX | 108000 | m | 599936.6172 |  |  | 64793154659.6025 |  | 13932024649.8283
8.2 | Cable ACSR -66KV –HORSE | 6000 | m | 539326.5823 |  |  | 3235959493.5589 |  | 2322004108.3047
8.3 | Shield wire -Horse | 24000 | m | 539326.5823 |  |  | 12943837974.2357
8.4 | Double Circuit 66 kv Overhead Line tower with accessories | 80 | no. | 5650088004.6267 |  |  | 452007040370.134 |  | 11610020541.5236
9 | Lighting
9.1 | Lighting Fixture
9.1.1 | INDUSTRIAL FLUORESCENT LIGHTING FIXTURE, FOR 2x36W TUBES, BODY OF GALVANIZED SHEET STEEL , CORROSION RESISTANT , INJECTED MOULDED BOWL OF IMPACT RESISTANT OPAL PATTERNED POLYCARBONATE, 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2, DEGREE OF PROTECTION: IP55, WITH FULL SUPPORTING ACCESSORIES FOR: SURFACE MOUNTING, WITH TWO BI PIN LAMPS, TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2 , AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 6 | SET | 29640000 |  |  | 177840000 |  | 696601232.4914
9.1.2 | INTERIOR FLUORESCENT LIGHTING FIXTURE WITH SYMMETRICAL LIGHT DISTRIBUTION, FOR 2x36 TUBES HOUSING OF STEEL SHEET SYMMETRICAL REFLECTOR AND LOUVRE, DEGREE OF PROTECTION: IP41, SURFACE MOUNTED, 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2, WITH TWO BI PIN LAMPS,TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 9 | SET | 29640000 |  |  | 266760000 |  | یک قلم در ردیف 9.1.1
9.1.3 | INDUSTRIAL FLUORESCENT LIGHTING FIXTURE, FOR 2x36W TUBES,BODY AND REFLECTOR OF WHITE SHEET STEEL WITHOUT DIFFUSER, SURFACE MOUNTED, DEGREE OF PROTECTION IP41, 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2,WITH BI PIN LAMPS, TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 121 | SET | 29640000 |  |  | 3586440000 |  | یک قلم در ردیف 9.1.1
9.1.4 | INTERIOR FLUORESCENT LIGHTING FIXTURE WITH SYMMETRICAL LIGHT DISTRIBUTION, FOR 2x36 TUBES HOUSING OF STEEL SHEET SYMMETRICAL REFLECTOR AND LOUVRE WEATHER PROOF, DEGREE OF PROTECTION: IP55, SURFACE MOUNTED, 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2, WITH TWO BI PIN LAMPS,TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 18 | SET | 29640000 |  |  | 533520000 |  | یک قلم در ردیف 9.1.1
9.1.5 | INDUSTRIAL LIGHTING FIXTURE SUITABLE FOR MOUNTING ON HAZARDOUS AREA ,ZONE 2 , 2x36W FLUORESCENT TUBES,BODY OF GALVANIZED SHEET STEEL , INJECTED MOULDED BOWL OF IMPACT RESISTANT OPAL .DEGREE OF PROTECTION :IP55 , PATTERNED POLYCARBONATE, PROTECTION CLASS : EEX de IIB T3 , 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2 , WITH SUPPORTING ACCESSORIES FOR SURFACE MOUNTED ,WITH TWO LAMPS,TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 40 | SET | 220480000 |  |  | 8819200000 |  | یک قلم در ردیف 9.1.1
9.1.6 | INTERIOR FLUORESCENT LIGHTING FIXTURE WITH OPAL DIFFUSER, 4x20W TUBES , BODY OF STEEL SHEET, OPAL DIFFUSER, DEGREE OF PROTECTION: IP41, SURFACE MOUNTED TYPE,6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2,WITH FOUR LAMPS, TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. DIMENSION:590x590x82mm | 160 | SET | 59280000 |  |  | 9484800000 |  | یک قلم در ردیف 9.1.1
9.1.7 | INTERIOR LIGHTING FIXTURE, 2x20W FLUORESCENT TUBES, BODY OF: STEEL SHEET,OPAL DIFFUSER, DEGREE OF PROTECTION IP41, SURFACE MOUNTED, WITH LAMP, COMPLETE WITH ON-OFF (KNOT TYPE) SWITCH, WITH BATTERY BACK UP FOR MAX. 1/2 HOUR, TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 35 | SET | 81640000 |  |  | 2857400000 |  | یک قلم در ردیف 9.1.1
9.1.8 | INTERIOR LIGHTING FIXTURE, EMERGENCY WHITE EXIT SIGN ON GREEN BACKGROUND, FLUORESCENT FIXTURE, 1x8WATTS,BODY OF STEEL SHEET, DEGREE OF PROTECTION IP41, SURFACE MOUNTED, 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2, WITH LAMP, WITH BACKUP BATTERY FOR 1/2 HOUR , TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 4 | SET | 74880000 |  |  | 299520000 |  | یک قلم در ردیف 9.1.1
9.1.9 | STREET LIGHTING,1x250W HIGH PRESSURE MERCURY VAPOUR LAMP,WEATHER PROOF BODY OF PRESSED ALUMINIUM SHEET WHICH IS CHROMATED AND ELECTROSTATICALLY STOVE-ENAMELLED, REFLECTOR OF ANODISED PURE ALUMINIUM AND BOWL OF GLASS, POLE MOUNTED, ON 44~60mm PIPE ANGELED AT 10 DEGREE TO HORIZONTAL, DEGREE OF PROTECTION: IP55, WITH CONTROL GEAR AND TERMINAL BLOCK SIZE 2.5 mm2,WITH LAMP AND POWER FACTOR CORRECTION CAPACITOR. | 46 | SET | 124800000 |  |  | 5740800000 |  | یک قلم در ردیف 9.1.1
9.1.10 | CORROSION RESISTANT HIGH-BAY LUMINAIRE FOR 1x250W MERCURY VAPOUR LAMP, WIDE BEAM LIGHT DISTRIBUTION, WITH CONTROL GEAR BOX INCLUDING TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2, HOT DIPPED GALVANIZED STEEL OR ALUMINIUM SHEET HOUSING , SYMMETRICAL REFLECTOR OF ANODISED ALUMINIUM. DEGREE OF PROTECTION IP55, M20 HOLE SUITABLE FOR CONNECTING FLEXIBLE CONDUIT SIZE M20 , HANG TYPE MOUNTING, WITH LAMP.WIRING BETWEEN CONTROL GEAR AND FIXTURE SHALL BE PROVIDED BY VENDOR.WITH POWER FACTOR CORRECTION CAPACITOR. | 72 | SET | 70200000 |  |  | 5054400000 |  | یک قلم در ردیف 9.1.1
9.1.11 | CORROSION RESISTANT OUTDOOR AREA FLOOD LIGHT,1x400W METAL HALIDE LAMP, SYMMETRIC WIDE ANGLE BEAM LIGHT DISTRIBUTION, HIGH INTENSITY TYPE, BODY OF DIE CAST ALUMINIUM, DUST-PROOF SEALING, REFLECTOR OF PURE ALUMINIUM, DEGREE OF PROTECTION: IP 55, M20 HOLE AND CABLE GLANDS SUITABLE FOR CABLE PVC/PVC 3x4mm2 ,CONTROL GEAR WITH 3x4mm2 TERMINAL BLOCKS,WITH LAMP AND MOUNTING BRACKET WHICH HAVING ADJUSTABLE VERTICAL AND HORIZENTAL ANGLES , WITH POWER FACTOR CORRECTION CAPACITOR. | 75 | SET | 42120000 |  |  | 3159000000 |  | یک قلم در ردیف 9.1.1
9.1.12 | INDOOR LIGHTING FITTING FOR 1x36W LOW CONSUMPTION LAMP, BODY OF PORCELAIN, DUST AND WEATHER-PROOF SEALING BY GASKET BETWEEN BODY AND BOWL, BOWL OF PRISMATIC GLASS, 3 POLE TERMINAL BLOCKS FOR 3x2.5mm2 WIRING,WALL MOUNTED, DEGREE OF PROTECTION IP41,WITH LAMP , TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG. | 9 | SET | 29640000 |  |  | 266760000 |  | یک قلم در ردیف 9.1.1
9.1.13 | OUTDOOR LIGHTING FITTING FOR 1x36W LOW CONSUMPTION LAMP, BULKHEAD TYPE , BODY OF DIE-CAST ALUMINUM,WITH GLASS AND CORROSION PROOF ,STEEL PROTECTIVE MESH, 3 POLE TERMINAL BLOCKS FOR 3x2.5mm2 WIRING,SURFACE MOUNTED, DEGREE OF PROTECTION IP55,WITH LAMP, TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG. | 11 | SET | 9617733.8948 |  |  | 105795072.8426 |  | یک قلم در ردیف 9.1.1
9.2 | Socket Outlet
9.2.1 | SOCKET OUTLET , OUTDOOR, LOCKABLE PLUG, SURFACE MOUNTING, GALVANIZED CAST IRON , THERMOPLASTIC ENCLOSURE, WEATHER PROOF, 230 V, 16 A, 3 PIN (PH+N+PE) DEGREE OF PROTECTION IP 55, WITH M25 HOLE AT TOP FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 4mm2 | 56 | NO | 107640000 |  |  | 6027840000 |  | یک قلم در ردیف 9.1.1
9.2.2 | SOCKET OUTLET, INDOOR , RECESSED MOUNTING, 230 V, 16 A, EQUIPED WITH ON-OFF SWITCH , DEGREE OF PROTECTION IP 23, TWO POLES PLUS EARTH LUG, WITH M25 HOLE AT TOP FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 4mm2, WITH SUITABLE GALVANIZED METAL FLUSH MOUNTING BOX WITH EARTH CONNECTION SCREW. METAL BOX HOLE SIZE PROPER FOR CONDUIT SIZE: M25 WITH DEPTH 35 mm. | 5 | NO | 7280000 |  |  | 36400000 |  | یک قلم در ردیف 9.1.1
9.2.3 | SOCKET OUTLET, INDOOR , RECESSED MOUNTING, 230 V, 16 A, DEGREE OF PROTECTION IP 23, TWO POLES PLUS EARTH LUG, WITH M25 HOLE AT TOP FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 4mm2 , WITH SUITABLE GALVANIZED METAL FLUSH MOUNTING BOX WITH EARTH CONNECTION SCREW. METAL BOX HOLE SIZE PROPER FOR CONDUIT SIZE: M25 WITH DEPTH 35 mm. | 58 | NO | 5720000 |  |  | 331760000 |  | یک قلم در ردیف 9.1.1
9.2.4 | WELDING SOCKET OUTLET, INDUSTRIAL , SURFACE MOUNTING METAL CLAD OR THERMO PLASTIC ENCLOSURE, HINGED FLAP, 400 V, 60 A, 4 POLES (3PH+PE) , LOCKABLE PLUG, DEGREE OF PROTECTION IP55. WITH M32 CABLE GLAND FOR SWA CABLE AT BOTTOM. | 3 | NO | 73840000 |  |  | 221520000 |  | یک قلم در ردیف 9.1.1
9.2.5 | SOCKET OUTLET, EXPLOSION PROOF, LOCKABLE, SURFACE MOUNTING, CAST IRON ENCLOUSURE OR THERMOPLASTIC ENCLOSURE, HOT DIP GALVANIZED IF METAL, PROTECTION CLASS: EEX de IIB T3, FLAME PROOF, 230 V, 16 A, 2 POLES , PLUS EARTH LUG. EXPLOSION PROOF CABLE GLAND FOR NON-SWA FIRE RESISTANCE CABLE SIZE 3x4MM2 AT TOP OF SOCKET. | 17 | NO | 110760000 |  |  | 1882920000 |  | یک قلم در ردیف 9.1.1
9.2.6 | WELDING SOCKET OUTLET, EXPLPSION PROOF,WEATHER PROOF , SURFACE MOUNTING METAL CLAD OR THERMOPLASTIC ENCLOSURE, HINGED FLAP, 400 V, 60 A, 4 POLES (3PH+PE) , LOCKABLE PLUG, DEGREE OF PROTECTION IP55. WITH M32 CABLE GLAND FOR SWA CABLE AT BOTTOM. | 4 | NO | 326560000 |  |  | 1306240000 |  | یک قلم در ردیف 9.1.1
9.3 | Lighting Switch
9.3.1 | ON-OFF SWITCH FOR LIGHTING LUMINAIRES, RECESSED MOUNTED, 230V,10A, DEGREE OF PROTECTION IP23 , SINGLE POLE, WITH SUITABLE GALVANIZED METAL FLUSH MOUNTING BOX WITH EARTH CONNECTION SCREW. METAL BOX HOLE SIZE PROPER FOR CONDUIT SIZE: M25 WITH DEPTH 35 mm. | 38 | NO | 3120000 |  |  | 118560000 |  | 696601232.4914
9.3.2 | OUT DOOR ONE POLE SWITCH FOR LIGHTING PURPOSE, 230V,10A, DEGREE OF PROTECTION IP55 MIN.,SURFACE MOUNTING,MADE OF DIE-CAST ALUMINIUM ALLOY OR THERMOPLASTIC ENCLOSURE,HIGH RESISTANT AGAINST IMPACTS, WITH ONE M25 HOLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2 | 20 | NO | 8320000 |  |  | 166400000 |  | 928801643.3219
9.3.3 | ON-OFF SWITCH FOR LIGHTING LUMINAIRS , 230V,10A, RECESSED MOUNTED, MULTIPOSITION TYPE ( FOR DISCONNECTING TWO SEPARATE LINE OF ONE FEEDER : (TWO POLE ), DEGREE OF PROTECTION IP23 , WITH SUITABLE GALVANIZED METAL FLUSH MOUNTING BOX, WITH EARTH CONNECTION SCREW. METAL BOX HOLE SIZE PROPER FOR CONDUIT SIZE: M25 , WITH DEPTH 35 mm. | 9 | NO | 3120000 |  |  | 28080000 |  | 232200410.8305
9.3.4 | ON-OFF SWITCH FOR LIGHTING LUMINAIRS , 230V,10A, RECESSED MOUNTED, TWO WAY TYPE, DEGREE OF PROTECTION IP23 , WITH SUITABLE GALVANIZED METAL FLUSH MOUNTING BOX, WITH EARTH CONNECTION SCREW. METAL BOX HOLE SIZE PROPER FOR CONDUIT SIZE: M25 , WITH DEPTH 35 mm. | 51 | NO | 3120000 |  |  | 159120000 |  | 928801643.3219
9.3.5 | ONE POLE SWITCH FOR LIGHTING PURPOSE, EXPLOSION PROOF, PROTECTION CLASS: EEX de IIB T3, WALL SURFACE MOUNTING, MADE OF DIE-CAST ALUMINIUM ALLOY OR THERMOPLASTIC ENCLOSURE,HIGH RESISTANT AGAINST IMPACTS, VIBRATION AND AGGRESSIVE CHEMICAL SUBSTANCES,WITH M20 EXP-CABLE GLAND FOR NON-SWA FIRE RESISTENCE CABLE SIZE:3x2.5MM2 , HOLE AT TOP | 5 | NO | 36400000 |  |  | 182000000 |  | 232200410.8305
9.4 | Lighting Pole
9.4.1 | STREET LIGHTING POLE, HEIGHT :10m , DETAIL AS BELOW: PIPE SIZE 6" ,168.28mm OD x 7.11mm THK, LENGTH:2700mm , PIPE SIZE 5" ,141.3mm OD x 6.55mm THK, LENGTH:2300mm , PIPE SIZE 4" ,114.3mm OD x 6.02mm THK, LENGTH:2300mm , PIPE SIZE 3" ,88.9mm OD x 5.5mm THK, LENGTH:2700mm, CARBON-STEEL PIPE,SAND BLOST,ANTI CORROSION COATED,SILVER COLORED FINISHING PAINT. | 44 | NO | 135720000 |  |  | 5971680000
9.4.2 | FLOODLIGHTING TOWER, HEIGHT: 15m, LATTICE TYPE WITH TOP PLATFORM (As per attached drawing), CARBONSTEEL PIPE,SAND BLOST,ANTICORROSION COATED,SILVER COLORED FINISHING PAINT. | 22 | NO | 1673360000 |  |  | 36813920000
9.4.3 | POLE MOUNTED FLUORESCENT LIGHTING,2.5m EXPLOSION PROOF, PROTECTION CLASS: EEX de IIB T3, IP55, WITH FLOURECENT LAMP 2x36W EXPLOSION PROOF TYPE. | 20 | NO | 265744184.6322 |  |  | 5314883692.6431
9.5 | Lighting panels | 1 |  |  |  |  | 0
9.5.1 | LIGHTING PANEL- 3PH + N + PE, 400/230V, 50HZ, 10KA, 1SEC, - OUTDOOR USE, IP55, SUPPORT MOUNTING TYPE,INCOMING FEERDE MCCB 63A 4P WITH CONTACTOR 50A AC3 AND MCB 50A,ALSO 10 OUTGOING FEEDER 10A. MCCB,4P FOR INCOMING FEERDER VOLTMETER ,AMMETER AND PHOTOCELL SHALL BE CONSIDERED. | 4 | NO | 1560000000 |  |  | 6240000000
9.5.2 | LIGHTING PANEL- 3PH + N + PE, 400/230V, 50HZ, 10KA, 1SEC, INDOOR USE, IP42, WALL / RECESSED MOUNTING TYPE, INCOMING FEERDE MCCB 80A 4P WITH 12 OUTGOING FEEDER 10A 1PH AND 11 OUTGOING FEEDER FOR SOCKET OUTLET 16A 1PH WITH EARTH LEAKAGE PROTECTION. FOR INCOMING FEERDER VOLTMETER ,AMMETER SHALL BE CONSIDERED. | 21 | NO | 1560000000 |  |  | 32760000000
9.5.3 | LIGHTING PANEL- 3PH + N + PE, 400/230V, 50HZ, 15KA, 1SEC, - EXPLOSION PROOF , PROTECTION CLASS : ZONE2, IIB, T3,- OUTDOOR USE, IP55, WALL / SURFACE MOUNTING TYPE, INCOMING FEERDE MCCB 25A 4P WITH 3 OUTGOING FEEDER 16A 1PH AND 2 OUTGOING FEEDER FOR SOCKET OUTLET 16A 1PH WITH EARTH LEAKAGE PROTECTION. FOR INCOMING FEERDER VOLTMETER ,AMMETER SHALL BE CONSIDERED. | 12 | NO | 2600000000 |  |  | 31200000000
10 | Comunication
10.1 | Telephone System | 1 | SET |  | 58575 |  | 0 | 58575 | 232200410.8305
10.2 | Telephone cable Outdoor(2500mX2pair, 350mX10pair, 300mX15pair) | 1 | r(2500mX2pair, 350mX10pair, 300mX15pair) | 5115281492.7706 |  |  | 5115281492.7706 |  | یک قلم در ردیف فوق
10.3 | Paging | 1 | SET |  | 81066.2688 |  |  | 81066.2688 | 232200410.8305
10.4 | Paging Cable | 1200 | m | 2054577.4562 |  |  | 2465492947.4735 |  | یک قلم در ردیف فوق
10.5 | Radio System | 1 | SET |  | 41250 |  |  | 41250 | 232200410.8305
| Radio Cable | 300 | m |  | 5 |  | 0 | 1500 | یک قلم در ردیف فوق
11 | Neutral Earthing Resistor | 2 | set | 2800000000 |  |  | 5600000000 | 0
12 | Gland & Tray | 1 |  | 20545774562.2788 |  |  | 20545774562.2788 |  | 232200410.8305
13 | BUS DUCT | 80 | m | 2028000000 |  |  | 162240000000 |  | 232200410.8305
14 | BULK MATERIALS | 1 |  | 51364436405.697 |  |  | 51364436405.697 |  | 2322004108.3047
|  |  |  | 74268.8215 | 151224768053.5619 | 37161986389.0529 | 3.0245e+12 | 1485376.4295 | 93344565413.9141
|  |  |  | Euro | Rls |  | Rls | Euro | Rls
|  |  |  | لوام یدکی |  | ترخيص | خرید |  | حمل
هزینه کل بدون ضریب
جدول 2.4 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي برق و مخابرات مورد نياز پروژه بر اساس پیوست 4
|  |  |  | رديف | شرح فعاليت ها | دلار | ريال | يورو
|  |  |  | 1 | تابلوها | 0 | 806342000000 | 0
|  |  |  | 2 | اتصالات برق (شامل گلندها، شرودها، جعبه هاي اتصال، مفصلها و ...) | 0 | 305000230367.9758 | 0
|  |  |  | 3 | كابلهاي قدرت | 0 | 627630805000
|  |  |  | 4 | ترانسفورماتورها، دستگاههاي شارژر صنعتي، UPS صنعتي و دیزل ژنراتور | 1413713.3544 | 575848000000 | 1302985.1606
|  |  |  | 5 | وسايل و تجهيزات مخابرات، و پیجینگ | 196263.4803 | 7580774440.244 | 180891.2688
|  |  |  | 6 | پایه ها و برجهاي روشنائي و سایر ملحقات و ادوات روشنایی | 0 | 169113558765.4857
|  |  |  | 7 | خط انتقال برق شامل کابل ، پایه ها و یراق آلات | 0 | 532979992497.531
[5 empty] | جمع كل بدون حمل و يدكي | 1609976.8347 | 3.0245e+12 | 1483876.4295

## P.IN
ITEM | DESCRIPTION | QUANTITY |  |  | هزینه واحد بدون ضریب |  | هزینه کل بدون ضریب
[5 empty] | خرید |  | خرید
|  | UNIT | QTY | Dollar | Rls | Euro | Rls | Euro
1 | ANALYZER
1.1 | BS&W ANALYZER TRANSMITTER / ELEMENT | NO. | 3 |  |  | 70000 |  | 210000
1.2 | DISSOLVED OXYGEN ANALYZER | NO. | 1 |  | 31147749755.5728 | 0 | 31147749755.5728 | 0
2 | CORROSION INSTRUMENTS
2.1 | CORROSION COUPON | NO. | 28 |  | 410122589.3482 | 0 | 11483432501.7498 | 0
2.2 | CORROSION PROBE | NO. | 15 |  | 1686059533.9871 | 0 | 25290893009.8061 | 0
2.3 | Local DATA LOGGER | NO. | 15 |  | 1367075297.8274 | 0 | 20506129467.4103 | 0
2.4 | RETRIVER AND SERVICE VALVE and Handheld Data Logger + REQUIRED SOFTWARE | NO. | 1 |  | 31952453000 | 0 | 31952453000 | 0
3 | FLOW TRANSMITTER (DIFF. PRESSURE TYPE) WITH 5-VALVE MANIFOLD | NO. | 37 |  | 940662000 | 0 | 34804494000 | 0
4 | FLOW SWITCH (DIFF. PRESSURE SWITCH TYPE) WITH 5-VALVE MANIFOLD | NO. | 10 |  | 946892000 | 0 | 9468920000 | 0
5 | FLOW GAGE (ROTAMETER) | NO. | 23 |  | 1152467000 | 0 | 26506741000 | 0
6 | ORIFICE PLATE WITH FLANGES | NO. | 37 |  | 716398000 | 0 | 26506726000 | 0
7 | RESTRICTION ORIFICE (WITHOUT FLANGES) | NO. | 6 |  | 654103000 | 0 | 3924618000 | 0
8 | LEVEL GAUGE (MAGNETIC) | NO. | 14 |  | 2180342000 | 0 | 30524788000 | 0
9 | LEVEL GAGE (FLOAT-CABLE) | NO. | 2 |  | 5295117000 | 0 | 10590234000 | 0
10 | LEVEL SWITCH (FLOAT; EXTERNAL WITH CHAMBER, SIDE/SIDE) | NO. | 31 |  | 2429524000 | 0 | 75315244000 | 0
11 | LEVEL SWITCH (DISPLACER; INTERNAL, TOP MOUNTED) | NO. | 7 |  | 2410836000 | 0 | 16875852000 | 0
12 | LEVEL TRANSMITTER (DISPLACER; EXTERNAL WITH CHAMBER, SIDE/SIDE) | NO. | 8 |  | 7039391000 | 0 | 56315128000 | 0
13 | LEVEL TRANSMITTER (DIFF. PRESSURE TYPE) WITH 5-VALVE MANIFOLD | NO. | 7 |  | 1214762000 | 0 | 8503334000 | 0
14 | PRESSURE GAUGE WITH 2-VALVE MANIFOLD | NO. | 134 |  | 233608000 | 0 | 31303472000 | 0
15 | DIFF. PRESSURE GAUGE WITH 5-VALVE MANIFOLD | NO. | 28 |  | 959351000 | 0 | 26861828000 | 0
16 | PRESSURE SWITCH WITH 2-VALVE MANIFOLD | NO. | 97 |  | 735087000 | 0 | 71303439000 | 0
17 | PRESSURE TRANSMITTER WITH 2-VALVE MANIFOLD | NO. | 82 |  | 1108860000 | 0 | 90926520000 | 0
18 | DIFF. PRESSURE TRANSMITTER WITH 5-VALVE MANIFOLD | NO. | 17 |  | 940662000 | 0 | 15991254000 | 0
19 | TEMPERATURE TRANSMITTER WITH THERMOWELL | NO. | 34 |  | 1196074000 | 0 | 40666516000 | 0
20 | TEMPERATURE SWITCH WITH THERMOWELL | NO. | 8 |  | 953121000 | 0 | 7624968000 | 0
21 | BIMETAL THERMOMETER WITH THERMOWELL | NO. | 57 |  | 485905000 | 0 | 27696585000 | 0
22 | DENSITY TRANSMITTER | NO. | 1 |  | 4983640000 | 0 | 4983640000 | 0
23 | FLOW COMPUTER | NO. | 1 |  | 109017124000 | 0 | 109017124000 | 0
24 | CONTROL VALVES
24.1 | 1" (300#) | NO. | 3 |  | 3000151000 | 0 | 9000453000 | 0
24.2 | 1 1/2" (300#) | NO. | 1 |  | 3114775000 | 0 | 3114775000 | 0
24.3 | 2" (300#) | NO. | 8 |  | 3311006000 | 0 | 26488048000 | 0
24.4 | 3" (300#) | NO. | 8 |  | 4049207000 | 0 | 32393656000 | 0
24.5 | 3" (600#) | NO. | 2 |  | 6541027000 | 0 | 13082054000 | 0
24.6 | 4" (300#) | NO. | 4 |  | 5918072000 | 0 | 23672288000 | 0
24.7 | 4" (600#) | NO. | 6 |  | 9468916000 | 0 | 56813496000 | 0
24.8 | 6" (300#) | NO. | 7 |  | 6351026000 | 0 | 44457182000 | 0
24.9 | 8" (300#) | NO. | 1 |  | 9805312000 | 0 | 9805312000 | 0
24.10 | 10" (300#) | NO. | 4 |  | 12233590000 | 0 | 48934360000 | 0
24.11 | 12" (300#) | NO. | 2 |  | 17442740000 | 0 | 34885480000 | 0
24.12 | 16" (300#) | NO. | 2 |  | 28032975000 | 0 | 56065950000 | 0
25 | SELF ACTUATED PRESSURE REGULATOR VALVE (1 1/2", 300#) | NO. | 1 |  | 3626844000 | 0 | 3626844000
26 | ON/OFF VALVE
26.1 | 1" (300#) | NO. | 1 |  | 1868865000 | 0 | 1868865000 | 0
25.2 | 2" (300#) | NO. | 5 |  | 2180342000 | 0 | 10901710000 | 0
25.3 | 4" (300#) | NO. | 5 |  | 2491820000 | 0 | 12459100000 | 0
25.4 | 6" (300#) | NO. | 7 |  | 4360685000 | 0 | 30524795000 | 0
25.5 | 6" (600#) | NO. | 2 |  | 5606595000 | 0 | 11213190000 | 0
25.6 | 10" (300#) | NO. | 18 |  | 9032847000 | 0 | 162591246000 | 0
25.7 | 12" (300#) | NO. | 6 |  | 15573875000 | 0 | 93443250000 | 0
25.8 | 20" (300#) | NO. | 5 |  | 31147750000 | 0 | 155738750000 | 0
27 | SAFETY / RELIEF VALVES
27.1 | 3/4" / 1" (300#) | NO. | 6 |  | 1619683000 | 0 | 9718098000 | 0
27.2 | 3/4" / 1" (600#) | NO. | 4 |  | 2429524000 | 0 | 9718096000 | 0
27.3 | 1" / 2" (300#) | NO. | 4 |  | 1868865000 | 0 | 7475460000 | 0
27.4 | 1 1/2" / 2" (300#) | NO. | 4 |  | 2554115000 | 0 | 10216460000 | 0
27.5 | 2" / 3" (300#) | NO. | 2 |  | 2118047000 | 0 | 4236094000 | 0
27.6 | 3" / 4" (300#) | NO. | 8 |  | 4049207000 | 0 | 32393656000 | 0
27.7 | 4" / 6" (300#) | NO. | 12 |  | 5232822000 | 0 | 62793864000 | 0
27.8 | 6" / 8" (300#) | NO. | 2 |  | 6541027000 | 0 | 13082054000 | 0
27.9 | 8" (300#; emergency relief) | NO. | 11 |  | 8098415000 | 0 | 89082565000 | 0
28 | PRESSURE & VACUUM RELIEF VALVE
28.1 | 2" (300#) | NO. | 4 |  | 8098415000 | 0 | 32393660000 | 0
28.2 | 4" (300#) | NO. | 1 |  | 8098415000 | 0 | 8098415000 | 0
29 | LINE BREAK VALVE (12", 300#) | NO. | 4 |  | 28032975000 | 0 | 112131900000 | 0
30 | CABLE
● | 1×2×2.5 mm2, PVC/OSCR/SWA/PVC (FLAME RETARDANT) | m | 4500 |  | 572300 |  | 2575350000
● | 1×2×AWG18 (FF CABLE), PVC/OSCR/SWA/PVC (FLAME RETARDANT) | m | 6100 |  | 287000 |  | 1750700000
● | 10×2×AWG18 (FF CABLE), PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 900 |  | 3153500 |  | 2838150000
● | 1×2×1.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 2900 |  | 1399800 |  | 4059420000
● | 1×2×1.5 mm2, PVC/OSCR/SWA/PVC (FLAME RETARDANT) | m | 4700 |  | 461100 |  | 2167170000
● | 20×1.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 6200 |  | 3775600 |  | 23408720000
● | 20×2.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 2800 |  | 5225600 |  | 14631680000
● | 1×3×1.5 mm2, MT-XLPE/OSCR/LC/SWA/LSFH (FIRE RESISTANT) | m | 800 |  | 1752200 |  | 1401760000
● | 1×3×1.5 mm2, MT-XLPE/OSCR/SWA/LSFH (FIRE RESISTANT) | m | 4000 |  | 671800 |  | 2687200000
● | 10×3×1.5 mm2, MT-XLPE/OSCR/ISCR/LC/SWA/LSFH (FIRE RESISTANT) | m | 2800 |  | 7863900 |  | 22018920000
● | 1×2×1.5 mm2, MT-XLPE/OSCR/LC/SWA/LSFH (FIRE RESISTANT) | m | 500 |  | 1647400 |  | 823700000
● | 1×2×1.5 mm2, MT-XLPE/OSCR/SWA/LSFH (FIRE RESISTANT) | m | 4700 |  | 574100 |  | 2698270000
● | 1×2×1.5 mm2, MT-XLPE/OSCR/LSFH (FIRE RESISTANT) | m | 1800 |  | 313700 |  | 564660000
● | 20×1.5 mm2, MT-XLPE/OSCR/LC/SWA/LSFH (FIRE RESISTANT) | m | 2100 |  | 5030800 |  | 10564680000
● | 40×1.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 4100 |  | 6712800 |  | 27522480000
● | 7×2×1.5 mm2, PVC/ISCR/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 300 |  | 4164400 |  | 1249320000
● | 28×2.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 600 |  | 7193900 |  | 4316340000
● | 6×1.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 1400 |  | 2127100 |  | 2977940000
● | 34×1.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 1100 |  | 6199700 |  | 6819670000
31 | Bulk (Gland, Junction Box, hook-up,…) | Lot | 1 |  | 78019338000 |  | 78019338000
32 | CONTROL SYSTEMS
32.1 | DCS (CONTROL SYSTEM OF DESALTING UNIT) | set | 1 |  | 285313388000 | 0 | 285313388000 | 0
32.2 | PLC BASED ESD SYSTEM (FOR DESALTING UNIT) | set | 1 |  | 153246929000 | 0 | 153246929000 | 0
32.3 | PLC (CONTROL SYSTEM OF PRODUCTION UNIT) | set | 1 |  | 47967535000 | 0 | 47967535000 | 0
32.4 | RELAY BASED ESD SYSTEM (FOR PRODUCTION UNIT) | set | 1 |  | 18688650000 | 0 | 18688650000 | 0
32.5 | PLC BASED F&G SYSTEM (OF DESALTING UNIT) | set | 1 |  | 158853524000 | 0 | 158853524000 | 0
32.6 | SIL3 ADDRESSABLE FIRE ALARM PANEL (OF DESALTING UNIT & 33KV STATION) | set | 2 |  | 18688650000 | 0 | 37377300000 | 0
33 | F&G EQUIPMENT (OF DESALTING UNIT & 33 KV STATION)
33.1 | HEAT DETECTORS
● | EX, ADDRESSABLE | NO. | 3 |  | 546830119.1309 | 0 | 1640490357.3928 | 0
● | NON EX, ADDRESSABLE | NO. | 4 |  | 61518388.4022 | 0 | 246073553.6089 | 0
33.2 | COMBUSTIBLE GAS DETECTORS | [5 empty] | 0
● | EX | NO. | 32 |  | 1139229414.8561 | 0 | 36455341275.3962 | 0
● | NON EX | NO. | 5 |  | 1139229414.8561 | 0 | 5696147074.2806 | 0
33.3 | TOXIC GAS DETECTORS | [5 empty] | 0
● | EX | NO. | 24 |  | 1256500000 | 0 | 30156000000 | 0
● | NON EX | NO. | 5 |  | 1230367768.0446 | 0 | 6151838840.2231 | 0
33.4 | SIREN | [5 empty] | 0
● | EX | NO. | 14 |  | 637968472.3194 | 0 | 8931558612.4721 | 0
● | NON EX, ADDRESSABLE | NO. | 6 |  | 95695270.8479 | 0 | 574171625.0875 | 0
33.5 | BEACON | [5 empty] | 0
● | EX | NO. | 24 |  | 729106825.5079 | 0 | 17498563812.1902 | 0
● | NON EX, ADDRESSABLE | NO. | 10 |  | 95695270.8479 | 0 | 956952708.4791 | 0
33.6 | UV/IR FLAME DETECTOR (EX) | NO. | 48 |  | 1731628710.5813 | 0 | 83118178107.9032 | 0
33.7 | COMBINED HEAT & SMOKE DETECTOR (NON EX, ADDRESSABLE) | NO. | 115 |  | 61518388.4022 | 0 | 7074614666.2566 | 0
33.8 | LINEAR HEAT DETECTOR (WITH BOX & CABLE) | NO. | 3 |  | 1299632916.4679 | 0 | 3898898749.4036 | 0
33.9 | MANUAL CALL POINT | [5 empty] | 0
● | EX | NO. | 34 |  | 205061294.6741 | 0 | 6972084018.9195 | 0
● | NON EX, ADDRESSABLE | NO. | 39 |  | 127593694.4639 | 0 | 4976154084.0916 | 0
33.10 | SPECIAL TOOLS + HHC HART | SET | 1 |  | 16177057690.957 | 0 | 16177057690.957 | 0
34 | CCTV | SET | 1 |  | 151547588000 | 0 | 151547588000 | 0
35 | CCTV Accessory | SET | 1 |  | 33228188000 | 0 | 33228188000 | 0
36 | CO2 TOOTAL FLOODING SYSTEM | SET | 5 |  | 74754599000 | 0 | 373772995000 | 0
37 | SPARE PARTS | [5 empty] | 378212890000 | 21000
|  | 21000 | 3782128899000 | 210000 | 15789720000 | 12780311000
|  | Euro | Rls | Euro | Rls | Rls
|  | لوازم یدکی | خرید |  | ترخیص | حمل
جدول 2.5 -جدول خلاصه مالی تفكيكي تهيه و خريدادوات و تجهیزات ابزاردقیق و تجهیزات آزمایشگاه مورد نياز پروژه بر اساس پیوست 5و6
|  | رديف | شرح فعاليت ها | دلار | یورو | ريال
|  | 1 | ادوات ابزار دقیق شامل : ترانسمیترها ، سوئیچ ها ، گیج ها و ... | 227845.883 | 210000 | 846092082734.5391
|  |  | كاهش قيمت ابزاردقيق به دليل تغيير از FCS به DCS | -22784.5883 | -21000 | -84609208273.4539
|  | 2 | شیرآلات ابزار شامل : شیر ON/OFF ، شیرهای کنترلی ، PSV ، PCV | 0 | 0 | 1232421126000
|  | 3 | سيستم كنترل ( DCS,FGS )، ESD | 0 | 0 | 701447326000
|  | 4 | ادوات F&G و CO2 Total Flooding و ابزار خاص | 0 | 0 | 604297120176.6621
|  | 5 | اقلام بالک ابزار دقیق | 0 |  | 78019338000
|  | 6 | کابلهای ابزار دقیق و ملحقات شامل : گلند سینی و ... | 0 |  | 135076130000
|  |  | افزايش كابلهاي ابزاردقيق به دليل تغيير FCS به DCS |  |  | 94178735358.2454
|  | 7 | تجهیزات آزمایشگاه | 0 | 0 | 436841074000
|  | 8 | Security CCTV | 0 | 0 | 184775776000
|  |  | جمع كل | 206000 | 189000 | 4.2285e+12

## P.PI
NO | ITEM | AREA | DESCRIPTION | [6 empty] | MATERIAL |  | هزینه واحد بدون ضریب | هزینه کل بدون ضریب
|  |  | TYPE | BORE 1 | BORE 2 | UNIT | QTY | CLASS | S.CH./thK | MATERIAL | MATERIAL REMARK |  | خرید | حمل و جنبي
[12 empty] | Euro | Euro | Rls
1 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 5/8" | 85 | No | 12 | AX01 | For flange:2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 14.5673 | 2880930.4011
2 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 5/8" | 90 | No | 100 | AX01 | For flange:3"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 121.3943 | 24007753.3429
3 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 5/8" | 90 | No | 256 | AX01 | For flange:4"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 310.7695 | 61459848.5579
4 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 3/4" | 105 | No | 320 | AX01 | For flange:6"150# | A193 GR.B7/A194 GR.BH | GALVD | 2.0834 | 666.6846 | 131847985.9265
5 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 3/4" | 110 | No | 64 | AX01 | For flange:8"150# | A193 GR.B7/A194 GR.BH | GALVD | 2.0834 | 133.3369 | 26369597.1853
6 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 7/8" | 115 | No | 912 | AX01 | For flange:10"150# | A193 GR.B7/A194 GR.BH | GALVD | 3.1606 | 2882.4923 | 525411206.8849
7 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 7/8" | 125 | No | 120 | AX01 | For flange:12"150# | A193 GR.B7/A194 GR.BH | GALVD | 3.3028 | 396.3361 | 72242844.8731
8 | Fitting | Fire Water Lines(Non Metal) | 45deg.Elbow | 10 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 421.695 | 3373.5598 | 384325854.6841
9 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 3 | - | No | 5 | AX01 | DR11 | HDPE 100 |  | 19.9043 | 99.5215 | 11337780.911
10 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 4 | - | No | 10 | AX01 | DR11 | HDPE 100 |  | 23.3766 | 233.7661 | 26631326.041
11 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 6 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 68.38 | 547.0401 | 62320417.711
12 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 8 | - | No | 6 | AX01 | DR11 | HDPE 100 |  | 187.8742 | 1127.2449 | 128419057.4673
13 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 10 | - | No | 27 | AX01 | DR11 | HDPE 100 |  | 421.695 | 11385.7643 | 1297099759.5587
14 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 12 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 558.414 | 4467.3119 | 508929312.8063
15 | Fitting | Fire Water Lines(Non Metal) | Pipe Nipple | 1 | - | No | 12 | AX01 | DR11 | HDPE 100 |  | 1.3671 | 16.4046 | 1868864.9853
16 | Fitting | Fire Water Lines(Non Metal) | Reducer | 4 | 3 | No | 1 | AX01 | DR11 | HDPE 100 |  | 18.1545 | 18.1545 | 2068210.5838
17 | Fitting | Fire Water Lines(Non Metal) | Reducer | 10 | 8 | No | 6 | AX01 | DR11 | HDPE 100 |  | 114.0806 | 684.4837 | 77978391.5131
18 | Fitting | Fire Water Lines(Non Metal) | Olet | 3 | 1 | No | 3 | AX01 | DR11 | HDPE 100 |  | 36.0902 | 108.2706 | 12334508.9032
19 | Fitting | Fire Water Lines(Non Metal) | Olet | 10 | 1 | No | 3 | AX01 | DR11 | HDPE 100 |  | 585.0989 | 1755.2966 | 199968553.4308
20 | Fitting | Fire Water Lines(Non Metal) | Olet | 12 | 1 | No | 5 | AX01 | DR11 | HDPE 100 |  | 842.1049 | 4210.5246 | 479675346.2358
21 | Fitting | Fire Water Lines(Non Metal) | Tee | 4 | 1 | No | 1 | AX01 | DR11 | HDPE 100 |  | 32.8913 | 32.8913 | 3747074.2956
22 | Fitting | Fire Water Lines(Non Metal) | Tee | 4 | 4 | No | 5 | AX01 | DR11 | HDPE 100 |  | 32.8913 | 164.4565 | 18735371.478
23 | Fitting | Fire Water Lines(Non Metal) | Tee | 8 | 4 | No | 2 | AX01 | DR11 | HDPE 100 |  | 225.0853 | 450.1707 | 51284769.9726
24 | Fitting | Fire Water Lines(Non Metal) | Tee | 10 | 6 | No | 32 | AX01 | DR11 | HDPE 100 |  | 586.0695 | 18754.2233 | 2136536287.6339
25 | Fitting | Fire Water Lines(Non Metal) | Tee | 10 | 10 | No | 17 | AX01 | DR11 | HDPE 100 |  | 586.0695 | 9963.1811 | 1135034902.8055
26 | Fitting | Fire Water Lines(Non Metal) | Tee | 12 | 10 | No | 14 | AX01 | DR11 | HDPE 100 |  | 842.3373 | 11792.7224 | 1343461627.6824
27 | Fitting | Fire Water Lines(Non Metal) | Tee | 12 | 12 | No | 2 | AX01 | DR11 | HDPE 100 |  | 842.3373 | 1684.6746 | 191923089.6689
28 | Fitting | Fire Water Lines(Non Metal) | Olet | 3 | 1/2" | No | 120 | AX01 | DR11 | HDPE 100 |  | 36.0902 | 4330.8253 | 493380356.1283
29 | Fitting | Fire Water Lines(Non Metal) | Olet | 6 | 3 | No | 12 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 976.2402 | 111216155.2772
30 | Fitting | Fire Water Lines(Non Metal) | Olet | 10 | 2 | No | 3 | AX01 | DR11 | HDPE 100 |  | 585.0989 | 1755.2966 | 199968553.4308
31 | Fitting | Fire Water Lines(Non Metal) | Olet | 12 | 2 | No | 2 | AX01 | DR11 | HDPE 100 |  | 842.1049 | 1684.2098 | 191870138.4943
32 | Fitting | Fire Water Lines(Non Metal) | Olet | 12 | 3 | No | 2 | AX01 | DR11 | HDPE 100 |  | 842.1049 | 1684.2098 | 191870138.4943
33 | Flange | Fire Water Lines(Non Metal) | Flange | 2 | - | No | 3 | AX01 | DR11 | ASTM A105 |  | 11.2372 | 33.7115 | 3840517.5449
34 | Flange | Fire Water Lines(Non Metal) | Flange | 3 | - | No | 25 | AX01 | DR11 | ASTM A105 |  | 22.9392 | 573.4789 | 65332405.1123
35 | Flange | Fire Water Lines(Non Metal) | Flange | 4 | - | No | 26 | AX01 | DR11 | ASTM A105 |  | 30.4306 | 791.1958 | 90135358.2427
36 | Flange | Fire Water Lines(Non Metal) | Flange | 6 | - | No | 40 | AX01 | DR11 | ASTM A105 |  | 46.7396 | 1869.5823 | 212988312.8286
37 | Flange | Fire Water Lines(Non Metal) | Flange | 8 | - | No | 8 | AX01 | DR11 | ASTM A105 |  | 73.3014 | 586.4112 | 66805693.6758
38 | Flange | Fire Water Lines(Non Metal) | Flange | 10 | - | No | 72 | AX01 | DR11 | ASTM A105 |  | 98.0314 | 7058.2609 | 804097848.59
39 | Flange | Fire Water Lines(Non Metal) | Flange | 12 | - | No | 13 | AX01 | DR11 | ASTM A105 |  | 136.7053 | 1777.1695 | 202460373.4112
40 | Gasket | Fire Water Lines(Non Metal) | - | 2 | - | No | 3 | AX01 | DR11 | FLAT |  | 1.4081 | 4.2242 | 769972.374
41 | Gasket | Fire Water Lines(Non Metal) | - | 3 | - | No | 25 | AX01 | DR11 | FLAT |  | 2.0916 | 52.2898 | 9531211.4252
42 | Gasket | Fire Water Lines(Non Metal) | - | 4 | - | No | 34 | AX01 | DR11 | FLAT |  | 3.3766 | 114.8051 | 20926304.1958
43 | Gasket | Fire Water Lines(Non Metal) | - | 6 | - | No | 40 | AX01 | DR11 | FLAT |  | 4.0328 | 161.3123 | 29403475.7693
44 | Gasket | Fire Water Lines(Non Metal) | - | 8 | - | No | 8 | AX01 | DR11 | FLAT |  | 5.728 | 45.8236 | 8352580.5745
45 | Gasket | Fire Water Lines(Non Metal) | - | 10 | - | No | 76 | AX01 | DR11 | FLAT |  | 30.2939 | 2302.3367 | 419662353.8268
46 | Gasket | Fire Water Lines(Non Metal) | - | 12 | - | No | 11 | AX01 | DR11 | FLAT |  | 41.4764 | 456.2404 | 83162000.0274
47 | Pipe | Fire Water Lines(Non Metal) | - | 3 | - | m | 467 | AX01 | SDR11 | HDPE 100 |  | 4.6602 | 2176.3276 | 148760187.6425
48 | Pipe | Fire Water Lines(Non Metal) | - | 4 | - | m | 147 | AX01 | SDR11 | HDPE 100 |  | 6.9024 | 1014.6553 | 69355508.2744
49 | Pipe | Fire Water Lines(Non Metal) | - | 6 | - | m | 80 | AX01 | SDR11 | HDPE 100 |  | 14.6621 | 1172.9712 | 80176999.0364
50 | Pipe | Fire Water Lines(Non Metal) | - | 8 | - | m | 40 | AX01 | SDR11 | HDPE 100 |  | 22.8615 | 914.4603 | 62506805.8455
51 | Pipe | Fire Water Lines(Non Metal) | - | 10 | - | m | 1734 | AX01 | SDR11 | HDPE 100 |  | 35.6112 | 61749.8125 | 4220832167.4145
52 | Pipe | Fire Water Lines(Non Metal) | - | 12 | - | m | 130 | AX01 | SDR11 | HDPE 100 |  | 56.2745 | 7315.6826 | 500054446.7639
53 | Special | Fire Water Lines(Non Metal) | Filter | 4 | - | No | 1 | AX01 | - | ASTM A216-GR.WCB |  | 527.6826 | 527.6826 | 60115157.0283
54 | Special | Fire Water Lines(Non Metal) | Filter | 10 | - | No | 3 | AX01 | - | ASTM A216-GR.WCB |  | 929.5963 | 2788.789 | 317707047.5068
55 | Special | Fire Water Lines(Non Metal) | Orifice Flange | 4 | - | No | 4 | AX01 | DR11 | ASTM A105 |  | 30.4306 | 121.7224 | 13866978.1912
56 | Special | Fire Water Lines(Non Metal) | Orifice Flange | 12 | - | No | 2 | AX01 | DR11 | ASTM A105 |  | 191.3875 | 382.775 | 43606849.6578
57 | Special | Fire Water Lines(Non Metal) | Quick Coupling | 3 | - | No | 6 | AX01 | DR11 | ASTM A105 |  | 150.3759 | 902.2553 | 102787574.1934
58 | Special | Fire Water Lines(Non Metal) | Quick Coupling | 4 | - | No | 1 | AX01 | DR11 | ASTM A105 |  | 205.058 | 205.058 | 23360812.3167
59 | Valve | Fire Water Lines(Non Metal) | Check | 4 | - | No | 4 | AX01 | - | ASTM B148 |  | 1460.1498 | 5840.5991 | 399226938.1671
60 | Valve | Fire Water Lines(Non Metal) | Check | 6 | - | No | 2 | AX01 | - | ASTM B148 |  | 2678.1944 | 5356.3888 | 366129339.2769
61 | Valve | Fire Water Lines(Non Metal) | Check | 10 | - | No | 3 | AX01 | - | ASTM B148 |  | 4101.1603 | 12303.4809 | 840989243.4005
62 | Valve | Fire Water Lines(Non Metal) | Gate | 1 | - | No | 12 | AX01 | - | ASTM B148 |  | 355.4339 | 4265.2067 | 291542937.7122
63 | Valve | Fire Water Lines(Non Metal) | Gate | 2 | - | No | 3 | AX01 | - | ASTM B148 |  | 697.1973 | 2091.5918 | 142968171.3781
64 | Valve | Fire Water Lines(Non Metal) | Gate | 3 | - | No | 6 | AX01 | - | ASTM B148 |  | 1107.3133 | 6643.8797 | 454134191.4363
65 | Valve | Fire Water Lines(Non Metal) | Gate | 4 | - | No | 7 | AX01 | - | ASTM B148 |  | 1435.4061 | 10047.8428 | 686807882.1104
66 | Valve | Fire Water Lines(Non Metal) | Gate | 6 | - | No | 2 | AX01 | - | ASTM B148 |  | 2050.5802 | 4101.1603 | 280329747.8002
67 | Valve | Fire Water Lines(Non Metal) | Gate | 10 | - | No | 32 | AX01 | - | ASTM B148 |  | 3896.1023 | 124675.2735 | 8522024333.1247
68 | Valve | Fire Water Lines(Non Metal) | Gate | 12 | - | No | 2 | AX01 | - | ASTM B148 |  | 5276.8263 | 10553.6525 | 721381884.3391
69 | Valve | Fire Water Lines(Non Metal) | Globe | 4 | - | No | 2 | AX01 | - | ASTM B148 |  | 1345.8641 | 2691.7282 | 183989757.8062
70 | StudBolt&nuts | In Production Unit4 | - | 5/8" | 85 | No | 4 | AN01 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 3.6418 | 663820.8428
71 | StudBolt&nuts | In Production Unit4 | - | 5/8" | 85 | No | 20 | AN06 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 18.2092 | 3319104.214
72 | StudBolt&nuts | In Production Unit4 | - | 5/8" | 85 | No | 4 | AN16 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 3.6418 | 663820.8428
73 | StudBolt&nuts | In Production Unit4 | - | 7/8" | 115 | No | 24 | AN16 | For flange:10"150# | A193 GR.B7/A194 GR.BH |  | 2.3705 | 56.8913 | 10369958.0306
74 | StudBolt&nuts | In Production Unit4 | - | 7/8" | 125 | No | 120 | AN16 | For flange:12"150# | A193 GR.B7/A194 GR.BH |  | 2.4771 | 297.2521 | 54182133.6548
75 | StudBolt&nuts | In Production Unit4 | - | 1" | 135 | No | 128 | AN16 | For flange:16"150# | A193 GR.B7/A194 GR.BH |  | 3.5024 | 448.306 | 81715747.7107
76 | StudBolt&nuts | In Production Unit4 | - | 1 1/8" | 160 | No | 120 | AN16 | For flange:20"150# | A193 GR.B7/A194 GR.BH |  | 5.0444 | 605.3313 | 110337788.7341
77 | StudBolt&nuts | In Production Unit4 | - | 3/4" | 125 | No | 48 | CN16 | For flange:6"300# | A193 GR.B7/A194 GR.BH |  | 1.7184 | 82.4825 | 15034645.034
78 | StudBolt&nuts | In Production Unit4 | - | 7/8" | 140 | No | 96 | CN16 | For flange:8"300# | A193 GR.B7/A194 GR.BH |  | 2.5837 | 248.0382 | 45211581.7252
79 | StudBolt&nuts | In Production Unit4 | - | 1" | 160 | No | 256 | CN16 | For flange:10"300# | A193 GR.B7/A194 GR.BH |  | 3.7813 | 968.0051 | 176444776.0874
80 | StudBolt&nuts | In Production Unit4 | - | 1 1/8" | 175 | No | 160 | CN16 | For flange:12"300# | A193 GR.B7/A194 GR.BH |  | 5.4135 | 866.1651 | 157881713.961
81 | StudBolt&nuts | In Production Unit4 | - | 1 1/8" | 180 | No | 80 | CN16 | For flange:14"300# | A193 GR.B7/A194 GR.BH |  | 5.4135 | 433.0825 | 78940856.9805
82 | StudBolt&nuts | In Production Unit4 | - | 1 1/4" | 205 | No | 264 | CN16 | For flange:20"300# | A193 GR.B7/A194 GR.BH |  | 7.5871 | 2003.0067 | 365101463.5349
83 | Fitting | In Production Unit4 | 90deg.Elbow | 2 | - | No | 4 | AN01 | SCH.STD | ASTM A234 |  | 2.8161 | 11.2645 | 1283287.2899
84 | Fitting | In Production Unit4 | 90deg.Elbow | 2 | - | No | 2 | AN06 | SCH.160 | ASTM A234 |  | 2.8161 | 5.6323 | 641643.645
85 | Fitting | In Production Unit4 | 90deg.Elbow | 6 | - | No | 4 | AN06 | SCH.80 | ASTM A234 |  | 34.7232 | 138.8926 | 15823056.8758
86 | Fitting | In Production Unit4 | 90deg.Elbow | 12 | - | No | 2 | AN16 | SCH.STD | ASTM A234 | NACE | 134.8735 | 269.747 | 30730369.9088
87 | Fitting | In Production Unit4 | 90deg.Elbow | 16 | - | No | 2 | AN16 | SCH.40 | ASTM A234 | NACE | 206.2884 | 412.5767 | 47001954.3812
88 | Fitting | In Production Unit4 | 90deg.Elbow | 20 | - | No | 3 | AN16 | SCH.30 | ASTM A234 | NACE | 260.4237 | 781.271 | 89004694.9265
89 | Fitting | In Production Unit4 | 90deg.Elbow | 6 | - | No | 2 | CN16 | SCH.80 | ASTM A234 | NACE | 34.7232 | 69.4463 | 7911528.4379
90 | Fitting | In Production Unit4 | 90deg.Elbow | 8 | - | No | 4 | CN16 | SCH.80 | ASTM A234 | NACE | 54.6685 | 218.6739 | 24911970.2545
91 | Fitting | In Production Unit4 | 90deg.Elbow | 10 | - | No | 2 | CN16 | SCH.60 | ASTM A234 | NACE | 85.9466 | 171.8933 | 19582590.2713
92 | Fitting | In Production Unit4 | 90deg.Elbow | 12 | - | No | 2 | CN16 | SCH.60 | ASTM A234 | NACE | 156.1859 | 312.3717 | 35586304.0957
93 | Fitting | In Production Unit4 | 90deg.Elbow | 14 | - | No | 2 | CN16 | SCH.60 | ASTM A234 | NACE | 180.4511 | 360.9021 | 41115029.6774
94 | Fitting | In Production Unit4 | 90deg.Elbow | 20 | - | No | 3 | CN16 | SCH.SCH.60 | ASTM A234 | NACE | 281.613 | 844.839 | 96246546.7447
95 | Fitting | In Production Unit4 | Cap | 6 | - | No | 1 | AN06 | SCH.80 |  |  | 10.7177 | 10.7177 | 1220991.7904
96 | Fitting | In Production Unit4 | Pipe Nipple | 1 | - | No | 16 | AN06 | SCH.XXS | API5L-GR.B |  | 1.3671 | 21.8729 | 2491819.9804
97 | Fitting | In Production Unit4 | Pipe Nipple | 1 | - | No | 25 | AN16 | SCH.XXS | API5L-GR.B | NACE | 1.3671 | 34.1763 | 3893468.7194
98 | Fitting | In Production Unit4 | Pipe Nipple | 1 | - | No | 17 | CN16 | SCH.XXS | API5L-GR.B | NACE | 1.3671 | 23.2399 | 2647558.7292
99 | Fitting | In Production Unit4 | Reducer | 12 | 10 | No | 2 | AN16 | SCH.STD | ASTM A234 | NACE | 45.2768 | 90.5536 | 10316134.719
100 | Fitting | In Production Unit4 | Reducer | 16 | 12 | No | 2 | AN16 | SCH.40 | ASTM A234 | NACE | 60.3691 | 120.7382 | 13754846.2921
101 | Fitting | In Production Unit4 | Reducer | 8 | 6 | No | 2 | CN16 | SCH.80 | ASTM A234 | NACE | 21.6951 | 43.3903 | 4943147.8862
102 | Fitting | In Production Unit4 | Reducer | 10 | 8 | No | 2 | CN16 | SCH.60 | ASTM A234 | NACE | 37.7443 | 75.4887 | 8599893.7075
103 | Fitting | In Production Unit4 | Reducer | 12 | 10 | No | 6 | CN16 | SCH.60 | ASTM A234 | NACE | 45.2768 | 271.6609 | 30948404.1571
104 | Fitting | In Production Unit4 | Reducer | 20 | 14 | No | 2 | CN16 | SCH.SCH.60 | ASTM A234 | NACE | 75.4613 | 150.9227 | 17193557.8651
105 | Fitting | In Production Unit4 | Sockolet | 2 | 1 | No | 8 | AN06 |  | ASTM A105 |  | 9.1729 | 73.3834 | 8360056.0344
106 | Fitting | In Production Unit4 | Sockolet | 6 | 1 | No | 8 | AN06 |  | ASTM A105 |  | 9.7608 | 78.0861 | 8895797.3302
107 | Fitting | In Production Unit4 | Sockolet | 12 | 1 | No | 12 | AN16 |  | ASTM A105 | NACE | 5.1128 | 61.3534 | 6989555.0452
108 | Fitting | In Production Unit4 | Sockolet | 16 | 1 | No | 12 | AN16 |  | ASTM A105 | NACE | 7.0677 | 84.812 | 9662031.9742
109 | Fitting | In Production Unit4 | Sockolet | 20 | 1 | No | 1 | AN16 |  | ASTM A105 | NACE | 7.0677 | 7.0677 | 805169.3312
110 | Fitting | In Production Unit4 | Sockolet | 10 | 1 | No | 8 | CN16 |  | ASTM A105 | NACE | 3.9781 | 31.825 | 3625598.0715
111 | Fitting | In Production Unit4 | Sockolet | 12 | 1 | No | 8 | CN16 |  | ASTM A105 | NACE | 5.1128 | 40.9022 | 4659703.3634
112 | Fitting | In Production Unit4 | Sockolet | 20 | 1 | No | 1 | CN16 |  | ASTM A105 | NACE | 7.0677 | 7.0677 | 805169.3312
113 | Fitting | In Production Unit4 | Tee | 2 | 2 | No | 1 | AN01 | SCH.STD | ASTM A234 |  | 3.8141 | 3.8141 | 434511.1091
114 | Fitting | In Production Unit4 | Tee | 6 | 2 | No | 1 | AN06 | SCH.80 | ASTM A234 |  | 129.1865 | 129.1865 | 14717311.7595
115 | Fitting | In Production Unit4 | Tee | 6 | 6 | No | 1 | AN06 | SCH.80 | ASTM A234 |  | 129.1865 | 129.1865 | 14717311.7595
116 | Fitting | In Production Unit4 | Tee | 20 | 10 | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 1134.545 | 129250702.3857
117 | Fitting | In Production Unit4 | Tee | 20 | 16 | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 1134.545 | 129250702.3857
118 | Fitting | In Production Unit4 | Tee | 20 | 20 | No | 1 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 567.2725 | 64625351.1929
119 | Fitting | In Production Unit4 | Tee | 8 | 6 | No | 2 | CN16 | SCH.80 | ASTM A234 | NACE | 73.8482 | 147.6965 | 16826014.418
120 | Fitting | In Production Unit4 | Tee | 20 | 10 | No | 2 | CN16 | SCH.SCH.60 | ASTM A234 | NACE | 567.2725 | 1134.545 | 129250702.3857
121 | Fitting | In Production Unit4 | Tee | 20 | 12 | No | 2 | CN16 | SCH.SCH.60 | ASTM A234 | NACE | 567.2725 | 1134.545 | 129250702.3857
122 | Fitting | In Production Unit4 | Tee | 20 | 14 | No | 2 | CN16 | SCH.SCH.60 | ASTM A234 | NACE | 567.2725 | 1134.545 | 129250702.3857
123 | Fitting | In Production Unit4 | Weldolet | 12 | 11/2" | No | 2 | AN16 | SCH.STD |  | NACE | 13.6979 | 27.3958 | 3121004.5255
124 | Fitting | In Production Unit4 | Weldolet | 16 | 11/2" | No | 2 | AN16 | SCH.40 |  | NACE | 13.6979 | 27.3958 | 3121004.5255
125 | Fitting | In Production Unit4 | Weldolet | 20 | 2 | No | 1 | AN16 | SCH.30 |  | NACE | 19.8906 | 19.8906 | 2265998.7947
126 | Fitting | In Production Unit4 | Weldolet | 20 | 11/2" | No | 1 | AN16 | SCH.30 |  | NACE | 13.6979 | 13.6979 | 1560502.2628
127 | Fitting | In Production Unit4 | Weldolet | 10 | 11/2" | No | 4 | CN16 | SCH.60 |  | NACE | 13.6979 | 54.7915 | 6242009.051
128 | Fitting | In Production Unit4 | Weldolet | 12 | 11/2" | No | 4 | CN16 | SCH.60 |  | NACE | 13.6979 | 54.7915 | 6242009.051
129 | Fitting | In Production Unit4 | Weldolet | 20 | 8 | No | 1 | CN16 | SCH.SCH.60 |  | NACE | 62.2009 | 62.2009 | 7086113.0694
130 | Flange | In Production Unit4 | Flange | 2 | - | No | 1 | AN01 | SCH.STD | ASTM A105 |  | 12.7683 | 12.7683 | 1454599.9136
131 | Flange | In Production Unit4 | Flange | 2 | - | No | 6 | AN06 | SCH.160 | ASTM A105 |  | 16.7327 | 100.3964 | 11437453.7102
132 | Flange | In Production Unit4 | Flange | 2 | - | No | 1 | AN16 | SCH.160 | ASTM A105 | NACE | 25.0991 | 25.0991 | 2859363.4276
133 | Flange | In Production Unit4 | Flange | 10 | - | No | 2 | AN16 | SCH.STD | ASTM A105 | NACE | 183.0348 | 366.0696 | 41703722.1477
134 | Flange | In Production Unit4 | Flange | 12 | - | No | 10 | AN16 | SCH.STD | ASTM A105 | NACE | 200.9569 | 2009.5686 | 228935960.7035
135 | Flange | In Production Unit4 | Flange | 16 | - | No | 8 | AN16 | SCH.40 | ASTM A105 | NACE | 302.1188 | 2416.9505 | 275346107.8393
136 | Flange | In Production Unit4 | Flange | 20 | - | No | 6 | AN16 | SCH.30 | ASTM A105 | NACE | 508.5439 | 3051.2633 | 347608887.2722
137 | Flange | In Production Unit4 | Flange | 11/2" | - | No | 5 | AN16 | SCH.160 | ASTM A105 | NACE | 16.6644 | 83.3219 | 9492276.738
138 | Flange | In Production Unit4 | Flange | 6 | - | No | 4 | CN16 | SCH.80 | ASTM A105 | NACE | 52.1804 | 208.7217 | 23778192.1634
139 | Flange | In Production Unit4 | Flange | 8 | - | No | 8 | CN16 | SCH.80 | ASTM A105 | NACE | 186.22 | 1489.7602 | 169717858.8682
140 | Flange | In Production Unit4 | Flange | 10 | - | No | 14 | CN16 | SCH.60 | ASTM A105 | NACE | 183.0348 | 2562.487 | 291926055.0342
141 | Flange | In Production Unit4 | Flange | 12 | - | No | 8 | CN16 | SCH.60 | ASTM A105 | NACE | 328.0928 | 2624.7426 | 299018397.6535
142 | Flange | In Production Unit4 | Flange | 14 | - | No | 4 | CN16 | SCH.60 | ASTM A105 | NACE | 218.7286 | 874.9142 | 99672799.2178
143 | Flange | In Production Unit4 | Flange | 20 | - | No | 9 | CN16 | SCH.SCH.60 | ASTM A105 | NACE | 369.1044 | 3321.9399 | 378445159.5302
144 | Flange | In Production Unit4 | Flange | 11/2" | - | No | 8 | CN16 | SCH.XXS | ASTM A105 | NACE | 11.1141 | 88.9132 | 10129248.2205
145 | Flange | In Production Unit4 | Spectace | 2 | - | No | 1 | AN06 |  | ASTM A516 |  | 22.9255 | 22.9255 | 2611738.817
146 | Flange | In Production Unit4 | Spectace | 12 | - | No | 2 | AN16 |  | ASTM A516 | NACE | 917.7577 | 1835.5153 | 209107303.2091
147 | Flange | In Production Unit4 | Spectace | 16 | - | No | 2 | AN16 |  | ASTM A516 | NACE | 1455.4334 | 2910.8669 | 331614517.7727
148 | Flange | In Production Unit4 | Spectace | 20 | - | No | 1 | AN16 |  | ASTM A516 | NACE | 2187.2855 | 2187.2855 | 249181998.0446
149 | Flange | In Production Unit4 | Spectace | 10 | - | No | 2 | CN16 |  | ASTM A516 | NACE | 356.6642 | 713.3285 | 81264479.1123
150 | Flange | In Production Unit4 | Spectace | 12 | - | No | 2 | CN16 |  | ASTM A516 | NACE | 917.7577 | 1835.5153 | 209107303.2091
151 | Flange | In Production Unit4 | Spectace | 20 | - | No | 1 | CN16 |  | ASTM A516 | NACE | 3417.6336 | 3417.6336 | 389346871.9447
152 | Gasket | In Production Unit4 | - | 2 | - | No | 1 | AN01 |  | FLAT |  | 1.4081 | 1.4081 | 256657.458
153 | Gasket | In Production Unit4 | - | 2 | - | No | 5 | AN06 |  | FLAT |  | 1.4081 | 7.0403 | 1283287.2899
154 | Gasket | In Production Unit4 | - | 2 | - | No | 1 | AN16 |  | FLAT | NACE | 1.4081 | 1.4081 | 256657.458
155 | Gasket | In Production Unit4 | - | 10 | - | No | 2 | AN16 |  | FLAT | NACE | 30.2939 | 60.5878 | 11043746.1533
156 | Gasket | In Production Unit4 | - | 12 | - | No | 12 | AN16 |  | FLAT | NACE | 41.4764 | 497.7168 | 90722181.8481
157 | Gasket | In Production Unit4 | - | 16 | - | No | 10 | AN16 |  | FLAT | NACE | 68.216 | 682.1597 | 124341817.0242
158 | Gasket | In Production Unit4 | - | 20 | - | No | 7 | AN16 |  | FLAT | NACE | 267.9425 | 1875.5973 | 341877701.3172
159 | Gasket | In Production Unit4 | - | 6 | - | No | 4 | CN16 |  | SPIRAL WOUND | NACE | 13.3288 | 53.3151 | 9718097.9237
160 | Gasket | In Production Unit4 | - | 8 | - | No | 8 | CN16 |  | SPIRAL WOUND | NACE | 17.7854 | 142.2829 | 25934862.3565
161 | Gasket | In Production Unit4 | - | 10 | - | No | 20 | CN16 |  | SPIRAL WOUND | NACE | 21.7772 | 435.5432 | 79389384.577
162 | Gasket | In Production Unit4 | - | 12 | - | No | 14 | CN16 |  | SPIRAL WOUND | NACE | 34.1763 | 478.4687 | 87213699.3156
163 | Gasket | In Production Unit4 | - | 14 | - | No | 4 | CN16 |  | SPIRAL WOUND | NACE | 41.0116 | 164.0464 | 29901839.7653
164 | Gasket | In Production Unit4 | - | 20 | - | No | 13 | CN16 |  | SPIRAL WOUND | NACE | 82.0232 | 1066.3017 | 194361958.4748
165 | Pipe | In Production Unit4 | - | 2 | - | m | 22 | AN01 | SCH.STD | API5L-GR.B |  | 10.3349 | 227.3683 | 15541481.218
166 | Pipe | In Production Unit4 | - | 2 | - | m | 48 | AN06 | SCH.160 | API5L-GR.B |  | 10.3349 | 496.0764 | 33908686.2939
167 | Pipe | In Production Unit4 | - | 6 | - | m | 50 | AN06 | SCH.80 | API5L-GR.B |  | 111.0321 | 5551.604 | 379473035.2721
168 | Pipe | In Production Unit4 | - | 12 | - | m | 10 | AN16 | SCH.STD | API5L-GR.B | NACE | 244.2514 | 2442.5144 | 166955053.4648
169 | Pipe | In Production Unit4 | - | 16 | - | m | 10 | AN16 | SCH.40 | API5L-GR.B | NACE | 254.9008 | 2549.0078 | 174234282.5827
170 | Pipe | In Production Unit4 | - | 20 | - | m | 32 | AN16 | SCH.30 | API5L-GR.B | NACE | 300.7518 | 9624.0562 | 657840474.8377
171 | Pipe | In Production Unit4 | - | 8 | - | m | 250 | CN16 | SCH.80 | API5L-GR.B | NACE | 175.393 | 43848.239 | 2997192220.23
172 | Pipe | In Production Unit4 | - | 10 | - | m | 10 | CN16 | SCH.60 | API5L-GR.B | NACE | 138.4142 | 1384.1416 | 94611289.8826
173 | Pipe | In Production Unit4 | - | 12 | - | m | 10 | CN16 | SCH.60 | API5L-GR.B | NACE | 244.2514 | 2442.5144 | 166955053.4648
174 | Pipe | In Production Unit4 | - | 20 | - | m | 105 | CN16 | SCH.SCH.60 | API5L-GR.B | NACE | 341.7634 | 35885.1527 | 4905770586.5027
175 | Special | In Production Unit4 | Filter | 12 | - | No | 2 | AN16 |  | ASTM A216-GR.WCB | NACE | 1244.0186 | 2488.0373 | 283444522.7757
176 | Special | In Production Unit4 | Filter | 16 | - | No | 2 | AN16 |  | ASTM A216-GR.WCB | NACE | 1804.5105 | 3609.0211 | 411150296.7736
177 | Special | In Production Unit4 | Orifice Flange | 10 | - | No | 4 | CN16 | SCH.60 | ASTM A105 | NACE | 183.0348 | 732.1391 | 83407444.2955
178 | Special | In Production Unit4 | Orifice Flange | 12 | - | No | 4 | CN16 | SCH.60 | ASTM A105 | NACE | 328.0928 | 1312.3713 | 149509198.8267
179 | Special | In Production Unit4 | Orifice Flange | 20 | - | No | 2 | CN16 | SCH.SCH.60 | ASTM A105 | NACE | 369.1044 | 738.2089 | 84098924.34
180 | Valve | In Production Unit4 | Check | 2 | - | No | 1 | AN06 | - | ASTM A216-GR.WCB |  | 102.529 | 102.529 | 7008243.695
181 | Valve | In Production Unit4 | Check | 10 | - | No | 2 | CN16 | - | ASTM A216-GR.WCB | NACE | 1640.4641 | 3280.9283 | 224263798.2401
182 | Valve | In Production Unit4 | Check | 12 | - | No | 2 | CN16 | - | ASTM A216-GR.WCB | NACE | 2460.6962 | 4921.3924 | 336395697.3602
183 | Valve | In Production Unit4 | Gate | 1 | - | No | 16 | AN06 |  | ASTM A105 |  | 54.6821 | 874.9142 | 59803679.5307
184 | Valve | In Production Unit4 | Gate | 2 | - | No | 1 | AN06 | - | ASTM A216-GR.WCB |  | 159.2617 | 159.2617 | 10886138.5396
185 | Valve | In Production Unit4 | Gate | 1 | - | No | 25 | AN16 |  | ASTM A105 | NACE | 54.6821 | 1367.0534 | 93443249.2667
186 | Valve | In Production Unit4 | Gate | 2 | - | No | 1 | AN16 | - | ASTM A216-GR.WCB | NACE | 195.4886 | 195.4886 | 13362384.6451
187 | Valve | In Production Unit4 | Gate | 12 | - | No | 2 | AN16 | - | ASTM A216-GR.WCB | NACE | 1864.6609 | 3729.3218 | 254913183.9996
188 | Valve | In Production Unit4 | Gate | 16 | - | No | 2 | AN16 | - | ASTM A216-GR.WCB | NACE | 7518.7939 | 15037.5878 | 1027875741.9339
189 | Valve | In Production Unit4 | Gate | 20 | - | No | 3 | AN16 | - | ASTM A216-GR.WCB | NACE | 12303.4809 | 36910.4428 | 2522967730.2014
190 | Valve | In Production Unit4 | Gate | 1 | - | No | 17 | CN16 |  | ASTM A105 | NACE | 54.6821 | 929.5963 | 63541409.5014
191 | Valve | In Production Unit4 | Gate | 10 | - | No | 2 | CN16 | - | ASTM A216-GR.WCB | NACE | 2050.5802 | 4101.1603 | 280329747.8002
192 | Valve | In Production Unit4 | Gate | 12 | - | No | 2 | CN16 | - | ASTM A216-GR.WCB | NACE | 2460.6962 | 4921.3924 | 336395697.3602
193 | Valve | In Production Unit4 | Gate | 14 | - | No | 1 | CN16 | - | ASTM A216-GR.WCB | NACE | 6151.7405 | 6151.7405 | 420494621.7002
194 | Valve | In Production Unit4 | Gate | 20 | - | No | 4 | CN16 | - | ASTM A216-GR.WCB | NACE | 17771.6947 | 71086.7788 | 4859048961.8694
195 | Valve | In Production Unit4 | Globe | 6 | - | No | 1 | CN16 | - | ASTM A216-GR.WCB | NACE | 2734.1069 | 2734.1069 | 186886498.5334
196 | StudBolt&nuts | In Desalting Plant 4 | - | 1/2" | 65 | No | 8 | AN01 | For flange:1"150# | A193 GR.B7/A194 GR.BH |  | 0.47573 | 3.8059 | 693722.6826
197 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 85 | No | 224 | AN01 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 203.9425 | 37173967.1963
198 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 360 | AN01 | For flange:3"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 327.7647 | 59743875.8512
199 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 496 | AN01 | For flange:4"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 451.587 | 82313784.5061
200 | StudBolt&nuts | In Desalting Plant 4 | - | 3/4" | 105 | No | 96 | AN01 | For flange:6"150# | A193 GR.B7/A194 GR.BH |  | 1.5625 | 150.004 | 27342242.2814
201 | StudBolt&nuts | In Desalting Plant 4 | - | 1/2" | 70 | No | 32 | AN01 | For flange:11/2"150# | A193 GR.B7/A194 GR.BH |  | 0.47573 | 15.2235 | 2774890.7302
202 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 8 | AN01 | For flange:21/2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 7.2837 | 1327641.6856
203 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 85 | No | 408 | AN06 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 371.4667 | 67709725.9647
204 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 336 | AN06 | For flange:3"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 305.9138 | 55760950.7944
205 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 368 | AN06 | For flange:4"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 335.0484 | 61071517.5368
206 | StudBolt&nuts | In Desalting Plant 4 | - | 3/4" | 105 | No | 168 | AN06 | For flange:6"150# | A193 GR.B7/A194 GR.BH |  | 1.5625 | 262.5071 | 47848923.9925
207 | StudBolt&nuts | In Desalting Plant 4 | - | 3/4" | 110 | No | 80 | AN06 | For flange:8"150# | A193 GR.B7/A194 GR.BH |  | 1.5625 | 125.0034 | 22785201.9012
208 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 85 | No | 372 | AN16 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 338.6902 | 61735338.3795
209 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 352 | AN16 | For flange:3"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 320.4811 | 58416234.1656
210 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 272 | AN16 | For flange:4"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 247.6445 | 45139817.3098
211 | StudBolt&nuts | In Desalting Plant 4 | - | 3/4" | 105 | No | 392 | AN16 | For flange:6"150# | A193 GR.B7/A194 GR.BH |  | 1.5625 | 612.5165 | 111647489.3159
212 | StudBolt&nuts | In Desalting Plant 4 | - | 3/4" | 110 | No | 528 | AN16 | For flange:8"150# | A193 GR.B7/A194 GR.BH |  | 1.5625 | 825.0222 | 150382332.5479
213 | StudBolt&nuts | In Desalting Plant 4 | - | 7/8" | 115 | No | 1428 | AN16 | For flange:10"150# | A193 GR.B7/A194 GR.BH |  | 2.3705 | 3385.0321 | 617012502.8221
214 | StudBolt&nuts | In Desalting Plant 4 | - | 7/8" | 125 | No | 96 | AN16 | For flange:12"150# | A193 GR.B7/A194 GR.BH |  | 2.4771 | 237.8017 | 43345706.9239
215 | StudBolt&nuts | In Desalting Plant 4 | - | 7/8" | 125 | No | 1224 | AN16 | For flange:12"150# | A193 GR.B7/A194 GR.BH |  | 2.4771 | 3031.9714 | 552657763.2791
216 | StudBolt&nuts | In Desalting Plant 4 | - | 1" | 135 | No | 192 | AN16 | For flange:16"150# | A193 GR.B7/A194 GR.BH |  | 3.5024 | 672.4591 | 122573621.5661
217 | StudBolt&nuts | In Desalting Plant 4 | - | 1 1/8" | 150 | No | 64 | AN16 | For flange:18"150# | A193 GR.B7/A194 GR.BH |  | 4.8804 | 312.3444 | 56933102.9132
218 | StudBolt&nuts | In Desalting Plant 4 | - | 1 1/8" | 160 | No | 340 | AN16 | For flange:20"150# | A193 GR.B7/A194 GR.BH |  | 5.0444 | 1715.1052 | 312623734.7467
219 | StudBolt&nuts | In Desalting Plant 4 | - | 1 1/4" | 230 | No | 24 | AN16 | For flange:26"150# | A193 GR.B7/A194 GR.BH |  | 8.0383 | 192.9186 | 35164563.5641
220 | StudBolt&nuts | In Desalting Plant 4 | - | 1/2" | 70 | No | 72 | AN16 | For flange:11/2"150# | A193 GR.B7/A194 GR.BH |  | 0.47573 | 34.2529 | 6243504.143
221 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 16 | AN16 | For flange:21/2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 14.5673 | 2655283.3712
222 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 85 | No | 56 | AZ00 | For flange:2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 67.9808 | 12391322.3988
223 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 40 | AZ00 | For flange:3"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 48.5577 | 8850944.5705
224 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 1 | - | No | 2 | AN01 | SCH.80 | ASTM A234 |  | 5.8783 | 11.7567 | 1339353.2395
225 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 2 | - | No | 62 | AN01 | SCH.STD | ASTM A234 |  | 2.8161 | 174.6001 | 19890952.9939
226 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 3 | - | No | 59 | AN01 | SCH.STD | ASTM A234 |  | 7.013 | 413.7661 | 47137447.0926
227 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 4 | - | No | 42 | AN01 | SCH.STD | ASTM A234 |  | 13.2331 | 555.7892 | 63317145.7031
228 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 6 | - | No | 9 | AN01 | SCH.STD | ASTM A234 |  | 34.7232 | 312.5084 | 35601877.9706
229 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 2 | 3 | No | 2 | AN06 | SCH.160 | ASTM A234 |  | 2.8161 | 5.6323 | 641643.645
230 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 2 | - | No | 89 | AN06 | SCH.160 | ASTM A234 |  | 2.8161 | 250.6356 | 28553142.2009
231 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 3 | - | No | 77 | AN06 | SCH.80 | ASTM A234 |  | 7.013 | 539.9998 | 61518363.1547
232 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 4 | - | No | 43 | AN06 | SCH.80 | ASTM A234 |  | 13.2331 | 569.0223 | 64824696.7913
233 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 6 | - | No | 40 | AN06 | SCH.80 | ASTM A234 |  | 34.7232 | 1388.9263 | 158230568.7583
234 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 8 | - | No | 13 | AN06 | SCH.60 | ASTM A234 |  | 54.6685 | 710.6901 | 80963903.3271
235 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 2 | - | No | 118 | AN16 | SCH.160 | ASTM A234 | NACE | 2.8161 | 332.3033 | 37856975.0529
236 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 3 | - | No | 52 | AN16 | SCH.80 | ASTM A234 | NACE | 7.013 | 364.6752 | 41544868.624
237 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 4 | - | No | 19 | AN16 | SCH.80 | ASTM A234 | NACE | 13.2331 | 251.4285 | 28643470.6752
238 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 6 | - | No | 51 | AN16 | SCH.80 | ASTM A234 | NACE | 34.7232 | 1770.881 | 201743975.1668
239 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 8 | - | No | 23 | AN16 | SCH.60 | ASTM A234 | NACE | 54.6685 | 1257.3747 | 143243828.9634
240 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 10 | - | No | 41 | AN16 | SCH.STD | ASTM A234 | NACE | 85.9466 | 3523.8126 | 401443100.5622
241 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 12 | - | No | 76 | AN16 | SCH.STD | ASTM A234 | NACE | 134.8735 | 10250.3854 | 1167754056.5362
242 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 16 | - | No | 11 | AN16 | SCH.40 | ASTM A234 | NACE | 206.2884 | 2269.172 | 258510749.0964
243 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 18 | - | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 246.8899 | 493.7797 | 56252836.0586
244 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 20 | - | No | 5 | AN16 | SCH.30 | ASTM A234 | NACE | 260.4237 | 1302.1184 | 148341158.2109
245 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 2 | - | No | 18 | AZ00 | SCH.40 | ASTM A234 | GALVD | 2.8161 | 50.6903 | 5774792.8047
246 | Fitting | In Desalting Plant 4 | Cap | 2 | - | No | 5 | AN06 | SCH.160 |  |  | 2.7614 | 13.8072 | 1572961.3627
247 | Fitting | In Desalting Plant 4 | Cap | 3 | - | No | 1 | AN06 | SCH.80 |  |  | 3.5817 | 3.5817 | 408035.5218
248 | Fitting | In Desalting Plant 4 | Cap | 2 | - | No | 1 | AN16 | SCH.160 |  | NACE | 2.7614 | 2.7614 | 314592.2725
249 | Fitting | In Desalting Plant 4 | Cap | 8 | - | No | 1 | AN16 | SCH.60 |  | NACE | 12.0848 | 12.0848 | 1376730.5392
250 | Fitting | In Desalting Plant 4 | Cap | 12 | - | No | 2 | AN16 | SCH.STD |  | NACE | 14.19 | 28.38 | 3233136.4246
251 | Fitting | In Desalting Plant 4 | Cap | 16 | - | No | 1 | AN16 | SCH.40 |  | NACE | 22.4197 | 22.4197 | 2554115.48
252 | Fitting | In Desalting Plant 4 | Cap | 3 | - | No | 1 | AZ00 | SCH.40 |  | GALVD | 3.5817 | 3.5817 | 408035.5218
253 | Fitting | In Desalting Plant 4 | Pipe Nipple | 1 | - | No | 66 | AN01 | SCH.80 | API5L-GR.B |  | 1.3671 | 90.2255 | 10278757.4193
254 | Fitting | In Desalting Plant 4 | Pipe Nipple | 3/4" | - | No | 11 | AN01 | SCH.80 | API5L-GR.B |  | 1.3671 | 15.0376 | 1713126.2366
255 | Fitting | In Desalting Plant 4 | Pipe Nipple | 1 | - | No | 42 | AN06 | SCH.XXS | API5L-GR.B |  | 1.3671 | 57.4162 | 6541027.4487
256 | Fitting | In Desalting Plant 4 | Pipe Nipple | 3/4" | - | No | 16 | AN06 | SCH.XXS | API5L-GR.B |  | 1.3671 | 21.8729 | 2491819.9804
257 | Fitting | In Desalting Plant 4 | Pipe Nipple | 1 | - | No | 140 | AN16 | SCH.XXS | API5L-GR.B | NACE | 1.3671 | 191.3875 | 21803424.8289
258 | Fitting | In Desalting Plant 4 | Pipe Nipple | 1 | - | No | 2 | AZ00 | SCH.80 | API5L-GR.B | GALVD | 1.3671 | 2.7341 | 311477.4976
259 | Fitting | In Desalting Plant 4 | Pipe Nipple | 11/2" | - | No | 1 | AZ00 | SCH.80 | API5L-GR.B | GALVD | 1.3671 | 1.3671 | 155738.7488
260 | Fitting | In Desalting Plant 4 | Plug | 3/4" | - | No | 3 | AN01 |  | ASTM A105 |  | 2.1189 | 6.3568 | 724185.1818
261 | Fitting | In Desalting Plant 4 | Plug | 3/4" | - | No | 16 | AN06 |  | ASTM A105 |  | 2.1189 | 33.9029 | 3862320.9697
262 | Fitting | In Desalting Plant 4 | Plug | 1 | - | No | 10 | AN16 |  | ASTM A105 | NACE | 2.1189 | 21.1893 | 2413950.6061
263 | Fitting | In Desalting Plant 4 | Reducer | 2 | 11/2" | No | 8 | AN01 | SCH.STD | ASTM A234 |  | 25.4135 | 203.3082 | 23161466.7182
264 | Fitting | In Desalting Plant 4 | Reducer | 3 | 2 | No | 3 | AN01 | SCH.STD | ASTM A234 |  | 53.0417 | 159.125 | 18127990.3577
265 | Fitting | In Desalting Plant 4 | Reducer | 3 | 4 | No | 4 | AN01 | SCH.STD | ASTM A234 |  | 53.0417 | 212.1667 | 24170653.8103
266 | Fitting | In Desalting Plant 4 | Reducer | 3 | 21/2" | No | 2 | AN01 | SCH.STD | ASTM A234 |  | 53.0417 | 106.0833 | 12085326.9052
267 | Fitting | In Desalting Plant 4 | Reducer | 4 | 3 | No | 13 | AN01 | SCH.STD | ASTM A234 |  | 5.7143 | 74.2857 | 8462843.6086
268 | Fitting | In Desalting Plant 4 | Reducer | 6 | 4 | No | 3 | AN01 | SCH.STD | ASTM A234 |  | 12.4812 | 37.4436 | 4265684.329
269 | Fitting | In Desalting Plant 4 | Reducer | 3 | 2 | No | 6 | AN06 | SCH.80 | ASTM A234 |  | 53.0417 | 318.25 | 36255980.7155
270 | Fitting | In Desalting Plant 4 | Reducer | 4 | 3 | No | 6 | AN06 | SCH.80 | ASTM A234 |  | 5.7143 | 34.2857 | 3905927.8193
271 | Fitting | In Desalting Plant 4 | Reducer | 6 | 4 | No | 1 | AN06 | SCH.80 | ASTM A234 |  | 12.4812 | 12.4812 | 1421894.7763
272 | Fitting | In Desalting Plant 4 | Reducer | 2 | 11/2" | No | 10 | AN16 | SCH.160 | ASTM A234 | NACE | 25.4135 | 254.1352 | 28951833.3978
273 | Fitting | In Desalting Plant 4 | Reducer | 3 | 2 | No | 18 | AN16 | SCH.80 | ASTM A234 | NACE | 53.0417 | 954.7501 | 108767942.1465
274 | Fitting | In Desalting Plant 4 | Reducer | 3 | 21/2" | No | 4 | AN16 | SCH.80 | ASTM A234 | NACE | 53.0417 | 212.1667 | 24170653.8103
275 | Fitting | In Desalting Plant 4 | Reducer | 4 | 3 | No | 2 | AN16 | SCH.80 | ASTM A234 | NACE | 5.7143 | 11.4286 | 1301975.9398
276 | Fitting | In Desalting Plant 4 | Reducer | 6 | 3 | No | 2 | AN16 | SCH.80 | ASTM A234 | NACE | 12.4812 | 24.9624 | 2843789.5527
277 | Fitting | In Desalting Plant 4 | Reducer | 6 | 4 | No | 4 | AN16 | SCH.80 | ASTM A234 | NACE | 12.4812 | 49.9248 | 5687579.1054
278 | Fitting | In Desalting Plant 4 | Reducer | 8 | 6 | No | 4 | AN16 | SCH.60 | ASTM A234 | NACE | 21.6951 | 86.7806 | 9886295.7724
279 | Fitting | In Desalting Plant 4 | Reducer | 10 | 8 | No | 14 | AN16 | SCH.STD | ASTM A234 | NACE | 37.7443 | 528.4208 | 60199255.9526
280 | Fitting | In Desalting Plant 4 | Reducer | 12 | 10 | No | 4 | AN16 | SCH.STD | ASTM A234 | NACE | 45.2768 | 181.1072 | 20632269.4381
281 | Fitting | In Desalting Plant 4 | Reducer | 20 | 12 | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 75.4613 | 150.9227 | 17193557.8651
282 | Fitting | In Desalting Plant 4 | Reducer | 20 | 18 | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 75.4613 | 150.9227 | 17193557.8651
283 | Fitting | In Desalting Plant 4 | Reducer | 26 | 16 | No | 1 | AN16 | SCH.30 | ASTM A234 | NACE | 98.0998 | 98.0998 | 11175812.6123
284 | Fitting | In Desalting Plant 4 | Reducer | 3 | 2 | No | 2 | AZ00 | SCH.40 | ASTM A234 | GALVD | 53.0417 | 106.0833 | 12085326.9052
285 | Fitting | In Desalting Plant 4 | Reducer | 4 | 3 | No | 2 | AZ00 | SCH.40 | ASTM A234 | GALVD | 5.7143 | 11.4286 | 1301975.9398
286 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 1 | No | 7 | AN01 |  | ASTM A105 |  | 9.1729 | 64.2105 | 7315049.0301
287 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 3/4" | No | 4 | AN01 |  | ASTM A105 |  | 9.1729 | 36.6917 | 4180028.0172
288 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 1 | No | 30 | AN01 |  | ASTM A105 |  | 3.9781 | 119.3438 | 13595992.7683
289 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 11/2" | No | 2 | AN01 |  | ASTM A105 |  | 3.9781 | 7.9563 | 906399.5179
290 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 3/4" | No | 2 | AN01 |  | ASTM A105 |  | 3.9781 | 7.9563 | 906399.5179
291 | Fitting | In Desalting Plant 4 | Sockolet | 4 | 1 | No | 38 | AN01 |  | ASTM A105 |  | 7.0677 | 268.5713 | 30596434.5849
292 | Fitting | In Desalting Plant 4 | Sockolet | 4 | 3/4" | No | 1 | AN01 |  | ASTM A105 |  | 7.0677 | 7.0677 | 805169.3312
293 | Fitting | In Desalting Plant 4 | Sockolet | 6 | 1 | No | 10 | AN01 |  | ASTM A105 |  | 9.7608 | 97.6076 | 11119746.6627
294 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 1 | No | 60 | AN06 |  | ASTM A105 |  | 9.1729 | 550.3757 | 62700420.258
295 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 2 | No | 5 | AN06 |  | ASTM A105 |  | 9.1729 | 45.8646 | 5225035.0215
296 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 3/4" | No | 10 | AN06 |  | ASTM A105 |  | 9.1729 | 91.7293 | 10450070.043
297 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 1 | No | 23 | AN06 |  | ASTM A105 |  | 3.9781 | 91.4969 | 10423594.4557
298 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 3/4" | No | 4 | AN06 |  | ASTM A105 |  | 3.9781 | 15.9125 | 1812799.0358
299 | Fitting | In Desalting Plant 4 | Sockolet | 4 | 1 | No | 18 | AN06 |  | ASTM A105 |  | 7.0677 | 127.218 | 14493047.9613
300 | Fitting | In Desalting Plant 4 | Sockolet | 4 | 3/4" | No | 4 | AN06 |  | ASTM A105 |  | 7.0677 | 28.2707 | 3220677.3247
301 | Fitting | In Desalting Plant 4 | Sockolet | 6 | 1 | No | 24 | AN06 |  | ASTM A105 |  | 9.7608 | 234.2583 | 26687391.9906
302 | Fitting | In Desalting Plant 4 | Sockolet | 6 | 3/4" | No | 8 | AN06 |  | ASTM A105 |  | 9.7608 | 78.0861 | 8895797.3302
303 | Fitting | In Desalting Plant 4 | Sockolet | 8 | 1 | No | 11 | AN06 |  | ASTM A105 |  | 7.0677 | 77.7443 | 8856862.643
304 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 1 | No | 17 | AN16 |  | ASTM A105 | NACE | 9.1729 | 155.9398 | 17765119.0731
305 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 11/2" | No | 4 | AN16 |  | ASTM A105 | NACE | 9.1729 | 36.6917 | 4180028.0172
306 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 1 | No | 28 | AN16 |  | ASTM A105 | NACE | 3.9781 | 111.3875 | 12689593.2504
307 | Fitting | In Desalting Plant 4 | Sockolet | 4 | 1 | No | 11 | AN16 |  | ASTM A105 | NACE | 7.0677 | 77.7443 | 8856862.643
308 | Fitting | In Desalting Plant 4 | Sockolet | 6 | 1 | No | 5 | AN16 |  | ASTM A105 | NACE | 9.7608 | 48.8038 | 5559873.3314
309 | Fitting | In Desalting Plant 4 | Sockolet | 8 | 1 | No | 20 | AN16 |  | ASTM A105 | NACE | 7.0677 | 141.3533 | 16103386.6236
310 | Fitting | In Desalting Plant 4 | Sockolet | 10 | 1 | No | 45 | AN16 |  | ASTM A105 | NACE | 3.9781 | 179.0156 | 20393989.1525
311 | Fitting | In Desalting Plant 4 | Sockolet | 12 | 1 | No | 38 | AN16 |  | ASTM A105 | NACE | 5.1128 | 194.2856 | 22133590.9763
312 | Fitting | In Desalting Plant 4 | Sockolet | 20 | 1 | No | 9 | AN16 |  | ASTM A105 | NACE | 7.0677 | 63.609 | 7246523.9806
313 | Fitting | In Desalting Plant 4 | Sockolet | 20 | 3/4" | No | 1 | AN16 |  | ASTM A105 | NACE | 7.0677 | 7.0677 | 805169.3312
314 | Fitting | In Desalting Plant 4 | Tee | 2 | 1 | No | 4 | AN01 | SCH.STD | ASTM A234 |  | 3.8141 | 15.2563 | 1738044.4364
315 | Fitting | In Desalting Plant 4 | Tee | 2 | 2 | No | 9 | AN01 | SCH.STD | ASTM A234 |  | 3.8141 | 34.3267 | 3910599.9818
316 | Fitting | In Desalting Plant 4 | Tee | 2 | 3/4" | No | 3 | AN01 | SCH.STD | ASTM A234 |  | 3.8141 | 11.4422 | 1303533.3273
317 | Fitting | In Desalting Plant 4 | Tee | 3 | 1 | No | 3 | AN01 | SCH.STD | ASTM A234 |  | 10.3896 | 31.1688 | 3550843.4721
318 | Fitting | In Desalting Plant 4 | Tee | 3 | 2 | No | 6 | AN01 | SCH.STD | ASTM A234 |  | 10.3896 | 62.3376 | 7101686.9443
319 | Fitting | In Desalting Plant 4 | Tee | 3 | 3 | No | 15 | AN01 | SCH.STD | ASTM A234 |  | 10.3896 | 155.8441 | 17754217.3607
320 | Fitting | In Desalting Plant 4 | Tee | 4 | 3 | No | 7 | AN01 | SCH.STD | ASTM A234 |  | 17.758 | 124.3062 | 14161324.4264
321 | Fitting | In Desalting Plant 4 | Tee | 4 | 4 | No | 8 | AN01 | SCH.STD | ASTM A234 |  | 17.758 | 142.0642 | 16184370.773
322 | Fitting | In Desalting Plant 4 | Tee | 6 | 4 | No | 2 | AN01 | SCH.STD | ASTM A234 |  | 129.1865 | 258.3731 | 29434623.519
323 | Fitting | In Desalting Plant 4 | Tee | 6 | 6 | No | 2 | AN01 | SCH.STD | ASTM A234 |  | 129.1865 | 258.3731 | 29434623.519
324 | Fitting | In Desalting Plant 4 | Tee | 2 | 2 | No | 10 | AN06 | SCH.160 | ASTM A234 |  | 3.8141 | 38.1408 | 4345111.0909
325 | Fitting | In Desalting Plant 4 | Tee | 3 | 3 | No | 21 | AN06 | SCH.80 | ASTM A234 |  | 10.3896 | 218.1817 | 24855904.3049
326 | Fitting | In Desalting Plant 4 | Tee | 4 | 2 | No | 4 | AN06 | SCH.80 | ASTM A234 |  | 17.758 | 71.0321 | 8092185.3865
327 | Fitting | In Desalting Plant 4 | Tee | 4 | 3 | No | 2 | AN06 | SCH.80 | ASTM A234 |  | 17.758 | 35.516 | 4046092.6932
328 | Fitting | In Desalting Plant 4 | Tee | 4 | 4 | No | 7 | AN06 | SCH.80 | ASTM A234 |  | 17.758 | 124.3062 | 14161324.4264
329 | Fitting | In Desalting Plant 4 | Tee | 6 | 4 | No | 4 | AN06 | SCH.80 | ASTM A234 |  | 129.1865 | 516.7462 | 58869247.038
330 | Fitting | In Desalting Plant 4 | Tee | 6 | 6 | No | 10 | AN06 | SCH.80 | ASTM A234 |  | 129.1865 | 1291.8655 | 147173117.5951
331 | Fitting | In Desalting Plant 4 | Tee | 8 | 4 | No | 2 | AN06 | SCH.60 | ASTM A234 |  | 73.8482 | 147.6965 | 16826014.418
332 | Fitting | In Desalting Plant 4 | Tee | 8 | 6 | No | 3 | AN06 | SCH.60 | ASTM A234 |  | 73.8482 | 221.5447 | 25239021.6269
333 | Fitting | In Desalting Plant 4 | Tee | 8 | 8 | No | 5 | AN06 | SCH.60 | ASTM A234 |  | 73.8482 | 369.2411 | 42065036.0449
334 | Fitting | In Desalting Plant 4 | Tee | 2 | 2 | No | 7 | AN16 | SCH.160 | ASTM A234 | NACE | 3.8141 | 26.6986 | 3041577.7636
335 | Fitting | In Desalting Plant 4 | Tee | 3 | 2 | No | 4 | AN16 | SCH.80 | ASTM A234 | NACE | 10.3896 | 41.5584 | 4734457.9628
336 | Fitting | In Desalting Plant 4 | Tee | 3 | 3 | No | 9 | AN16 | SCH.80 | ASTM A234 | NACE | 10.3896 | 93.5065 | 10652530.4164
337 | Fitting | In Desalting Plant 4 | Tee | 4 | 4 | No | 6 | AN16 | SCH.80 | ASTM A234 | NACE | 17.758 | 106.5481 | 12138278.0797
338 | Fitting | In Desalting Plant 4 | Tee | 6 | 3 | No | 2 | AN16 | SCH.80 | ASTM A234 | NACE | 129.1865 | 258.3731 | 29434623.519
339 | Fitting | In Desalting Plant 4 | Tee | 6 | 4 | No | 6 | AN16 | SCH.80 | ASTM A234 | NACE | 129.1865 | 775.1193 | 88303870.557
340 | Fitting | In Desalting Plant 4 | Tee | 6 | 6 | No | 2 | AN16 | SCH.80 | ASTM A234 | NACE | 129.1865 | 258.3731 | 29434623.519
341 | Fitting | In Desalting Plant 4 | Tee | 8 | 8 | No | 2 | AN16 | SCH.60 | ASTM A234 | NACE | 73.8482 | 147.6965 | 16826014.418
342 | Fitting | In Desalting Plant 4 | Tee | 10 | 6 | No | 4 | AN16 | SCH.STD | ASTM A234 | NACE | 107.2864 | 429.1454 | 48889508.0163
343 | Fitting | In Desalting Plant 4 | Tee | 10 | 8 | No | 12 | AN16 | SCH.STD | ASTM A234 | NACE | 107.2864 | 1287.4362 | 146668524.049
344 | Fitting | In Desalting Plant 4 | Tee | 10 | 10 | No | 12 | AN16 | SCH.STD | ASTM A234 | NACE | 107.2864 | 1287.4362 | 146668524.049
345 | Fitting | In Desalting Plant 4 | Tee | 12 | 10 | No | 10 | AN16 | SCH.STD | ASTM A234 | NACE | 157.4299 | 1574.2987 | 179348743.0926
346 | Fitting | In Desalting Plant 4 | Tee | 12 | 12 | No | 24 | AN16 | SCH.STD | ASTM A234 | NACE | 157.4299 | 3778.317 | 430436983.4222
347 | Fitting | In Desalting Plant 4 | Tee | 16 | 16 | No | 2 | AN16 | SCH.40 | ASTM A234 | NACE | 453.8207 | 907.6415 | 103401184.8636
348 | Fitting | In Desalting Plant 4 | Tee | 20 | 12 | No | 3 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 1701.8175 | 193876053.5786
349 | Fitting | In Desalting Plant 4 | Tee | 20 | 18 | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 1134.545 | 129250702.3857
350 | Fitting | In Desalting Plant 4 | Tee | 20 | 20 | No | 1 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 567.2725 | 64625351.1929
351 | Fitting | In Desalting Plant 4 | Tee | 3 | 1 | No | 11 | AZ00 | SCH.40 | ASTM A234 | GALVD | 10.3896 | 114.2857 | 13019759.3978
352 | Fitting | In Desalting Plant 4 | Tee | 3 | 2 | No | 4 | AZ00 | SCH.40 | ASTM A234 | GALVD | 10.3896 | 41.5584 | 4734457.9628
353 | Fitting | In Desalting Plant 4 | Tee | 3 | 3 | No | 1 | AZ00 | SCH.40 | ASTM A234 | GALVD | 10.3896 | 10.3896 | 1183614.4907
354 | Fitting | In Desalting Plant 4 | Tee | 3 | 3/4" | No | 1 | AZ00 | SCH.40 | ASTM A234 | GALVD | 10.3896 | 10.3896 | 1183614.4907
355 | Fitting | In Desalting Plant 4 | Tee | 4 | 11/2" | No | 1 | AZ00 | SCH.40 | ASTM A234 | GALVD | 17.758 | 17.758 | 2023046.3466
356 | Fitting | In Desalting Plant 4 | Weldolet | 3 | 2 | No | 2 | AN01 | SCH.STD |  |  | 19.8906 | 39.7813 | 4531997.5894
357 | Fitting | In Desalting Plant 4 | Weldolet | 3 | 11/2" | No | 4 | AN01 | SCH.STD |  |  | 19.8906 | 79.5625 | 9063995.1789
358 | Fitting | In Desalting Plant 4 | Weldolet | 4 | 2 | No | 1 | AN01 | SCH.STD |  |  | 19.8906 | 19.8906 | 2265998.7947
359 | Fitting | In Desalting Plant 4 | Weldolet | 4 | 11/2" | No | 5 | AN01 | SCH.STD |  |  | 19.8906 | 99.4531 | 11329993.9736
360 | Fitting | In Desalting Plant 4 | Weldolet | 6 | 11/2" | No | 1 | AN01 | SCH.STD |  |  | 19.8906 | 19.8906 | 2265998.7947
361 | Fitting | In Desalting Plant 4 | Weldolet | 3 | 11/2" | No | 1 | AN06 | SCH.80 |  |  | 19.8906 | 19.8906 | 2265998.7947
362 | Fitting | In Desalting Plant 4 | Weldolet | 4 | 11/2" | No | 3 | AN06 | SCH.80 |  |  | 19.8906 | 59.6719 | 6797996.3842
363 | Fitting | In Desalting Plant 4 | Weldolet | 6 | 2 | No | 15 | AN06 | SCH.80 |  |  | 19.8906 | 298.3594 | 33989981.9208
364 | Fitting | In Desalting Plant 4 | Weldolet | 6 | 3 | No | 2 | AN06 | SCH.80 |  |  | 30.9364 | 61.8728 | 7048735.7697
365 | Fitting | In Desalting Plant 4 | Weldolet | 8 | 2 | No | 11 | AN06 | SCH.60 |  |  | 19.8906 | 218.7969 | 24925986.7419
366 | Fitting | In Desalting Plant 4 | Weldolet | 8 | 3 | No | 3 | AN06 | SCH.60 |  |  | 30.9364 | 92.8093 | 10573103.6545
367 | Fitting | In Desalting Plant 4 | Weldolet | 8 | 4 | No | 3 | AN06 | SCH.60 |  |  | 19.8906 | 59.6719 | 6797996.3842
368 | Fitting | In Desalting Plant 4 | Weldolet | 10 | 2 | No | 7 | AN16 | SCH.STD |  | NACE | 19.8906 | 139.2344 | 15861991.563
369 | Fitting | In Desalting Plant 4 | Weldolet | 10 | 3 | No | 5 | AN16 | SCH.STD |  | NACE | 30.9364 | 154.6821 | 17621839.4242
370 | Fitting | In Desalting Plant 4 | Weldolet | 10 | 4 | No | 1 | AN16 | SCH.STD |  | NACE | 50.827 | 50.827 | 5790366.6796
371 | Fitting | In Desalting Plant 4 | Weldolet | 10 | 11/2" | No | 17 | AN16 | SCH.STD |  | NACE | 13.6979 | 232.8639 | 26528538.4668
372 | Fitting | In Desalting Plant 4 | Weldolet | 12 | 2 | No | 6 | AN16 | SCH.STD |  | NACE | 19.8906 | 119.3438 | 13595992.7683
373 | Fitting | In Desalting Plant 4 | Weldolet | 12 | 4 | No | 4 | AN16 | SCH.STD |  | NACE | 50.827 | 203.3082 | 23161466.7182
374 | Fitting | In Desalting Plant 4 | Weldolet | 12 | 6 | No | 8 | AN16 | SCH.STD |  | NACE | 45.7963 | 366.3703 | 41737984.6725
375 | Fitting | In Desalting Plant 4 | Weldolet | 12 | 11/2" | No | 16 | AN16 | SCH.STD |  | NACE | 13.6979 | 219.166 | 24968036.2041
376 | Fitting | In Desalting Plant 4 | Weldolet | 16 | 2 | No | 5 | AN16 | SCH.40 |  | NACE | 19.8906 | 99.4531 | 11329993.9736
377 | Fitting | In Desalting Plant 4 | Weldolet | 16 | 3 | No | 9 | AN16 | SCH.40 |  | NACE | 30.9364 | 278.4278 | 31719310.9636
378 | Fitting | In Desalting Plant 4 | Weldolet | 16 | 6 | No | 3 | AN16 | SCH.40 |  | NACE | 45.7963 | 137.3889 | 15651744.2522
379 | Fitting | In Desalting Plant 4 | Weldolet | 16 | 11/2" | No | 1 | AN16 | SCH.40 |  | NACE | 13.6979 | 13.6979 | 1560502.2628
380 | Fitting | In Desalting Plant 4 | Weldolet | 20 | 2 | No | 1 | AN16 | SCH.30 |  | NACE | 19.8906 | 19.8906 | 2265998.7947
381 | Fitting | In Desalting Plant 4 | Weldolet | 20 | 3 | No | 1 | AN16 | SCH.30 |  | NACE | 30.9364 | 30.9364 | 3524367.8848
382 | Fitting | In Desalting Plant 4 | Weldolet | 20 | 4 | No | 1 | AN16 | SCH.30 |  | NACE | 50.827 | 50.827 | 5790366.6796
383 | Fitting | In Desalting Plant 4 | Weldolet | 20 | 6 | No | 1 | AN16 | SCH.30 |  | NACE | 45.7963 | 45.7963 | 5217248.0841
384 | Fitting | In Desalting Plant 4 | Weldolet | 20 | 11/2" | No | 2 | AN16 | SCH.30 |  | NACE | 13.6979 | 27.3958 | 3121004.5255
385 | Flange | In Desalting Plant 4 | Flange | 1 | - | No | 2 | AN01 | SCH.80 | ASTM A105 |  | 4.0738 | 8.1476 | 928202.9427
386 | Flange | In Desalting Plant 4 | Flange | 2 | - | No | 55 | AN01 | SCH.STD | ASTM A105 |  | 12.7683 | 702.2554 | 80002995.2472
387 | Flange | In Desalting Plant 4 | Flange | 3 | - | No | 82 | AN01 | SCH.STD | ASTM A105 |  | 22.9392 | 1881.0108 | 214290288.7684
388 | Flange | In Desalting Plant 4 | Flange | 4 | - | No | 48 | AN01 | SCH.STD | ASTM A105 |  | 32.4812 | 1559.0971 | 177616928.2062
389 | Flange | In Desalting Plant 4 | Flange | 6 | - | No | 13 | AN01 | SCH.STD | ASTM A105 |  | 52.1804 | 678.3456 | 77279124.5311
390 | Flange | In Desalting Plant 4 | Flange | 11/2" | - | No | 17 | AN01 | SCH.80 | ASTM A105 |  | 11.1141 | 188.9405 | 21524652.4686
391 | Flange | In Desalting Plant 4 | Flange | 21/2" | - | No | 2 | AN01 | SCH.STD | ASTM A105 |  | 19.8223 | 39.6445 | 4516423.7146
392 | Flange | In Desalting Plant 4 | Flange | 2 | - | No | 106 | AN06 | SCH.160 | ASTM A105 |  | 16.7327 | 1773.6698 | 202061682.2144
393 | Flange | In Desalting Plant 4 | Flange | 3 | - | No | 72 | AN06 | SCH.80 | ASTM A105 |  | 22.9392 | 1651.6193 | 188157326.7235
394 | Flange | In Desalting Plant 4 | Flange | 4 | - | No | 44 | AN06 | SCH.80 | ASTM A105 |  | 32.4812 | 1429.1723 | 162815517.5223
395 | Flange | In Desalting Plant 4 | Flange | 6 | - | No | 22 | AN06 | SCH.80 | ASTM A105 |  | 52.1804 | 1147.9695 | 130780056.8987
396 | Flange | In Desalting Plant 4 | Flange | 8 | - | No | 9 | AN06 | SCH.60 | ASTM A105 |  | 77.2932 | 695.6388 | 79249219.7031
397 | Flange | In Desalting Plant 4 | Flange | 11/2" | - | No | 4 | AN06 | SCH.160 | ASTM A105 |  | 11.1141 | 44.4566 | 5064624.1103
398 | Flange | In Desalting Plant 4 | Flange | 2 | - | No | 94 | AN16 | SCH.160 | ASTM A105 | NACE | 25.0991 | 2359.3155 | 268780162.1908
399 | Flange | In Desalting Plant 4 | Flange | 3 | - | No | 90 | AN16 | SCH.80 | ASTM A105 | NACE | 34.4087 | 3096.7862 | 352794987.6065
400 | Flange | In Desalting Plant 4 | Flange | 4 | - | No | 33 | AN16 | SCH.80 | ASTM A105 | NACE | 48.7218 | 1607.8189 | 183167457.2126
401 | Flange | In Desalting Plant 4 | Flange | 6 | - | No | 38 | AN16 | SCH.80 | ASTM A105 | NACE | 78.2638 | 2974.0248 | 338809647.9662
402 | Flange | In Desalting Plant 4 | Flange | 8 | - | No | 59 | AN16 | SCH.60 | ASTM A105 | NACE | 117.3889 | 6925.9438 | 789023895.0958
403 | Flange | In Desalting Plant 4 | Flange | 10 | - | No | 105 | AN16 | SCH.STD | ASTM A105 | NACE | 183.0348 | 19218.6524 | 2189445412.7562
404 | Flange | In Desalting Plant 4 | Flange | 12 | - | No | 4 | AN16 | SCH.STD | ASTM A105 | NACE | 200.9569 | 803.8274 | 91574384.2814
405 | Flange | In Desalting Plant 4 | Flange | 12 | - | No | 92 | AN16 | SCH.STD | ASTM A105 | NACE | 200.9569 | 18488.0307 | 2106210838.4718
406 | Flange | In Desalting Plant 4 | Flange | 16 | - | No | 14 | AN16 | SCH.40 | ASTM A105 | NACE | 302.1188 | 4229.6633 | 481855688.7187
407 | Flange | In Desalting Plant 4 | Flange | 18 | - | No | 4 | AN16 | SCH.30 | ASTM A105 | NACE | 407.3819 | 1629.5277 | 185640588.5432
408 | Flange | In Desalting Plant 4 | Flange | 20 | - | No | 15 | AN16 | SCH.30 | ASTM A105 | NACE | 508.5439 | 7628.1582 | 869022218.1805
409 | Flange | In Desalting Plant 4 | Flange | 26 | - | No | 1 | AN16 | SCH.30 | ASTM A105 | NACE | 594.6682 | 594.6682 | 67746355.7184
410 | Flange | In Desalting Plant 4 | Flange | 11/2" | - | No | 48 | AN16 | SCH.160 | ASTM A105 | NACE | 16.6644 | 799.8903 | 91125856.6849
411 | Flange | In Desalting Plant 4 | Flange | 21/2" | - | No | 4 | AN16 | SCH.160 | ASTM A105 | NACE | 31.784 | 127.136 | 14483703.6363
412 | Flange | In Desalting Plant 4 | Flange | 2 | - | No | 14 | AZ00 | SCH.40 | ASTM A105 | GALVD | 15.311 | 214.354 | 24419835.8084
413 | Flange | In Desalting Plant 4 | Flange | 3 | - | No | 9 | AZ00 | SCH.40 | ASTM A105 | GALVD | 27.5188 | 247.6691 | 28215189.1161
414 | Flange | In Desalting Plant 4 | Flange | 11/2" | - | No | 1 | AZ00 | SCH.80 | ASTM A105 | GALVD | 13.3288 | 13.3288 | 1518452.8006
415 | Flange | In Desalting Plant 4 | Spectace | 1 | - | No | 2 | AN01 |  | ASTM A516 |  | 5.1675 | 10.3349 | 1177384.9408
416 | Flange | In Desalting Plant 4 | Spectace | 2 | - | No | 1 | AN01 |  | ASTM A516 |  | 22.9255 | 22.9255 | 2611738.817
417 | Flange | In Desalting Plant 4 | Spectace | 3 | - | No | 8 | AN01 |  | ASTM A516 |  | 34.3814 | 275.0512 | 31334636.2541
418 | Flange | In Desalting Plant 4 | Spectace | 4 | - | No | 10 | AN01 |  | ASTM A516 |  | 57.3069 | 573.0688 | 65285683.4877
419 | Flange | In Desalting Plant 4 | Spectace | 6 | - | No | 2 | AN01 |  | ASTM A516 |  | 114.6001 | 229.2002 | 26111158.6201
420 | Flange | In Desalting Plant 4 | Spectace | 2 | - | No | 11 | AN06 |  | ASTM A516 |  | 22.9255 | 252.1803 | 28729126.9871
421 | Flange | In Desalting Plant 4 | Spectace | 3 | - | No | 9 | AN06 |  | ASTM A516 |  | 34.3814 | 309.4325 | 35251465.7859
422 | Flange | In Desalting Plant 4 | Spectace | 4 | - | No | 11 | AN06 |  | ASTM A516 |  | 57.3069 | 630.3757 | 71814251.8364
423 | Flange | In Desalting Plant 4 | Spectace | 6 | - | No | 3 | AN06 |  | ASTM A516 |  | 114.6001 | 343.8003 | 39166737.9301
424 | Flange | In Desalting Plant 4 | Spectace | 8 | - | No | 1 | AN06 |  | ASTM A516 |  | 296.0491 | 296.0491 | 33726783.4353
425 | Flange | In Desalting Plant 4 | Spectace | 2 | - | No | 9 | AN16 |  | ASTM A516 | NACE | 27.5461 | 247.9151 | 28243222.0909
426 | Flange | In Desalting Plant 4 | Spectace | 3 | - | No | 8 | AN16 |  | ASTM A516 | NACE | 41.2577 | 330.0614 | 37601563.5049
427 | Flange | In Desalting Plant 4 | Spectace | 4 | - | No | 1 | AN16 |  | ASTM A516 | NACE | 68.7628 | 68.7628 | 7833659.0635
428 | Flange | In Desalting Plant 4 | Spectace | 6 | - | No | 6 | AN16 |  | ASTM A516 | NACE | 137.5256 | 825.1535 | 94003908.7623
429 | Flange | In Desalting Plant 4 | Spectace | 8 | - | No | 6 | AN16 |  | ASTM A516 | NACE | 355.2562 | 2131.5371 | 242830971.8694
430 | Flange | In Desalting Plant 4 | Spectace | 10 | - | No | 19 | AN16 |  | ASTM A516 | NACE | 181.0662 | 3440.2583 | 391924348.2369
431 | Flange | In Desalting Plant 4 | Spectace | 12 | - | No | 14 | AN16 |  | ASTM A516 | NACE | 917.7577 | 12848.6072 | 1463751122.4634
432 | Flange | In Desalting Plant 4 | Spectace | 16 | - | No | 2 | AN16 |  | ASTM A516 | NACE | 1455.4334 | 2910.8669 | 331614517.7727
433 | Flange | In Desalting Plant 4 | Spectace | 20 | - | No | 2 | AN16 |  | ASTM A516 | NACE | 2187.2855 | 4374.571 | 498363996.0892
434 | Gasket | In Desalting Plant 4 | - | 1 | - | No | 2 | AN01 |  | FLAT |  | 0.62884 | 1.2577 | 229247.4382
435 | Gasket | In Desalting Plant 4 | - | 2 | - | No | 59 | AN01 |  | FLAT |  | 1.4081 | 83.0758 | 15142790.0212
436 | Gasket | In Desalting Plant 4 | - | 3 | - | No | 101 | AN01 |  | FLAT |  | 2.0916 | 211.2508 | 38506094.1578
437 | Gasket | In Desalting Plant 4 | - | 4 | - | No | 68 | AN01 |  | FLAT |  | 3.3766 | 229.6103 | 41852608.3916
438 | Gasket | In Desalting Plant 4 | - | 6 | - | No | 14 | AN01 |  | FLAT |  | 4.0328 | 56.4593 | 10291216.5192
439 | Gasket | In Desalting Plant 4 | - | 11/2" | - | No | 8 | AN01 |  | FLAT |  | 0.91593 | 7.3274 | 1335615.5095
440 | Gasket | In Desalting Plant 4 | - | 21/2" | - | No | 2 | AN01 |  | FLAT |  | 1.9139 | 3.8277 | 697709.5945
441 | Gasket | In Desalting Plant 4 | - | 2 | - | No | 112 | AN06 |  | FLAT |  | 1.4081 | 157.7033 | 28745635.2944
442 | Gasket | In Desalting Plant 4 | - | 3 | - | No | 90 | AN06 |  | FLAT |  | 2.0916 | 188.2433 | 34312361.1307
443 | Gasket | In Desalting Plant 4 | - | 4 | - | No | 54 | AN06 |  | FLAT |  | 3.3766 | 182.3376 | 33235894.8992
444 | Gasket | In Desalting Plant 4 | - | 6 | - | No | 24 | AN06 |  | FLAT |  | 4.0328 | 96.7874 | 17642085.4616
445 | Gasket | In Desalting Plant 4 | - | 8 | - | No | 11 | AN06 |  | FLAT |  | 5.728 | 63.0075 | 11484798.2899
446 | Gasket | In Desalting Plant 4 | - | 2 | 1 | No | 21 | AN16 |  | FLAT | NACE | 1.4081 | 29.5694 | 5389806.6177
447 | Gasket | In Desalting Plant 4 | - | 2 | - | No | 82 | AN16 |  | FLAT | NACE | 1.4081 | 115.4613 | 21045911.5548
448 | Gasket | In Desalting Plant 4 | - | 3 | 1 | No | 18 | AN16 |  | FLAT | NACE | 2.0916 | 37.6487 | 6862472.2261
449 | Gasket | In Desalting Plant 4 | - | 3 | - | No | 80 | AN16 |  | FLAT | NACE | 2.0916 | 167.3273 | 30499876.5607
450 | Gasket | In Desalting Plant 4 | - | 4 | - | No | 35 | AN16 |  | FLAT | NACE | 3.3766 | 118.1818 | 21541783.731
451 | Gasket | In Desalting Plant 4 | - | 6 | - | No | 51 | AN16 |  | FLAT | NACE | 4.0328 | 205.6732 | 37489431.6058
452 | Gasket | In Desalting Plant 4 | - | 8 | - | No | 72 | AN16 |  | FLAT | NACE | 5.728 | 412.4127 | 75173225.1701
453 | Gasket | In Desalting Plant 4 | - | 10 | - | No | 143 | AN16 |  | FLAT | NACE | 30.2939 | 4332.0283 | 789627849.9635
454 | Gasket | In Desalting Plant 4 | - | 12 | 15 | No | 8 | AN16 |  | FLAT | NACE | 41.4764 | 331.8112 | 60481454.5654
455 | Gasket | In Desalting Plant 4 | - | 12 | - | No | 122 | AN16 |  | FLAT | NACE | 41.4764 | 5060.121 | 922342182.1221
456 | Gasket | In Desalting Plant 4 | - | 16 | - | No | 15 | AN16 |  | FLAT | NACE | 68.216 | 1023.2395 | 186512725.5364
457 | Gasket | In Desalting Plant 4 | - | 18 | - | No | 4 | AN16 |  | FLAT | NACE | 257.006 | 1028.0242 | 187384862.5295
458 | Gasket | In Desalting Plant 4 | - | 20 | - | No | 20 | AN16 |  | FLAT | NACE | 267.9425 | 5358.8495 | 976793432.3348
459 | Gasket | In Desalting Plant 4 | - | 26 | - | No | 1 | AN16 |  | FLAT | NACE | 267.9425 | 267.9425 | 48839671.6167
460 | Gasket | In Desalting Plant 4 | - | 11/2" | - | No | 18 | AN16 |  | FLAT | NACE | 0.91593 | 16.4867 | 3005134.8964
461 | Gasket | In Desalting Plant 4 | - | 21/2" | - | No | 4 | AN16 |  | FLAT | NACE | 1.9139 | 7.6555 | 1395419.189
462 | Gasket | In Desalting Plant 4 | - | 2 | - | No | 14 | AZ00 |  | FLAT | GALVD | 1.4081 | 19.7129 | 3593204.4118
463 | Gasket | In Desalting Plant 4 | - | 3 | - | No | 9 | AZ00 |  | FLAT | GALVD | 2.0916 | 18.8243 | 3431236.1131
464 | Pipe | In Desalting Plant 4 | - | 1 | - | m | 2 | AN01 | SCH.80 | API5L-GR.B |  | 6.1517 | 12.3035 | 840989.2434
465 | Pipe | In Desalting Plant 4 | - | 2 | - | m | 957.5 | AN01 | SCH.STD | API5L-GR.B |  | 10.3349 | 9895.6897 | 676407648.467
466 | Pipe | In Desalting Plant 4 | - | 3 | - | m | 222.9 | AN01 | SCH.STD | API5L-GR.B |  | 20.3281 | 4531.1301 | 309719798.8893
467 | Pipe | In Desalting Plant 4 | - | 4 | - | m | 439.5 | AN01 | SCH.STD | API5L-GR.B |  | 28.9405 | 12719.3591 | 869416081.4761
468 | Pipe | In Desalting Plant 4 | - | 6 | - | m | 33.5 | AN01 | SCH.STD | API5L-GR.B |  | 111.0321 | 3719.5747 | 254246933.6323
469 | Pipe | In Desalting Plant 4 | - | 2 | - | m | 909.5 | AN06 | SCH.160 | API5L-GR.B |  | 10.3349 | 9399.6134 | 642498962.1731
470 | Pipe | In Desalting Plant 4 | - | 3 | - | m | 1054 | AN06 | SCH.80 | API5L-GR.B |  | 20.3281 | 21425.8012 | 1464534176.8923
471 | Pipe | In Desalting Plant 4 | - | 4 | - | m | 325 | AN06 | SCH.80 | API5L-GR.B |  | 28.9405 | 9405.6694 | 642912915.7673
472 | Pipe | In Desalting Plant 4 | - | 6 | - | m | 980 | AN06 | SCH.80 | API5L-GR.B |  | 111.0321 | 108811.4386 | 7437671491.334
473 | Pipe | In Desalting Plant 4 | - | 8 | - | m | 336 | AN06 | SCH.60 | API5L-GR.B |  | 167.1906 | 56176.0535 | 3839844753.4674
474 | Pipe | In Desalting Plant 4 | - | 2 | - | m | 2452 | AN16 | SCH.160 | API5L-GR.B | NACE | 11.702 | 28693.2486 | 1961291572.0491
475 | Pipe | In Desalting Plant 4 | - | 3 | - | m | 387 | AN16 | SCH.80 | API5L-GR.B | NACE | 22.5564 | 8729.3197 | 596681868.1926
476 | Pipe | In Desalting Plant 4 | - | 4 | - | m | 171 | AN16 | SCH.80 | API5L-GR.B | NACE | 34.1763 | 5844.1534 | 399469890.6152
477 | Pipe | In Desalting Plant 4 | - | 6 | - | m | 455 | AN16 | SCH.80 | API5L-GR.B | NACE | 124.7026 | 56739.6896 | 3878371405.1401
478 | Pipe | In Desalting Plant 4 | - | 8 | - | m | 243 | AN16 | SCH.60 | API5L-GR.B | NACE | 175.393 | 42620.4883 | 2913270838.0636
479 | Pipe | In Desalting Plant 4 | - | 10 | - | m | 1311 | AN16 | SCH.STD | API5L-GR.B | NACE | 165.4135 | 216857.0539 | 14822996074.4288
480 | Pipe | In Desalting Plant 4 | - | 12 | - | m | 647.5 | AN16 | SCH.STD | API5L-GR.B | NACE | 244.2514 | 158152.8059 | 10810339711.8488
481 | Pipe | In Desalting Plant 4 | - | 16 | - | m | 939 | AN16 | SCH.40 | API5L-GR.B | NACE | 254.9008 | 239351.8362 | 32721198269.0354
482 | Pipe | In Desalting Plant 4 | - | 20 | - | m | 1010 | AN16 | SCH.30 | API5L-GR.B | NACE | 300.7518 | 303759.2738 | 41526179974.1297
483 | Pipe | In Desalting Plant 4 | - | 2 | - | m | 182 | AZ00 | SCH.40 | API5L-GR.B | GALVD | 10.3349 | 1880.9562 | 128570435.5311
484 | Special | In Desalting Plant 4 | Filter | 3 | - | No | 3 | AN01 |  | ASTM A216-GR.WCB |  | 390.9773 | 1172.9318 | 133623846.4514
485 | Special | In Desalting Plant 4 | Filter | 4 | - | No | 9 | AN01 |  | ASTM A216-GR.WCB |  | 527.6826 | 4749.1436 | 541036413.2543
486 | Special | In Desalting Plant 4 | Filter | 6 | - | No | 1 | AN01 |  | ASTM A216-GR.WCB |  | 574.1624 | 574.1624 | 65410274.4867
487 | Special | In Desalting Plant 4 | Filter | 3 | - | No | 2 | AN06 |  | ASTM A216-GR.WCB |  | 390.9773 | 781.9546 | 89082564.3009
488 | Special | In Desalting Plant 4 | Filter | 4 | - | No | 2 | AN06 |  | ASTM A216-GR.WCB |  | 527.6826 | 1055.3653 | 120230314.0565
489 | Special | In Desalting Plant 4 | Filter | 3 | - | No | 2 | AN16 |  | ASTM A216-GR.WCB | NACE | 468.8993 | 937.7987 | 106836781.6616
490 | Special | In Desalting Plant 4 | Filter | 8 | - | No | 2 | AN16 |  | ASTM A216-GR.WCB | NACE | 765.5499 | 1531.0999 | 174427398.6312
491 | Special | In Desalting Plant 4 | Filter | 12 | - | No | 2 | AN16 |  | ASTM A216-GR.WCB | NACE | 1244.0186 | 2488.0373 | 283444522.7757
492 | Special | In Desalting Plant 4 | Footvalve | 3 | - | No | 2 | AN06 |  | ASTM A216-GR.WCB |  | 546.8214 | 1093.6428 | 124590999.0223
493 | Special | In Desalting Plant 4 | Orifice Flange | 3 | - | No | 2 | AN01 |  | ASTM A105 |  | 22.9392 | 45.8783 | 5226592.409
494 | Special | In Desalting Plant 4 | Orifice Flange | 4 | - | No | 4 | AN01 |  | ASTM A105 |  | 30.4306 | 121.7224 | 13866978.1912
495 | Special | In Desalting Plant 4 | Orifice Flange | 6 | - | No | 2 | AN16 | SCH.80 | ASTM A105 | NACE | 52.1804 | 104.3609 | 11889096.0817
496 | Special | In Desalting Plant 4 | Orifice Flange | 10 | - | No | 10 | AN16 | SCH.STD | ASTM A105 | NACE | 98.0314 | 980.314 | 111680256.7486
497 | Special | In Desalting Plant 4 | Orifice Flange | 12 | - | No | 8 | AN16 | SCH.STD | ASTM A105 | NACE | 191.3875 | 1531.0999 | 174427398.6312
498 | Special | In Desalting Plant 4 | Orifice Flange | 3 | - | No | 2 | AZ00 |  | ASTM A105 | GALVD | 22.9392 | 45.8783 | 5226592.409
499 | Special | In Desalting Plant 4 | Quick Coupling | 3 | 21/2" | No | 1 | AN01 | - | ASTM A105 |  | 150.3759 | 150.3759 | 17131262.3656
500 | Special | In Desalting Plant 4 | Water Trap | 2 | - | No | 1 | AN01 |  | ASTM A216-GR.WCB |  | 273.4107 | 273.4107 | 31147749.7556
501 | Valve | In Desalting Plant 4 | Ball | 2 | - | No | 4 | AN01 | - | ASTM A216-GR.WCB |  | 117.5666 | 470.2664 | 32144477.7478
502 | Valve | In Desalting Plant 4 | Ball | 3 | - | No | 5 | AN01 | - | ASTM A216-GR.WCB |  | 225.5638 | 1127.8191 | 77090680.645
503 | Valve | In Desalting Plant 4 | Ball | 8 | - | No | 1 | AN06 | - | ASTM A216-GR.WCB |  | 1861.6534 | 1861.6534 | 127251016.8514
504 | Valve | In Desalting Plant 4 | Ball | 1 | - | No | 10 | AN16 |  | ASTM A105 | NACE | 83.6637 | 836.6367 | 57187268.5512
505 | Valve | In Desalting Plant 4 | Ball | 2 | - | No | 16 | AN16 | - | ASTM A216-GR.WCB | NACE | 123.855 | 1981.6807 | 135455334.137
506 | Valve | In Desalting Plant 4 | Ball | 3 | - | No | 24 | AN16 | - | ASTM A216-GR.WCB | NACE | 226.2473 | 5429.9363 | 371156586.0874
507 | Valve | In Desalting Plant 4 | Ball | 4 | - | No | 3 | AN16 | - | ASTM A216-GR.WCB | NACE | 287.0812 | 861.2437 | 58869247.038
508 | Valve | In Desalting Plant 4 | Ball | 6 | - | No | 7 | AN16 | - | ASTM A216-GR.WCB | NACE | 1127.8191 | 7894.7336 | 539634764.5153
509 | Valve | In Desalting Plant 4 | Ball | 8 | - | No | 5 | AN16 | - | ASTM A216-GR.WCB | NACE | 1861.6534 | 9308.2669 | 636255084.2571
510 | Valve | In Desalting Plant 4 | Ball | 10 | - | No | 11 | AN16 | - | ASTM A216-GR.WCB | NACE | 2790.8396 | 30699.2355 | 2098408327.1581
511 | Valve | In Desalting Plant 4 | Ball | 16 | - | No | 5 | AN16 | - | ASTM A216-GR.WCB | NACE | 8947.3647 | 44736.8237 | 3057930332.2534
512 | Valve | In Desalting Plant 4 | Ball | 3 | - | No | 2 | AZ00 | - | ASTM B148 |  | 236.0901 | 472.1803 | 32275298.2967
513 | Valve | In Desalting Plant 4 | Check | 1 | - | No | 1 | AN01 |  | ASTM A105 |  | 50.581 | 50.581 | 3457400.2229
514 | Valve | In Desalting Plant 4 | Check | 3 | - | No | 6 | AN01 | - | ASTM A216-GR.WCB |  | 194.1216 | 1164.7295 | 79613648.3752
515 | Valve | In Desalting Plant 4 | Check | 4 | - | No | 4 | AN01 | - | ASTM A216-GR.WCB |  | 287.0812 | 1148.3249 | 78492329.384
516 | Valve | In Desalting Plant 4 | Check | 2 | - | No | 13 | AN06 | - | ASTM A216-GR.WCB |  | 102.529 | 1332.8771 | 91107168.0351
517 | Valve | In Desalting Plant 4 | Check | 3 | - | No | 7 | AN06 | - | ASTM A216-GR.WCB |  | 194.1216 | 1358.8511 | 92882589.7711
518 | Valve | In Desalting Plant 4 | Check | 4 | - | No | 5 | AN06 | - | ASTM A216-GR.WCB |  | 287.0812 | 1435.4061 | 98115411.7301
519 | Valve | In Desalting Plant 4 | Check | 6 | - | No | 2 | AN06 | - | ASTM A216-GR.WCB |  | 615.174 | 1230.3481 | 84098924.34
520 | Valve | In Desalting Plant 4 | Check | 8 | - | No | 1 | AN06 | - | ASTM A216-GR.WCB |  | 710.8678 | 710.8678 | 48590489.6187
521 | Valve | In Desalting Plant 4 | Check | 2 | - | No | 4 | AN16 | - | ASTM A216-GR.WCB | NACE | 135.3383 | 541.3532 | 37003526.7096
522 | Valve | In Desalting Plant 4 | Check | 3 | - | No | 1 | AN16 | - | ASTM A216-GR.WCB | NACE | 231.5789 | 231.5789 | 15829286.4258
523 | Valve | In Desalting Plant 4 | Check | 10 | - | No | 4 | AN16 | - | ASTM A216-GR.WCB | NACE | 1105.2627 | 4421.0508 | 302195468.1286
524 | Valve | In Desalting Plant 4 | Check | 20 | - | No | 1 | AN16 | - | ASTM A216-GR.WCB | NACE | 12303.4809 | 12303.4809 | 840989243.4005
525 | Valve | In Desalting Plant 4 | Gate | 1 | - | No | 66 | AN01 |  | ASTM A105 |  | 54.6821 | 3609.0211 | 246690178.0641
526 | Valve | In Desalting Plant 4 | Gate | 2 | - | No | 16 | AN01 | - | ASTM A216-GR.WCB |  | 159.2617 | 2548.1876 | 174178216.6332
527 | Valve | In Desalting Plant 4 | Gate | 3 | - | No | 18 | AN01 | - | ASTM A216-GR.WCB |  | 248.1202 | 4466.1636 | 305279095.3544
528 | Valve | In Desalting Plant 4 | Gate | 4 | - | No | 12 | AN01 | - | ASTM A216-GR.WCB |  | 314.4223 | 3773.0675 | 257903367.9761
529 | Valve | In Desalting Plant 4 | Gate | 6 | - | No | 4 | AN01 | - | ASTM A216-GR.WCB |  | 526.3156 | 2105.2623 | 143902603.8707
530 | Valve | In Desalting Plant 4 | Gate | 3/4" | - | No | 11 | AN01 |  | ASTM A105 |  | 36.9104 | 406.0149 | 27752645.0322
531 | Valve | In Desalting Plant 4 | Gate | 1 | - | No | 42 | AN06 |  | ASTM A105 |  | 54.6821 | 2296.6498 | 156984658.7681
532 | Valve | In Desalting Plant 4 | Gate | 2 | - | No | 28 | AN06 | - | ASTM A216-GR.WCB |  | 159.2617 | 4459.3283 | 304811879.108
533 | Valve | In Desalting Plant 4 | Gate | 3 | - | No | 26 | AN06 | - | ASTM A216-GR.WCB |  | 248.1202 | 6451.1252 | 440958693.2896
534 | Valve | In Desalting Plant 4 | Gate | 4 | - | No | 17 | AN06 | - | ASTM A216-GR.WCB |  | 314.4223 | 5345.1789 | 365363104.6329
535 | Valve | In Desalting Plant 4 | Gate | 6 | - | No | 5 | AN06 | - | ASTM A216-GR.WCB |  | 526.3156 | 2631.5779 | 179878254.8384
536 | Valve | In Desalting Plant 4 | Gate | 8 | - | No | 1 | AN06 | - | ASTM A216-GR.WCB |  | 765.5499 | 765.5499 | 52328219.5894
537 | Valve | In Desalting Plant 4 | Gate | 3/4" | - | No | 16 | AN06 |  | ASTM A105 |  | 36.9104 | 590.5671 | 40367483.6832
538 | Valve | In Desalting Plant 4 | Gate | 1 | - | No | 132 | AN16 |  | ASTM A105 | NACE | 54.6821 | 7218.0422 | 493380356.1283
539 | Valve | In Desalting Plant 4 | Gate | 2 | - | No | 17 | AN16 | - | ASTM A216-GR.WCB | NACE | 195.4886 | 3323.3069 | 227160538.9674
540 | Valve | In Desalting Plant 4 | Gate | 3 | - | No | 6 | AN16 | - | ASTM A216-GR.WCB | NACE | 332.3307 | 1993.9841 | 136296323.3804
541 | Valve | In Desalting Plant 4 | Gate | 4 | - | No | 4 | AN16 | - | ASTM A216-GR.WCB | NACE | 448.1201 | 1792.4805 | 122522788.4385
542 | Valve | In Desalting Plant 4 | Gate | 6 | - | No | 6 | AN16 | - | ASTM A216-GR.WCB | NACE | 604.511 | 3627.0662 | 247923628.9545
543 | Valve | In Desalting Plant 4 | Gate | 8 | - | No | 6 | AN16 | - | ASTM A216-GR.WCB | NACE | 998.4958 | 5990.975 | 409505695.5865
544 | Valve | In Desalting Plant 4 | Gate | 10 | - | No | 28 | AN16 | - | ASTM A216-GR.WCB | NACE | 1410.5257 | 39494.7206 | 2699612848.6152
545 | Valve | In Desalting Plant 4 | Gate | 12 | - | No | 4 | AN16 | - | ASTM A216-GR.WCB | NACE | 1864.6609 | 7458.6436 | 509826367.9992
546 | Valve | In Desalting Plant 4 | Gate | 12 | - | No | 33 | AN16 | - | ASTM A216-GR.WCB | NACE | 1864.6609 | 61533.8093 | 4206067535.9935
547 | Valve | In Desalting Plant 4 | Gate | 20 | - | No | 5 | AN16 | - | ASTM A216-GR.WCB | NACE | 12303.4809 | 61517.4047 | 4204946217.0023
548 | Valve | In Desalting Plant 4 | Gate | 1 | - | No | 2 | AZ00 |  | ASTM B148 |  | 355.4339 | 710.8678 | 48590489.6187
549 | Valve | In Desalting Plant 4 | Gate | 3 | - | No | 2 | AZ00 | - | ASTM B148 |  | 1107.3133 | 2214.6266 | 151378063.8121
550 | Valve | In Desalting Plant 4 | Glob | 4 | - | No | 2 | AN16 | - | ASTM A216-GR.WCB | NACE | 546.8214 | 1093.6428 | 74754599.4134
551 | Valve | In Desalting Plant 4 | Globe | 1 | - | No | 1 | AN01 |  | ASTM A105 |  | 136.7053 | 136.7053 | 9344324.9267
552 | Valve | In Desalting Plant 4 | Globe | 2 | - | No | 2 | AN01 | - | ASTM A216-GR.WCB |  | 159.3984 | 318.7969 | 21790965.729
553 | Valve | In Desalting Plant 4 | Globe | 4 | - | No | 1 | AN01 | - | ASTM A216-GR.WCB |  | 478.4687 | 478.4687 | 32705137.2434
554 | Valve | In Desalting Plant 4 | Globe | 2 | - | No | 2 | AN16 | - | ASTM A216-GR.WCB | NACE | 136.7053 | 273.4107 | 18688649.8533
555 | Valve | In Desalting Plant 4 | Globe | 3 | - | No | 5 | AN16 | - | ASTM A216-GR.WCB | NACE | 235.1332 | 1175.666 | 80361194.3694
556 | Valve | In Desalting Plant 4 | Globe | 4 | - | No | 4 | AN16 | - | ASTM A216-GR.WCB | NACE | 546.8214 | 2187.2855 | 149509198.8267
557 | Valve | In Desalting Plant 4 | Globe | 8 | - | No | 11 | AN16 | - | ASTM A216-GR.WCB | NACE | 1054.1349 | 11595.484 | 792594984.6052
558 | Valve | In Desalting Plant 4 | Globe | 18 | - | No | 1 | AN16 | - | ASTM A216-GR.WCB | NACE | 10252.9008 | 10252.9008 | 700824369.5004
559 | Valve | In Desalting Plant 4 | Globe | 11/2" | - | No | 2 | AN16 |  | ASTM A105 | NACE | 90.2255 | 180.4511 | 12334508.9032
560 | Valve | In Desalting Plant 4 | Globe | 2 | - | No | 1 | AZ00 | - | ASTM B148 |  | 833.9026 | 833.9026 | 57000382.0527
561 | StudBolt&nuts | Non Metal In Production Unit4 | - | 5/8" | 85 | No | 36 | AX00 | For flange:2"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 87.4039 | 15931700.227
562 | StudBolt&nuts | Non Metal In Production Unit4 | - | 5/8" | 90 | No | 12 | AX00 | For flange:3"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 29.1346 | 5310566.7423
563 | StudBolt&nuts | Non Metal In Production Unit4 | - | 5/8" | 90 | No | 128 | AX00 | For flange:4"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 310.7695 | 56646045.2515
564 | StudBolt&nuts | Non Metal In Production Unit4 | - | 1/2" | 70 | No | 8 | AX00 | For flange:11/2"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 1.2686 | 10.149 | 1849927.1535
565 | StudBolt&nuts | Non Metal In Production Unit4 | - | 5/8" | 85 | No | 16 | AX01 | For flange:2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 19.4231 | 3540377.8282
566 | Fitting | Non Metal In Production Unit4 | 90deg.Elbow | 2 | - | No | 6 | AX00 | - | GRE |  | 117.0745 | 702.4467 | 80024798.672
567 | Fitting | Non Metal In Production Unit4 | 90deg.Elbow | 4 | - | No | 15 | AX00 | - | GRE |  | 230.4852 | 3457.2781 | 393863295.6592
568 | Fitting | Non Metal In Production Unit4 | 90deg.Elbow | 2 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 10.3896 | 83.1168 | 9468915.9257
569 | Fitting | Non Metal In Production Unit4 | Pipe Nipple | 1 | - | No | 5 | AX00 | - | API5L-GR.B |  | 1.3671 | 6.8353 | 778693.7439
570 | Fitting | Non Metal In Production Unit4 | Reducer | 2 | 11/2" | No | 2 | AX00 | - | GRE |  | 69.2823 | 138.5645 | 15785679.5761
571 | Fitting | Non Metal In Production Unit4 | Reducer | 4 | 3 | No | 3 | AX00 | - | GRE |  | 199.043 | 597.1289 | 68026685.4662
572 | Fitting | Non Metal In Production Unit4 | Olet | 2 | 1 | No | 1 | AX00 | - | GRE |  | 120.6835 | 120.6835 | 13748616.7421
573 | Fitting | Non Metal In Production Unit4 | Olet | 4 | 1 | No | 4 | AX00 | - | GRE |  | 212.9869 | 851.9477 | 97056388.2384
574 | Fitting | Non Metal In Production Unit4 | Tee | 2 | 2 | No | 2 | AX00 | - | GRE |  | 171.9753 | 343.9506 | 39183869.1925
575 | Fitting | Non Metal In Production Unit4 | Tee | 4 | 4 | No | 2 | AX00 | - | GRE |  | 214.7368 | 429.4735 | 48926885.3161
576 | Fitting | Non Metal In Production Unit4 | Tee | 2 | 2 | No | 2 | AX01 | DR11 | HDPE 100 |  | 12.987 | 25.974 | 2959036.2268
577 | Fitting | Non Metal In Production Unit4 | Union | 2 | - | No | 2 | AX01 | DR11 | HDPE 100 |  | 2.7341 | 5.4682 | 622954.9951
578 | Fitting | Non Metal In Production Unit4 | Olet | 4 | 2 | No | 1 | AX00 | - | GRE |  | 212.9869 | 212.9869 | 24264097.0596
579 | Fitting | Non Metal In Production Unit4 | Olet | 4 | 11/2" | No |  | AX00 | - | GRE |  | 212.9869 | 0 | 0
580 | Flange | Non Metal In Production Unit4 | Flange | 2 | - | No | 9 | AX00 | - | ASTM A105 |  | 11.2372 | 101.1346 | 11521552.6346
581 | Flange | Non Metal In Production Unit4 | Flange | 3 | - | No | 3 | AX00 | - | ASTM A105 |  | 22.9392 | 68.8175 | 7839888.6135
582 | Flange | Non Metal In Production Unit4 | Flange | 4 | - | No | 15 | AX00 | - | ASTM A105 |  | 30.4306 | 456.4591 | 52001168.2169
583 | Flange | Non Metal In Production Unit4 | Flange | 11/2" | - | No | 2 | AX00 | - | ASTM A105 |  | 6.0834 | 12.1668 | 1386074.8641
584 | Flange | Non Metal In Production Unit4 | Flange | 2 | - | No | 4 | AX01 | DR11 | ASTM A105 |  | 11.2372 | 44.9487 | 5120690.0598
585 | Flange | Non Metal In Production Unit4 | Spectace | 4 | - | No | 2 | AX00 | - | ASTM A516 |  | 57.3069 | 114.6138 | 13057136.6975
586 | Flange | Non Metal In Production Unit4 | Spectace | 2 | - | No | 1 | AX01 | DR11 | ASTM A516 |  | 22.9255 | 22.9255 | 2611738.817
587 | Gasket | Non Metal In Production Unit4 | - | 2 | - | No | 9 | AX00 | - | FLAT |  | 1.4081 | 12.6726 | 2309917.1219
588 | Gasket | Non Metal In Production Unit4 | - | 3 | - | No | 3 | AX00 | - | FLAT |  | 2.0916 | 6.2748 | 1143745.371
589 | Gasket | Non Metal In Production Unit4 | - | 4 | - | No | 19 | AX00 | - | FLAT |  | 3.3766 | 64.1558 | 11694111.1682
590 | Gasket | Non Metal In Production Unit4 | - | 11/2" | - | No | 2 | AX00 | - | FLAT |  | 0.91593 | 1.8319 | 333903.8774
591 | Gasket | Non Metal In Production Unit4 | - | 2 | - | No | 5 | AX01 | DR11 | FLAT |  | 1.4081 | 7.0403 | 1283287.2899
592 | Pipe | Non Metal In Production Unit4 | - | 2 | - | m | 235 | AX00 | - | GRE |  | 36.6917 | 8622.5529 | 589383950.4249
593 | Pipe | Non Metal In Production Unit4 | - | 4 | - | m | 876.5 | AX00 | - | GRE |  | 44.4019 | 38918.2615 | 2660209699.2644
594 | Pipe | Non Metal In Production Unit4 | - | 2 | - | m | 47 | AX01 | SDR11 | HDPE 100 |  | 1.464 | 68.8087 | 4703336.6264
595 | Special | Non Metal In Production Unit4 | Filter | 4 | - | No |  | AX00 | - | ASTM A216-GR.WCB |  | 527.6826 | 0 | 0
596 | Special | Non Metal In Production Unit4 | Orifice Flange | 4 | - | No | 2 | AX00 | - | ASTM A105 |  | 30.4306 | 60.8612 | 6933489.0956
597 | Valve | Non Metal In Production Unit4 | Check | 4 | - | No | 1 | AX00 | - | ASTM B148 |  | 1460.1498 | 1460.1498 | 99806734.5418
598 | Valve | Non Metal In Production Unit4 | Gate | 1 | - | No | 5 | AX00 | - | ASTM B148 |  | 355.4339 | 1777.1695 | 121476224.0467
599 | Valve | Non Metal In Production Unit4 | Gate | 2 | - | No | 3 | AX00 | - | ASTM B148 |  | 697.1973 | 2091.5918 | 142968171.3781
600 | Valve | Non Metal In Production Unit4 | Gate | 4 | - | No | 6 | AX00 | - | ASTM B148 |  | 1435.4061 | 8612.4367 | 588692470.3803
601 | Valve | Non Metal In Production Unit4 | Gate | 2 | - | No | 1 | AX01 | - | ASTM B148 |  | 697.1973 | 697.1973 | 47656057.126
602 | Valve | Non Metal In Production Unit4 | Globe | 2 | - | No | 1 | AX00 | - | ASTM B148 |  | 833.9026 | 833.9026 | 57000382.0527
603 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 85 | No | 24 | AX00 | For flange:2"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 58.2693 | 10621133.4847
604 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 90 | No | 200 | AX00 | For flange:3"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 485.5774 | 88509445.7054
605 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 90 | No | 560 | AX00 | For flange:4"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 1359.6167 | 247826447.9752
606 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 3/4" | 105 | No | 144 | AX00 | For flange:6"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 4.1668 | 600.0162 | 109368969.1257
607 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 3/4" | 110 | No | 256 | AX00 | For flange:8"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 4.1668 | 1066.6954 | 194433722.8902
608 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 7/8" | 115 | No | 420 | AX00 | For flange:10"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 6.3213 | 2654.9271 | 483931374.7624
609 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 7/8" | 125 | No | 84 | AX00 | For flange:12"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 6.6056 | 554.8706 | 101139982.8223
610 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 85 | No | 156 | AX01 | For flange:2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 189.3752 | 34518683.8251
611 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 90 | No | 52 | AX01 | For flange:3"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 63.1251 | 11506227.9417
612 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 90 | No | 40 | AX01 | For flange:4"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 48.5577 | 8850944.5705
613 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 3/4" | 105 | No | 96 | AX01 | For flange:6"150# | A193 GR.B7/A194 GR.BH | GALVD | 2.0834 | 200.0054 | 36456323.0419
614 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 90 | No | 4 | AX01 | For flange:21/2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 4.8558 | 885094.4571
615 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 3/4" | 130 | No | 24 | FX00 | For flange:3"600# | A193 GR.B7/A194 GR.BH | CADMIUM PLATED | 4.5824 | 109.9767 | 20046193.3787
616 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 7/8" | 150 | No | 192 | FX00 | For flange:4"600# | A193 GR.B7/A194 GR.BH | CADMIUM PLATED | 7.1743 | 1377.4649 | 251079768.1417
617 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 1" | 170 | No | 224 | FX00 | For flange:5"600# | A193 GR.B7/A194 GR.BH | CADMIUM PLATED | 10.4552 | 2341.9703 | 426886638.3141
618 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 1" | 175 | No | 252 | FX00 | For flange:6"600# | A193 GR.B7/A194 GR.BH | CADMIUM PLATED | 10.8271 | 2728.4199 | 497327398.9773
619 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 1 1/8" | 195 | No | 48 | FX00 | For flange:8"600# | A193 GR.B7/A194 GR.BH | CADMIUM PLATED | 15.4204 | 740.1774 | 134917101.0213
620 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 3 | - | No | 25 | AX00 | - | GRE |  | 167.2727 | 4181.8165 | 476404832.5115
621 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 4 | - | No | 64 | AX00 | - | GRE |  | 230.4852 | 14751.0534 | 1680483394.8127
622 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 6 | - | No | 16 | AX00 | - | GRE |  | 262.1462 | 4194.3387 | 477831399.4503
623 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 8 | - | No | 14 | AX00 | - | GRE |  | 295.8304 | 4141.6251 | 471826113.2974
624 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 10 | - | No | 58 | AX00 | - | GRE |  | 354.9964 | 20589.7933 | 2345649820.3929
625 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 12 | - | No | 2 | AX00 | - | GRE |  | 423.7866 | 847.5731 | 96558024.2423
626 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 2 | - | No | 56 | AX01 | DR11 | HDPE 100 |  | 10.3896 | 581.8179 | 66282411.4799
627 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 3 | - | No | 9 | AX01 | DR11 | HDPE 100 |  | 19.9043 | 179.1387 | 20408005.6399
628 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 4 | - | No | 7 | AX01 | DR11 | HDPE 100 |  | 23.3766 | 163.6363 | 18641928.2287
629 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 6 | - | No | 11 | AX01 | DR11 | HDPE 100 |  | 68.38 | 752.1801 | 85690574.3526
630 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 4 | - | No | 15 | FX00 | - | GRE |  | 230.4852 | 3457.2781 | 393863295.6592
631 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 5 | - | No | 8 | FX00 | - | GRE |  | 246.8899 | 1975.1188 | 225011344.2343
632 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 6 | - | No | 15 | FX00 | - | GRE |  | 262.1462 | 3932.1925 | 447966936.9846
633 | Fitting | Non Metal Lines In Desalting Plant4 | Cap | 4 | - | No | 1 | AX00 | - | GRE |  | 317.7032 | 317.7032 | 36193685.216
634 | Fitting | Non Metal Lines In Desalting Plant4 | Cap | 2 | - | No | 2 | AX01 | DR11 | HDPE 100 |  | 4.7027 | 9.4053 | 1071482.5916
635 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 1 | No | 8 | AX00 | - | GRE |  | 318.0313 | 2544.2505 | 289848500.1255
636 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 11/2" | No | 4 | AX00 | - | GRE |  | 318.0313 | 1272.1252 | 144924250.0627
637 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 1 | No | 7 | AX00 | - | GRE |  | 381.6376 | 2671.463 | 304340925.1317
638 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 11/2" | No | 1 | AX00 | - | GRE |  | 381.6376 | 381.6376 | 43477275.0188
639 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 1 | No | 2 | FX00 | - | GRE |  | 318.0313 | 636.0626 | 72462125.0314
640 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 11/2" | No | 2 | FX00 | - | GRE |  | 318.0313 | 636.0626 | 72462125.0314
641 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 1 | - | No | 67 | AX00 | - | API5L-GR.B |  | 1.3671 | 91.5926 | 10434496.1681
642 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 11/2" | - | No | 1 | AX00 | - | API5L-GR.B |  | 1.3671 | 1.3671 | 155738.7488
643 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 3/4" | - | No | 8 | AX00 | - | API5L-GR.B |  | 1.3671 | 10.9364 | 1245909.9902
644 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 1 | - | No | 14 | AX01 | DR11 | HDPE 100 |  | 1.3671 | 19.1387 | 2180342.4829
645 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 11/2" | - | No | 2 | AX01 | DR11 | HDPE 100 |  | 1.3671 | 2.7341 | 311477.4976
646 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 1 | - | No | 32 | FX00 | - | GRE |  | 1.3671 | 43.7457 | 4983639.9609
647 | Fitting | Non Metal Lines In Desalting Plant4 | Plug | 3/4" | - | No | 2 | AX00 |  | ASTM A105 |  | 2.1189 | 4.2379 | 482790.1212
648 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 4 | 3 | No | 11 | AX00 | - | GRE |  | 199.043 | 2189.4728 | 249431180.0426
649 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 6 | 4 | No | 3 | AX00 | - | GRE |  | 281.3943 | 844.1828 | 96171792.1453
650 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 10 | 6 | No | 2 | AX00 | - | GRE |  | 519.9724 | 1039.9449 | 118473580.9703
651 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 12 | 8 | No | 2 | AX00 | - | GRE |  | 623.9669 | 1247.9339 | 142168297.1644
652 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 3 | 2 | No | 1 | AX01 | DR11 | HDPE 100 |  | 12.0984 | 12.0984 | 1378287.9267
653 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 3 | 21/2" | No | 1 | AX01 | DR11 | HDPE 100 |  | 12.0984 | 12.0984 | 1378287.9267
654 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 4 | 3 | No | 3 | FX00 | - | GRE |  | 5.7143 | 17.1429 | 1952963.9097
655 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 6 | 4 | No | 3 | FX00 | - | GRE |  | 12.4812 | 37.4436 | 4265684.329
656 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 3 | 1 | No | 2 | AX00 | - | GRE |  | 209.8154 | 419.6307 | 47805566.3249
657 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 3 | 3/4" | No | 4 | AX00 | - | GRE |  | 209.8154 | 839.2614 | 95611132.6497
658 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 4 | 1 | No | 27 | AX00 | - | GRE |  | 212.9869 | 5750.647 | 655130620.609
659 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 6 | 1 | No | 18 | AX00 | - | GRE |  | 237.4298 | 4273.7371 | 486876705.9793
660 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 1 | No | 8 | AX00 | - | GRE |  | 318.0313 | 2544.2505 | 289848500.1255
661 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 3/4" | No | 4 | AX00 | - | GRE |  | 318.0313 | 1272.1252 | 144924250.0627
662 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 12 | 1 | No | 2 | AX00 | - | GRE |  | 445.2438 | 890.4877 | 101446975.0439
663 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 2 | 1 | No | 5 | AX01 | DR11 | HDPE 100 |  | 36.0902 | 180.4511 | 20557514.8387
664 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 4 | 1 | No | 1 | AX01 | DR11 | HDPE 100 |  | 45.1128 | 45.1128 | 5139378.7097
665 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 4 | 1 | No | 12 | FX00 | - | GRE |  | 212.9869 | 2555.8431 | 291169164.7151
666 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 5 | 1 | No | 6 | FX00 | - | GRE |  | 226.9309 | 1361.5852 | 155115793.7828
667 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 6 | 1 | No | 12 | FX00 | - | GRE |  | 237.4298 | 2849.1581 | 324584470.6529
668 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 3 | 3 | No | 6 | AX00 | - | GRE |  | 191.3875 | 1148.3249 | 130820548.9734
669 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 4 | 3 | No | 4 | AX00 | - | GRE |  | 214.7368 | 858.947 | 97853770.6321
670 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 4 | 4 | No | 6 | AX00 | - | GRE |  | 214.7368 | 1288.4205 | 146780655.9482
671 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 2 | No | 2 | AX00 | - | GRE |  | 318.0313 | 636.0626 | 72462125.0314
672 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 4 | No | 8 | AX00 | - | GRE |  | 453.0415 | 3624.3321 | 412894570.7599
673 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 8 | No | 2 | AX00 | - | GRE |  | 453.0415 | 906.083 | 103223642.69
674 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 1 | No | 4 | AX00 | - | GRE |  | 381.6376 | 1526.5503 | 173909100.0753
675 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 2 | No | 2 | AX00 | - | GRE |  | 333.9438 | 667.8876 | 76087723.1029
676 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 3 | No | 2 | AX00 | - | GRE |  | 400.7326 | 801.4652 | 91305267.7235
677 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 10 | 4 | No | 8 | AX00 | - | GRE |  | 484.265 | 3874.1201 | 441351154.9366
678 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 10 | 6 | No | 4 | AX00 | - | GRE |  | 484.265 | 1937.06 | 220675577.4683
679 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 10 | 8 | No | 4 | AX00 | - | GRE |  | 484.265 | 1937.06 | 220675577.4683
680 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 10 | 10 | No | 6 | AX00 | - | GRE |  | 484.265 | 2905.5901 | 331013366.2024
681 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 11/2" | No | 1 | AX00 | - | GRE |  | 381.6376 | 381.6376 | 43477275.0188
682 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 12 | 6 | No | 2 | AX00 | - | GRE |  | 580.7243 | 1161.4486 | 132315640.9617
683 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 12 | 8 | No | 1 | AX00 | - | GRE |  | 580.7243 | 580.7243 | 66157820.4808
684 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 12 | 10 | No | 2 | AX00 | - | GRE |  | 580.7243 | 1161.4486 | 132315640.9617
685 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 2 | 1 | No | 4 | AX01 | DR11 | HDPE 100 |  | 12.987 | 51.948 | 5918072.4536
686 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 2 | 2 | No | 15 | AX01 | DR11 | HDPE 100 |  | 12.987 | 194.8051 | 22192771.7008
687 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 3 | 1 | No | 7 | AX01 | DR11 | HDPE 100 |  | 20.7929 | 145.5502 | 16581504.5824
688 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 3 | 3 | No | 2 | AX01 | DR11 | HDPE 100 |  | 20.7929 | 41.5858 | 4737572.7378
689 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 1 | No | 6 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 488.1201 | 55608077.6386
690 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 2 | No | 2 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 162.7067 | 18536025.8795
691 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 4 | No | 4 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 325.4134 | 37072051.7591
692 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 6 | No | 2 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 162.7067 | 18536025.8795
693 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 11/2" | No | 2 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 162.7067 | 18536025.8795
694 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 4 | 4 | No | 6 | FX00 | - | GRE |  | 17.758 | 106.5481 | 12138278.0797
695 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 6 | No | 6 | FX00 | - | GRE |  | 129.1865 | 775.1193 | 88303870.557
696 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 3 | No | 2 | FX00 | - | GRE |  | 73.8482 | 147.6965 | 16826014.418
697 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 4 | No | 8 | FX00 | - | GRE |  | 73.8482 | 590.7858 | 67304057.6718
698 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 5 | No | 6 | FX00 | - | GRE |  | 73.8482 | 443.0894 | 50478043.2539
699 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 6 | No | 6 | FX00 | - | GRE |  | 73.8482 | 443.0894 | 50478043.2539
700 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 4 | 11/2" | No | 3 | AX00 | - | GRE |  | 212.9869 | 638.9608 | 72792291.1788
701 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 6 | 11/2" | No | 3 | AX00 | - | GRE |  | 237.4298 | 712.2895 | 81146117.6632
702 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 11/2" | No | 2 | AX00 | - | GRE |  | 318.0313 | 636.0626 | 72462125.0314
703 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 5 | 11/2" | No | 2 | FX00 | - | GRE |  | 226.9309 | 453.8617 | 51705264.5943
704 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 2 | - | No | 8 | AX00 | - | ASTM A105 |  | 11.2372 | 89.8974 | 10241380.1196
705 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 3 | - | No | 50 | AX00 | - | ASTM A105 |  | 22.9392 | 1146.9578 | 130664810.2246
706 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 4 | - | No | 69 | AX00 | - | ASTM A105 |  | 30.4306 | 2099.7121 | 239205373.7979
707 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 6 | - | No | 15 | AX00 | - | ASTM A105 |  | 46.7396 | 701.0934 | 79870617.3107
708 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 8 | - | No | 30 | AX00 | - | ASTM A105 |  | 73.3014 | 2199.0422 | 250521351.2841
709 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 10 | - | No | 35 | AX00 | - | ASTM A105 |  | 98.0314 | 3431.0991 | 390880898.6201
710 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 12 | - | No | 7 | AX00 | - | ASTM A105 |  | 136.7053 | 956.9374 | 109017124.1445
711 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 11/2" | - | No | 14 | AX00 | - | ASTM A105 |  | 6.0834 | 85.1674 | 9702524.0489
712 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 2 | - | No | 36 | AX01 | DR11 | ASTM A105 |  | 11.2372 | 404.5385 | 46086210.5383
713 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 3 | - | No | 10 | AX01 | DR11 | ASTM A105 |  | 22.9392 | 229.3916 | 26132962.0449
714 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 4 | - | No | 5 | AX01 | DR11 | ASTM A105 |  | 30.4306 | 152.153 | 17333722.739
715 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 6 | - | No | 12 | AX01 | DR11 | ASTM A105 |  | 46.7396 | 560.8747 | 63896493.8486
716 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 11/2" | - | No | 2 | AX01 | DR11 | ASTM A105 |  | 6.0834 | 12.1668 | 1386074.8641
717 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 21/2" | - | No | 1 | AX01 | DR11 | ASTM A105 |  | 19.1387 | 19.1387 | 2180342.4829
718 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 3 | - | No | 3 | FX00 | - | ASTM A105 |  | 40.4374 | 121.3123 | 13820256.5665
719 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 4 | - | No | 21 | FX00 | - | ASTM A105 |  | 205.058 | 4306.2183 | 490577058.6503
720 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 5 | - | No | 32 | FX00 | - | ASTM A105 |  | 410.116 | 13123.713 | 1495091988.2675
721 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 6 | - | No | 18 | FX00 | - | ASTM A105 |  | 160.9022 | 2896.2394 | 329948113.1608
722 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 8 | - | No | 8 | FX00 | - | ASTM A105 |  | 341.7634 | 2734.1069 | 311477497.5557
723 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 11/2" | - | No | 4 | FX00 | - | ASTM A105 |  | 15.9809 | 63.9234 | 7282343.8929
724 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 3 | - | No | 2 | AX00 | - | ASTM A516 |  | 34.3814 | 68.7628 | 7833659.0635
725 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 4 | - | No | 7 | AX00 | - | ASTM A516 |  | 57.3069 | 401.1482 | 45699978.4414
726 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 6 | - | No | 6 | AX00 | - | ASTM A516 |  | 114.6001 | 687.6005 | 78333475.8603
727 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 8 | - | No | 2 | AX00 | - | ASTM A516 |  | 296.0491 | 592.0982 | 67453566.8707
728 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 10 | - | No | 3 | AX00 | - | ASTM A516 |  | 181.0662 | 543.1987 | 61882791.8269
729 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 12 | - | No | 1 | AX00 | - | ASTM A516 |  | 917.7577 | 917.7577 | 104553651.6045
730 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 6 | - | No | 1 | AX01 | DR11 | ASTM A516 |  | 114.6001 | 114.6001 | 13055579.31
731 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 4 | - | No | 3 | FX00 | - | ASTM A516 |  | 57.3069 | 171.9206 | 19585705.0463
732 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 6 | - | No | 3 | FX00 | - | ASTM A516 |  | 328.0928 | 984.2785 | 112131899.1201
733 | Gasket | Non Metal Lines In Desalting Plant4 | - | 2 | - | No | 6 | AX00 | - | FLAT |  | 1.4081 | 8.4484 | 1539944.7479
734 | Gasket | Non Metal Lines In Desalting Plant4 | - | 3 | - | No | 54 | AX00 | - | FLAT |  | 2.0916 | 112.946 | 20587416.6784
735 | Gasket | Non Metal Lines In Desalting Plant4 | - | 4 | - | No | 74 | AX00 | - | FLAT |  | 3.3766 | 249.87 | 45545485.6026
736 | Gasket | Non Metal Lines In Desalting Plant4 | - | 6 | - | No | 21 | AX00 | - | FLAT |  | 4.0328 | 84.689 | 15436824.7789
737 | Gasket | Non Metal Lines In Desalting Plant4 | - | 8 | - | No | 40 | AX00 | - | FLAT |  | 5.728 | 229.1182 | 41762902.8723
738 | Gasket | Non Metal Lines In Desalting Plant4 | - | 10 | - | No | 38 | AX00 | - | FLAT |  | 30.2939 | 1151.1684 | 209831176.9134
739 | Gasket | Non Metal Lines In Desalting Plant4 | - | 12 | - | No | 8 | AX00 | - | FLAT |  | 41.4764 | 331.8112 | 60481454.5654
740 | Gasket | Non Metal Lines In Desalting Plant4 | - | 2 | - | No | 35 | AX01 | DR11 | FLAT |  | 1.4081 | 49.2823 | 8983011.0295
741 | Gasket | Non Metal Lines In Desalting Plant4 | - | 3 | - | No | 17 | AX01 | DR11 | FLAT |  | 2.0916 | 35.5571 | 6481223.7691
742 | Gasket | Non Metal Lines In Desalting Plant4 | - | 4 | - | No | 5 | AX01 | DR11 | FLAT |  | 3.3766 | 16.8831 | 3077397.6759
743 | Gasket | Non Metal Lines In Desalting Plant4 | - | 6 | - | No | 14 | AX01 | DR11 | FLAT |  | 4.0328 | 56.4593 | 10291216.5192
744 | Gasket | Non Metal Lines In Desalting Plant4 | - | 21/2" | - | No | 1 | AX01 | DR11 | FLAT |  | 1.9139 | 1.9139 | 348854.7973
745 | Gasket | Non Metal Lines In Desalting Plant4 | - | 3 | - | No | 3 | FX00 | - | SPIRAL WOUND |  | 11.4286 | 34.2857 | 6249484.511
746 | Gasket | Non Metal Lines In Desalting Plant4 | - | 4 | - | No | 27 | FX00 | - | SPIRAL WOUND |  | 11.4286 | 308.5713 | 56245360.5986
747 | Gasket | Non Metal Lines In Desalting Plant4 | - | 5 | - | No | 20 | FX00 | - | SPIRAL WOUND |  | 26.9856 | 539.7127 | 98377052.828
748 | Gasket | Non Metal Lines In Desalting Plant4 | - | 6 | - | No | 24 | FX00 | - | SPIRAL WOUND |  | 18.6876 | 448.5029 | 81751629.9185
749 | Gasket | Non Metal Lines In Desalting Plant4 | - | 8 | - | No | 6 | FX00 | - | SPIRAL WOUND |  | 26.9856 | 161.9138 | 29513115.8484
750 | Pipe | Non Metal Lines In Desalting Plant4 | - | 3 | - | m | 263 | AX00 | - | GRE |  | 42.0506 | 11059.2983 | 755944673.3778
751 | Pipe | Non Metal Lines In Desalting Plant4 | - | 4 | - | m | 1439 | AX00 | - | GRE |  | 44.4019 | 63894.3278 | 4367417863.3674
752 | Pipe | Non Metal Lines In Desalting Plant4 | - | 6 | - | m | 98 | AX00 | - | GRE |  | 46.8626 | 4592.534 | 313916989.3166
753 | Pipe | Non Metal Lines In Desalting Plant4 | - | 8 | - | m | 56.9 | AX00 | - | GRE |  | 53.8072 | 3061.631 | 209274005.9658
754 | Pipe | Non Metal Lines In Desalting Plant4 | - | 10 | - | m | 1444 | AX00 | - | GRE |  | 64.5687 | 93237.1565 | 6373110677.284
755 | Pipe | Non Metal Lines In Desalting Plant4 | - | 12 | - | m | 9 | AX00 | - | GRE |  | 77.4299 | 696.8692 | 47633630.7462
756 | Pipe | Non Metal Lines In Desalting Plant4 | - | 2 | - | m | 1241.5 | AX01 | SDR11 | HDPE 100 |  | 1.464 | 1817.5756 | 124238136.631
757 | Pipe | Non Metal Lines In Desalting Plant4 | - | 3 | - | m | 35 | AX01 | SDR11 | HDPE 100 |  | 4.6602 | 163.1081 | 11149050.4657
758 | Pipe | Non Metal Lines In Desalting Plant4 | - | 4 | - | m | 55 | AX01 | SDR11 | HDPE 100 |  | 6.9024 | 379.6329 | 25949339.8306
759 | Pipe | Non Metal Lines In Desalting Plant4 | - | 6 | - | m | 83.5 | AX01 | SDR11 | HDPE 100 |  | 14.6621 | 1224.2887 | 83684742.7443
760 | Pipe | Non Metal Lines In Desalting Plant4 | - | 4 | - | m | 36 | FX00 | - | GRE |  | 44.4019 | 1598.4682 | 109261322.5026
761 | Pipe | Non Metal Lines In Desalting Plant4 | - | 5 | - | m | 430 | FX00 | - | GRE |  | 45.933 | 19751.1881 | 1350068065.4055
762 | Pipe | Non Metal Lines In Desalting Plant4 | - | 6 | - | m | 36 | FX00 | - | GRE |  | 46.8626 | 1687.0533 | 115316445.0551
763 | Pipe | Non Metal Lines In Desalting Plant4 | - | 8 | - | m | 54 | FX00 | - | GRE |  | 53.8072 | 2905.5901 | 198608019.7215
764 | Special | Non Metal Lines In Desalting Plant4 | Filter | 4 | - | No | 5 | AX00 | - | ASTM A216-GR.WCB |  | 527.6826 | 2638.4131 | 300575785.1413
765 | Special | Non Metal Lines In Desalting Plant4 | Filter | 6 | - | No | 3 | AX00 | - | ASTM A216-GR.WCB |  | 574.1624 | 1722.4873 | 196230823.4601
766 | Special | Non Metal Lines In Desalting Plant4 | Filter | 3 | - | No | 1 | AX01 | - | ASTM A216-GR.WCB |  | 390.9773 | 390.9773 | 44541282.1505
767 | Special | Non Metal Lines In Desalting Plant4 | Orifice Flange | 8 | - | No | 4 | AX00 | - | ASTM A105 |  | 73.3014 | 293.2056 | 33402846.8379
768 | Special | Non Metal Lines In Desalting Plant4 | Orifice Flange | 6 | - | No | 2 | AX01 | DR11 | ASTM A105 |  | 46.7396 | 93.4791 | 10649415.6414
769 | Special | Non Metal Lines In Desalting Plant4 | Orifice Flange | 4 | - | No | 6 | FX00 | - | ASTM A105 |  | 205.058 | 1230.3481 | 140164873.9001
770 | Special | Non Metal Lines In Desalting Plant4 | Orifice Flange | 5 | - | No | 4 | FX00 | - | ASTM A105 |  | 410.116 | 1640.4641 | 186886498.5334
771 | Special | Non Metal Lines In Desalting Plant4 | Orifice Flange | 6 | - | No | 6 | FX00 | - | ASTM A105 |  | 160.9022 | 965.4131 | 109982704.3869
772 | Special | Non Metal Lines In Desalting Plant4 | Quick Coupling | 3 | 21/2" | No | 1 | AX01 | DR11 | ASTM A105 |  | 150.3759 | 150.3759 | 17131262.3656
773 | Valve | Non Metal Lines In Desalting Plant4 | Check | 1 | - | No | 5 | AX00 | - | ASTM B148 |  | 205.058 | 1025.2901 | 70082436.95
774 | Valve | Non Metal Lines In Desalting Plant4 | Check | 3 | - | No | 1 | AX00 | - | ASTM B148 |  | 1063.5676 | 1063.5676 | 72698847.9295
775 | Valve | Non Metal Lines In Desalting Plant4 | Check | 4 | - | No | 5 | AX00 | - | ASTM B148 |  | 1460.1498 | 7300.7489 | 499033672.7089
776 | Valve | Non Metal Lines In Desalting Plant4 | Check | 10 | - | No | 1 | AX00 | - | ASTM B148 |  | 4101.1603 | 4101.1603 | 280329747.8002
777 | Valve | Non Metal Lines In Desalting Plant4 | Check | 3 | - | No | 2 | AX01 | - | ASTM B148 |  | 1063.5676 | 2127.1351 | 145397695.859
778 | Valve | Non Metal Lines In Desalting Plant4 | Check | 4 | - | No | 3 | FX00 | - | ASTM B148 |  | 628.8446 | 1886.5337 | 128951683.9881
779 | Valve | Non Metal Lines In Desalting Plant4 | Check | 6 | - | No | 3 | FX00 | - | ASTM B148 |  | 3417.6336 | 10252.9008 | 700824369.5004
780 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 1 | - | No | 67 | AX00 | - | ASTM B148 |  | 355.4339 | 23814.0709 | 1627781402.2262
781 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 2 | - | No | 2 | AX00 | - | ASTM B148 |  | 697.1973 | 1394.3945 | 95312114.2521
782 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 3 | - | No | 6 | AX00 | - | ASTM B148 |  | 1107.3133 | 6643.8797 | 454134191.4363
783 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 4 | - | No | 16 | AX00 | - | ASTM B148 |  | 1435.4061 | 22966.4978 | 1569846587.6809
784 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 6 | - | No | 6 | AX00 | - | ASTM B148 |  | 2050.5802 | 12303.4809 | 840989243.4005
785 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 8 | - | No | 7 | AX00 | - | ASTM B148 |  | 2187.2855 | 15310.9985 | 1046564391.7872
786 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 10 | - | No | 1 | AX00 | - | ASTM B148 |  | 3896.1023 | 3896.1023 | 266313260.4101
787 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 10 | - | No | 6 | AX00 | - | ASTM B148 |  | 3896.1023 | 23376.6138 | 1597879562.4609
788 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 12 | - | No | 3 | AX00 | - | ASTM B148 |  | 5276.8263 | 15830.4788 | 1082072826.5086
789 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 3/4" | - | No | 8 | AX00 | - | ASTM B148 |  | 247.4367 | 1979.4934 | 135305824.9382
790 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 1 | - | No | 14 | AX01 | - | ASTM B148 |  | 355.4339 | 4976.0745 | 340133427.3309
791 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 2 | - | No | 14 | AX01 | - | ASTM B148 |  | 697.1973 | 9760.7615 | 667184799.7644
792 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 3 | - | No | 5 | AX01 | - | ASTM B148 |  | 1107.3133 | 5536.5664 | 378445159.5302
793 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 4 | - | No | 2 | AX01 | - | ASTM B148 |  | 1435.4061 | 2870.8122 | 196230823.4601
794 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 6 | - | No | 4 | AX01 | - | ASTM B148 |  | 2050.5802 | 8202.3206 | 560659495.6003
795 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 1 | - | No | 32 | FX00 | - | ASTM B148 |  | 54.6821 | 1749.8284 | 119607359.0614
796 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 4 | - | No | 3 | FX00 | - | ASTM B148 |  | 738.2089 | 2214.6266 | 151378063.8121
797 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 5 | - | No | 10 | FX00 | - | ASTM B148 |  | 2050.5802 | 20505.8016 | 1401648739.0008
798 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 6 | - | No | 3 | FX00 | - | ASTM B148 |  | 1503.7588 | 4511.2763 | 308362722.5802
799 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 8 | - | No | 2 | FX00 | - | ASTM B148 |  | 2460.6962 | 4921.3924 | 336395697.3602
800 | Valve | Non Metal Lines In Desalting Plant4 | Globe | 3 | - | No | 6 | AX00 | - | ASTM B148 |  | 1401.2298 | 8407.3786 | 574675982.9903
801 | Valve | Non Metal Lines In Desalting Plant4 | Globe | 6 | - | No | 1 | AX00 | - | ASTM B148 |  | 3150.3746 | 3150.3746 | 215339967.9352
802 | Valve | Non Metal Lines In Desalting Plant4 | Globe | 6 | - | No | 1 | AX01 | - | ASTM B148 |  | 3150.3746 | 3150.3746 | 215339967.9352
803 | Valve | Non Metal Lines In Desalting Plant4 | Globe | 5 | - | No | 2 | FX00 | - | ASTM B148 |  | 2460.6962 | 4921.3924 | 336395697.3602
804 |  | خرید پایپینگ مربوط به تفکیک نفت نمکی یک قلم |  |  |  | Lot | 1 |  |  |  |  | 683526.7188 | 683526.7188 | 62295499511.1456
805 | pipe, fitting | Draining material |  |  |  | Lot | 1 |  |  |  |  | 98977.1887 | 98977.1887
806 | pipe, valves,fitting | اتصال توربين شماره 3 به خط هدر 30 اينچ نفت خروجي واحد بهره‌برداري گچساران4 |  |  |  | Lot | 1 |  |  |  |  | 700000 | 700000 | 63796847231.9433
807 | Pipe | Replacement of Existing Lines | - | 4 | - | m | 500 | AN16 | SCH.80 | API5L-GR.B | NACE | 34.1763 | 17088.168 | 1168040615.834
808 |  | لوازم یدکی شیر الات معادل 5% قیمت خرید شیرآلات | [10 empty] | 123983.1722
809 |  | حمل زمینی اقلام پایپینگ در حدود 190 کفی | [11 empty] | 30000293079.2969
[8 empty] | 123983.1722 | 4824605.2955 | 30000293079.2969 | 426282640073.0584
[8 empty] | Euro | Euro |  | Rls
[8 empty] | لوازم یدکی |  | حمل | جنبي
هزینه کل بدون ضریب
[15 empty] | اجرای پایپینگ بر اساس dia-in |  | 45000 | ریال
[15 empty] | هزینه حمل زمینی یک کانتینر |  | 6,500,000 ~ 8,000,000 | ریال
[15 empty] | حق گمرک و ترخیص لوله اتصالات فلزی |  | 20%
[15 empty] | نرخ ازاد یورو | اتاق ارز
[15 empty] | 18.576 | 420000

## P.PL
ITEM | DESCRIPTION |  | QUANTITY |  | MATERIAL | هزینه واحد خرید بدون ضریب | هزینه کل بدون ضریب
[7 empty] | خرید | ترخیص | حمل
| PIPELINE | SIZE(in) | LENGTH(M) | unit |  | Euro | Euro | Rls | Rls
1 | احداث خط لوله انتقال نفت نمکی از واحد بهره برداری گچساران 4 به واحد نمک زدایی گچساران 4 ب | 20" | 400 | m | API 5L GR.X52/SCH.30/NACE | 300.7518 | 120300.7025 | 16446011870.9424 | 1857603286.6438
2 | احداث خط لوله انتقال نفت نمک زدایی شده 20 اینچ روزمینی با جنس API 5L GR.X52/SCH.30/NACE از واحد نمک زدایی گچساران 4 به واحد بهره برداری گچساران 4 به طول تقریبی 1500 متر. | 20" | 400 | m | API 5L GR.X52/SCH.30/NACE | 300.7518 | 120300.7025 | 16446011870.9424 | 1857603286.6438
| ساپورت فلزی و فونداسیون (بر اساس تناژ) |  | 2500 | kg | C.S. |  |  |  | 1393202464.9828
3 | تعویض خط لوله انتقال نفت از واحد بهره برداری پازنان 2 به واحد بهره برداری گچساران 2 با سایز 12 اینچ | 12" | 17000 | m | API 5L GR.X52/SCH.40 | 211.8933 | 3602185.808 | 246222961817.803 | 16718429579.794
| ساپورت فلزی و فونداسیون(61000/کیلو) |  | 8000 | kg |  |  |  | 0 | 3483006162.4571
4 | جابجایی خط فشار بالای گاز موجود در سمت شرق سایت و احداث مجدد آن در فاصله حداقل 200 متر از حصار تسهیلات بیرون واحد | 4" | 1900 | m | API5L GR.X52/SCH.80/NACE | 31.4422 | 59740.2352 | 4083469992.9556 | 696601232.4914
5 | احداث خط لوله انتقال گاز 6 اینچ فلزی با جنس API5L GR.X52/SCH.80/NACE به صورت روزمینی از واحد بهره برداری گچساران 4 به واحد نمک زدایی گچساران 4 | 6" | 500 | m | API5L GR.X52/SCH.80/NACE | 71.0868 | 35543.3894 | 2429524480.9347 | 975241725.488
6 | ·احداث خط انتقال آب 6 اینچ فلزی با جنس API 5L0 به صورت رو زمینی از تصفیه خانه خیر آباد به واحدنمکزدایی گچساران-4 | 6" | 2000 | m | API 5L GR.X52/SCH.STD | 71.0868 | 142173.5575 | 9718097923.7387 | 1857603286.6438
7 | احداث خط لوله انتقال آب ازاد غیر فلزی با جنس RTP زیر زمینی از واحد بهره برداری گچساران-4 به واحدنمکزدایی گچساران-4 | 4" | 500 |  | RTP | 133.9712 | 66985.6184 | 4578719214.0692 | 743041314.6575
| ساپورت فلزی و فونداسیون(61000/کیلو) |  | 1500 | kg | RTP |  |  | 0 | 3483006162.4571
8 | احداث دو خط لوله انتقال پساب غیر فلزی با جنس RTP زیر زمینی از واحدنمکزدایی گچساران-4 به چاههای تزریق در فاصله تقریبی 3 کیلومتر برای هر خط لوله. | 5" | 6000 | m | RTP | 150.3759 | 1804510.5376 | 123345089032.0683 | 18576032866.4377
| کندن کانال |  | 6000 | m |  |  | 0
9 | خط لوله آب "6 از چاههای لیشتر با جنس PE-100 | 6" | 8500 | m | PE-100 | 14.6685 | 124682.1088 |  | 1857603286.6438
10 | خط لوله "12 آب آتش نشانی اتصال بین دو واحد با جنس PE-100 | 12" | 500 | m | PE-100 | 35.6117 | 17805.871 |  | 1857603286.6438
|  | 6094228.531 | 423269886203.4544 | 55356577941.9844
|  | Euro | Rls | Rls
|  | خرید | ترخیص | حمل
|  | هزینه حمل دریایی یک کانتینر |  | 1500$
|  | حق گمرک و ترخیص لوله فلزی |  | 20%
|  | حق گمرک و ترخیص لوله غیر فلزی |  | 5%

## P.LAB
|  |  | هزینه واحد بدون ضریب |  | هزینه کل بدون ضریب
|  |  | خرید |  | خرید
| DESCRIPTION | Qty. | Rls | Euro | Rls | Euro
1 | Microwave Digestion System | 1 |  | 41011.6031 |  | 41011.6031
2 | Ion Meter | 1 |  | 18796.9848 |  | 18796.9848
3 | Oxygen Meter | 2 |  | 1722.4873 |  | 3444.9747
4 | Barometer | 2 |  | 3909.7728 |  | 7819.5457
5 | Oil Test Centrifuge | 2 |  | 34859.8627 |  | 69719.7253
6 | Dual Extraction Apparatus | 5 |  | 28024.5955 |  | 140122.9774
7 | Evaporator Mantless (500 cc) | 2 |  | 1640.4641 |  | 3280.9283
8 | Water Still For Douuble Distillation | 4 |  | 9159.258 |  | 36637.0321
9 | Ph Meter | 2 |  | 3417.6336 |  | 6835.2672
10 | Balance | 2 |  | 8885.8473 |  | 17771.6947
11 | R.V.P Automatic | 2 |  | 76281.5818 |  | 152563.1636
12 | Thermostatic Water Baths | 2 |  | 7382.0886 |  | 14764.1771
13 | Density/Visco Meter | 2 |  | 86534.4826 |  | 173068.9652
14 | Oxygen Meter | 2 |  | 1722.4873 |  | 3444.9747
15 | Baro Meter | 2 |  | 3909.7728 |  | 7819.5457
16 | Salt In Crude Analyzer | 2 |  | 42378.6566 |  | 84757.3131
17 | H2S Analyzer For The Determination Of H2S in Fuel Oil | 2 |  | 66985.6184 |  | 133971.2369
18 | Industrial Hood (complete set with valves , sinks , exhoust , etc) | 1 | 19504834509.7596 |  | 19504834509.7596
19 | Sink (Chemically resistant with attachments) | 10 | یک قلم در ردیف 19 |  | یک قلم در ردیف 19
20 | Industrial cupboards(floor & wall mounted) | 1 | یک قلم در ردیف 19 |  | یک قلم در ردیف 19
21 | Safty shower & eyewash | 4 | یک قلم در ردیف 19 |  | یک قلم در ردیف 19
22 | Exhaust Fan(Wall mounted) | 4 | یک قلم در ردیف 19 |  | یک قلم در ردیف 19
23 | Ice Maker | 4 | یک قلم در ردیف 19 |  | یک قلم در ردیف 19
|  |  | هزینه کل بدون ضریب |  | 19504834509.7596 | 915830.1094
[5 empty] | Rls | Euro
ITEM | DESCRIPTION | Volume (Liters) (S.G.~1) | هرینه واحد (Rial/Kg) | هزینه کل (ریال) | توضیحات
1 | Ethylene Glycol | 55000 | 1021681.8077 | 56192499420.9741
2 | Anti-Scale | 77500 | 464400.8217 | 35991063678.7231
3 | Biocide TYPE A | 24000 | 668737.1832 | 16049692396.6022
4 | Biocide TYPE B | 70080 | 613009.0846 | 42959676648.2386
5 | Corrosion Inhibitor | 22000 | 780193.3804 | 17164254368.5885
6 | Demulsifier | 265500 | 1188866.1035 | 315643950466.5099
7 | O 2 Scavenger | 146550 | 482976.8545 | 70780258030.9877
8 | Reverse Demulsifier | 43800 | 780193.3804 | 34172470061.0989
9 | Any other chemical required for operation | 1 | 3715206573.2875 | 3715206573.2875
|  | هزینه کل بدون ضریب |  | 592669071645.0105
Rls

## E.Endorsement
Endorsement
Item | Title | نفر ساعت نقشه کش | نفر ساعت کارشناس | نفر ساعت کارشناس ارشد
1 | Basic Document Endorcement Report
1.1 | Process Document |  |  | 600
1.2 | Safety Document |  |  | 500
1.3 | Civil Document |  |  | 400
1.4 | Structural Document |  |  | 400
1.5 | Architectural Document |  |  | 400
1.6 | Mechanical Document |  |  | 600
1.7 | HVAC Document |  |  | 400
1.8 | Piping & Pipeline Document |  |  | 400
1.9 | Electrical Document |  |  | 500
1.10 | Telecommunication Document |  |  | 350
1,11 | Instrumentation Document |  |  | 400
| Total : |  |  | 4950

## E.Process
Process Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification and Criteria | [24 empty] | 0
1.1 | Environmental Data (Site Condition) |  | 10
1.2 | Process Design Basis | 40 | 20
1.3 | Process Design Criteria | 40 | 20
1.4 | Process Description | 40 | 20
1.5 | Technical Specification For Desalter Package | 20 | 5 | 5 | 2 |  |  |  |  | 5 | 2 | 10 | 3 | 10 | 3
1.6 | Technical specification for waste water treatment package | 20 | 5 | 8 | 4 |  |  |  |  | 5 | 2 | 10 | 3 | 5 | 2
2 | Lists | [24 empty] | 0
2.1 | Equipment List | 40 | 10 | 8 | 3 |  |  | 2 | 1
2.2 | Utility Consumption List | 60 | 15 |  |  |  |  | 1 |  |  |  | 2 | 1 | 2 | 1
2.3 | Chemical List | 40 | 5 | [9 empty] | 1
2.4 | Laboratory Equipment List | 10 | 2
2.5 | Flare Load Summary | 50 | 10
2.6 | Set point & Alarm list | 60 | 20 | [8 empty] | 40 | 20
3 | Calculation | [24 empty] | 0
3.1 | Process Simulation Report | 120 | 40
3.2 | Pump Hydrolic Calculation | 100 | 40 | 20
3.3 | Line Sizing And Hydraulic Calculation | 150 | 30 | [6 empty] | 20 | 2
3.4 | Vessel Sizing Report | 80 | 20 |  | 2
3.5 | Flare Sizing Calculation | 60 | 20
3.6 | Burn Pit Calculation | 30 | 10
3.7 | Pipeline Hydranlic Simulation Report | 150 | 40 | [6 empty] | 20 | 5
3.8 | Nace Calculation Report | 10 | 5 |  | 2 |  |  |  |  | 10 | 2
4 | PFD(s) | [24 empty] | 10
4.1 | Overall Block Flow Diagram | 10 | 5 | [22 empty] | 5
4.2 | PFD - Desalting unit | 80 | 40 | [22 empty] | 5
5 | UFD | [24 empty] | 30
5.1 | UFD - Dilution Water | 40 | 10 | [22 empty] | 5
5.2 | UFD - Waste Water Treatment | 40 | 10 | [22 empty] | 5
10 | UFD - Instrument & Plant Air | 40 | 10 | [22 empty] | 5
11 | UFD - Fuel Gas | 40 | 10 | [22 empty] | 5
4 | UFD-Hydrocarbon Drain System | 40 | 10 | [22 empty] | 5
5 | UFD-Flare System | 40 | 10 | [22 empty] | 5
6 | P&ID(s) | [24 empty] | 255
6.1 | P&ID Legend & Symbols | 5 | 5 | [8 empty] | 5 | [13 empty] | 5
6.2 | P&ID- List Of drawings | 5 | 5 | [22 empty] | 5
6.3 | P&ID-Transfer Pumps | 30 | 5 | [6 empty] | 10 | 3 | 0 | 3 | [12 empty] | 10
6.4 | P&ID-Salty Crude/Desalted Crude heat Exchanger | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.5 | P&ID-Crude Oil Indirect Fired Heater | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.6 | P&ID-Electrostatic Desalters | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.7 | P&ID-Water/Water Heat Exchanger | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.8 | P&ID-Chemical Injection Packages | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.9 | P&ID-Instrument & Plant Air | 40 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 8
6.10 | P&ID-Deaeration Package | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.11 | P&ID-Dilution Water | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.12 | P&ID-Potable Water | 30 | 5 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 8
6.13 | P&ID-Skimmer Tank | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.14 | P&ID-Waste Water Treatment | 60 | 15 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 12
6.15 | P&ID-Disposal Storage tank | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.16 | P&ID-Water Water Injection Pumps | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.17 | P&ID-Oily Water Separator | 40 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.18 | P&ID-Fuel Oil System | 20 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
6.19 | P&ID-Hydrocarbon Drain Header & System | 20 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
6.20 | P&ID-Flare Header & System | 20 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
6.21 | P&ID-Fuel Gas K.O.Drum | 40 | 10 | [6 empty] | 10 | 2 | 0 | 2 | [12 empty] | 8
6.22 | P&ID-Fuel Gas Header | 20 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 10
6.23 | P&ID-Burn Pit | 30 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 8
6.24 | P&ID-Oily Water Network | 30 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
6.25 | P&ID-Evaporation Pond | 40 | 10 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
6.26 | P&ID-Off-Spec Tank | 50 | 10 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 10
6.27 | P&ID-Dirty Oil Tank | 40 | 10 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 10
6.28 | P&ID-Free Water K.O. Drum | 40 | 10 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 8
6.29 | P&ID-P.U.4 Instrument Air System | 30 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 8
6.30 | P&ID-PU4 Salty/Desalted Crude oil Separation | 80 | 20 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 10
6.31 | P&ID-Supply Water | 25 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
7 | Process Datasheets
7.1 | Process Data Sheet For Dilution Water Pump (P-103) | 5 | 2 | 1
7.2 | Process Data Sheet For Potable Water Pump (P-104) | 5 | 2 | 1
7.3 | Process Data Sheet For Injection Water Pump (P-201-A/B) | 5 | 2 | 1
7.4 | Process Data Sheet For Clean Water Pump (P-703-A/B) | 5 | 2 | 1
7.5 | Process Data Sheet For Diesel Oil Pump (P-801) | 5 | 2 | 1
7.6 | Process Data Sheet For HC Closed Drain Sump Pump (P-702) | 5 | 2 | 1
7.7 | Process Data Sheet For HC Closed Drain Transfer Pump (P-701-A/B) | 5 | 2 | 1
7.8 | Process Data Sheet For Flare K.O. Drum Liquid Pump (P-601-A/B) | 5 | 2 | 1
7.9 | Process Data Sheet For Dirty Oil Pumps(P-705-A/B) | 5 | 2 | 1
7.10 | Process Data Sheet For Degassing Water Pumps(P-005-A/B) | 5 | 2 | 1
7.11 | Process Data Sheet For Waste Water Injection Pumps (P-206-A/B/C) | 5 | 2 | 1
7.12 | Process Data Sheet For Oily Water Separator Pump(P-750) | 5 | 2 | 1
7.13 | Process Data Sheet For Deaerated Water Pump(P-105) | 5 | 2 | 1
7.14 | Process Data Sheet For Dilution Water Pumps(P-106-A1/A2) | 5 | 2 | 1
7.15 | Process Data Sheet For Recovered Waste Water Pumps(P-706-A/B) | 5 | 2 | 1
7.16 | Process Data Sheet For Salty Crude Transfer Pumps (P-002-A/B) | 5 | 2 | 1
7.17 | Process Data Sheet For Dearated Water Pumps (P-102-A/B) | 5 | 2 | 1
7.18 | Process Data Sheet For Salty Crude Transfer Pump (P-001-A/B) | 5 | 2 | 1
7.19 | Process Data Sheet For Off-Spec Pump (P-003-A/B) | 5 | 2 | 1
7.20 | Process Data Sheet for OWS Water Oil Pump (P-704) | 5 | 2 | 1
7.21 | Process Data Sheet For Firewater Loading Pump P-904 | 5 | 2 | 1
7.22 | Process Data Sheet For Chemical Injection Portable Pump (P-508 A/B/C) | 5 | 2 | 1
7.23 | Process Data Sheet For Salty Crude/Desalted Crude Heat Exchanger (E-001-A/B) | 10 | 5 | 1
7.24 | Process Data Sheet For Crude Oil Indirect Fired Heater (H-001-A1/A2/B1/B2) | 20 | 5 | 1 |  |  |  | 1 | 1
7.25 | Process Data Sheet For Water/Water Heat Exchanger (E-002-A/B) | 10 | 5 | 1
7.26 | Process Data Sheet For Demulsifier Injection Package (PK-501) | 5 | 2 | 1
7.27 | Process Data Sheet For Oxygen Scavenger Injection Package (PK-503) | 5 | 2 | 1
7.28 | Process Data Sheet For Corrosion Inhibitor injection Package (PK-504) | 5 | 2 | 1
7.29 | Process Data Sheet For Reverse Demulsifier Injection Package (PK-505) | 5 | 2 | 1
7.30 | Process Data Sheet For Biocide Injection Package (Type A) (PK-506-A) | 5 | 2 | 1
7.31 | Process Data Sheet For Anti Scalant Injection Package (PK-507) | 5 | 2 | 1
7.32 | Process Data Sheet For Air Receiver (V-401) | 5 | 2 | 1
7.33 | Process Data Sheet For Air Compressor Package & Air Dryer package (PK-401-A/B) & (PK-402) | 10 | 2 | 1
7.34 | Process Data Sheet For Air Compressor Package & Air Dryer package (PK-002-A/B) & (PK-003) | 10 | 2 | 1
7.35 | Process Data Sheet For Vacuum Deaerator Package (PK-101) | 10 | 5 | 1
7.36 | Process Data Sheet For Dilution Water Storage Tank (TK-101) | 10 | 2 | 1
7.37 | Process Data Sheet For Potable Water Tank (TK-102) | 10 | 2 | 1
7.38 | Process Data Sheet For Skimmer Tank (OS-201) | 10 | 2 | 1 |  |  |  | 1
7.39 | Process Data Sheet For Disposal Storage Tank (TK-201) | 10 | 2 | 1
7.40 | Process Data Sheet For Oily Water Separator (SU-701) | 10 | 2 | 1
7.41 | Process Data Sheet For Diesel Oil Storage Tank (V-801) | 5 | 2 | 1
7.42 | Process Data Sheet For HC Closed Drain Drum (V-701) | 5 | 2 | 1
7.43 | Process Data Sheet For Flare K.O.Drum (V-601) | 5 | 2 | 1
7.44 | Process Data Sheet For Flare Package (PK-602) | 5 | 5 | 1
7.45 | Process Data Sheet For Cold Flare Package (PK-603) | 5 | 5 | 1
7.46 | Process Data Sheet For Fuel Gas K.O.Drum (V-301) | 5 | 2 | 1
7.47 | Process Data Sheet For Burn Pit Ignition Package (PK-701) | 5 | 2 | 1
7.48 | Process Data Sheet For Dual Polarity Electrostatic Desalter (PK-001-A/B) | 15 | 10 | 1
7.49 | Process Data Sheet For Off-Spec Tank (TK-003) | 10 | 2 | 1 |  |  | 1
7.50 | Process Data Sheet For Free Water K.O. Drum (V-001-A/B) | 5 | 2 | 1
7.51 | Process Data Sheet For Biocide Injection Package (Type B) (PK-506-B) | 5 | 2 | 1
7.52 | Process Data Sheet For Demulsifier Injection Package (PK-502-A/B) | 5 | 2 | 1
7.53 | Process Data Sheet for Dirty Oil Tank (TK-701) | 5 | 2 | 1
7.54 | Process Data Sheet for IGF Package (PK-201-A/B) | 15 | 5 | 1
7.55 | Process Data Sheet for Nutshell Filter Package (PK-202) | 10 | 5 | 1
7.56 | Process Data Sheet For Water Treatment Package | 5 | 2 | 1
7.57 | Process Data Sheet For Portable Skimmer(X-704) | 5 | 2 | 1
7.58 | Process Data Sheet For Air Receiver ( V-002) | 5 | 2 | 1
7.59 | Process Data Sheet For Supply water pump(P-108A/B) | 8 | 2 | 1
7.60 | Process Data Sheet For Supply water Tank(TK-104) | 5 | 2 | 1
8 | Cause & Effect | [24 empty] | 0
8.1 | Cause & Effect Chart | 40 | 30 | [8 empty] | 10 | 2
8.2 | ESD Cause & Effect Block Diagram | 100 | 20 | [8 empty] | 10 | 2
9 | Control Philosophy | [24 empty] | 0
9.1 | FCS Control Philosophy | 120 | 30 | [8 empty] | 10 | 2
9.2 | DCS Control Philosophy (for PU4) | 30 | 10 | [8 empty] | 5 | 1
9.3 | Relief Philosophy | 50 | 20 | [8 empty] | 5 | 1
9.4 | ESD Control Philosophy | 50 | 20 | [8 empty] | 5 | 1
9.5 | Isolation Philosophy | 10 | 5 | [8 empty] | 5 | 1
9.6 | Sparing Philosophy | 10 | 5 | [8 empty] | 5 | 1
10 | Manual | [24 empty] | 0
10.1 | Commissioning and start-up Manual | 200 | 50 | 30 | 5 | [6 empty] | 20 | 5 | 30 | 5
10.2 | Operating Manual | 200 | 50 | 30 | 5 | [6 empty] | 20 | 5 | 30 | 5
11 | خدمات پس از اجرا
11.1 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | 192.65 | [23 empty] | 29.75
| Total : | 4045.65 | 1109 | 161 | 23 | 0 | 1 | 5 | 2 | 425 | 73 | 162 | 109 | 77 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624.75
|  | 3853 | 1109 | 161 | 23 | 0 | 1 | 5 | 2 | 425 | 73 | 162 | 109 | 77 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595

## E.Mechanic
Mechanical Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification, Criteria, Standard Drawing
1.1 | Mechanical Design Criteria |  |  |  | 10
1.2 | General Requirements for Welded Fabrication |  |  |  | 5
1.3 | Specification for Centrifugal Pumps for General Duty Services |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.4 | Specification for Centrifugal Pumps for Process Services |  |  |  | 8 | [6 empty] | 0.5 |  | 0.5
1.5 | Specification for Fire Water Pumps |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.6 | Specification for Indirect Fired Heaters |  |  |  | 8 | [6 empty] | 1 |  | 1
1.7 | Specification for Instrument Air Compressor Package |  |  |  | 8 | [6 empty] | 0.5 |  | 0.5
1.8 | Specification for Minimum Requirements for Packaged Equipment |  |  |  | 8
1.9 | Specification for Plate & Frame Heat Exchangers |  |  |  | 8 | [6 empty] | 0.5 |  | 0.5
1.10 | Specification for Pressure Vessels |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.11 | Specification for Safeguarding of Machinery |  |  |  | 4
1.12 | Specification for Vertical Cylindrical Storage Tanks |  |  |  | 5
1.13 | Specificaion for Flare |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.14 | Specificaion for Cranes |  |  |  | 5 | [8 empty] | 0.5 | [5 empty] | 5
1.15 | Specification for Chemical Injection Package |  |  |  | 5
1.16 | Specification for Electrostatic Crude Oil Desalting Package |  |  |  | 8 | [6 empty] | 1 |  | 1
1.17 | specification for metering pumps API 675 |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.18 | Specification for Waste Water Treatment Unit |  |  |  | 8 | [6 empty] | 1 |  | 1
1.19 | Specifcation for Rotary Pump |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.20 | specification for Lubrication System |  |  |  | 5
1.21 | Standard Drawing for Storage Tanks |  |  |  | 4 | [20 empty] | 10
1.22 | Standard Drawing for Pressure Vessel |  |  |  | 4 | [20 empty] | 10
2 | Process Packkages and Equipment Datasheet
2.1 | Heat Exchanger Datasheet
2.1.1 | Data Sheet For Salty Crude/Desalted Crude Heat Exchanger(E-001-A/B) | 1 |  |  | 5 | [6 empty] | 1
2.1.2 | Data Sheet For Water/Water Heat Exchanger(E-002-A/B) | 1 |  |  | 5 | [6 empty] | 1
2.2 | Data Sheet For Crude Oil Indirect Fired Heater(H-001-A1/A2/B1/B2) | 2 |  |  | 10 | [6 empty] | 2 |  | 1
2.3 | Air Compressors and Dryer Datasheet | [12 empty] | 0.5
2.3.1 | DATA SHEET FOR AIR COMPRESSOR PKG. (PK-401-A/B) & AIR DRYER PKG. (PK-402) | 2 |  |  | 5 | [6 empty] | 2 |  | 1
2.3.2 | Data Sheet For Air COMPRESSOR PKG. (PK-002-A/B) & AIR DRYER PKG. (PK-003) | 2 |  |  | 5 | [6 empty] | 2 |  | 1
2.4 | Data Sheet For Vacuum Deaerator Package | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.5 | Flares Datasheet
2.5.1 | Data Sheet For HOT FLARE PACKAGE AND IGNITION PACKAGE | 1 |  |  | 5 | [6 empty] | 2 |  | 0.5
2.5.2 | Data Sheet For Cold Flare Package(PK-603) | 1 |  |  | 5 | [6 empty] | 1
2.6 | DATA Sheet For Desalter Package (PK-001A/B) | 3 |  |  | 10 | [6 empty] | 2 |  | 2
2.7 | Waste Water Treatment Packages Datasheet
2.7.1 | Data Sheet For Nutshell Filter Package(PK-202) | 3 |  |  | 5 | [6 empty] | 2 |  | 1
2.7.2 | Data Sheet For IGF Package (PK-201A/B) | 1 |  |  | 8 | [6 empty] | 1 |  | 1
2.8 | Data Sheet For Cranes | 1 |  |  | 16 | [8 empty] | 2
2.9 | Injection Packages Datasheet
2.9.1 | Data Sheet For Demulsifier Injection Package (PK-501) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.2 | Data Sheet For Oxygen Scavenger Injection Package(PK-503) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.3 | Data Sheet For Corrosion Inhibitor injection Package(PK-504) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.4 | Data Sheet For Reverse Demulsifier Injection Package(PK-505) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.5 | Data Sheet For Biocide Injection Package (Type A)(PK-506-A) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.6 | Data Sheet For Anti Scalant Injection Package(PK-507) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.7 | Data Sheet For Biocide Injection Package (Type B)(PK-506-B) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.8 | Data Sheet For Demulsifier Injection Package (PK-502-A/B) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
3 | Pumps Datasheet
3.1 | Data Sheet For Dilution Water Pump(P-103) | 1 |  |  | 5 | [8 empty] | 0.5
3.2 | Data Sheet For Potable Water Pump(P-104) | 1 |  |  | 5 | [8 empty] | 0.5
3.3 | Data Sheet For Waste Water Injection Pump(P-201-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.4 | Data Sheet For OWS Clean Water Pump(p-703-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.5 | Data Sheet For Diesel Oil Pump(P-801) | 1 |  |  | 5 | [8 empty] | 0.5
3.6 | Data Sheet For HC Closed Drain Sump Pump(P-702) | 1 |  |  | 5 | [8 empty] | 0.5
3.7 | Data Sheet For HC Closed Drain Transfer Pump(P-701-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.8 | Data Sheet For Flare K.O. Drum Liquid Pump(P-601-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.9 | Data Sheet for Dilution Water Pumps(P-106-A1/A2) | 1 |  |  | 5 | [8 empty] | 0.5
3.10 | Data Sheet For Dearated Water Pump(p-102-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.11 | Data Sheet for Dirty Oil Pumps(P-705-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.12 | Data Sheet for Booster Pumps (P-002-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.13 | Data Sheet for Booster Pumps (P-001-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.14 | Data Sheet for Evaporation Pond Pumps(P-706-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.15 | Data Sheet for Free Water Transfer PUMPS (P-005-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.16 | Data Sheet for Dearated Water Pump(p-105) | 1 |  |  | 5 | [8 empty] | 0.5
3.17 | Data Sheet for Ows Oil Pump(P-704-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.18 | Data Sheet for Oily Water Separator Pump(P-750) | 1 |  |  | 5 | [8 empty] | 0.5
3.19 | Data Sheet for Waste Water Injection Pump(p-206-A/B/C) | 1 |  |  | 5 | [8 empty] | 0.5
3.20 | Data Sheet For Chemical Injection Portable Pump(P508 A/B/C) | 1 |  |  | 5 | [8 empty] | 0.5
3.21 | Data Sheet For Off-Spec Pump | 1 |  |  | 5 | [8 empty] | 0.5
3.22 | Data Sheet For Firewater Loading Pump P-904 | 1 |  |  | 5 |  |  | 1 | [5 empty] | 0.5
3.23 | Data Sheet For Supply water Pump P-108A/B | 1 |  |  | 5 | [8 empty] | 0.5
4 | Pressure Vessels Datasheet
4.1 | Data Sheet For Air Receiver(v-401) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
4.2 | Data Sheet For Diesel Oil Storage Tank(v-801) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
4.3 | Data Sheet For HC Closed Drain Drum(V-701) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
4.4 | Data Sheet For Flare K.O.Drum(V-601) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
4.5 | Data Sheet For Fuel Gas K.O.Drum(V-301) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
4.6 | Data Sheet For Free Water K.O. Drum(v-001-A/B) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 12
4.7 | Data Sheet For Air Receiver ( V-002) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
5 | Storage Tanks Datasheet
5.1 | Data Sheet For Dilution Water Storage Tank(TK-101) | 1 |  |  | 12 | [6 empty] | 1 | [13 empty] | 10
5.2 | Data Sheet For Potable Water Tank(TK-102) | 1 |  |  | 12 |  |  | 1 |  |  |  | 1 | [13 empty] | 10
5.3 | Data Sheet For Skimmer Tank(OS-201) | 1 |  |  | 12 | [6 empty] | 1 | [13 empty] | 20
5.4 | Data Sheet For Disposal Storage Tank(TK-201) | 1 |  |  | 12 | [6 empty] | 1 | [13 empty] | 15
5.5 | Data Sheet For Off-Spec Tank | 1 |  |  | 12 |  |  | 1 |  |  |  | 1 | [13 empty] | 20
5.6 | Data Sheet for Dirty Oil Tank(TK-701) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 10
5.7 | Data Sheet for Fire Water Tank(TK-902-A/B) | 1 |  |  | 15 |  |  | 3 | 1 |  |  | 1 | [13 empty] | 20
5.8 | Data Sheet For Supply Water Storage Tank(TK-104) | 1 |  |  | 12 | [6 empty] | 1 | [13 empty] | 10
6 | M.R., M.T.O. and T.B.E.
6.1 | MR for Process Centrifugal Pumps |  |  | 10 | 5
6.2 | MR for General Services Centrifugal Pumps |  |  | 10 | 5
6.3 | MR for Rotary Pumps |  |  | 10 | 5
6.4 | MR for Desalters |  |  | 10 | 5
6.5 | MR for indirect Heaters |  |  | 10 | 5
6.6 | MR for Air Compressors and Dryers |  |  | 10 | 5
6.7 | MR for Pressure Vessels |  |  | 10 | 5
6.8 | MR for Storage Tanks |  |  | 10 | 5
6.9 | MR for Heat Exchanger |  |  | 10 | 5
"6.10 | MR for Vacuum Deaerator Package |  |  | 10 | 5
6.11 | MR for Injection Packages |  |  | 10 | 5
6.12 | MR for Flares and Ignition Packages |  |  | 10 | 5
6.13 | MR for Waste Water Treatment Packages |  |  | 10 | 5
6.14 | MR for Cranes |  |  | 10 | 5
6.15 | TBE for Process Centrifugal Pumps | 25 | 5 | 70 | 12 | [8 empty] | 5 | 1
6.16 | TBE for General Services Centrifugal Pumps | 20 | 4 | 50 | 8 | [8 empty] | 5 | 1
6.17 | TBE for Rotary Pumps | 5 | 1 | 20 | 4 | [8 empty] | 3 | 1
6.18 | TBE for Desalters | 25 | 5 | 70 | 12 | [6 empty] | 10 | 5 | 8 | 2
6.19 | TBE for indirect Heaters | 25 | 5 | 70 | 12 | [6 empty] | 8 | 5 | 2 | 1
6.20 | TBE for Air Compressors and Dryers | 15 | 5 | 40 | 6 | [6 empty] | 8 | 5 | 5 | 1
6.21 | TBE for Pressure Vessels | 8 | 2 | 50 | 8 | [6 empty] | 3 | 1
6.22 | TBE for Storage Tanks | 8 | 2 | 50 | 8 | [6 empty] | 3 | 1
6.23 | TBE for Heat Exchanger | 8 | 2 | 40 | 8 | [6 empty] | 3 | 1
6.24 | TBE for Vacuum Deaerator Package | 8 | 2 | 50 | 8 | [6 empty] | 5 | 1 | 2 | 1
6.25 | TBE for Injection Packages | 8 | 2 | 50 | 8 | [6 empty] | 8 | 2 | 3 | 1
6.26 | TBE for Flares and Ignition Packages | 8 | 2 | 40 | 8 | [6 empty] | 8 | 2 | 3 | 1
6.27 | TBE for Waste Water Treatment Packages | 8 | 2 | 50 | 8 | [6 empty] | 8 | 2 | 5 | 1
6.28 | TBE for Cranes |  |  | 50 | 8 | [8 empty] | 4 | 1
7 | Review of Suppliers Technical Document
7.1 | Review of technical document of Process Centrifugal Pumps | 40 | 2 | 300 | 12 |  |  |  |  | 5 |  | 1 |  | 0 | 2
7.2 | Review of technical document of General Services Centrifugal Pumps | 16 | 2 | 120 | 8 |  |  |  |  | 5 |  | 1 |  | 0 | 2
7.3 | Review of technical document of Rotary Pumps | 4 | 1 | 30 | 5 |  |  |  |  | 1 |  | 1 |  | 0 | 1
7.4 | Review of technical document of Desalters | 40 | 5 | 300 | 30 |  |  |  |  | 8 |  | 80 | 8 | 50 | 8
7.5 | Review of technical document of indirect Heaters | 36 | 5 | 270 | 30 |  |  |  |  | 8 |  | 80 | 8 | 5 | 1
7.6 | Review of technical document of Air Compressors and Dryers | 16 | 4 | 300 | 25 | [6 empty] | 25 | 4 | 10 | 2
7.7 | Review of technical document of Pressure Vessels | 24 | 1 | 180 | 5 |  |  |  |  | 5 |  | 5
7.8 | Review of technical document of Storage Tanks | 40 | 1 | 300 | 10 |  |  |  |  | 5 |  | 5
7.9 | Review of technical document of Heat Exchanger | 16 | 1 | 120 | 15 |  |  |  |  | 5 |  | 3
7.10 | Review of technical document of Vacuum Deaerator Package | 28 | 3 | 300 | 20 |  |  |  |  | 5 |  | 50 | 8 | 5 | 1
7.11 | Review of technical document of Injection Packages | 36 | 4 | 270 | 30 |  |  |  |  | 8 |  | 80 | 8 | 10 | 2
7.12 | Review of technical document of Flares and Ignition Packages | 40 | 4 | 300 | 30 |  |  |  |  | 2 |  | 40 | 5 | 5 | 1
7.13 | Review of technical document of Waste Water Treatment Packages | 32 | 5 | 240 | 30 |  |  |  |  | 5 |  | 80 | 8 | 10 | 2
7.14 | Review of technical document of Cranes |  |  | 90 | 5 | [8 empty] | 15 | 3 |  |  |  |  | 90 | 5
8 | خدمات مرتبط با اجرا و پس از اجرا
8.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) |  |  | 396 | 96.6 | [20 empty] | 19.5
8.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی |  |  | 198 | [21 empty] | 9.75
8.3 | سیاهه کالا (Material Take-off) پس از اجرا |  |  | 30
8.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا |  |  | 25
8.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها |  |  | 40 | 8
| TOTAL : | 604 | 77 | 4649 | 1070.6 | 0 | 0 | 6 | 1 | 62 | 0 | 562.5 | 74 | 193.5 | 37 | 0 | 0 | 0 | 0 | 95 | 5 | 0 | 0 | 0 | 0 | 224.25
|  | 604 | 77 | 3960 | 966 | 0 | 0 | 6 | 1 | 62 | 0 | 562.5 | 74 | 193.5 | 37 | 0 | 0 | 0 | 0 | 95 | 5 | 0 | 0 | 0 | 0 | 195

## E.HVAC
HVAC Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification
1.1 | Specification for HVAC & Plumbing | [5 empty] | 25
1.2 | Typical Detail For Plumbing & HVAC | [5 empty] | 20
1.3 | Specification for HVAC Equipment | [5 empty] | 40
1.4 | HVAC & Plumbing Abbriviation & Symbol |  |  |  |  | 5
1.5 | HVAC & Plumbing Design Criteria | [5 empty] | 25
1.6 | HVAC & Plumbing Installation Detail | [5 empty] | 20
2 | HVAC Calculation
2.1 | HVAC Calculation for Control &Telecommunication Building |  |  |  |  | 100 | 5
2.2 | HVAC Calculation for Guard House |  |  |  |  | 30 | 5
2.3 | HVAC Calculation for DE4 Substation Building |  |  |  |  | 90 | 5
2.4 | HVAC Calculation Extension For PU4 Switchgear Room |  |  |  |  | 40 | 5
2.5 | HVAC Calculation For PU4 Accommodation Building |  |  |  |  | 50 | 5
2.6 | HVAC Calculation for Laboratory |  |  |  |  | 90 | 5
2.7 | HVAC Calculation for Work Shop |  |  |  |  | 60 | 5
2.8 | HVAC Calculation for 3.3 Switch Gear Building Of PU4 Outdoor Substaion |  |  |  |  | 80 | 5
2.9 | HVAC Calculation for 33 KV Switch Gear Building Of 33 KV Station |  |  |  |  | 80 | 5
2.10 | HVAC Calculation for 33 KV Station Guard House |  |  |  |  | 40 | 5
3 | Buildings HVAC Drawings
3.1 | HVAC Drawings for Control &Telecommunication Building |  |  |  |  | 25 | 2 | [10 empty] | 2 | [7 empty] | 150
3.2 | HVAC Drawings for Guard House |  |  |  |  | 15 | 2 | [10 empty] | 1 | [7 empty] | 60
3.3 | HVAC Drawings for DE4 Substation Building |  |  |  |  | 25 | 2 | [10 empty] | 2 | [7 empty] | 150
3.4 | HVAC Drawings Extension For PU4 Switchgear Room |  |  |  |  | 15 | 2 | [10 empty] | 1 | [7 empty] | 40
3.5 | HVAC Drawings For PU4 Accommodation Building |  |  |  |  | 25 | 2 | [10 empty] | 2 | [7 empty] | 120
3.6 | HVAC Drawings for Laboratory |  |  |  |  | 30 | 2 | [10 empty] | 3 | [7 empty] | 160
3.7 | HVAC Drawings for Work Shop |  |  |  |  | 20 | 2 | [10 empty] | 2 | [7 empty] | 80
3.8 | HVAC Drawings for 3.3 Switch Gear Building Of PU4 Outdoor Substaion |  |  |  |  | 25 | 2 | [10 empty] | 2 | [7 empty] | 120
3.9 | HVAC Drawings for 33 KV Switch Gear Building Of 33 KV Station |  |  |  |  | 25 | 2 | [10 empty] | 2 | [7 empty] | 120
3.10 | HVAC Drawings for 33 KV Station Guard House |  |  |  |  | 15 | 2 | [10 empty] | 2 | [7 empty] | 40
4 | Site Drawings
4.1 | Site Plumbing Network Layout |  |  |  |  | 5 | 2 |  |  | 1 | [5 empty] | 5 | 2 | [8 empty] | 80
4.2 | Site Sewage Network Layout |  |  |  |  | 5 | 2 |  |  | 1 | [5 empty] | 5 | 2 | [8 empty] | 80
5 | Equipment Specification
5.1 | HVAC Main Equipment Data Sheet |  |  |  |  | 150 | 40
5.2 | HVAC Equipment List |  |  |  |  | 30 | 5
6 | MTO. MR & TBE
6.1 | HVAC & Plumbing Material Take Off |  |  |  |  | 10
6.2 | MR For Hvac Equipment |  |  |  |  | 12
6.3 | TBE For Hvac Equipment Suppliers |  |  |  |  | 80 | 5
7 | Review of Suppliers Technical Document
8 | خدمات مرتبط با اجرا و پس از اجرا
8.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) |  |  |  |  | 117.7 | 25.4 | [18 empty] | 120
8.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی |  |  |  |  | 58.85 | [19 empty] | 60
8.3 | سیاهه کالا (Material Take-off) پس از اجرا |  |  |  |  | 50
8.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا |  |  |  |  | 60
8.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها |  |  |  |  | 80 | 8
| TOTAL : | 0 | 0 | 0 | 0 | 1543.55 | 287.4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380
|  | 0 | 0 | 0 | 0 | 1177 | 254 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200

## E.HSE
Safety Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification and Criteria
1.1 | HSE Design Criteria | [7 empty] | 15
1.2 | Safety Design Criteria | [7 empty] | 15
1.3 | Safety Philosophy | [7 empty] | 15
1.4 | Safety Equipment Specification | [7 empty] | 15
1.5 | Specification for CO2 Total Flooding | [7 empty] | 15
1.6 | specification for hazardous area classification | [7 empty] | 15
1.7 | specification for fire water system | [7 empty] | 15
1.8 | specification for safety signs | [7 empty] | 15
1.9 | Specification for Water Spray System | [7 empty] | 15
1.10 | Specification for Fire Alarm System | [7 empty] | 15
1.11 | Hazard Source List | 2 | [5 empty] | 30 | 25 |  |  |  |  | 4 | 1
1.12 | Specification for Foam System | [7 empty] | 15
1.13 | Specification for Foam Chamber | [7 empty] | 8
1.14 | Waste mangaement Plan | [6 empty] | 20 | 5
1.15 | safety boundary limit | [7 empty] | 15
2 | Calculation
2.1 | CO2 Demand Calculation for DE4 Substation | [6 empty] | 25 | 8
2.2 | CO2 Demand Calculation for 33/3.45 Gachsaran-4 Station | [6 empty] | 25 | 8
2.3 | Fire Water Demand Calculation | [6 empty] | 25 | 8
2.4 | Fire Water Hydrolic Calculations | [6 empty] | 60 | 8
2.5 | Flare Radiation and Disperasion Report | [6 empty] | 30 | 8
3 | P&ID
3.1 | Legend and Abbreviation For Safety & Fire Fighting P&ID | [6 empty] | 5 | [17 empty] | 10
3.2 | P&ID for CO2 total Flooding System | [6 empty] | 15 | 5 | [16 empty] | 10
3.3 | P&ID For Fire Water | 5 | 1 |  |  |  |  | 25 | 5 | [16 empty] | 20
4 | Datasheet
4.1 | Fire Water Tank data Sheet |  |  | 4 |  |  |  | 8 | 8
4.2 | Data Sheet For Fire Water Diesel Pump |  |  | 3 |  |  |  | 8 | 8
4.3 | Data Sheet For Fire Water Electrical Pump |  |  | 3 |  |  |  | 8 | 8 | 4 |  | 8 | 2
4.4 | Fire Water Jocy Pump Data Sheet | [6 empty] | 8 | 8
4.5 | Deludge Valve Datasheets | [6 empty] | 8 | 8
4.6 | Water Spray Nozzle Datasheets | [6 empty] | 12 | 8
4.7 | Hydrant data sheet | [6 empty] | 20 | 8
4.8 | Monitor data sheet | [6 empty] | 20 | 8
4.9 | Portable extinguishers data sheet | [6 empty] | 25 | 8
4.10 | Wheeled extinguishers data sheet | [6 empty] | 25 | 8
4.11 | Safety shower data sheet | [6 empty] | 20 | 8
4.12 | Data sheet for Co2 Automatic extinguishing system | [6 empty] | 30 | 8
4.13 | Data sheet for hose box | [6 empty] | 15 | 8
4.14 | Data sheet for Foam Skid | [6 empty] | 10 | 4
5 | Drawings
5.1 | Fire Water Network Piping Plan for Gachsaran-4 Desalting Unit | [6 empty] | 30 | 10 | [16 empty] | 50
5.2 | Fire Water Network Piping Plan for Gachsaran-4 Production Unit | [6 empty] | 30 | 5 | [16 empty] | 30
5.3 | Safety and Fire Fighting Equipment Layout for Gachsaran-4 Desalting Unit Buildings | [6 empty] | 15 | 5 | [16 empty] | 20
5.4 | Safety and Fire Fighting Equipment Layout for Gachsaran-4 Production Unit Buildings | [6 empty] | 15 | 5 | [16 empty] | 20
5.5 | Safety and Fire Fighting Equipment Layout For 33KV Outdoor Station Gachsaran 3 | [6 empty] | 15 | 5 | [16 empty] | 20
5.6 | Safety and Fire Fighting Equipment Layout For 33/3.45KV Outdoor Station Gachsaran 4 | [6 empty] | 15 | 5 | [16 empty] | 20
5.7 | escape routes and safety sign layout for Gachsaran-4 Desalting Unit Buildings | [6 empty] | 20 | 5 | [16 empty] | 40
5.8 | escape routes and safety sign layout for Gachsaran-4 Desalting Unit Buildings | [6 empty] | 15 | 5 | [16 empty] | 20
5.9 | escape routes and safety sign layout For 33KV Outdoor Station Gachsaran 3 | [6 empty] | 15 | 5 | [16 empty] | 20
5.10 | Fire Alarm Layout | [6 empty] | 20 | 8
5.11 | Emergency Response Plane for Gachsaran-4 Desalting Unit | [6 empty] | 15 | 5 | [16 empty] | 20
5.12 | Emergency Response Plane for Gachsaran-4 Production Unit | [6 empty] | 15 | 5 | [16 empty] | 20
6 | M.R. and T.B.E.
6.1 | Safety/fire fighting system equipment list | [6 empty] | 40 | 10
6.2 | MR for CO2 automatic extinguishing system | [6 empty] | 20 | 5
6.3 | MR for fire fighting/safety system Equipment | [6 empty] | 40 | 5
6.4 | MR for Fire Water Pumps | [6 empty] | 20 | 5
6.5 | TBE for CO2 automatic extinguishing system | [6 empty] | 40 | 5
6.6 | TBE for fire fighting/safety system Equipment | [6 empty] | 50 | 5
6.7 | TBE for Fire Water Pumps | [6 empty] | 40 | 5
7 | Review of Suppliers Technical Document
7.1 | Review of Suppliers Technical Document of for CO2 automatic extinguishing system | [6 empty] | 150 | 30
7.2 | Review of Suppliers Technical Document of for fire fighting/safety system Equipment | [6 empty] | 150 | 30
7.3 | Review of Suppliers Technical Document of for Fire Water Pumps |  |  | 10 |  |  |  | 70 | 20 |  |  |  |  | 3
8 | خدمات مرتبط با اجرا و پس از اجرا
8.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [6 empty] | 131.7 | 56.4 | [16 empty] | 32
8.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [6 empty] | 65.85 | [17 empty] | 16
8.3 | سیاهه کالا (Material Take-off) پس از اجرا | [6 empty] | 30
8.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [6 empty] | 40
8.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [6 empty] | 40 | 8
| Total | 7 | 1 | 20 | 0 | 0 | 0 | 1624.55 | 628.4 | 4 | 0 | 8 | 2 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368
|  | 7 | 1 | 20 | 0 | 0 | 0 | 1317 | 564 | 4 | 0 | 8 | 2 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320

## E.Piping&Pipeline
لیست مدارک مهندسی تفصیلی پروژه احداث واحد نمکردایی گچساران-4 به روش EPC
Piping & Pipeline Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification & Criteria
1.1 | Piping Specification & Criteria | [8 empty] | 135 | 77 | [14 empty] | 0
1.1.1 | Piping Desing Criteria | [8 empty] | 15 | 2
1.1.2 | Piping Standard Drawings | [8 empty] | 20 | 5
1.1.3 | Piping Standard Assembly Drawings | [8 empty] | 20 | 5
1.1.4 | Piping Material Specification | 10 | 5 | [6 empty] | 20 | 5
1.1.5 | Specification For Thermal Insulation (Hot Services) | [8 empty] | 5 | 5
1.1.6 | Specification For Painting, Color Coding & Marking | [8 empty] | 5 | 5
1.1.7 | Specification For Coating Of Under Ground Piping | [8 empty] | 5 | 5
1.1.8 | Specification For Stress Analysis | [8 empty] | 5 | 5
1.1.9 | Specification For Pipe Support | [8 empty] | 5 | 5
1.1.10 | Specification For Valves | [8 empty] | 5 | 5
1.1.11 | Specification For Supply Pipe & Piping Component | [8 empty] | 5 | 5
1.1.12 | Specification For Construction piping Fabrication and Erection | [8 empty] | 5 | 5
1.1.13 | Specification For Welding , heat Treatment and inspection of Piping | [8 empty] | 5 | 5
1.1.14 | Specification For Hydrostatic Pressure Testing Of Piping System | [8 empty] | 5 | 5
1.1.15 | Specification For Cleaning & Flushing Of Piping System | [8 empty] | 5 | 5
1.1.16 | Specification For Non-Metal Pipes and Fittings | [8 empty] | 5 | 5 |  |  |  |  | 2 | 2
1.2 | Pipeline Specification & Criteria
1.2.1 | PipeLine Design Criteria | 5 | 2 | [6 empty] | 10 | 5
1.2.2 | PipeLine Material Specification | [8 empty] | 15 | 8
1.2.3 | Specification of Hydrostatic Testing | [8 empty] | 15 | 8
1.2.4 | Welding Specification For Pipeline | [8 empty] | 20 | 10
1.2.5 | Specification for Construction of Pipeline | [8 empty] | 10 | 5 |  |  |  |  | 10 | 5
2 | 3D Modeling by PDMS Software
2.1 | 3D Modeling for Gachsaran-4 Desalting Unit |  | 2 |  | 2 |  |  |  | 2 | 800 | 300 |  | 1 |  | 2 |  | 2 | [8 empty] | 500
2.2 | 3D Modeling for Gachsaran-4 Production Unit Extension |  | 2 |  | 2 |  |  |  | 2 | 500 | 100 |  | 1 |  | 2 |  | 2 | [8 empty] | 300
2.3 | 3D Modeling for Existing Gachsaran-4 Production Unit | [8 empty] | 1000 | 300 | [14 empty] | 700
2.4 | PIPING ISOMETRICS | [8 empty] | 300 | 100 | [14 empty] | 200
3 | Plot Plan
3.1 | Overal Plot Plan For Desalting Unit |  | 8 |  | 8 |  |  |  | 4 | 80 | 50 |  | 2 |  | 8 | 10 | 5 |  |  |  | 5 |  |  |  |  | 300
3.2 | Overal Plot Plan For gachsaran-4 Production Unit Extension Area |  | 4 |  | 4 |  |  |  | 2 | 80 | 50 |  | 2 |  | 4 | 3 | 3 |  |  |  | 3 |  |  |  |  | 250
3.3 | Overal Plot Plan For Existing area od Gachsaran-4 Production Unit | [8 empty] | 120 | 50 |  |  |  |  | 3 | 3 | [8 empty] | 500
3.4 | Off Site Overal Plot Plan |  | 3 |  | 3 |  |  |  | 3 | 80 | 10 |  |  |  | 2 | 10 | 5 |  |  |  | 1 |  |  |  |  | 200
3.5 | Plan For Flare Area |  | 1 |  | 1 |  |  |  |  | 50 | 10 | [14 empty] | 100
3.6 | Piping Plan For Cold Flare Area |  | 1 |  | 1 |  |  |  |  | 50 | 10 | [14 empty] | 100
3.7 | Plot Plan For Burn pit Area |  | 1 |  | 1 |  |  |  |  | 50 | 10 | [14 empty] | 100
3.8 | Plot Plan For Evaporation Pound Area | [8 empty] | 50 | 10 | [14 empty] | 100
3.9 | Plot Plan For 33KV Outdoor Substation In gachsaran NO.4 Area |  |  |  | 3 |  |  |  | 2 | 50 | 10 |  |  |  | 8 |  | 3 |  |  |  | 1 |  |  |  |  | 100
3.10 | Plot Plan For 33KV Outdoor Substation In gachsaran NO.3 Area |  |  |  | 3 |  |  |  | 2 | 50 | 10 |  |  |  | 8 |  | 3 |  |  |  | 1 |  |  |  |  | 100
4 | Piping Plan
4.1 | overal Piping Plan For Desalting Unit
4.1.1 | Key Plan For Desalting Unit | [8 empty] | 20 | 5 | [14 empty] | 10
4.1.2 | Piping Plan for Area 1 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.3 | Piping Plan for Area 2 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.4 | Piping Plan for Area 3 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.5 | Piping Plan for Area 4 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.6 | Piping Plan for Area 5 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.7 | Piping Plan for Area 6 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.8 | Piping Plan for Area 7 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.9 | Piping Plan for Area 8 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.10 | Piping Plan for Area 9 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2 | Overal Piping Plan For Production Unit |  |  |  | 1
4.2.1 | Key Plan For Production Unit | [8 empty] | 20 | 5 | [14 empty] | 10
4.2.2 | overal Piping Plan For Gachsaran-4 Production Unit Extension Area | [8 empty] | 20 | 5 | [14 empty] | 10
4.2.3 | overal Piping Plan For Existing Gachsaran-4 Production Unit |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.4 | Piping Plan for Salty/Desalted Crude oil Separation |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.5 | Key Plan For Offsite |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.6 | Plan For Flare Area |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.7 | Piping Plan For Cold Flare Area |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.8 | Piping Plan For Burn pit Area |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.9 | Piping Plan For Evaporation Pound Area |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
5 | Support Layout and List
5.1 | Support Layout For Desalting Unit | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.2 | Support Layout For gachsaran-4 Production Unit Extension Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.3 | Support Layout For Existing area od Gachsaran-4 Production Unit | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.4 | Support Layout For Flare Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.5 | Support Layout For Cold Flare Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.6 | Support Layout For Burn pit Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.7 | Support Layout For Evaporation Pound Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.8 | Support List For Desalting Unit | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.9 | Support List For gachsaran-4 Production Unit Extension Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.10 | Support List For Existing area od Gachsaran-4 Production Unit | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.11 | Support List For Flare Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.12 | Support List For Cold Flare Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.13 | Support List For Burn pit Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.14 | Support List For Evaporation Pound Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
6 | Calculation
6.1 | Stress Analysis Report for Desalting Unit | [8 empty] | 300 | 300 | [14 empty] | 300
6.2 | Stress Analysis Report for Production Unit | [8 empty] | 100 | 50 | [14 empty] | 50
6.3 | Piping Thickness Calculation | [8 empty] | 20 | 5 | [14 empty] | 10
6.4 | Pipelines Wall thickness calculation | [8 empty] | 20 | 5 | [14 empty] | 10
7 | LIST
7.1 | TIE IN POINT LIST | [8 empty] | 100 | 50 | [14 empty] | 0
7.2 | LINE LIST | 50 | 20 | [6 empty] | 150 | 30
8 | MTO. , M.R. and T.B.E.
8.1 | Piping MTO
8.1.1 | MTO. for Pipes | [8 empty] | 20 | 5
8.1.2 | MTO. for Manual Valve | [8 empty] | 20 | 5
8.1.3 | MTO. for Flange | [8 empty] | 20 | 5
8.1.4 | MTO. for Gasket | [8 empty] | 20 | 5
8.1.5 | MTO. for Fitting | [8 empty] | 20 | 5
8.1.6 | MTO. for Bults & Nuts | [8 empty] | 20 | 5
8.1.7 | MTO. for Supports | [8 empty] | 20 | 5
8.1.8 | MTO. for Non-Metallic piping component | [8 empty] | 20 | 5
8.1.9 | MTO.FOR SPECIAL ITEMS | [8 empty] | 20 | 5
8.1.10 | MTO.FOR ORIFICE FLANGES | [8 empty] | 20 | 5
8.1.11 | MTO.FOR PAINT | [8 empty] | 20 | 5
8.1.12 | MTO.FOR COATING &WRAPPING | [8 empty] | 20 | 5
8.1.13 | MTO.FOR INSULATION | [8 empty] | 20 | 5
8.1.14 | MTO.FOR ELECTRODE | [8 empty] | 20 | 5
8.1.15 | MTO.FOR STRAINER | [8 empty] | 20 | 5
8.2 | Piping M.R.
8.2.1 | M.R. for Pipes | [8 empty] | 20 | 5
8.2.2 | M.R. for Manual Valve | [8 empty] | 20 | 5
8.2.3 | M.R. for Flange | [8 empty] | 20 | 5
8.2.4 | M.R. for Gasket | [8 empty] | 20 | 5
8.2.5 | M.R. for Fitting | [8 empty] | 20 | 5
8.2.6 | M.R. for Bults & Nuts | [8 empty] | 20 | 5
8.2.7 | M.R. for Supports | [8 empty] | 20 | 5
8.2.8 | M.R. for Non-Metallic piping component | [8 empty] | 20 | 5
8.2.9 | M.R.FOR SPECIAL ITEMS | [8 empty] | 20 | 5
8.2.10 | M.R.FOR ORIFICE FLANGES | [8 empty] | 20 | 5
8.2.11 | M.R.FOR PAINT | [8 empty] | 20 | 5
8.2.12 | M.R.FOR COATING &WRAPPING | [8 empty] | 20 | 5
8.2.13 | M.R.FOR INSULATION | [8 empty] | 20 | 5
8.2.14 | M.R.FOR ELECTRODE | [8 empty] | 20 | 5
8.2.15 | M.R.FOR STRAINER | [8 empty] | 20 | 5
8.3 | Piping T.B.E.
8.3.1 | T.B.E. for Pipes | [8 empty] | 20 | 5
8.3.2 | T.B.E. for Manual Valve | [8 empty] | 20 | 5
8.3.3 | T.B.E. for Flange | [8 empty] | 20 | 5
8.3.4 | T.B.E. for Gasket | [8 empty] | 20 | 5
8.3.5 | T.B.E. for Fitting | [8 empty] | 20 | 5
8.3.6 | T.B.E. for Bults & Nuts | [8 empty] | 20 | 5
8.3.7 | T.B.E. for Non-Metallic piping component | [8 empty] | 20 | 5
8.3.8 | T.B.E.FOR SPECIAL ITEMS | [8 empty] | 20 | 5
8.3.9 | T.B.E.FOR ORIFICE FLANGES | [8 empty] | 20 | 5
8.3.10 | T.B.E.FOR INSULATION | [8 empty] | 20 | 5
8.3.11 | T.B.E.FOR STRAINER | [8 empty] | 20 | 5
9 | Pipe Line MTO. , M.R. and T.B.E.
9.1 | Pipe Line MTO
9.1.1 | M.T.O. for Metallic Pipeline and component | [8 empty] | 60 | 3
9.1.2 | M.T.O. for Non-Metallic Pipeline and component | [8 empty] | 40 | 3
9.2 | Pipe Line MR
9.2.1 | M.R. for Metallic Pipeline and component | [8 empty] | 40 | 10
9.2.2 | M.R. for Non-Metallic Pipeline and component | [8 empty] | 30 | 10
9.3 | Pipe Line TBE | [8 empty] | 80 | 20
9.3.1 | T.B.E.. for Metallic Pipeline and component | [8 empty] | 50 | 10
9.3.2 | T.B.E.. for Non-Metallic Pipeline and component | [8 empty] | 30 | 10
10 | خدمات مرتبط با اجرا و پس از اجرا
10.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [8 empty] | 610 | 208.6 | [14 empty] | 425
10.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [8 empty] | 305 | [15 empty] | 212.5
10.3 | سیاهه کالا (Material Take-off) پس از اجرا | [8 empty] | 120
10.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [8 empty] | 150
10.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [8 empty] | 80 | 8
| Total : | 65 | 49 | 0 | 45 | 0 | 0 | 0 | 17 | 7365 | 2302.6 | 0 | 6 | 0 | 34 | 66 | 33 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 4887.5
|  | 65 | 49 | 0 | 45 | 0 | 0 | 0 | 17 | 6100 | 2086 | 0 | 6 | 0 | 34 | 66 | 33 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 4250

## E.Instrument
Instrumentation Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification & Criteria
1.1 | Instrumentaion and Control Design Criteria | [11 empty] | 55
1.2 | Specification for Instrumentation | [11 empty] | 50
1.3 | Specification for FCS Control System | [11 empty] | 55
1.4 | Specification for Emergency Shutdown System | [11 empty] | 55
1.5 | Specification for Fire & Gas Detection and Alarm Systems | [11 empty] | 55
1.6 | Specification for Instrument Cables | [11 empty] | 40
1.8 | Specification for Instrumentation of Packaged Units | [11 empty] | 50
1.7 | specification for CCTV And Intruder detection System | [11 empty] | 8
1.8 | Specification forJB & Bulk Material | [11 empty] | 30
2 | Datasheet
2.1 | Data Sheet for Orifice Plates | 12 | [9 empty] | 40 | 20
2.2 | Data Sheet for Local Flow Indicators | 12 | [9 empty] | 40 | 20
2.3 | Data Sheet for Flow Switches | 12 | [9 empty] | 40 | 20
2.4 | Data Sheet for Flow Transmitters | 12 | [9 empty] | 40 | 20
2.5 | Data sheet for level Gage | 12 | [9 empty] | 40 | 20
2.6 | Data Sheet for Level Switches | 12 | [9 empty] | 40 | 20
2.7 | Data Sheet for Level Transmitters | 12 | [9 empty] | 40 | 20
2.8 | Data Sheet for Pressure Indicators (Gages) | 12 | [9 empty] | 40 | 20
2.9 | Data Sheet for Pressure Switches | 12 | [9 empty] | 40 | 20
2.10 | Data Sheet for Pressure & Diff. Pressure Transmitters | 12 | [9 empty] | 40 | 20
2.11 | Data Sheet for Temperature Indicators (Gages) | 12 | [9 empty] | 40 | 20
2.12 | Data Sheet for Temperature Switches | 12 | [9 empty] | 40 | 20
2.13 | Data Sheet for Temperature Transmitters | 12 | [9 empty] | 40 | 20
2.14 | Data Sheet for Control Valves | 12 | [9 empty] | 45 | 30
2.15 | Data Sheet for Safety & Relief Valve | 12 | [9 empty] | 45 | 30
2.16 | Datasheet for ESD & On/Off Valves | 12 | [9 empty] | 45 | 20
2.17 | Data Sheet for Corrosion Coupon & Corrosion Transmitters | 12 | [9 empty] | 45 | 20
2.18 | Datasheet for Analyzers | 12 | [9 empty] | 15 | 25
2.19 | Data sheet for regulator valve | 12 | [9 empty] | 25 | 20
2.20 | Data Sheet for Laboratory Test Equipments | 12 | [9 empty] | 15 | 40
2.21 | Data sheet for CCTV Equipment | [10 empty] | 100 | 40
2.22 | Datasheet for F&G Instrument | [6 empty] | 8 |  |  |  | 40 | 45
3 | List
3.1 | Instrument Index | 8 | [9 empty] | 90 | 30
3.2 | FCS I/O List | 4 | [9 empty] | 65 | 25
3.3 | ESD I/O List | 4 | [9 empty] | 60 | 25
3.4 | F&G I/O List | 4 | [9 empty] | 40 | 30
3.5 | Alarm & Trip Setpoint List | 4 | 8 | [8 empty] | 40 | 20
3.6 | Power Consumption List | [10 empty] | 25 | 30
3.7 | Instrument Air Consumption List | [10 empty] | 25 | 25
3.8 | Instrument Cable List | [10 empty] | 80 | 30
3.9 | CCTV Cable list | [10 empty] | 30 | 5
4 | Calculation
4.1 | Calculation for Control Valve | [10 empty] | 80 | 50
4.2 | Calculation for Safety & Relief Valve | [10 empty] | 80 | 50
4.3 | Calculation for Orifice Plates | [10 empty] | 80 | 50
4.4 | Calculation for Comp. Air Sup. | [10 empty] | 10 | 5
4.5 | FCS Risk Management Report | [10 empty] | 25 | 20
5 | Philosophy
5.1 | F&G Philosophy |  | 8 | [9 empty] | 80
6 | Layout
6.1 | Gachsaran-4 Desalting Unit Layouts | [24 empty] | 335
6.1.1 | Desalting Unit Control Building arrangement Layout | [10 empty] | 40 | 20 |  |  |  |  | 2 | [7 empty] | 35
6.1.2 | Instrument Cable Routing for Desalting Unit Control Building | [10 empty] | 20 | 15 |  |  | 2 | 2 | [8 empty] | 35
6.1.3 | Instrument Location Layout of Desalting Unit |  | 4 |  | 4 | [6 empty] | 60 | 30 | [12 empty] | 65
6.1.4 | Instrument Main Cable Routing Layout for Desalting Unit | [10 empty] | 60 | 30 |  | 4 | 2 | 2 | [8 empty] | 65
6.1.5 | Instrument Air Layout for Desalting Unit | [9 empty] | 4 | 25 | 20 | [12 empty] | 55
6.1.6 | F&G Detection Layouts for Gachsaran-4 Desalting Unit | [7 empty] | 4 |  |  | 65 | 30 | [12 empty] | 20
6.1.8 | CCTV Cable Rout and Equipment layout Drawing for Desalting Unit | [10 empty] | 40 | 10 |  |  | 1 | 1 | [8 empty] | 60
6.2 | Gachsaran-4 Production Unit Layouts
6.2.1 | Production Unit Control Building arrangement Layout | [10 empty] | 20 | 10 |  |  |  |  | 2 | [7 empty] | 20
6.2.2 | Instrument Cable Routing for Production Unit Control Building | [10 empty] | 15 | 10 |  |  | 2 | 2 | [8 empty] | 20
6.2.3 | Instrument Location Layout of Production Unit |  | 4 |  | 4 | [6 empty] | 25 | 15 | [12 empty] | 30
6.2.4 | Instrument Main Cable Routing Layout for Production Unit | [10 empty] | 25 | 15 |  | 4 | 2 | 2 | [8 empty] | 30
6.2.5 | Instrument Air Layout for Production Unit | [10 empty] | 20 | 10 | [12 empty] | 20
6.3 | PU3 33KV Station Layouts | [24 empty] | 10
6.3.1 | F&G Detection Layouts for Gachsaran-3 33KV Station | [7 empty] | 3 |  |  | 10 | 10 | [12 empty] | 15
6.3.1 | F&G cable Route for Gachsaran-3 33KV Station | [7 empty] | 3 |  |  | 5 | 4 | [12 empty] | 10
7 | Instrument Diagrams
7.1 | Control System Architcture Diagram | [10 empty] | 30 | 45 | [12 empty] | 20
7.2 | F&G Cause & Effect Chart | [10 empty] | 30 | 50
7.4 | Loop Diagram For FCS System | [10 empty] | 80 | 25
7.5 | Loop Diagram For ESD System | [10 empty] | 75 | 25
7.6 | Loop Diagram For F&G System | [10 empty] | 75 | 25
7.7 | Logic Diagram for Instrument | [10 empty] | 80 | 40
7.8 | ESD Logic Block Diagram | 10 | 5 | [8 empty] | 80 | 10
7.9 | Junction Box Wiring Diagram For FCS | [10 empty] | 60 | 30
7.10 | Junction Box Wiring Diagram For ESD | [10 empty] | 55 | 30
7.11 | Junction Box Wiring Diagram For F&G | [10 empty] | 55 | 30
7.12 | Instrument Earthing Diagram | [10 empty] | 40 | 25
7.13 | CCTV system block diagram | [10 empty] | 80 | 30 | [12 empty] | 50
8 | Hook-Up & Mounting Diagrams
8.1 | Hook-Up for Instrument | [10 empty] | 30 | 15 | [12 empty] | 20
8.2 | Instrument Mounting Detail | [10 empty] | 40 | 25 | [12 empty] | 10
8.2 | Hook-Up for Instrument Air System | [10 empty] | 25 | 10 | [12 empty] | 10
9 | M.R., M.T.O. and T.B.E.
9.1 | M.T.O.
9.1.1 | MTO for Instrument Cables | [10 empty] | 40 | 10
9.1.2 | MTO for Instrument Bulk Material | [10 empty] | 40 | 10
9.1.3 | MTO for Junction Box & Glands | [10 empty] | 45 | 10
9.1.4 | MTO for Field Indtrumentation | [10 empty] | 50 | 10
9.1.5 | MTO for FCS System | [10 empty] | 20 | 10
9.1.6 | MTO for ESD System | [10 empty] | 30 | 10
9.1.7 | MTO for F&G System | [10 empty] | 50 | 10
9.1.8 | MTO for CCTV | [10 empty] | 20 | 10
9.1.9 | MTO for Laboratory Testing Equipment | [10 empty] | 20 | 10
9.1.10 | MTO for Packages Instrument | [10 empty] | 50 | 10
9.2 | M.R.
9.2.1 | MR for Orifice Plates | [10 empty] | 15 | 5
9.2.2 | MR for Local Flow Indicators | [10 empty] | 15 | 5
9.2.3 | MR for Flow Switches | [10 empty] | 15 | 5
9.2.4 | MR for Flow Transmitters | [10 empty] | 15 | 5
9.2.5 | MR for Level gauge | [10 empty] | 15 | 5
9.2.6 | MR for Level Switches | [10 empty] | 15 | 5
9.2.7 | MR for Level Transmitters | [10 empty] | 15 | 5
9.2.8 | MR for Pressure Indicators (Gages) | [10 empty] | 15 | 5
9.2.9 | MR for Pressure Switches | [10 empty] | 15 | 5
9.2.10 | MR for Pressure & Diff Pressure Transmitters | [10 empty] | 15 | 5
9.2.11 | MR for Temperature Indicators (Gages) | [10 empty] | 15 | 5
9.2.12 | MR for Temperature Switches | [10 empty] | 15 | 5
9.2.13 | MR for Temperature Transmitters | [10 empty] | 15 | 5
9.2.14 | MR for Control Valves | [10 empty] | 15 | 5
9.2.15 | MR for Safety & Relief Valves | [10 empty] | 15 | 5
9.2.16 | MR for ESD & On/Off Valves | [10 empty] | 15 | 5
9.2.17 | MR for Corrosion Coupon & Corrosion Transmitters | [10 empty] | 15 | 5
9.2.18 | MR for Analyzers | [10 empty] | 15 | 5
9.2.19 | MR for Regulators | [10 empty] | 15 | 5
9.2.20 | MR for FCS System | [10 empty] | 8 | 5
9.2.20 | MR for ESD System | [10 empty] | 8 | 5
9.2.21 | MR for F & G System & Equipment | [10 empty] | 15 | 5
9.2.22 | MR for Instrument Cables | [10 empty] | 15 | 5
9.2.23 | MR for Instrument Bulk Material | [10 empty] | 15 | 5
9.2.24 | MR for Junction Box & Glands | [10 empty] | 15 | 5
9.2.25 | M.R. for CCTV system | [10 empty] | 10 | 10
9.2.26 | MR For Laboratory Test Equipment | [10 empty] | 15 | 5
9.3 | T.B.E.
9.3.1 | TBE for Orifice Plates | [10 empty] | 20 | 40
9.3.2 | TBE for Local Flow Indicators | [10 empty] | 20 | 40
9.3.3 | TBE for Flow Switches | [10 empty] | 20 | 40
9.3.4 | TBE for Flow Transmitters | [10 empty] | 20 | 40
9.3.5 | TBE for Level gauge | [10 empty] | 20 | 40
9.3.6 | TBE for Level Switches | [10 empty] | 20 | 40
9.3.7 | TBE for Level Transmitters | [10 empty] | 20 | 40
9.3.8 | TBE for Pressure Indicators (Gages) | [10 empty] | 20 | 40
9.3.9 | TBE for Pressure Switches | [10 empty] | 20 | 40
9.3.10 | TBE for Pressure & Diff Pressure Transmitters | [10 empty] | 20 | 40
9.3.11 | TBE for Temperature Indicators (Gages) | [10 empty] | 20 | 40
9.3.12 | TBE for Temperature Switches | [10 empty] | 20 | 40
9.3.13 | TBE for Temperature Transmitters | [10 empty] | 20 | 40
9.3.14 | TBE for Control Valves | [10 empty] | 20 | 40
9.3.15 | TBE for Safety & Relief Valves | [10 empty] | 20 | 40
9.3.16 | TBE for ESD & On/Off Valves | [10 empty] | 20 | 40
9.3.17 | TBE for Corrosion Coupon & Corrosion Transmitters | [10 empty] | 20 | 40
9.3.18 | TBE for Analyzers | [10 empty] | 20 | 40
9.3.19 | TBE for Regulators | [10 empty] | 20 | 40
9.3.20 | TBE for FCS System | [10 empty] | 20 | 40
9.3.20 | TBE for ESD System | [10 empty] | 20 | 40
9.3.21 | TBE for F&G Equipment | [10 empty] | 20 | 40
9.3.22 | TBE for Instrument Cables | [10 empty] | 20 | 40
9.3.23 | TBE for Instrument Bulk Material | [10 empty] | 20 | 40
9.3.24 | TBE for Junction Box & Glands | [10 empty] | 20 | 40
9.3.25 | T.B.E. for CCTV system | [10 empty] | 50 | 60
9.3.26 | TBE For Laboratory Test Equipment | [10 empty] | 20 | 40
10 | Review of Suppliers Technical Document
10.1 | Review of technical document for Orifice Plates | 8 | [9 empty] | 60 | 40
10.2 | Review of technical document for Local Flow Indicators | 8 | [9 empty] | 60 | 40
10.3 | Review of technical document for Flow Switches | 8 | [9 empty] | 60 | 40
10.4 | Review of technical document for Flow Transmitters | 8 | [9 empty] | 60 | 40
10.5 | Review of technical document for Level gauge | 8 | [9 empty] | 60 | 40
10.6 | Review of technical document for Level Switches | 8 | [9 empty] | 60 | 40
10.7 | Review of technical document for Level Transmitters | 8 | [9 empty] | 60 | 40
10.8 | Review of technical document for Pressure Indicators (Gages) | 8 | [9 empty] | 60 | 40
10.9 | Review of technical document for Pressure Switches | 8 | [9 empty] | 60 | 40
10.10 | Review of technical document for Pressure & Diff Pressure Transmitters | 8 | [9 empty] | 60 | 40
10.11 | Review of technical document for Temperature Indicators (Gages) | 8 | [9 empty] | 60 | 40
10.12 | Review of technical document for Temperature Switches | 8 | [9 empty] | 60 | 40
10.13 | Review of technical document for Temperature Transmitters | 8 | [9 empty] | 60 | 40
10.14 | Review of technical document for Control Valves | 8 | [9 empty] | 70 | 55
10.15 | Review of technical document for Safety & Relief Valves | 8 | [9 empty] | 70 | 55
10.16 | Review of technical document for ESD & On/Off Valves | 8 | [9 empty] | 70 | 55 | 8
10.17 | Review of technical document for Corrosion Coupon & Corrosion Transmitters | 8 | [9 empty] | 60 | 50
10.18 | Review of technical document for Analyzers | 8 | [9 empty] | 40 | 50
10.19 | Review of technical document for Regulators | 8 | [9 empty] | 40 | 50
10.20 | Review of technical document for FCS & ESD System | 8 | [9 empty] | 60 | 75
10.21 | Review of technical document for F & G System & Equipment | 8 | [5 empty] | 5 |  |  |  | 60 | 75
10.22 | Review of technical document for Instrument Cables | 8 | [9 empty] | 50 | 40
10.23 | Review of technical document for Instrument Bulk Material | 8 | [9 empty] | 45 | 40
10.24 | Review of technical document for Junction Box & Glands | 8 | [9 empty] | 40 | 40
10.25 | Review of technical document of CCTV | [10 empty] | 80 | 15 | [8 empty] | 80 | 15
10.26 | Review of technical document for Laboratory Test Equipment | 10 | [9 empty] | 40 | 60
11 | خدمات مرتبط با اجرا و پس از اجرا
11 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [10 empty] | 571.6 | 456.7 | [12 empty] | 93.5
11.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [10 empty] | 285.8 | [13 empty] | 46.75
11.3 | سیاهه کالا (Material Take-off) پس از اجرا | [10 empty] | 120
11.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [10 empty] | 100
11.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [10 empty] | 40 | 8
| TOTAL : | 476 | 29 | 0 | 8 | 0 | 0 | 13 | 10 | 0 | 4 | 6833.4 | 5031.7 | 8 | 8 | 9 | 9 | 4 | 0 | 0 | 0 | 80 | 15 | 0 | 0 | 1075.25
|  | 476 | 29 | 0 | 8 | 0 | 0 | 13 | 10 | 0 | 4 | 5716 | 4567 | 8 | 8 | 9 | 9 | 4 | 0 | 0 | 0 | 80 | 15 | 0 | 0 | 935

## E.Electrical
Electrical Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification, Criteria, Standard Drawing
1.1 | Electrical Design Criteria & Philosophy | [13 empty] | 20
1.2 | Specification for neutral grounding resistor | [13 empty] | 10
1.3 | Specification for DC System | [13 empty] | 20
1.4 | Specification for Diesel Generator | [13 empty] | 20
1.5 | Specification for Electrical Bulk Material | [13 empty] | 20
1.6 | Specification for Grounding & lightning system | [13 empty] | 10
1.7 | Specification for LV Induction Motors | [13 empty] | 15
1.8 | Specification for LV Switchgears | [13 empty] | 20
1.9 | Specification for MV Induction Motors | [13 empty] | 20
1.10 | Specification for MV Switchgears | [13 empty] | 20
1.11 | Specification for Package Units | [13 empty] | 10
1.12 | Specification for Transformers | [13 empty] | 20
1.13 | Specification for UPS System | [13 empty] | 20
1.14 | Specification for Capacitor Banks | [13 empty] | 10
1.15 | Specification for Transmission Lines | [13 empty] | 20
1.16 | Specification for LV Cables and Wires | [13 empty] | 10
1.17 | Specification for MV Power Cables | [13 empty] | 20
1.18 | Typical Lighting Details Drawing | [12 empty] | 15 | [11 empty] | 10
1.19 | Typical Earthing Details drawing | [12 empty] | 15 | [11 empty] | 10
2 | Electrical Equipment Datasheet
2.1 | Data Sheet for Battery & Battery Charger | [12 empty] | 40 | 10
2.2 | Data Sheet for UPS | [12 empty] | 40 | 10
2.3 | Data Sheet for Transformers | [12 empty] | 40 | 10
2.4 | Data Sheet for Diesel Generator |  |  |  | 4 | [8 empty] | 40 | 10
2.5 | Data Sheet for Transmission Lines | [12 empty] | 40 | 10
2.6 | Data Sheet for Induction Motors (LV ) | [12 empty] | 60 | 10
2.7 | Data Sheet for Induction Motors (MV ) | [12 empty] | 40 | 10
2.8 | Data Sheet For LV Capacitor Bank | [12 empty] | 40 | 10
2.9 | Data Sheet For LV & MV Switchgears | [12 empty] | 40 | 10
2.10 | Data Sheet for Neutral Earthing Resistors | [12 empty] | 40 | 10
2.11 | Datasheet for 33KV for Outdoor Disconnector Switch | [12 empty] | 40 | 10
2.12 | Datasheet for 33KV for Outdoor Line Equipment | [12 empty] | 30 | 8
2.13 | Datasheet for 33KV for Outdoor Circuit Breaker | [12 empty] | 30 | 8
2.14 | Datasheet for 33KV for Earthing Switch | [12 empty] | 30 | 8
2.15 | Datasheet for 33KV for Current Transformer | [12 empty] | 30 | 8
2.16 | Datasheet for 33KV for Capacitor Transformer | [12 empty] | 30 | 8
3 | Electrical List
3.1 | Electrical Load List | 5 |  | 30 | [9 empty] | 120 | 50
3.2 | Power & Control cable List for Gachsaran-4 Desalting Plant |  |  | 3 | [9 empty] | 180 | 40
3.3 | Power & Control cable List for Gachsaran-3 33kv outdoor Station |  |  | 2 | [9 empty] | 150 | 40
3.4 | Power & Control cable List for Gachsaran-4 Production Unit |  |  | 1 | [9 empty] | 80 | 35
3.5 | Power & Control cable List for Gachsaran-4 33kv outdoor Station |  |  | 1 | [9 empty] | 150 | 35
3.6 | Power cable list for 33 kv station |  |  | 1 | [9 empty] | 50 | 15
3.7 | Lighting Cable List | [12 empty] | 150 | 30
4 | Single Line Diagram
4.1 | General Single Line Diagram
4.1.1 | Electrical & Telecom. Symbol List & Legend | [12 empty] | 5 | [11 empty] | 10
4.1.2 | Overal Single Line Diagram for Gachsaran D.E.4 | [12 empty] | 60 | 40 | [10 empty] | 80
4.1.3 | L.V. Single Line Diagram for Gachsaran D.E.4 | [12 empty] | 60 | 30 | [10 empty] | 80
4.1.4 | M.V. Single Line Diagram for Gachsaran D.E.4 | [12 empty] | 40 | 20 | [10 empty] | 50
4.1.5 | Overal Single Line Diagram for Gachsaran-3 33KV outdoor substation | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.6 | Overal Single Line Diagram for Gachsaran-4 33KV outdoor substation | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.7 | SLD for Main MV Switchgear (33 KV) in Gachsaran-3 outdoor substation | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.8 | SLD for Main MV Switchgear (3.3 KV) in Gachsaran-4 outdoor substation | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.9 | Overal Single Line Diagram for Gachsaran P.U.4 | [12 empty] | 50 | 35 | [10 empty] | 80
4.1.10 | L.V. Single Line Diagram for Gachsaran P.U.4 | [12 empty] | 60 | 40 | [10 empty] | 50
4.1.11 | M.V. Single Line Diagram for Gachsaran P.U.4 | [12 empty] | 20 | 20 | [10 empty] | 50
4.1.12 | UPS System Single Line Diagram | [12 empty] | 30 | 20 | [10 empty] | 50
4.1.13 | 110VDC Power Supply Single Line Diagram | [12 empty] | 25 | 10 | [10 empty] | 40
4.1.14 | 24VDC Power Supply Single Line Diagram | [12 empty] | 25 | 10 | [10 empty] | 40
4.1.15 | Area Lighting Panel Single Line Diagram Gachsaran D.E | [12 empty] | 25 | 10 | [10 empty] | 70
4.1.16 | Single line Diagram Main Normal/emergency Lighting Distribution Panel D.E | [12 empty] | 30 | 10 | [10 empty] | 80
4.1.17 | Single line Diagram Main Distribution Panel out door substation | [12 empty] | 10 | 10 | [10 empty] | 30
4.1.18 | Single line Diagram Main Normal/emergency Distribution Panel 33kv station | [12 empty] | 10 | 10 | [10 empty] | 30
4.1.19 | Area Lighting Panel Single Line Diagram for PU3 33kv station | [12 empty] | 10 | 10 | [10 empty] | 30
4.1.20 | Area Lighting Panel Single Line Diagram for PU4 33kv station | [12 empty] | 10 | 10 | [10 empty] | 30
4.1.21 | Control, Protection & Metering Schematic Diagrams for 3.3 & 33 KV Switchgear | [12 empty] | 40 | 10 | [10 empty] | 60
4.1.22 | Control, Protection & Metering Schematic Diagrams for 3.3 MV MCC of DP4 | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.23 | Control, Protection & Metering Schematic Diagrams for 3.3 MV MCC of PU4 | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.24 | Control, Protection & Metering Schematic Diagrams for LV MCC of DP4 | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.25 | Control, Protection & Metering Schematic Diagrams for LV MCC of PU4 | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.26 | Control, Protection & Metering Schematic Diagrams for 33KV Gachsaran-4 33KV Station | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.27 | Logic Diagram For MV Switchgears | [12 empty] | 40 | 10 | [10 empty] | 40
4.1.28 | Logic Diagram For LV Switchgears | [12 empty] | 40 | 10 | [10 empty] | 40
4.2 | Single Line Diagram for Buildings
4.2.1 | SLD for lighting Distribution for Air Compressor Room & Emergency Diesel Generator Building | [12 empty] | 10 | 2 | [10 empty] | 20
4.2.2 | SLD for lighting Distribution for Control &Telecommunication Building | [12 empty] | 20 | 2 | [10 empty] | 40
4.2.3 | SLD for lighting Distribution for Guard House | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.4 | SLD for lighting Distribution for DE4 Substation Building | [12 empty] | 15 | 2 | [10 empty] | 40
4.2.5 | SLD for lighting Distribution for DE4 Chemical storage shelter no.1 | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.6 | SLD for lighting Distribution for DE4 Chemical storage shelter no.2 | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.7 | SLD for lighting Distribution for DE4 Chemical injection package shelter no.1 | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.8 | SLD for lighting Distribution for DE4 Chemical injection package shelter no.2 | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.9 | SLD for lighting Distribution for DE4 Process Pumps shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.10 | SLD for lighting Distribution for DE4 Dilution Water Pumps shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.11 | SLD for lighting Distribution for DE4 Waste Water Pumps shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.12 | SLD for lighting Distribution for DE4 Dearated Water Pumps shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.13 | SLD for lighting Distribution for DE4 Fire Water Pumps shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.14 | SLD for lighting Distribution Extension For PU4 Switchgear Room | [12 empty] | 10 | 2 | [10 empty] | 20
4.2.15 | SLD for lighting Distribution Extension Of Control Building For PU4 | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.16 | SLD for lighting Distribution for PU4 pump shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.17 | SLD for lighting Distribution for PU4 Chemical storage shelter | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.18 | SLD for lighting Distribution for PU4 Chemical injection package shelter | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.19 | SLD for lighting Distribution For PU4 Accommodation Building | [12 empty] | 10 | 2 | [10 empty] | 30
4.2.20 | SLD for lighting Distribution for PU4 Air Compressor Room | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.21 | SLD for lighting Distribution for Laboratory | [12 empty] | 10 | 2 | [10 empty] | 30
4.2.22 | SLD for lighting Distribution for Work Shop | [12 empty] | 10 | 2 | [10 empty] | 20
4.2.23 | SLD for lighting Distribution for 3.3 Switch Gear Building Of PU4 Outdoor Substaion | [12 empty] | 10 | 2 | [10 empty] | 30
4.2.24 | SLD for lighting Distribution for 33 KV Switch Gear Building Of 33 KV Station | [12 empty] | 10 | 2 | [10 empty] | 30
4.2.25 | SLD for lighting Distribution for 33 KV Station Guard House | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.26 | SLD for lighting Distribution for 33 KV Station Diesel Generator Building | [12 empty] | 10 | 2 | [10 empty] | 30
5 | Calculations
5.1 | Lighting Calculation | [12 empty] | 80 | 10
5.2 | Grounding Calculation | [12 empty] | 60 | 10
5.3 | Cable Sizing Calculation | [12 empty] | 90 | 10
5.4 | Relay Setting | [12 empty] | 60 | 10
5.5 | Capacitor Bank Capacity Calculation | [12 empty] | 20 | 10
5.6 | 110 V AC UPS Calculation | [12 empty] | 20 | 10
5.7 | DC UPS Calculation | [12 empty] | 20 | 10
5.8 | Power System Study (Short Circuit, load flow, motor starting) | [12 empty] | 100 | 10
5.9 | Diesel Generator Calculation | [12 empty] | 40 | 10
5.10 | Transmission Line Calculation | [12 empty] | 20 | 5
5.11 | Calculation for 33 & 66 KV String Insulator | [12 empty] | 25 | 5
5.12 | NGR Calculation | [12 empty] | 15 | 5
5.13 | Lightning Calculation in Gachsaran-4 Desalting Unit | [12 empty] | 15 | 5
5.14 | Lightning Arrester Calculation for 33KV Outdorr Switchgear in Gachsaran-4 Station | [12 empty] | 15 | 5
5.15 | Lightning Protection Calculation for 33KV Outdorr Switchgear in Gachsaran-4 Station | [12 empty] | 15 | 5
6 | Drawings & Layouts
6.1 | Cable Routs
6.1.1 | Overal main Cable Route for Gachsaran P.U 4 |  |  | 4 | [5 empty] | 4 |  | 2 |  | 50 | 10 | 4 | [9 empty] | 120
6.1.2 | Overal main Cable Route for Gachsaran D.E.4 |  |  | 3 | [5 empty] | 3 |  | 2 |  | 30 | 5 | 4 | [9 empty] | 60
6.1.3 | Overal main Cable Route for PU3 Gachsaran 33kv station |  |  | 2 | [5 empty] | 2 |  | 1 |  | 10 | 3 | 2 | [9 empty] | 25
6.1.4 | Overal main Cable Route for PU4 outdoor substation |  |  | 2 | [5 empty] | 2 |  | 1 |  | 10 | 3 | 2 | [9 empty] | 25
6.1.5 | Cable Route Between Desalting Unit and PU4 33/3.45KV Station | [12 empty] | 10 | 3 | 4 | [9 empty] | 25
6.1.6 | Cable Route Between NGL-1200 station and PU3 33KV Station | [12 empty] | 10 | 3 | 4 | [9 empty] | 25
6.1.7 | Overal main Cable Route for Offsite Areas | [12 empty] | 20 | 5 | 3 | [9 empty] | 25
6.1.8 | Overal main Cable Route for Diesel Generator Room | [12 empty] | 20 | 5 | 2 | [9 empty] | 25
6.1.9 | Overal main Cable Route for Switchgear Building Gachsaran D.E.4 | [12 empty] | 40 | 8 | 2 | [9 empty] | 30
6.1.10 | Overal main Cable Route for Workshop | [12 empty] | 20 | 3 | 2 | [9 empty] | 25
6.1.11 | Overal main Cable Route for DE4 Telecom Room | [12 empty] | 20 | 3 | 2 | [9 empty] | 25
6.2 | Switchgears Equipment Arrangemenst
6.2.1 | Equipment Equipment Layout for Switchgear Building Gachsaran D.E.4 | [12 empty] | 30 | 5 | [10 empty] | 80
6.2.2 | Equipment Equipment Layout for Switchgear Building Gachsaran P.U.4 | [12 empty] | 10 | 2 | [10 empty] | 30
6.2.3 | Equipment Equipment Layout for Switchgear Building of Gachsaran-4 outdoor Station | [12 empty] | 10 | 2 | [10 empty] | 30
6.2.4 | Equipment Equipment Layout for Switchgear Building of Gachsaran-3 outdoor Station | [12 empty] | 10 | 2 | [10 empty] | 30
6.3 | Area Lighting
6.3.1 | Area Lighting layout for Gachsaran D.E.4 | [12 empty] | 15 | 2 | [10 empty] | 80
6.3.2 | Area Lighting layout for Gachsaran PU4 outdoor substation | [12 empty] | 10 | 2 | [10 empty] | 30
6.3.3 | Area Lighting layout forGachsaran PU3 33kv station | [12 empty] | 10 | 2 | [10 empty] | 30
6.4 | Buildings Lighting Layout
6.4.1 | Lighting layout for Air Compressor Room & Emergency Diesel Generator Building | [12 empty] | 5 | [11 empty] | 10
6.4.2 | Lighting layout for Control &Telecommunication Building | [12 empty] | 5 | [11 empty] | 25
6.4.3 | Lighting layout for Guard House | [12 empty] | 5 | [11 empty] | 15
6.4.4 | Lighting layout for DE4 Substation Building | [12 empty] | 5 | [11 empty] | 25
6.4.5 | Lighting layout for DE4 Chemical storage shelter no.1 | [12 empty] | 3 | [11 empty] | 10
6.4.6 | Lighting layout for DE4 Chemical storage shelter no.2 | [12 empty] | 3 | [11 empty] | 10
6.4.7 | Lighting layout for DE4 Chemical injection package shelter no.1 | [12 empty] | 3 | [11 empty] | 10
6.4.8 | Lighting layout for DE4 Chemical injection package shelter no.2 | [12 empty] | 3 | [11 empty] | 10
6.4.9 | Lighting layout for DE4 Process Pumps shelter | [12 empty] | 3 | [11 empty] | 10
6.4.10 | Lighting layout for DE4 Dilution Water Pumps shelter | [12 empty] | 3 | [11 empty] | 10
6.4.11 | Lighting layout for DE4 Waste Water Pumps shelter | [12 empty] | 3 | [11 empty] | 10
6.4.12 | Lighting layout for DE4 Dearated Water Pumps shelter | [12 empty] | 3 | [11 empty] | 10
6.4.13 | Lighting layout for DE4 Fire Water Pumps shelter | [12 empty] | 3 | [11 empty] | 10
6.4.14 | Lighting layout Extension For PU4 Switchgear Room | [12 empty] | 3 | [11 empty] | 25
6.4.15 | Lighting layout Extension Of Control Building For PU4 | [12 empty] | 2 | [11 empty] | 5
6.4.16 | Lighting layout for PU4 pump shelter | [12 empty] | 3 | [11 empty] | 10
6.4.17 | Lighting layout for PU4 Chemical storage shelter | [12 empty] | 3 | [11 empty] | 10
6.4.18 | Lighting layout for PU4 Chemical injection package shelter | [12 empty] | 3 | [11 empty] | 10
6.4.19 | Lighting layout For PU4 Accommodation Building | [12 empty] | 5 | [11 empty] | 10
6.4.20 | Lighting layout for PU4 Air Compressor Room | [12 empty] | 5 | [11 empty] | 10
6.4.21 | Lighting layout for Laboratory | [12 empty] | 10 | [11 empty] | 25
6.4.22 | Lighting layout for Work Shop | [12 empty] | 5 | [11 empty] | 20
6.4.23 | Lighting layout for 3.3 Switch Gear Building Of PU4 Outdoor Substaion | [12 empty] | 5 | [11 empty] | 20
6.4.24 | Lighting layout for 33 KV Switch Gear Building Of 33 KV Station | [12 empty] | 5 | [11 empty] | 20
6.4.25 | Lighting layout for 33 KV Station Guard House | [12 empty] | 5 | [11 empty] | 10
6.4.26 | Lighting layout for 33 KV Station Diesel Generator Building | [12 empty] | 5 | [11 empty] | 20
6.5 | Area Earthing Layout
6.5.1 | Overal Earthing Layout for Gachsaran D.E. | [12 empty] | 50 | 5 | [10 empty] | 80
6.5.2 | Overal Earthing Layout for Gachsaran PU4 Extension Area | [12 empty] | 10 | 2 | [10 empty] | 40
6.5.3 | Overal Earthing Layout for Gachsaran outdoor substation | [12 empty] | 10 | 2 | [10 empty] | 40
6.5.4 | Overal Earthing Layout for 33kv station | [12 empty] | 10 | 2 | [10 empty] | 40
6.6 | Buildings Earthing Layout
6.6.1 | Earthing Layout for Substations Gachsaran D.E. | [12 empty] | 10 | 2 | [10 empty] | 30
6.6.2 | Earthing Layout for Substations 33kv station | [12 empty] | 10 | 2 | [10 empty] | 30
6.6.3 | Earthing Layout for Substations Gachsaran out door substation | [12 empty] | 5 | 2 | [10 empty] | 20
6.6.4 | Earthing Layout for Control Room | [12 empty] | 10 | 2 | [10 empty] | 40
6.6.5 | Earthing Layout for Chemical Shelter | [12 empty] | 5 | 2 | [10 empty] | 10
6.6.6 | Earthing Layout for Pump Shelter | [12 empty] | 5 | 2 | [10 empty] | 10
6.7 | Hazardous Area Classification
6.7.1 | Hazardous Area Classification for Gachsaran D.E.4 | [12 empty] | 20 | 5 | [10 empty] | 20
6.7.2 | Hazardous Area Classification for Gachsaran P.U.4 | [12 empty] | 20 | 5 | [10 empty] | 20
7 | M.R , M.T.O, and T.B.E.
7.1 | M.T.O.(s)
7.1.1 | M.T.O. for Cables and Bulk | [12 empty] | 80 | 10
7.1.2 | M.T.O for cables | [12 empty] | 120 | 10
7.1.3 | M.T.O for cables of out door substation | [12 empty] | 50 | 10
7.1.4 | M.T.O for cables of 33kv station | [12 empty] | 50 | 10
7.1.5 | M.T.O for Earthing & lightning equipment | [12 empty] | 150 | 25
7.1.6 | MTO for tower &gantry for 33kv transmission line | [12 empty] | 50 | 10
7.1.7 | MTO for Transmission Lines | [12 empty] | 40 | 10
7.1.8 | MTO for NGR | [12 empty] | 20 | 5
7.1.9 | MTO for Capacitor Banks | [12 empty] | 20 | 5
7.2 | M.R.(s)
7.2.1 | M.R. for UPS & DC System | [12 empty] | 25 | 15
7.2.2 | M.R. for Transformer | [12 empty] | 25 | 10
7.2.3 | M.R. for Diesel Generator | [12 empty] | 15 | 10
7.2.4 | M.R. for control & protection panels | [12 empty] | 20 | 15
7.2.5 | M.R. for LV/MV Switchgears | [12 empty] | 25 | 15
7.2.6 | M.R. for Capacitor Bank | [12 empty] | 10 | 5
7.2.7 | M.R. for Cables | [12 empty] | 25 | 20
7.2.8 | M.R. for Lighting Panel | [12 empty] | 20 | 15
7.2.9 | M.R. for Cable Gland & LCS | [12 empty] | 20 | 15
7.2.10 | M.R. for cable tray & ladder | [12 empty] | 30 | 15
7.2.11 | M.R. for Electrical Bulk Material | [12 empty] | 50 | 25
7.2.12 | M.R. for Lighting Material | [12 empty] | 40 | 15
7.2.13 | M.R for Neutral Earthing Resistor | [12 empty] | 30 | 10
7.2.14 | M.R for bus duct | [12 empty] | 20 | 5
7.3 | T.B.E.(s)
7.3.1 | T.B.E. for UPS & battery charger | [12 empty] | 40 | 15
7.3.2 | T.B.E. for Transformer | [12 empty] | 40 | 10
7.3.3 | T.B.E. for Diesel Generator | [12 empty] | 40 | 10
7.3.4 | T.B.E. for Main LV/MV Switchgears | [12 empty] | 80 | 30
7.3.5 | T.B.E. for bus duct | [12 empty] | 30 | 10
7.3.6 | T.B.E. for Cable | [12 empty] | 80 | 40
7.3.7 | T.B.E for Cable Gland & LCS | [12 empty] | 40 | 20
8 | Review of Suppliers Technical Document
8.1 | Review of technical document ups & battery charger | [12 empty] | 300 | 50
8.2 | Review of technical document for transformers | [12 empty] | 250 | 30
8.3 | Review of technical document for diesel generator |  |  | 30 | 4 | [8 empty] | 200 | 30
8.4 | Review of technical document for LV/MV switchgear | [12 empty] | 500 | 150
8.5 | Review of technical document for bus duct | [12 empty] | 100 | 20
8.6 | Review of technical document for cable | [12 empty] | 50 | 15
8.7 | Review of technical document for gland & LCS | [12 empty] | 50 | 15
9 | خدمات مرتبط با اجرا و پس از اجرا
9.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [12 empty] | 65.01 | 208.8 | [10 empty] | 328
9.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [12 empty] | 325.05 | [11 empty] | 164
9.3 | سیاهه کالا (Material Take-off) پس از اجرا | [12 empty] | 120
9.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [12 empty] | 100
9.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [12 empty] | 50 | 8
| TOTAL : | 5 | 0 | 79 | 8 | 0 | 0 | 0 | 0 | 11 | 0 | 6 | 0 | 7161.06 | 2304.8 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3772
|  | 5 | 0 | 79 | 8 | 0 | 0 | 0 | 0 | 11 | 0 | 6 | 0 | 6501 | 2088 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3280

## E.TELECOM
Telecommunication Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification and Criteria
1.1 | Specification for Radio System | [21 empty] | 8
1.2 | specification for telephony and paging system | [21 empty] | 8
1.3 | Telecom typical installation Detail | [20 empty] | 20 | 5 |  |  | 30
2 | Data sheet for Telecom Equipment | [20 empty] | 80 | 40
3 | Paging Calculation | [20 empty] | 70 | 30
4 | Buildings Telecom Block Diagram
4.1 | telephone system block diagram | [20 empty] | 80 | 30 |  |  | 30
4.2 | paging system block diagram | [20 empty] | 60 | 20 |  |  | 30
5 | Buildings Telecom. system Layout
5.1 | Telephone andpaging Layout for Control &Telecommunication Building | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 40
5.2 | Telephone andpaging Layout for DE4 Guard House | [12 empty] | 1 | [7 empty] | 5 |  |  |  | 20
5.3 | Telephone andpaging Layout for DE4 Substation Building | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 30
5.4 | Telephone andpaging Layout Extension For PU4 Switchgear Room | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 40
5.5 | Telephone andpaging Layout For Accommodation Building in PU4 | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 30
5.6 | Telephone andpaging Layout for Laboratory | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 40
5.7 | Telephone andpaging Layout for Work Shop | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 30
5.8 | Telephone andpaging Layout fo33 KV Switch Gear Building Of 33 KV Station | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 40
5.9 | Telephone andpaging Layout fo33 KV Station Guard House | [12 empty] | 1 | [7 empty] | 5 |  |  |  | 20
6 | Site Telecom. system Layout & List
6.1 | Telecom equipment layout drawing for Desalting Unit | [12 empty] | 1 | [7 empty] | 15 | 5 |  |  | 40
6.2 | Telecom equipment layout drawing for Production Unit Extension | [12 empty] | 1 | [7 empty] | 10 | 2 |  |  | 20
6.3 | Telecom system cable routing drawing for Desalting Unit | [12 empty] | 1 | [7 empty] | 25 | 2 |  |  | 60
6.4 | Telecom system cable routing drawing for Production Unit Extension | [12 empty] | 1 | [7 empty] | 10 | 2 |  |  | 20
6.5 | Telecom system Cable list for Desalting Unit | [12 empty] | 1 | [7 empty] | 50 | 5
6.6 | Telecom system Cable list for Production Unit Extension | [12 empty] | 1 | [7 empty] | 20 | 3
7 | MTO
7.1 | M.T.O. for Telephone system | [20 empty] | 10 | 3
7.2 | M.T.O. for Paging System | [20 empty] | 10 | 3
7.3 | M.T.O. for Radio system | [20 empty] | 10 | 3
7.5 | M.T.O. for Telephone Cable | [20 empty] | 20 | 5
8 | M.R. and T.B.E.
8.1 | M.R. for Telephone system | [20 empty] | 10 | 3
8.2 | M.R. for Paging/Intercom | [20 empty] | 10 | 3
8.3 | M.R. for Radio system | [20 empty] | 10 | 3
8.5 | T.B.E. for Telephone system | [20 empty] | 30 | 10
8.6 | T.B.E. for Paging/Intercom | [20 empty] | 30 | 10
8.8 | T.B.E. for Radio system | [20 empty] | 30 | 10
9 | Review of Suppliers Technical Document
9.1 | Review of technical document of Telephone System | [20 empty] | 80 | 15
9.2 | Review of technical document of Paging/Intercom System | [20 empty] | 80 | 15
9.3 | Review of technical document of Radio System | [20 empty] | 60 | 15
10 | خدمات مرتبط با اجرا و پس از اجرا
10.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [20 empty] | 91 | 25.8 |  |  | 52
10.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [20 empty] | 45.5 |  |  |  | 26
1-.3 | سیاهه کالا (Material Take-off) پس از اجرا | [20 empty] | 50
10.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [20 empty] | 60
10.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [20 empty] | 30 | 8
| Total : | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1186.5 | 291.8 | 0 | 0 | 598
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910 | 258 | 0 | 0 | 520

## E.Civil
Civil Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specifications and Design Criteria
1.1 | Design Criteria for Civil Works | [14 empty] | 20 | 8
1.2 | Specification for Earth Works | [14 empty] | 20 | 8
1.3 | Specification for Grading and slope protection | [14 empty] | 16 | 8
1.4 | Specification for fence and gate | [14 empty] | 16 | 8
1.5 | Specification for Sanitary sewer | [14 empty] | 16 | 8
1.6 | Specification for Sewers, Drainage and Underground Systems | 4 | 2 |  |  |  |  | 2 | 1 | 4 | 2 |  |  |  |  | 16 | 8
1.7 | Specification for paving | [14 empty] | 16 | 8
1.8 | Scope of work for Geotechnic | [14 empty] | 16 | 8
1.9 | Scope Of Surveying Work For EPC Contractor | [14 empty] | 16 | 8
1.10 | مشخصات فني فضاي سبز پروژه | [14 empty] | 16 | 8
1.11 | شرح خدمات فضاي سبز پروژه | [14 empty] | 16 | 8
1.12 | Specification for potable water treatment package |  |  | 4 | 2 | [6 empty] | 2 | 1 | 4 | 2 | 16 | 8
1.13 | Specification for sanitary wastewater treatment package |  |  | 4 | 2 |  |  | 2 | 1 |  |  | 2 | 1 | 4 | 2 | 16 | 8
1.14 | Specification for Fireproofing | [14 empty] | 16 | 8
1.15 | Roeport on civil material selection | [14 empty] | 15 | 5
2 | Typical and standard Drawings
2.1 | Typical Civil Detail Drawing | [14 empty] | 20 | 10 | [8 empty] | 30
2.2 | Typical Evaporation Pond Drawing | [14 empty] | 8 | 2 | [8 empty] | 8
2.3 | Typical Fencing Detail Drawing | [14 empty] | 8 | 2 | [8 empty] | 8
2.4 | Typical Irrigation Ditch Crossing For Pipelines | [14 empty] | 8 | 2 | [8 empty] | 8
2.5 | Typical Detail For Crossing Of Existing Facilities | [14 empty] | 8 | 2 | [8 empty] | 8
2.6 | Typical Details For Watercourse And Minor Stream Crossing | [14 empty] | 8 | 2 | [8 empty] | 8
2.7 | Typical Details For Warning Slab & Bearing Slab | [14 empty] | 8 | 2 | [8 empty] | 8
2.8 | Typical Details For R.O.W. Sections - Single Pipeline | [14 empty] | 8 | 2 | [8 empty] | 8
2.9 | Typical Details For Major And Minor Road Crossing | [14 empty] | 8 | 2 | [8 empty] | 8
2.10 | Typical Pipeline Details For Continuous Concrete Coating | [14 empty] | 8 | 2 | [8 empty] | 8
2.11 | Typical Pipeline Details For Irish Crossing | [14 empty] | 8 | 2 | [8 empty] | 8
2.12 | Typical Pipeline Details For Pipeline Marker | [14 empty] | 8 | 2 | [8 empty] | 8
2.13 | Typical Details For Existing Above Ground Pipelines Crossing | [14 empty] | 8 | 2 | [8 empty] | 8
2.14 | Typical Details For Anchor Block | [14 empty] | 8 | 2 | [8 empty] | 8
2.15 | Typical Pipeline detail for Set on weight | [14 empty] | 8 | 2 | [8 empty] | 8
2.16 | Typical Culvert Details For Pipelines | [14 empty] | 8 | 2 | [8 empty] | 8
2.17 | Typical Detail for Stoppage - Backfill on Slope(Pipeline Hillside Anchor) | [14 empty] | 8 | 2 | [8 empty] | 8
2.18 | Typical Detail for Gabion | [14 empty] | 8 | 2 | [8 empty] | 8
2.19 | Typical Road Cross Section for Access Earth Road | [14 empty] | 8 | 2 | [8 empty] | 8
2.20 | Standard Civil Drawing for U.G. | [14 empty] | 20 | 4
3 | Plan and Profile for Pipeline and Transition line
3.1 | Plan and profile for Production Unit-4 to Desalting Unit-4 Salty/Desalted crude oil | [8 empty] | 5 | [5 empty] | 10 | 5 | [8 empty] | 16
3.2 | Plan and profile for Kheirabad Raw water | [8 empty] | 5 | [5 empty] | 30 | 5 | [8 empty] | 16
3.3 | Plan and profile for Lishter Raw water | [8 empty] | 5 | [5 empty] | 30 | 5 | [8 empty] | 16
3.4 | Plan and profile for Waste Water Lines from DE-4 to inhjection wells | [8 empty] | 5 | [5 empty] | 30 | 5 | [8 empty] | 16
3.5 | Plan and profile for Waste Water Lines from PU4 to DE4 | [8 empty] | 5 | [5 empty] | 8 | 5 | [8 empty] | 16
3.6 | Plan and profile for Gachsaran-2 to Gachsaran-3 Crade Oil Line | [8 empty] | 5 | [5 empty] | 30 | 5 | [8 empty] | 16
3.7 | Plan and profile for power tranmission line | [8 empty] | 5 |  |  |  | 30 | 5 | 30 | 5 | [8 empty] | 16
4 | Civil Document for Gachsaran-4 Desalting Unit
4.1 | Topogeraphical drawing for Desalting unit-4 Area | [14 empty] | 30 | 5 | [8 empty] | 16
4.2 | Topographical drawing for Offsite | [14 empty] | 30 | 5 | [8 empty] | 16
4.3 | Rough Grading Plan for Gachsarn-4 Desalting unit | [14 empty] | 50 | 8 | [8 empty] | 25
4.4 | Rough Grading Plan for cold flare | [14 empty] | 20 | 3 | [8 empty] | 10
4.5 | Rough Grading Plan for flare | [14 empty] | 20 | 3 | [8 empty] | 10
4.6 | Rough Grading Plan for burn pit | [14 empty] | 20 | 3 | [8 empty] | 10
4.7 | Rough Grading Plan for Evaporation pond | [14 empty] | 20 | 3 | [8 empty] | 10
4.8 | Finished Grading Plan for Gachsarn-4 Desalting unit | [8 empty] | 5 | [5 empty] | 75 | 5 | [8 empty] | 50
4.9 | Finished Grading Plan for cold flare | [14 empty] | 8 | 3 | [8 empty] | 10
4.10 | Finished Grading Plan for flare | [8 empty] | 2 | [5 empty] | 8 | 3 | [8 empty] | 10
4.11 | Finished Grading Plan for burn pit | [8 empty] | 2 | [5 empty] | 8 | 3 | [8 empty] | 10
4.12 | Finished Grading Plan for Evaporation pond | [8 empty] | 2 | [5 empty] | 20 | 3 | [8 empty] | 10
4.13 | Horizontal And Vertical Alignment Plan for Gachsarn-4 Desalting unit | [14 empty] | 30 | 5 | [8 empty] | 20
4.14 | Civil details for Gachsarn-4 Desalting unit | [14 empty] | 30 | 2 | [8 empty] | 20
4.15 | Civil details for burn pit | [14 empty] | 24 | 8 | [8 empty] | 10
4.16 | Civil details for Evaporation pond | [14 empty] | 24 | 8 | [8 empty] | 10
4.17 | Civil details for overal area of Gachsarn-4 Deslating unit complex | [14 empty] | 10 | 2 | [8 empty] | 10
4.18 | Typical Drawing for Fence and Gate details | [14 empty] | 20 | 4 | [8 empty] | 30
4.19 | Fence and Gate plan for Gachsarn-4 Desalting unit | [14 empty] | 4 | 1 | [8 empty] | 8
4.20 | Fence and Gate plan for cold flare | [14 empty] | 2 | 1 | [8 empty] | 3
4.21 | Fence and Gate plan for flare | [14 empty] | 2 | 1 | [8 empty] | 3
4.22 | Fence and Gate plan for burn pit | [14 empty] | 2 | 1 | [8 empty] | 3
4.23 | Fence and Gate plan for Evaporation pond | [14 empty] | 4 | 1 | [8 empty] | 5
4.24 | Fence and Gate plan for overal area of Gachsarn-4 Deslating unit complex | [14 empty] | 4 | 2 | [8 empty] | 12
4.25 | Road Section and detail for Gachsarn-4 Desalting unit Roads | [14 empty] | 15 | 2 | [8 empty] | 10
4.26 | Road Section and detail for Gachsarn-4 Desalting unit Access Road | [14 empty] | 15 | 2 | [8 empty] | 10
4.27 | Road Section and detail for Gachsarn-4 Desalting unit Patrol Road | [14 empty] | 15 | 2 | [8 empty] | 10
4.28 | Road Section and detail for cold flare Roads | [14 empty] | 15 | 2 | [8 empty] | 10
4.29 | Road Section and detail for flare Roads | [14 empty] | 15 | 2 | [8 empty] | 10
4.30 | Road Section and detail for Evaporation pond | [14 empty] | 15 | 2 | [8 empty] | 10
4.31 | Road Section and detail for overal area of Gachsarn-4 Deslating unit complex | [14 empty] | 20 | 2 | [8 empty] | 10
4.32 | Roads Longitudinal Profiles for Gachsarn-4 Desalting unit Roads | [14 empty] | 50 | 3 | [8 empty] | 30
4.33 | Roads Longitudinal Profiles for Gachsarn-4 Desalting unit Access Road | [14 empty] | 30 | 3 | [8 empty] | 10
4.34 | Roads Longitudinal Profiles for Gachsarn-4 Desalting unit Patrol Road | [14 empty] | 30 | 3 | [8 empty] | 10
4.35 | Roads Longitudinal Profiles for cold flare Roads | [14 empty] | 30 | 3 | [8 empty] | 10
4.36 | Roads Longitudinal Profiles for flare Roads | [14 empty] | 30 | 3 | [8 empty] | 10
4.37 | Roads Longitudinal Profiles for Evaporation pond | [14 empty] | 30 | 3 | [8 empty] | 10
4.38 | Roads Longitudinal Profiles for overal area of Gachsarn-4 Deslating unit complex | [14 empty] | 30 | 3 | [8 empty] | 10
4.39 | Pipe Sleeper Sections And Details | [14 empty] | 15 | 2 | [8 empty] | 10
4.40 | U.G. Composite and Civil Detail Layout for DE-4 | [8 empty] | 10 | 5 | 10 | 5 | 10 | 5 | 70 | 5 | [8 empty] | 50
4.41 | Sanitary Manhole Section And Details | [14 empty] | 15 | 2 | [8 empty] | 8
4.42 | Stormwater Drainage System Layout for DE-4 | [14 empty] | 50 | 5 | [8 empty] | 25
4.43 | Channel Section and Details | [14 empty] | 10 | 2 | [8 empty] | 8
4.44 | Septic Tank Section And Details | [14 empty] | 16 | 4 | [8 empty] | 16
4.45 | Oily Water Separator Section And Details | [14 empty] | 25 | 5 | [8 empty] | 25
4.46 | Burn pit Section And Details | 2 | 1 | [6 empty] | 2 | 1 |  |  |  |  | 10 | 3 | [8 empty] | 8
4.47 | IGF Pit Section And Details | [8 empty] | 1 | [5 empty] | 16 | 4 | [8 empty] | 16
4.48 | Evaporation Pond Rough Grading Plan | [14 empty] | 10 | 3 | [8 empty] | 8
4.49 | Pipe Way Section And Details | [14 empty] | 20 | 3 | [8 empty] | 10
4.50 | Duct Bank Section And Details | [14 empty] | 10 | 2 | [8 empty] | 5
4.51 | Valve Pit Section And Details | [14 empty] | 10 | 2 | [8 empty] | 5
4.52 | Off-site Storm watewr drainage plan | [14 empty] | 80 | 20 | [8 empty] | 5
4.53 | Paving plan for Desalting Unit | [14 empty] | 15 | 8 | [8 empty] | 25
4.54 | Foundation Location Plan for Desalting Unit | [14 empty] | 30 | 8 | [8 empty] | 80
4.55 | Road crossing detail, plan and section | [14 empty] | 15 | 8 | [8 empty] | 40
4.56 | Drawing for Retainig Structure | [14 empty] | 25 | 10 | [8 empty] | 60
5 | Civil Document for Gachsaran-4 Production Unit Unit
5.1 | Topogeraphical drawing for Production unit-4 (Existing Unit) | [14 empty] | 8 | 2 | [8 empty] | 10
5.2 | Topogeraphical drawing for Production unit-4 (extension Area) | [14 empty] | 8 | 2 | [8 empty] | 10
5.3 | Rough Grading Plan for Gachsaran-4 Production Unit Extension | [14 empty] | 20 | 2 | [8 empty] | 20
5.4 | Finished Grading Plan for Gachsaran-4 Production Unit Extension | [8 empty] | 4 | [5 empty] | 20 | 2 | [8 empty] | 20
5.5 | Horizontal And Vertical Alignment Plan for Gachsaran-4 Production Unit Extension | [14 empty] | 30 | 2 | [8 empty] | 10
5.6 | Civil details for Gachsaran-4 Production Unit Extension | [14 empty] | 10 | 2 | [8 empty] | 10
5.7 | Fence and Gate details for Gachsaran-4 Production Unit Extension | [14 empty] | 15 | 2 | [8 empty] | 10
5.8 | Road Section and detail for Gachsaran-4 Production Unit Extension | [14 empty] | 15 | 2 | [8 empty] | 10
5.9 | Roads Longitudinal Profiles for Gachsaran-4 Production Unit Extension | [14 empty] | 30 | 2 | [8 empty] | 10
5.10 | U.G. Composite and Civil Detail Layout for Gachsaran-4 Production Unit Extension | [8 empty] | 5 | 2 | 5 | 2 | 5 | 2 | 35 | 2 | [8 empty] | 40
5.11 | Stormwater Drainage System Layout for Gachsaran-4 Production Unit Extension | [14 empty] | 20 | 2 | [8 empty] | 8
5.12 | Paving plan for Gachsaran-4 Production Unit Extension | [14 empty] | 10 | 5 | [8 empty] | 20
5.13 | Foundation Location Plan for Gachsaran-4 Production Unit Extension | [14 empty] | 20 | 5 | [8 empty] | 30
6 | Calculation
6.1 | Calculation for Storm Water Network | [14 empty] | 60 | 20
6.2 | Calculation for oily water | [14 empty] | 30 | 10
6.3 | Calculation for Earthwork volumes | [14 empty] | 25 | 5
6.4 | Calculation for Paving Design | [14 empty] | 30 | 5
6.5 | Calculation for Retainig Structure | [14 empty] | 60 | 20
7 | Civil Document for Gachsaran-3 33 Kv Station
7.1 | Rough Grading Plan for Gachsaran-3 33KV Station | [14 empty] | 30 | 8 | [8 empty] | 10
7.2 | Finished Grading Plan for Gachsaran-3 33KV Station | [14 empty] | 30 | 8 | [8 empty] | 10
7.3 | Horizontal And Vertical Alignment Plan for Gachsaran-3 33KV Station | [14 empty] | 30 | 8 | [8 empty] | 10
7.4 | Civil details for Gachsaran-3 33KV Station | [14 empty] | 10 | 2 | [8 empty] | 10
7.5 | Fence and Gate details for Gachsaran-3 33KV Station | [14 empty] | 15 | 2 | [8 empty] | 10
7.6 | Road Section and detail for Gachsaran-3 33KV Station | [14 empty] | 15 | 2 | [8 empty] | 10
7.7 | Roads Longitudinal Profiles for Gachsaran-3 33KV Station | [14 empty] | 30 | 2 | [8 empty] | 10
7.8 | Paving plan for Gachsaran-3 33KV Station | [14 empty] | 10 | 5 | [8 empty] | 20
8 | Civil Document for Gachsaran-4 33/3.45 Kv Station | [24 empty] | 100
8.1 | Topogeraphical drawing for Gachsaran-4 33KV Outdoor Station | [14 empty] | 20 | 8 | [8 empty] | 10
8.2 | Rough Grading Plan for Gachsaran-4 33KV Outdoor Station | [14 empty] | 30 | 8 | [8 empty] | 10
8.3 | Finished Grading Plan for Gachsaran-4 33KV Outdoor Station | [14 empty] | 30 | 8 | [8 empty] | 10
8.4 | Horizontal And Vertical Alignment Plan for Gachsaran-4 33KV Outdoor Station | [14 empty] | 30 | 2 | [8 empty] | 10
8.5 | Civil details for Gachsaran-4 33KV Outdoor Station | [14 empty] | 10 | 2 | [8 empty] | 10
8.6 | Fence and Gate details for Gachsaran-4 33KV Outdoor Station | [14 empty] | 15 | 2 | [8 empty] | 10
8.7 | Road Section and detail for Gachsaran-4 33KV Outdoor Station | [14 empty] | 15 | 2 | [8 empty] | 10
8.8 | Roads Longitudinal Profiles for Gachsaran-4 33KV Outdoor Station | [14 empty] | 30 | 2 | [8 empty] | 10
8.9 | Paving Plan for Gachsaran-4 33KV Outdoor Station | [14 empty] | 10 | 5 | [8 empty] | 20
9 | خدمات مرتبط با اجرا و پس از اجرا
9.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [14 empty] | 265.2 | 58.4 | [8 empty] | 166.9
9.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [14 empty] | 132.6 | [9 empty] | 83.45
9.3 | سیاهه کالا (Material Take-off) پس از اجرا | [14 empty] | 120
9.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [14 empty] | 100
9.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [14 empty] | 100 | 8
| Total : | 6 | 3 | 8 | 4 | 0 | 0 | 4 | 2 | 72 | 10 | 19 | 9 | 53 | 16 | 3369.8 | 650.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.35
|  | 6 | 3 | 8 | 4 | 0 | 0 | 4 | 2 | 72 | 10 | 19 | 9 | 53 | 16 | 2652 | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669
Calculation for Storm Water Network
Calculation for oily water
Calculation for Earthwork volumes
Calculation for Paving Design
Roeport on civil material selection

## E.Arichitectural
Architectural Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Building Specification | [16 empty] | 16 | 3
2 | General Drawings | [16 empty] | 10 | 3 | [6 empty] | 40
3 | Gachsaran-4 Deadsalting Unit Buildings
3.1 | Architectural drawing-Phase 1
3.1.1 | Architectural drawing-Phase 1 for Air Compressor Room & Emergency Diesel Generator Building | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.2 | Architectural drawing-Phase 1 for Control &Telecommunication Building | [5 empty] | 2 |  | 2 |  |  |  | 2 |  | 2 |  |  | 5 | 2 | [6 empty] | 16
3.1.3 | Architectural drawing-Phase 1 for Guard House | [11 empty] | 1 |  |  |  |  | 5 | 2 | [6 empty] | 10
3.1.4 | Architectural drawing-Phase 1 for DE4 Substation Building | [5 empty] | 2 |  | 2 | [5 empty] | 2 |  |  | 5 | 2 | [6 empty] | 16
3.1.5 | Architectural drawing-Phase 1 for DE4 Parking Shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.6 | Architectural drawing-Phase 1 for DE4 Chemical storage shelter no.1 | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.7 | Architectural drawing-Phase 1 for DE4 Chemical storage shelter no.2 | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.8 | Architectural drawing-Phase 1 for Chemical injection package shelter no.1 | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.9 | Architectural drawing-Phase 1 for Chemical injection package shelter no.2 | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.10 | Architectural drawing-Phase 1 for Process Pumps shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.11 | Architectural drawing-Phase 1 for Dilution Water Pumps shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.12 | Architectural drawing-Phase 1 for Waste Water Pumps shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.13 | Architectural drawing-Phase 1 for Dearated Water Pumps shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.14 | Architectural drawing-Phase 1 for Fire Water Pumps shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.15 | Architectural drawing-Phase 1 for Fire extinguisher shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.16 | Architectural drawing-Phase 1 for Foam Storage Building | [16 empty] | 5 | 2
3.1.17 | Architectural drawing-Phase 1 for Consumable Storage Building | [16 empty] | 5 | 2
3.2 | Architectural drawing-Phase 2
3.2.1 | Architectural drawing-Phase 2 for Air Compressor Room & Emergency Diesel Generator Building |  |  | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 25 | 5 | [6 empty] | 80
3.2.2 | Architectural drawing-Phase 2 for Control &Telecommunication Building |  |  |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 120 | 10 | [6 empty] | 200
3.2.3 | Architectural drawing-Phase 2 for Guard House | [16 empty] | 20 | 5 | [6 empty] | 50
3.2.4 | Architectural drawing-Phase 2 for DE4 Substation Building |  |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 100 | 10 | [6 empty] | 180
3.2.5 | Architectural drawing-Phase 2 for DE4 Parking Shelter | [16 empty] | 15 | 5 | [6 empty] | 40
3.2.6 | Architectural drawing-Phase 2 for DE4 Chemical storage shelter no.1 |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
3.2.7 | Architectural drawing-Phase 2 for DE4 Chemical storage shelter no.2 |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
3.2.8 | Architectural drawing-Phase 2 for Chemical injection package shelter no.1 |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
3.2.9 | Architectural drawing-Phase 2 for Chemical injection package shelter no.2 |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
3.2.10 | Architectural drawing-Phase 2 for Process Pumps shelter |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 100
3.2.11 | Architectural drawing-Phase 2 for Dilution Water Pumps shelter |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 50
3.2.12 | Architectural drawing-Phase 2 for Waste Water Pumps shelter |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 50
3.2.13 | Architectural drawing-Phase 2 for Dearated Water Pumps shelter |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 50
3.2.14 | Architectural drawing-Phase 2 for Fire Water Pumps shelter | [6 empty] | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 80
3.2.15 | Architectural drawing-Phase 2 for Fire extinguisher shelter | [6 empty] | 1 | [9 empty] | 8 | 5 | [6 empty] | 20
3.1.16 | Architectural drawing-Phase 2 for Foam Storage Building | [6 empty] | 1 | [9 empty] | 20 | 5 | [6 empty] | 30
3.1.17 | Architectural drawing-Phase 2 for Consumable Storage Building | [16 empty] | 20 | 5 | [6 empty] | 30
4 | Gachsaran-4Production Unit Buildings
4.1 | Architectural drawing-Phase 1
4.1.1 | Architectural drawing-Phase 1 Extension For PU4 Switchgear Room | [13 empty] | 1 |  |  | 5 | 2 | [6 empty] | 8
4.1.2 | Architectural drawing-Phase 1 Extension Of Control Building For PU4 | [11 empty] | 1 |  | 1 |  |  | 5 | 2 | [6 empty] | 10
4.1.3 | Architectural drawing-Phase 1 for pump shelter in production units | [16 empty] | 5 | 2 | [6 empty] | 10
4.1.4 | Architectural drawing-Phase 1 for Chemical storage shelter in production units | [16 empty] | 5 | 2 | [6 empty] | 10
4.1.5 | Architectural drawing-Phase 1 for Chemical injection package shelter in production units | [16 empty] | 5 | 2 | [6 empty] | 10
4.1.6 | Architectural drawing-Phase 1 For Accommodation Building | [16 empty] | 5 | 2 | [6 empty] | 10
4.1.7 | Architectural drawing-Phase 1 for Air Compressor Room | [16 empty] | 5 | 2 | [6 empty] | 10
4.2 | Architectural drawing-Phase 2
4.2.1 | Architectural drawing-Phase 2 Extension of PU4 Switchgear Room |  |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 40 | 10 | [6 empty] | 120
4.2.2 | Architectural drawing-Phase 2 Extension Of Control Building For PU4 |  |  |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 40 | 10 | [6 empty] | 80
4.2.3 | Architectural drawing-Phase 2 for pump shelter in production units |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 80
4.2.4 | Architectural drawing-Phase 2 for Chemical storage shelter in production units |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
4.2.5 | Architectural drawing-Phase 2 for Chemical injection package shelter in production units |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
4.2.6 | Architectural drawing-Phase 2 For Accommodation Building |  |  |  |  | 1 |  |  | 1 | [8 empty] | 25 | 5 | [6 empty] | 120
4.2.7 | Architectural drawing-Phase 2 for Air Compressor Room |  |  | 1 | [5 empty] | 1 | [7 empty] | 20 | 5 | [6 empty] | 60
5 | Off-Site Buildings
5.1 | Architectural drawing-Phase 1
5.1.1 | Architectural drawing-Phase 1 for Laboratory |  | 1 | [14 empty] | 5 | 2 | [6 empty] | 10
5.1.2 | Architectural drawing-Phase 1 for Work Shop |  |  |  | 1 | [7 empty] | 1 |  | 1 |  |  | 5 | 2 | [6 empty] | 10
5.1.3 | Architectural drawing-Phase 1 for 3.3 Switch Gear Building Of PU4 Outdoor Substaion | [13 empty] | 1 |  |  | 5 | 2 | [6 empty] | 10
5.1.4 | Architectural drawing-Phase 1 for 33 KV Switch Gear Building Of 33 KV Station | [16 empty] | 5 | 2 | [6 empty] | 10
5.1.5 | Architectural drawing-Phase 1 for 33 KV Station Guard House | [16 empty] | 5 | 2 | [6 empty] | 10
5.1.6 | Architectural drawing-Phase 1 for 33 KV Station Diesel Generator Building | [16 empty] | 5 | 2 | [6 empty] | 10
5.2 | Architectural drawing-Phase 2
5.2.1 | Architectural drawing-Phase 2 for Laboratory | 2 |  |  |  | 2 |  |  | 1 |  |  |  |  | 1 |  |  |  | 70 | 10 | [6 empty] | 180
5.2.2 | Architectural drawing-Phase 2 for Work Shop |  |  | 1 |  | 2 |  |  | 1 |  |  |  |  | 1 |  |  |  | 50 | 10 | [6 empty] | 150
5.2.3 | Architectural drawing-Phase 2 fo3.3 Switch Gear Building Of PU4 Outdoor Substaion |  |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 1 |  |  |  | 50 | 10 | [6 empty] | 150
5.2.4 | Architectural drawing-Phase 2 fo33 KV Switch Gear Building Of PU3 33 KV Station |  |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 1 |  |  |  | 50 | 12 | [6 empty] | 200
5.2.5 | Architectural drawing-Phase 2 for 33 KV Station Guard House |  |  |  |  | 1 | [11 empty] | 15 | 4 | [6 empty] | 40
5.2.6 | Architectural drawing-Phase 2 for 33 KV Station Diesel Generator Building | [12 empty] | 1 |  |  |  | 25 | 5 | [6 empty] | 120
6 | Report onarchitectural material selection | [16 empty] | 20 | 5
7 | خدمات مرتبط با اجرا و پس از اجرا
7.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [16 empty] | 120.9 | 26.2 | [6 empty] | 283
7.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [16 empty] | 60.45 | [7 empty] | 141.5
7.3 | سیاهه کالا (Material Take-off) پس از اجرا | [16 empty] | 120
7.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [16 empty] | 100
7.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [16 empty] | 100 | 8
| Total : | 2 | 1 | 14 | 1 | 12 | 4 | 5 | 13 | 14 | 0 | 14 | 5 | 22 | 8 | 0 | 0 | 1710.35 | 296.2 | 0 | 0 | 0 | 0 | 0 | 0 | 3254.5
|  | 2 | 1 | 14 | 1 | 12 | 4 | 5 | 13 | 14 | 0 | 14 | 5 | 22 | 8 | 0 | 0 | 1209 | 262 | 0 | 0 | 0 | 0 | 0 | 0 | 2830

## E.Structure
Structural & Buildings Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification, Criteria, Standard Drawing
1.1 | Design Criteria for Steel Structure | [18 empty] | 10 | 3
1.2 | Design Criteria for Concrete Structure | [18 empty] | 10 | 3
1.3 | Design Criteria for Loads & Forces | [18 empty] | 10 | 3
1.4 | Specification for Powerline transition structure | [18 empty] | 10 | 4
1.5 | Specification for Grouting | [18 empty] | 8 | 3
1.6 | Specification for Structural Concrete Works | [18 empty] | 10 | 4
1.7 | Specification for Structural Steel Fabrication | [18 empty] | 8 | 3
1.8 | Specification for Structural Steel Erection | [18 empty] | 8 | 3
1.9 | Specification for Anchor bolts | [18 empty] | 10 | 4
1.10 | Testing & Inspection Procedure for Concrete Works | [18 empty] | 8 | 3
1.11 | Testing & Inspection Procedure for Steel Works | [18 empty] | 8 | 3
1.12 | Typical Structural Detail Drawing | [18 empty] | 16 | 5 |  |  |  |  | 50
1.11 | Report on overhead crane bridge design | [18 empty] | 40 | 10
1.13 | Report on structural material selection | [18 empty] | 20 | 5
2 | Foundations Calculation
2.1 | Buildings foundations Calculation | [24 empty] | 0
2.1.1 | Foundation Calculation for DE4 Air Compressor Room & Emergency Diesel Generator Building | [18 empty] | 16 | 3
2.1.2 | Foundation Calculation for Control &Telecommunication Building | [18 empty] | 24 | 3
2.1.3 | Foundation Calculation for DE4 Guard House | [18 empty] | 16 | 3
2.1.4 | Foundation Calculation for DE4 Substation Building | [18 empty] | 24 | 3
2.1.5 | Foundation Calculation for DE4 for Foam Storage Building | [18 empty] | 16 | 3
2.1.6 | Foundation Calculation for DE4 for Consumable Storage Building | [18 empty] | 16 | 3
2.1.7 | Foundation Calculation Extension For PU4 Switchgear Room | [18 empty] | 10 | 3
2.1.8 | Foundation Calculation For Accommodation Building in PU4 | [18 empty] | 16 | 3
2.1.9 | Foundation Calculation for Air Compressor Room in PU4 | [18 empty] | 16 | 3
2.1.10 | Foundation Calculation for Laboratory | [18 empty] | 16 | 3
2.1.11 | Foundation Calculation for Work Shop | [18 empty] | 24 | 3
2.1.12 | Foundation Calculation fo3.3 Switch Gear Building Of PU4 Outdoor Substaion | [18 empty] | 10 | 3
2.1.13 | Foundation Calculation fo33 KV Switch Gear Building Of 33 KV Station | [18 empty] | 16 | 3
2.1.14 | Foundation Calculation fo33 KV Station Guard House | [18 empty] | 16 | 3
2.1.15 | Foundation Calculation fo33 KV Station Diesel Generator Building | [18 empty] | 16 | 3
2.2 | Shelters foundations Calculation | [24 empty] | 0
2.2.1 | Foundation Calculation for DE4 Parking Shelter | [18 empty] | 16 | 2
2.2.2 | Foundation Calculation for DE4 Chemical storage shelter no.1 | [18 empty] | 16 | 2
2.2.3 | Foundation Calculation for DE4 Chemical storage shelter no.2 | [18 empty] | 10 | 2
2.2.4 | Foundation Calculation for DE4 Chemical injection package shelter no.1 | [18 empty] | 16 | 2
2.2.5 | Foundation Calculation for DE4 Chemical injection package shelter no.2 | [18 empty] | 10 | 2
2.2.6 | Foundation Calculation for DE4 Process Pumps shelter | [18 empty] | 16 | 2
2.2.7 | Foundation Calculation for DE4 Dilution Water Pumps shelter | [18 empty] | 16 | 2
2.2.8 | Foundation Calculation for DE4 Waste Water Pumps shelter | [18 empty] | 16 | 2
2.2.9 | Foundation Calculation for DE4 Dearated Water Pumps shelter | [18 empty] | 16 | 2
2.2.10 | Foundation Calculation for DE4 Fire Water Pumps shelter | [18 empty] | 16 | 2
2.2.11 | Foundation Calculation for Fire extinguisher shelter | [18 empty] | 10 | 2
2.2.12 | Foundation Calculation for pump shelter in PU4 | [18 empty] | 16 | 2
2.2.13 | Foundation Calculation for Chemical storage shelter in PU4 | [18 empty] | 16 | 2
2.2.14 | Foundation Calculation for Chemical injection package shelter in PU4 | [18 empty] | 10 | 2
2.3 | Process Packages and Equipment Foundation Calculation
2.3.1 | Heat Exchanger Foundation Calculation | [18 empty] | 32 | 6 |  |  |  |  | 0
2.3.1.1 | Foundation Calculation For Salty Crude/Desalted Crude Heat Exchanger(E-001-A/B) | [18 empty] | 16 | 3
2.3.1.2 | Foundation Calculation For Water/Water Heat Exchanger(E-002-A/B) | [18 empty] | 16 | 3
2.3.2 | Foundation Calculation For Crude Oil Indirect Fired Heater(H-001-A1/A2/B1/B2) | [18 empty] | 32 | 5
2.3.3 | Air Compressors and Dryer Foundation Calculation | [18 empty] | 32 | 6 |  |  |  |  | 0
2.3.3.1 | Foundation Calculation FOR AIR COMPRESSOR PKG. (PK-401-A/B) & AIR DRYER PKG. (PK-402) | [18 empty] | 16 | 3
2.3.3.2 | Foundation Calculation For Air COMPRESSOR PKG. (PK-002-A/B) & AIR DRYER PKG. (PK-003) | [18 empty] | 16 | 3
2.3.4 | Foundation Calculation For Vacuum Deaerator Package | [18 empty] | 24 | 3
2.3.5 | Flares Foundation Calculation | [18 empty] | 74 | 13 |  |  |  |  | 0
2.3.5.1 | Foundation Calculation For HOT FLARE | [18 empty] | 32 | 5
2.3.5.2 | Foundation Calculation For IGNITION PACKAGE | [18 empty] | 10 | 3
2.3.5.3 | Foundation Calculation For Cold Flare | [18 empty] | 32 | 5
2.3.6 | Foundation Calculation For Desalter Package (PK-001A/B) | [18 empty] | 32 | 5
2.3.7 | Waste Water Treatment Packages Foundation Calculation | [18 empty] | 40 | 6 |  |  |  |  | 0
2.3.7.1 | Foundation Calculation For Nutshell Filter Package(PK-202) | [18 empty] | 16 | 3
2.3.7.2 | Foundation Calculation For IGF Package (PK-201A/B) | [18 empty] | 24 | 3
2.3.8 | Injection Packages Foundation Calculation | [18 empty] | 96 | 16 |  |  |  |  | 0
2.3.8.1 | Foundation Calculation For Demulsifier Injection Package (PK-501) | [18 empty] | 12 | 2
2.3.8.2 | Foundation Calculation For Oxygen Scavenger Injection Package(PK-503) | [18 empty] | 12 | 2
2.3.8.3 | Foundation Calculation For Corrosion Inhibitor injection Package(PK-504) | [18 empty] | 12 | 2
2.3.8.4 | Foundation Calculation For Reverse Demulsifier Injection Package(PK-505) | [18 empty] | 12 | 2
2.3.8.5 | Foundation Calculation For Biocide Injection Package (Type A)(PK-506-A) | [18 empty] | 12 | 2
2.3.8.6 | Foundation Calculation For Anti Scalant Injection Package(PK-507) | [18 empty] | 12 | 2
2.3.8.7 | Foundation Calculation For Biocide Injection Package (Type B)(PK-506-B) | [18 empty] | 12 | 2
2.3.8.8 | Foundation Calculation For Demulsifier Injection Package (PK-502-A/B) | [18 empty] | 12 | 2
2.4 | Pumps Foundation Calculation | [24 empty] | 0
2.4.1 | Foundation Calculation For Dilution Water Pump(P-103) | [18 empty] | 30 | 5
2.4.2 | Foundation Calculation For Potable Water Pump(P-104) | [18 empty] | 30 | 5
2.4.3 | Foundation Calculation For Waste Water Injection Pump(P-201-A/B) | [18 empty] | 30 | 5
2.4.4 | Foundation Calculation For OWS Clean Water Pump(p-703-A/B) | [18 empty] | 20 | 4
2.4.5 | Foundation Calculation For Diesel Oil Pump(P-801) | [18 empty] | 20 | 4
2.4.6 | Foundation Calculation For HC Closed Drain Sump Pump(P-702) | [18 empty] | 20 | 4
2.4.7 | Foundation Calculation For HC Closed Drain Transfer Pump(P-701-A/B) | [18 empty] | 20 | 4
2.4.8 | Foundation Calculation For Flare K.O. Drum Liquid Pump(P-601-A/B) | [18 empty] | 20 | 4
2.4.9 | Foundation Calculation for Dilution Water Pumps(P-106-A1/A2) | [18 empty] | 30 | 5
2.4.10 | Foundation Calculation For Dearated Water Pump(p-102-A/B) | [18 empty] | 30 | 5
2.4.11 | Foundation Calculation for Dirty Oil Pumps(P-705-A/B) | [18 empty] | 20 | 4
2.4.12 | Foundation Calculation for Booster Pumps (P-002-A/B) | [18 empty] | 30 | 5
2.4.13 | Foundation Calculation for Booster Pumps (P-001-A/B) | [18 empty] | 30 | 5
2.4.14 | Foundation Calculation for Evaporation Pond Pumps(P-706-A/B) | [18 empty] | 20 | 4
2.4.15 | Foundation Calculation for Free Water Transfer PUMPS (P-005-A/B) | [18 empty] | 30 | 5
2.4.16 | Foundation Calculation for Dearated Water Pump(p-105) | [18 empty] | 30 | 5
2.4.17 | Foundation Calculation for Ows Oil Pump(P-704-A/B) | [18 empty] | 20 | 4
2.4.18 | Foundation Calculation for Oily Water Separator Pump(P-750) | [18 empty] | 20 | 4
2.4.19 | Foundation Calculation for Waste Water Injection Pump(p-206-A/B/C) | [18 empty] | 30 | 5
2.4.20 | Foundation Calculation For Off-Spec Pump | [18 empty] | 20 | 4
2.4.21 | Foundation Calculation For Firewater Loading Pump P-904 | [18 empty] | 20 | 4
2.4.22 | Foundation Calculation For Supply Water Pump P-108A/B | [18 empty] | 30 | 5
2.5 | Pressure Vessels Foundation Calculation | [24 empty] | 0
2.5.1 | Foundation Calculation For Air Receiver(v-401) | [18 empty] | 20 | 3
2.5.2 | Foundation Calculation For Diesel Oil Storage Tank(v-801) | [18 empty] | 20 | 3
2.5.3 | Foundation Calculation For HC Closed Drain Drum(V-701) | [18 empty] | 20 | 3
2.5.4 | Foundation Calculation For Flare K.O.Drum(V-601) | [18 empty] | 20 | 3
2.5.5 | Foundation Calculation For Fuel Gas K.O.Drum(V-301) | [18 empty] | 20 | 3
2.5.6 | Foundation Calculation For Free Water K.O. Drum(v-001-A/B) | [18 empty] | 20 | 3
2.5.7 | Foundation Calculation For Air Receiver ( V-002) | [18 empty] | 20 | 3
2.6 | Storage Tanks Foundation Calculation | [24 empty] | 0
2.6.1 | Foundation Calculation For Dilution Water Storage Tank(TK-101) | [18 empty] | 32 | 5
2.6.2 | Foundation Calculation For Potable Water Tank(TK-102) | [18 empty] | 32 | 5
2.6.3 | Foundation Calculation For Skimmer Tank(OS-201) | [18 empty] | 32 | 5
2.6.4 | Foundation Calculation For Disposal Storage Tank(TK-201) | [18 empty] | 32 | 5
2.6.5 | Foundation Calculation For Off-Spec Tank | [18 empty] | 32 | 5
2.6.6 | Foundation Calculation for Dirty Oil Tank(TK-701) | [18 empty] | 32 | 5
2.6.7 | Foundation Calculation For Supply Water Tank (TK-104) | [18 empty] | 32 | 5
2.6.8 | Foundation Calculation for Fire Water Tank(TK-902-A/B) | [18 empty] | 32 | 5
2.7 | Electrical Foundation Calculation | [24 empty] | 0
2.7.1 | Foundation Calculation ForTransformers | [18 empty] | 24 | 4
2.7.2 | Foundation Calculation ForDeisel Generator | [18 empty] | 30 | 5
2.7.3 | Foundation Calculation For Lighting towers | [18 empty] | 30 | 5
2.7.4 | Foundation Calculation For Lighting Poles | [18 empty] | 20 | 4
3 | Foundations Drawing
3.1 | Buildings foundations Drawing | [24 empty] | 273
3.1.1 | Foundation Drawing for DE4 Air Compressor Room & Emergency Diesel Generator Building | [18 empty] | 4 | 2 |  |  |  |  | 16
3.1.2 | Foundation Drawing for Control &Telecommunication Building | [18 empty] | 4 | 2 |  |  |  |  | 30
3.1.3 | Foundation Drawing for DE4 Guard House | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.4 | Foundation Drawing for DE4 Substation Building | [18 empty] | 4 | 2 |  |  |  |  | 25
3.1.5 | Foundation Drawing for DE4 Foam Storage Building | [18 empty] | 4 | 2 |  |  |  |  | 16
3.1.6 | Foundation Drawing for DE4 Consumable Storage Building | [18 empty] | 4 | 2 |  |  |  |  | 16
3.1.7 | Foundation Drawing Extension For PU4 Switchgear Room | [18 empty] | 2 | [5 empty] | 8
3.1.8 | Foundation Drawing For Accommodation Building in PU4 | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.9 | Foundation Drawing for Air Compressor Room in PU4 | [18 empty] | 4 | 2 |  |  |  |  | 16
3.1.10 | Foundation Drawing for Laboratory | [18 empty] | 4 | 2 |  |  |  |  | 25
3.1.11 | Foundation Drawing for Work Shop | [18 empty] | 4 | 2 |  |  |  |  | 25
3.1.12 | Foundation Drawing fo3.3 Switch Gear Building Of PU4 Outdoor Substaion | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.13 | Foundation Drawing fo33 KV Switch Gear Building Of 33 KV Station | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.14 | Foundation Drawing fo33 KV Station Guard House | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.15 | Foundation Drawing fo33 KV Station Diesel Generator Building | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.16 | Floor Slab & Detail for DE4 Air Compressor Room & Emergency Diesel Generator Building |  |  |  | 1 | [8 empty] | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.1.17 | Floor Slab & Detail for Control &Telecommunication Building |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.1.18 | Floor Slab & Detail for Air Compressor Room in PU4 |  |  |  | 1 | [8 empty] | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.1.19 | Floor Slab & Detail fo33 KV Station Diesel Generator Building | [12 empty] | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2 | Shelters foundations Drawing | [24 empty] | 251
3.2.1 | Foundation Drawing for DE4 Parking Shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.2 | Foundation Drawing for DE4 Chemical storage shelter no.1 | [18 empty] | 5 | 2 |  |  |  |  | 25
3.2.3 | Foundation Drawing for DE4 Chemical storage shelter no.2 | [18 empty] | 5 | 2 |  |  |  |  | 25
3.2.4 | Foundation Drawing for DE4 Chemical injection package shelter no.1 | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.5 | Foundation Drawing for DE4 Chemical injection package shelter no.2 | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.6 | Foundation Drawing for DE4 Process Pumps shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.7 | Foundation Drawing for DE4 Dilution Water Pumps shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.8 | Foundation Drawing for DE4 Waste Water Pumps shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.9 | Foundation Drawing for DE4 Dearated Water Pumps shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.10 | Foundation Drawing for DE4 Fire Water Pumps shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.11 | Foundation Drawing for Fire extinguisher shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.12 | Foundation Drawing for pump shelter in PU4 | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.13 | Foundation Drawing for Chemical storage shelter in PU4 | [18 empty] | 5 | 2 |  |  |  |  | 25
3.2.14 | Foundation Drawing for Chemical injection package shelter in PU4 | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.15 | Floor Slab & Detail for DE4 Chemical injection package shelter no.1 |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.16 | Floor Slab & Detail for DE4 Chemical injection package shelter no.2 |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.17 | Floor Slab & Detail for DE4 Process Pumps shelter |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.18 | Floor Slab & Detail for DE4 Dilution Water Pumps shelter |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.19 | Floor Slab & Detail for DE4 Waste Water Pumps shelter |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.20 | Floor Slab & Detail for DE4 Dearated Water Pumps shelter |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.21 | Floor Slab & Detail for DE4 Fire Water Pumps shelter |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.22 | Floor Slab & Detail for pump shelter in PU4 |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.23 | Floor Slab & Detail for Chemical injection package shelter in PU4 |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.3 | Process Packkages and Equipment Foundation Drawing
3.3.1 | Heat Exchanger Foundation Drawing | [24 empty] | 24
3.3.1.1 | Foundation Drawing For Salty Crude/Desalted Crude Heat Exchanger(E-001-A/B) | [18 empty] | 2 | [5 empty] | 12
3.3.1.2 | Foundation Drawing For Water/Water Heat Exchanger(E-002-A/B) | [18 empty] | 2 | [5 empty] | 12
3.3.2 | Foundation Drawing For Crude Oil Indirect Fired Heater(H-001-A1/A2/B1/B2) | [18 empty] | 4 | 2 |  |  |  |  | 25
3.3.3 | Air Compressors and Dryer Foundation Drawing | [18 empty] | 8 | 4 |  |  |  |  | 40
3.3.3.1 | Foundation Drawing FOR AIR COMPRESSOR PKG. (PK-401-A/B) & AIR DRYER PKG. (PK-402) | [18 empty] | 4 | 2 |  |  |  |  | 20
3.3.3.2 | Foundation Drawing For Air COMPRESSOR PKG. (PK-002-A/B) & AIR DRYER PKG. (PK-003) | [18 empty] | 4 | 2 |  |  |  |  | 20
3.3.4 | Foundation Drawing For Vacuum Deaerator Package | [18 empty] | 3 | 2 |  |  |  |  | 16
3.3.5 | Flares Foundation Drawing | [18 empty] | 11 | 4 |  |  |  |  | 50
3.3.5.1 | Foundation Drawing For HOT FLARE | [18 empty] | 4 | 2 |  |  |  |  | 25
3.3.5.2 | Foundation Drawing For IGNITION PACKAGE | [18 empty] | 3 | [5 empty] | 10
3.3.5.3 | Foundation Drawing For Cold Flare | [18 empty] | 4 | 2 |  |  |  |  | 15
3.3.6 | Foundation Drawing For Desalter Package (PK-001A/B) | [18 empty] | 4 | 2 |  |  |  |  | 25
3.3.7 | Waste Water Treatment Packages Foundation Drawing | [18 empty] | 6 | 4 |  |  |  |  | 36
3.3.7.1 | Foundation Drawing For Nutshell Filter Package(PK-202) | [18 empty] | 3 | 2 |  |  |  |  | 16
3.3.7.2 | Foundation Drawing For IGF Package (PK-201A/B) | [18 empty] | 3 | 2 |  |  |  |  | 20
3.3.8 | Injection Packages Foundation Drawing | [18 empty] | 16 | 0 |  |  |  |  | 96
3.3.8.1 | Foundation Drawing For Demulsifier Injection Package (PK-501) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.2 | Foundation Drawing For Oxygen Scavenger Injection Package(PK-503) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.3 | Foundation Drawing For Corrosion Inhibitor injection Package(PK-504) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.4 | Foundation Drawing For Reverse Demulsifier Injection Package(PK-505) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.5 | Foundation Drawing For Biocide Injection Package (Type A)(PK-506-A) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.6 | Foundation Drawing For Anti Scalant Injection Package(PK-507) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.7 | Foundation Drawing For Biocide Injection Package (Type B)(PK-506-B) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.8 | Foundation Drawing For Demulsifier Injection Package (PK-502-A/B) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.4 | Pumps Foundation Drawing
3.4.1 | Foundation Drawing For Dilution Water Pump(P-103) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.2 | Foundation Drawing For Potable Water Pump(P-104) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.3 | Foundation Drawing For Waste Water Injection Pump(P-201-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.4 | Foundation Drawing For OWS Clean Water Pump(p-703-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.5 | Foundation Drawing For Diesel Oil Pump(P-801) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.6 | Foundation Drawing For HC Closed Drain Sump Pump(P-702) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.7 | Foundation Drawing For HC Closed Drain Transfer Pump(P-701-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.8 | Foundation Drawing For Flare K.O. Drum Liquid Pump(P-601-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.9 | Foundation Drawing for Dilution Water Pumps(P-106-A1/A2) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.10 | Foundation Drawing For Dearated Water Pump(p-102-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.11 | Foundation Drawing for Dirty Oil Pumps(P-705-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.12 | Foundation Drawing for Booster Pumps (P-002-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.13 | Foundation Drawing for Booster Pumps (P-001-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.14 | Foundation Drawing for Evaporation Pond Pumps(P-706-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.15 | Foundation Drawing for Free Water Transfer PUMPS (P-005-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.16 | Foundation Drawing for Dearated Water Pump(p-105) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.17 | Foundation Drawing for Ows Oil Pump(P-704-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.18 | Foundation Drawing for Oily Water Separator Pump(P-750) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.19 | Foundation Drawing for Waste Water Injection Pump(p-206-A/B/C) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.20 | Foundation Drawing For Off-Spec Pump |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.21 | Foundation Drawing For Firewater Loading Pump P-904 |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.22 | Foundation Drawing For Supply Water Pump P-108A/B |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.5 | Pressure Vessels Foundation Drawing
3.5.1 | Foundation Drawing For Air Receiver(v-401) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.2 | Foundation Drawing For Diesel Oil Storage Tank(v-801) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.3 | Foundation Drawing For HC Closed Drain Drum(V-701) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.4 | Foundation Drawing For Flare K.O.Drum(V-601) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.5 | Foundation Drawing For Fuel Gas K.O.Drum(V-301) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.6 | Foundation Drawing For Free Water K.O. Drum(v-001-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.7 | Foundation Drawing For Air Receiver ( V-002) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.6 | Storage Tanks Foundation Drawing
3.6.1 | Foundation Drawing For Dilution Water Storage Tank(TK-101) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.2 | Foundation Drawing For Potable Water Tank(TK-102) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.3 | Foundation Drawing For Skimmer Tank(OS-201) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.4 | Foundation Drawing For Disposal Storage Tank(TK-201) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.5 | Foundation Drawing For Off-Spec Tank |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.6 | Foundation Drawing for Dirty Oil Tank(TK-701) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.7 | Foundation Drawing For Supply Water Tank TK-104 |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.8 | Foundation Drawing for Fire Water Tank(TK-902-A/B) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.7 | Electrical Foundation Drawing
3.7.1 | Foundation Drawing For Transformers | [18 empty] | 4 | 2 |  |  |  |  | 30
3.7.2 | Foundation Drawing For Deisel Generator | [18 empty] | 3 | 2 |  |  |  |  | 16
3.7.3 | Foundation Drawing For Lighting towers | [18 empty] | 3 | 2 |  |  |  |  | 16
3.7.4 | Foundation Drawing For Lighting Poles | [18 empty] | 3 | 2 |  |  |  |  | 16
4 | Structurs Calculation
4.1 | Buildings Structural Calculation
4.1.1 | Structural Calculation for DE4 Air Compressor Room & Emergency Diesel Generator Building | [18 empty] | 30 | 5
4.1.2 | Structural Calculation for Control &Telecommunication Building | [18 empty] | 40 | 8
4.1.3 | Structural Calculation for DE4 Guard House | [18 empty] | 30 | 5
4.1.4 | Structural Calculation for DE4 Substation Building | [18 empty] | 40 | 8
4.1.5 | Structural Calculation for DE4 for Foam Storage Building | [18 empty] | 20 | 5
4.1.6 | Structural Calculation for DE4 for Consumable Storage Building | [18 empty] | 20 | 5
4.1.7 | Structural Calculation Extension For PU4 Switchgear Room | [18 empty] | 30 | 5
4.1.8 | Structural Calculation For Accommodation Building in PU4 | [18 empty] | 30 | 5
4.1.9 | Structural Calculation for Air Compressor Room in PU4 | [18 empty] | 30 | 5
4.1.10 | Structural Calculation for Laboratory | [18 empty] | 30 | 5
4.1.11 | Structural Calculation for Work Shop | [18 empty] | 30 | 5
4.1.12 | Structural Calculation fo3.3 Switch Gear Building Of PU4 Outdoor Substaion | [18 empty] | 30 | 5
4.1.13 | Structural Calculation fo33 KV Switch Gear Building Of 33 KV Station | [18 empty] | 30 | 5
4.1.14 | Structural Calculation fo33 KV Station Guard House | [18 empty] | 30 | 5
4.1.15 | Structural Calculation fo33 KV Station Diesel Generator Building | [18 empty] | 30 | 5
4.2 | Shelters Structural Calculation
4.2.1 | Structural Calculation for DE4 Parking Shelter | [18 empty] | 30 | 5
4.2.2 | Structural Calculation for DE4 Chemical storage shelter no.1 | [18 empty] | 30 | 5
4.2.3 | Structural Calculation for DE4 Chemical storage shelter no.2 | [18 empty] | 30 | 5
4.2.4 | Structural Calculation for DE4 Chemical injection package shelter no.1 | [18 empty] | 30 | 5
4.2.5 | Structural Calculation for DE4 Chemical injection package shelter no.2 | [18 empty] | 30 | 5
4.2.6 | Structural Calculation for DE4 Process Pumps shelter | [18 empty] | 30 | 5
4.2.7 | Structural Calculation for DE4 Dilution Water Pumps shelter | [18 empty] | 30 | 5
4.2.8 | Structural Calculation for DE4 Waste Water Pumps shelter | [18 empty] | 30 | 5
4.2.9 | Structural Calculation for DE4 Dearated Water Pumps shelter | [18 empty] | 30 | 5
4.2.10 | Structural Calculation for DE4 Fire Water Pumps shelter | [18 empty] | 30 | 5
4.2.11 | Structural Calculation for Fire extinguisher shelter | [18 empty] | 30 | 5
4.2.12 | Structural Calculation for pump shelter in PU4 | [18 empty] | 30 | 5
4.2.13 | Structural Calculation for Chemical storage shelter in PU4 | [18 empty] | 30 | 5
4.2.14 | Structural Calculation for Chemical injection package shelter in PU4 | [18 empty] | 30 | 5
4.3 | Others Structural Calculation
4.3.1 | Structural Calculation for Diesel Oil Support Structure | [18 empty] | 20 | 5
4.3.2 | Structural Calculation for Stand Pipes | [18 empty] | 20 | 5
4.3.3 | Structural Calculation for Platforms | [18 empty] | 30 | 5
5 | Structurs Drawings
5.1 | Buildings Structural Drawings
5.1.1 | Structural Drawing for DE4 Air Compressor Room & Emergency Diesel Generator Building | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.2 | Structural Drawing for Control &Telecommunication Building | [16 empty] | 1 |  | 8 | 5 |  |  |  |  | 50
5.1.3 | Structural Drawing for DE4 Guard House | [16 empty] | 1 |  | 3 | 2 |  |  |  |  | 16
5.1.4 | Structural Drawing for DE4 Substation Building | [16 empty] | 1 |  | 8 | 5 |  |  |  |  | 50
5.1.5 | Structural Drawing for DE4 Foam Storage Building | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.6 | Structural Drawing for DE4 Consumable Storage Building | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.7 | Structural Drawing Extension For PU4 Switchgear Room | [16 empty] | 1 |  | 3 | 2 |  |  |  |  | 10
5.1.8 | Structural Drawing For Accommodation Building in PU4 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 20
5.1.9 | Structural Drawing for Air Compressor Room in PU4 | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.10 | Structural Drawing for Laboratory | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.11 | Structural Drawing for Work Shop | [16 empty] | 1 |  | 8 | 4 |  |  |  |  | 40
5.1.12 | Structural Drawing fo3.3 Switch Gear Building Of PU4 Outdoor Substaion | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.13 | Structural Drawing fo33 KV Switch Gear Building Of 33 KV Station | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.14 | Structural Drawing fo33 KV Station Guard House | [16 empty] | 1 |  | 3 | 2 |  |  |  |  | 16
5.1.15 | Structural Drawing fo33 KV Station Diesel Generator Building | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.2 | Shelters Structural Drawings
5.2.1 | Structural Drawing for DE4 Parking Shelter | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.2 | Structural Drawing for DE4 Chemical storage shelter no.1 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.3 | Structural Drawing for DE4 Chemical storage shelter no.2 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.4 | Structural Drawing for DE4 Chemical injection package shelter no.1 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.5 | Structural Drawing for DE4 Chemical injection package shelter no.2 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.6 | Structural Drawing for DE4 Process Pumps shelter | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.7 | Structural Drawing for DE4 Dilution Water Pumps shelter | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.8 | Structural Drawing for DE4 Waste Water Pumps shelter | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.9 | Structural Drawing for DE4 Dearated Water Pumps shelter | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.10 | Structural Drawing for DE4 Fire Water Pumps shelter | [6 empty] | 4 | [9 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.11 | Structural Drawing for Fire extinguisher shelter | [6 empty] | 4 | [9 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.12 | Structural Drawing for pump shelter in PU4 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.13 | Structural Drawing for Chemical storage shelter in PU4 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.14 | Structural Drawing for Chemical injection package shelter in PU4 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.3 | Others Structural Draiwngs
5.3.1 | Structural Drawing for Diesel Oil Support Structure | [16 empty] | 1 |  | 3 | 2 |  |  |  |  | 20
5.3.2 | Structural Drawing for Stand Pipes |  |  | 4 | [7 empty] | 4 | [7 empty] | 3 | 2 |  |  |  |  | 20
5.3.3 | Structural Drawing for Platforms | [8 empty] | 5 | [9 empty] | 3 | 2 |  |  |  |  | 30
6 | Other Structures
6.1 | Calculation
6.1.1 | Structural Calculation for Bridges | [18 empty] | 100 | 10
6.1.2 | Structural Calculation for Tanks Dike wall | [18 empty] | 30 | 5
6.1.3 | Structural Calculation for Transmission Tower | [18 empty] | 40 | 10
6.1.4 | Foundation Calculation for Transmission Tower | [18 empty] | 25 | 5
6.2 | Structural Drawing for Bridges | [24 empty] | 50
6.2.1 | Structural Drawing for Tanks Dike wall | [7 empty] | 2 | [10 empty] | 5 | 2 |  |  |  |  | 20
6.2.2 | Structural Drawing for Transmission Tower | [7 empty] | 2 | [10 empty] | 5 | 2 |  |  |  |  | 40
6.2.3 | Foundation Drawing for Transmission Tower | [18 empty] | 5 | 2 |  |  |  |  | 20
6.2.4 | HC Closed Drain Pit Section And Details | [9 empty] | 5 | [8 empty] | 25 | 5 |  |  |  |  | 16
7 | خدمات مرتبط با اجرا و پس از اجرا
7.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [18 empty] | 397.3 | 89.5 |  |  |  |  | 340.4
7.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [18 empty] | 198.65 | [5 empty] | 170.2
7.3 | سیاهه کالا (Material Take-off) پس از اجرا | [18 empty] | 100
7.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [18 empty] | 120
7.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [18 empty] | 100 | 8
| TOTAL : | 0 | 0 | 26.5 | 12 | 0 | 0 | 8 | 4 | 15 | 15 | 14 | 10 | 13 | 13 | 0 | 0 | 30 | 0 | 4888.95 | 992.5 | 0 | 0 | 0 | 0 | 3914.6
|  | 0 | 0 | 26.5 | 12 | 0 | 0 | 8 | 4 | 15 | 15 | 14 | 10 | 13 | 13 | 0 | 0 | 30 | 0 | 3973 | 895 | 0 | 0 | 0 | 0 | 3404

## E.Project Control
Project Control Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | دستورالعمل هماهنگی اجرای پروژه | [22 empty] | 60 | 20
2 | دستورالعمل هماهنگی مهندسی پروژه | [22 empty] | 60 | 20
3 | دستورالعمل هماهنگی خرید پروژه | [22 empty] | 60 | 20
4 | دستورالعمل راه اندازی ، به کار گیری و راهبریسیستم اتوماسیون گردش کار | [22 empty] | 200 | 10
5 | برنامه زمانبندی (Time Schedule) | [22 empty] | 120 | 40
6 | ساختار شکست پروژه (W.B.S & C.B.S) | [22 empty] | 120 | 40
7 | لیست مدارک مهندسی پروژه | [22 empty] | 120 | 40
8 | لیست مدارک مهندسی تامین کنندگان کالا | [22 empty] | 120 | 40
| TOTAL : | [22 empty] | 860 | 230