## عملكرد كلي
رديف | شرح | (هزار ريال)
(هزار دلار)
1 | هزينه هاي در تعهد كارفرما | 88895228
2 | هزينه انجام شده تاكنون طراحي و مهندسي | 54048717
3 | جمع هزينه شده | 94095222
4 | برآورد اعتبار بخش ريالي زير پروژه 002 | 53048195982
5 | برآورد اعتبار بخش ارزي زير پروژه 002 | 15771
6 | پیش بینی تعديل معادل 40 درصد برآورد بخش ريالي زيرپروژه 002 | 19648571858
7 | پيش بيني اضافه­كاري در سقف 25 درصد برآورد بخش ريالي زير پروژه 002 | 9147177302
8 | پيش بيني اضافه­كاري در سقف 25 درصد برآورد بخش ارزي زير پروژه 002 | 5848
9 | جمع كل درخواست بخش ريالي | 98653541717
10 | جمع كل درخواست بخش ارزي | 33208
11 | اعتبار مصوب بخش ريالي | 271361276
12 | اعتبار مصوب بخش ارزي | 22116
13 | مبلغ افزايش اعتبار بخش ريالي | 53646227585
14 | مبلغ افزايش اعتبار بخش ارزي | 14478

## EPC Summary
| برآورد هزينه هاي مستقيم |  |  |  |  | برآورد با اعمال بالاسري
بخش |  | بخش ريالي | بخش ارزي (دلار) | مجموع (ريال) | درصد از كل پروژه | بخش ريالي با اعمال سربار | بخش ارزي(دلار) با اعمال سربار | مجموع (ريال با اعمال سربار) | درصد از كل پروژه
E | مهندسي | 1148738203798 |  | 1148738203798 | 0.020546 | 1720717288953 |  | 1720717288953 | 0.020546
P | كالا | 20057906473315 | 30009013 | 36890083542856 | 0.69876 | 35447286264205 | 30009013 | 43212047838909 | 0.69876
C | اجرا | 11355183168297 |  | 11355183168297 | 0.2708 | 10513407318072 |  | 10513407318072 | 0.2708
Development | توسعه فناوري | 302936703055 |  | 302936703055 | 0.0099011 | 488003914050 |  | 488003914050 | 0.0099011
| جمع | 39942029203771 | 30009013 | 65478773284888 | 1 | 57002959939762 | 30009013 | 69631720910718 | 1
| FR(EPC Initial Capex) | ریال | ارز - دلار | مجموع (ريال + ارز تسعير شده) |  | Adjustment | Over Work | Elevated Price | 89205005
0.0214 | مهندسي -E | 825658738764 |  | 825658738764 |  | 316851629326 | 382543783293 | 2075013518378 | 52395538927
0.69815 | کالا- P | 35447286264205 | 30009013 | 43212047838909 |  | 15552458072105 | 6373157036633 | 35715336407960 | Expenditure
0.27056 | اجرا- C | 10513407318072 |  | 10513407318072 |  | 7568032571872 | 5030659740397 | 35670506247948 | 126668568954
0.0098925 | توسعه - De | 488003914050 |  | 488003914050 |  | 170652475821 | 91526408240 |  | Request
58346572894095 | مجموع | 67742640583824 | 30009013 | 58346572894095 |  | 16661415586082 | 9076898839913 | 67954853841113 | 112986239185917
|  |  |  | Bpd_Cost_rate |  |  | 7057579 | 67954853841113 | 30623786
فناوري سخت | 551182035079 |  |  | 1333.5171 |  |  |  |  | Approved Finance
توسعه مديريت | 22047891381 | [7 empty] | 286740463305
سهم داخل | 22047891381 | RFCS | [6 empty] | 14724420
|  | 67742640583824 | [6 empty] | Finance Increment
|  | 20419403 | [6 empty] | 96690273724484
نيروگاه خورشيدي | 129734587058 | [7 empty] | 8304329
تصفيه پساب | 538194132171

## PEP
ردیف | شرح |  |  | ريال | یورو
1 | خدمات مهندسی | الف | بازنگری و تائید مهندسی مقدماتی | 34855813285 | 0
|  | ب | انجام خدمات مهندسی تفصیلی | 671194558707 | 0
|  | ج | مطالعات ارزیابی اثرات زیست محیطی، پيوست سلامت، هزاپ، ژئوتكنيك تكميلي، و نقشه برداري تكميلي | 38346608851 | 0
|  | د | مديريت مهندسي | 163454561547
|  |  | جمع خدمات مهندسی | 1042479218935 | 0
2 | 2-1 تهیه و تامین کالا و تجهیزات خارجی بر مبنای DAP (تحويل در محل پروژه) | الف | هزینه تهیه و تامین کالا و تجهیزات خارجی | 0 | 27984795
|  |  | هزینه تهیه و تامین قطعات یدکی برای دوران راه اندازی و 2 ساله تعمیر و نگهداری | 0 | 3208415
|  | ب | هزینه حمل خارجی | 0 | در آيتم الف از 1-2 در نظر گرفته شده است
|  | ج | هزینه بیمه کالا و تجهیزات خارجی |  | در آيتم الف از 1-2 و ج از 2-2 در نظر گرفته شده است
|  | د | هزینه ترخیص شامل عوارض گمرکی و سود بازرگانی کالا و تجهیزات خارجی | 1134224764444 | 0
|  | ه‍ | هزینه حمل داخلی کالا و تجهیزات خرید خارج و هزينه حمل كالاي داخلي | 602216012292 | 0
|  | و | هزینه خدمات فنی سازندگان در دوران نصب و راه اندازی | 815086857062 | 0
|  | ز | هزینه بازرسی کالا و تجهیزات خارجی | 280708718347 | 0
| 2-2 تهیه و تامین کالا و تجهیزات داخلی برمبنای تحويل در محل پروژه | الف | هزینه تهیه و تامین کالا و تجهیزات داخلی | 14466759773977 | 0
|  |  | هزینه تهیه و تامین قطعات یدکی برای دوران راه اندازی و 2 ساله تعمیر و نگهداری | 1621132687361 | 0
|  | ب | هزینه حمل داخلی | در آيتم ه از 1-2 در نظر گرفته شده است | 0
|  | ج | هزینه بیمه کالا و تجهیزات داخلی و هزينه هاي داخلي بيمه كالا و تجهيزات خريد خارج | 280708718347 | 0
|  | د | هزینه خدمات فنی سازندگان در دوران نصب و راه اندازی | در آيتم و از 1-2 در نظر گرفته شده است | 0
|  | ه‍ | هزینه بازرسی کالا و تجهیزات داخلی | در آيتم ز از 1-2 در نظر گرفته شده است | 0
|  |  | جمع خدمات تهیه و تامین کالا و تجهیزات | 24588340638708 | 18940867
3 | عملیات ساختمانی و اجرا | الف | تجهیز و برچیدن | 374049037854 | 0
|  | ب | ساخت و نصب و راه اندازی | 6843028160904 | 0
|  | ج | تسهیلات مورد نیاز کارفرما | 1289533114269 | 0
|  | د | الزامات HSE (مقررات ایمنی، بهداشت و محیط زیست شرکت ملی نفت ایران) | 133894045982 | 0
|  | ه‍ | ه: هزینه دفتر فنی کارگاه | 70230265512
|  |  | جمع خدمات ساختمانی | 14144788668806 | 0
4 | توسعه فناوريهاي سخت، توسعه قابليتهاي مديريتي و توسعه سهم داخل | الف | يك درصد از كل برآورد | 444153142068
|  |  | جمع کل پروژه ( ردیف های 5 ، 4 ، 3 ، 2 ، 1) | 36012472276287 | 18940867

## basic data
per Euro | 1.085 |  | Year | ME0 | ME | IN | EL | ME0 | ME | IN | EL | درصد تغيير شاخص قيمت توليد كننده در بخش صنعت - طبق آمار منتشر شده در بهمن ماه 1401 در مركز آمار ايران | Year | Ind. PPI | Ind. PPI Variation | 1395=100
per $ | 393219 | ريال | 94 | -12.6 | -0.62 | -2.3 | -1.6 | 0.874 | 0.9938 | 0.977 | 0.984 | ME0: ساخت فلزات پايه | 1395 |  | 4.7
overhead factor (E,G,D) | 1.2713 |  | 95 | 1.9 | 3.4 | 2.7 | 2 | 1.019 | 1.034 | 1.027 | 1.02 | ME: ساخت محصولات فلزي ساخته شده به جز ماشين آلات و تجهيزات | 1396 |  | 13.3
overhead factor (P) | 1.2713 |  | 96 | 31.8 | 6.7 | 0.8 | 11.5 | 1.318 | 1.067 | 1.008 | 1.115 | IN: ساخت محصولات رايانه اي، الكترونيكي و نوري | 1397 |  | 58.6
overhead factor (C) | 1.2713 |  | 97 | 67.9 | 66.7 | 58.8 | 68.1 | 1.679 | 1.667 | 1.588 | 1.681 | EL: ساخت تجهيزات برقي | 1398 | 246.2 | 37.1
سال مبنا | تورم ريالي | تورم ارزي | 98 | 32.7 | 49.2 | 43.1 | 43 | 1.327 | 1.492 | 1.431 | 1.43 |  | 1399 | 386.1 | 56.8
1392 | 0.373 | 0.02 | 99 | 105.6 | 62.9 | 37.3 | 71 | 2.056 | 1.629 | 1.373 | 1.71 |  | 1400 | 605 | 56.7
1393 | 0.156 | 0.02 | 1400 | 54.9 | 53.4 | 37.6 | 46.9 | 1.549 | 1.534 | 1.376 | 1.469 |  | 99.2 | 355.6 | 23.9
1394 | 0.119 | 0.02 | 1400.2 | 98.2 | 71.5 | 53.3 | 79.3 | 1 | 1 | 1 | 1 |  | 99.3 | 433.1 | 37.4
1395 | 0.09 | 0.02 | 1400.3 | 72.3 | 61.9 | 45 | 60.9 | 1 | 1 | 1 | 1 |  | 99.4 | 485.8 | 56.8
1396 | 0.096 | 0.02 | 1400.4 | 54.9 | 53.4 | 37.6 | 46.9 | 1 | 1 | 1 | 1 |  | 1400.1 | 525.6 | 78.5
1397 | 0.312 | 0.02 | 1401.1 | 36.5 | 46 | 27.3 | 38.2 | 1.365 | 1.46 | 1.273 | 1.382 |  | 1400.2 | 577 | 80.4
1398 | 0.412 | 0.02 | 1401.2 | 21.6 | 41.6 | 21.2 | 35.4 | 1 | 1 | 1 | 1 |  | 1400.3 | 633.9 | 69.7
1399 | 0.471 | 0.012 | [5 empty] | 11.3692 | 9.9492 | 5.5276 | 9.339 | ضريب تغيير قيمت نسبت به سال مبنا (1395) | 1400.4 | 683.6 | 56.7
1400 | 0.462 | 0.047 | [10 empty] | 1401.1 | 768.9 | 48
1401 | 0.465 | 0.08 | [10 empty] | 1401.2 | 750.9 | 40.4
1402 | 0.5 | 0.04
| 18.576 | 1.3671

## Procurement
جدول 2.1 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي مکانیک و لوله و اتصالات مورد نياز پروژه بر اساس پیوست 1،2 و3 |  |  |  | ارز مرجع | 393219
رديف | شرح فعاليت ها | دلار | ريال | ضريب تورم عمومي ريالي | 18.576
1 | الكترواستاتيك ها و ادوات مربوطه | 10152685 | 0 | ضريب تورم ارزي دلار | 1.3671
2 | كوره ها و ادوات مربوطه | 4663098 | 0
3 | مبدل نفت / نفت و مبدل آب / آب | 0 | 508645912183
4 | تلمبه ها | 0 | 2494635482223
5 | شيرآلات و اتصالات ، رنگها و لوله های داخل سایت | 0 | 3243807684789
6 | خرید لوله های بیرون سایت | 0 | 2477897909125
7 | مخزن های اتمسفریک و تحت فشار | 0 | 492572895140
8 | سیستم پساب | 5125048 | 0
9 | air compressor Packages | 0 | 536273046912
10 | Flare & Ignitor | 0 | 491830659036
| بسته های تزریق مواد شیمیایی | 0 | 232942541372
12 | Vacuum Deaerator Package | 0 | 174968753515
13 | سیستم HVAC | 0 | 511942420507
14 | جرثقیلهای سقفی | 0 | 273200054599
15 | خرید اقلام ایمنی و آتش نشانی | 0 | 104966724045
16 | گیرنده و فرستنده توپک | 0 | 92437172040
17 | مواد شیمیایی مصرفی | 0 | 740415223179
| جمع كل | 12750596 | 7462351092867

## P.ME
ITEM | TAG. NO. |  | SERVICE | SPECIFICATION | UNIT | Quantity | هزینه واحد بدون ضریب |  |  | هزینه کل بدون ضریب
[7 empty] | خرید |  |  | خرید |  | ترخیص | حمل
[7 empty] | Rls | Dollar | Euro | Rls | Euro | Rls
1 | DE | -001-A/B | 1at TRAIN DESALTER | 536 m3/hr , 19.5 bar D.P. T/T=18000 mm , ID=5300 mm | SET | 1 |  |  | 2823626 |  | 2823626 | 214189659684 | 4436260201
2 | DE | -002-A/B | 2nd TRAIN DESALTER | 537 m3/hr , 19.5 bar D.P. T/T=18000 mm , ID=5300 mm | SET | 1 |  |  | 2823626 |  | 2823626 | 214189659684 | 4436260201
3 | E | -001-A/B | SALTY CRUDE / DESALTED CRUDE HEAT EXCHANGER | COLD = 527 m³/h, HOT = 421 m³/h , D.P.=19.5barg, 5275 kw | No. | 2 | 363348092985 |  | 0 | 384253410187 | 0 | 0 | 2964498483
4 | E | -002-A/B | WATER / WATER HEAT EXCHANGER | COLD = 21 m³/h, HOT = 136.5 m³/h , D.P.=19.5barg, 1250 kw | No. | 2 | 8189489299 |  | 0 | 30355601271 | 0 | 0 | 1100642431
5 | H | -001-A1/A2 | CRUDE OIL INDIRECT FIRED HEATER | 245.4 m³/h (each) , D.P.=19.5barg 7155 kw | No. | 2 |  |  | 2089832 |  | 3981891 | 86050183905 | 4436260201
6 | H | -001-B1/B2 | CRUDE OIL INDIRECT FIRED HEATER | 245.4 m³/h (each) , D.P.=19.5barg 7155 kw | No. | 2 |  |  | 2089832 |  | 3981891 | 86050183905 | 4436260201
7 | TK | -003 | OFF-SPEC TANK | 7363 m³,H=15000mm.D=25000mm | Kg | 142134 | 530386 |  |  | 90340713883 |  |  | 2633972470
8 | P | -001-A/B | MAIN TRANSFER PUMPS | 500m3/hr, 15.2 bar, 216.3 kw | No. | 2 | 150436748608 |  | 0 | 390095441611 | 0 | 0 | 2773543697
9 | P | -002-A/B | AUXILLIARY TRANSFER PUMPS | 250m3/hr, 15.2 bar, 108.1 kw | No. | 2 | 72089205351 |  | 0 | 157260661232 | 0 | 0 | 2773543697
10 | P | -003-A/B | OFF-SPEC PUMPS | 100 m3/hr , 15.5 bar,44.2 kw | No. | 2 | 42048791743 |  | 0 | 167769172093 | 0 | 0 | 2773543697
11 | P | -005-A/B | DEGASSING WATER PUMPS | 30m3/hr, 3bar, 2.7 kw | No. | 2 | 19192788063 |  | 0 | 21004899388 | 0 | 0 | 2773543697
12 | V | -001-A/B | FREE WATER K.O DRUM | 340 m³, L=21250mm, ID=4250mm | Kg | 305647 | 1225516 |  |  | 246329473078 |  |  | 85562096
13 | TK | -101 | DILUTION WATER TANK | 1472 m³,H=12000mm, ID=12500mm | Kg | 75997 | 530386 |  |  | 41224119728 |  |  | 1321638459
14 | P | -103 | DILUTION WATER PUMPS | 40m3/hr , 10.4 bar, 12 kw | No. | 1 | 16533883040 |  | 0 | 16533883040 | 0 | 0 | 2204077501
15 | P | -106-A1/A2 | DILUTION WATER PUMPS | 20 m3/hr, 10.4 bar, 6 kw | No. | 2 | 14736900931 |  | 0 | 28807064335 | 0 | 0 | 2204077501
16 | PK | -101 | VACUUM DEAERATOR PACKAGE | 41 m³/h | No. | 1 | 174968753515 |  | 0 | 174968753515 | 0 | 0 | 308991054
17 | P | -102-A/B | DEAERATED WATER PUMPS | 20m3/hr, 2.4 bar, 1.35 kw | No. | 2 | 7367999377 |  | 0 | 13856186213 | 0 | 0 | 2204077501
18 | P | -105 | DEAERATED WATER PUMPS | 40m3/hr, 2.4 bar, 2.7 kw | No. | 1 | 6910171822 |  | 0 | 6910171822 | 0 | 0 | 2204077501
19 | TK | -102 | POTABLE WATER TANK | 32.6 m³,H=2600mm, D=4000mm | Kg | 16620 | 530386 |  |  | 18150667293 |  |  | 308991054
20 | P | -104 | POTABLE WATER FILLING PUMP | 20m3/hr, 2.5 bar, 1.4 kw | No. | 1 | 6483446849 |  | 0 | 6483446849 | 0 | 0 | 2204077501
21 | P | -201-A/B/C | WATER INJECTION MAIN PUMPS | 73m3/hr (each),36.3 bar, 73.6 kw | No. | 3 | 176769586356 |  | 0 | 660173385528 | 0 | 0 | 2773543697
22 | P | -206-A/B/C | WATER INJECTION BOOSTER PUMPS | 36.5m3/hr (each),36.3 bar, 36.5 kw | No. | 3 | 123693742350 |  | 0 | 450681034846 | 0 | 0 | 2773543697
23 | OS | -201 | OIL SKIMMER TANK | 392.5 m³,H=5000mm, D=10000mm | Kg | 40625 | 530386 |  |  | 31224404086 |  |  | 1558429746
24 | PK | -201-A/B | IGF PACKAGE | 18105 SBPD (each) | SET | 1 |  |  | 3551860 |  | 3551860 | 121851525406 | 4436260201
25 | PK | -202 | NUTSHELL FILTER PACKAGE | 36100 SBPD | SET | 1 |  |  | 1077590 |  | 1077590 | 42048791743 | 4436260201
26 | TK | -201 | DISPOSAL TANK | 942 m³,H=12000mm,D=10000mm | Kg | 39559 | 530386 |  |  | 35041294556 |  |  | 2122665422
27 | V | -301 | FUEL GAS K.O. DRUM | 1.5 m³ , T/T=2810 mm, D=860 mm | Kg | 1000 | 2111973 |  |  | 2968249503 |  |  | 85562096
28 | V | -401 | AIR RECIEVER | 30 m³, T/T=7000mm, ID=2335mm | Kg | 8140 | 762977 |  |  | 7568028429 |  |  | 85562096
29 | PK | -401-A/B | AIR COMPRESSOR PACKAGE | 553 N m³/h, 10barg | No. | 2 | 154627286732 |  | 0 | 152151580125 | 0 |  | 4436260201
30 | PK | -402 | AIR DRYER PACKAGE | 453 N m³/h | No. | 1 | 5676890635 |  | 0 | 5676890635 | 0 |  | 4436260201
31 | PK | -002-A/B | AIR COMPRESSOR PACKAGE | 300 N m³/h, 10barg | No. | 2 | 123409872698 |  | 0 | 189150877635 | 0 |  | 4436260201
32 | PK | -003 | AIR DRYER PACKAGE | 525 N m³/h | No. | 1 | 2829621352 |  | 0 | 2829621352 | 0 |  | 4436260201
33 | P | -501-A/B/C | CHEMICAL INJECTION PORTABLE PUMPS | .8m³/h, 2bar, 0.45 kw | No. | 3 | 3787165926 |  | 0 | 10899544261 | 0 | 0 | 2204077501
34 | PK | -501 | DEMULSIFIER INJECTION PACKAGE | 10-20 LIT/HR Injection Pressure = 5 barg | No. | 1 | 38330117771 |  | 0 | 38330117771 | 0 |  | 85562096
35 | PK | -502-A/B | DEMULSIFIER INJECTION PACKAGE | 10-20 LIT/HR Injection Pressure = 15 bar | No. | 2 | 39685809784 |  | 0 | 69302779250 | 0 |  | 85562096
36 | PK | -503 | OXYGEN SCAVENGER INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 4.5 bar | No. | 1 | 42943850358 |  | 0 | 42943850358 | 0 |  | 85562096
37 | PK | -504 | CORROSION INHIBITOR INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 3 bar | No. | 1 | 38330117771 |  | 0 | 38330117771 | 0 |  | 85562096
38 | PK | -505 | REVERSE DEMULSIFIER INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 3 bar | No. | 1 | 38330117771 |  | 0 | 38330117771 | 0 |  | 85562096
39 | PK | -506-A | BIOCIDE INJECTION PACKAGE (TYPE A) | 20-70 LIT/HR Injection Pressure = 3 bar | No. | 1 | 23425473998 |  | 0 | 23425473998 | 0 |  | 85562096
40 | PK | -506-B | BIOCIDE INJECTION PACKAGE (TYPE B) | 20-70 LIT/HR Injection Pressure = 3 bar | No. | 1 | 43597164993 |  | 0 | 43597164993 | 0 |  | 85562096
41 | PK | -507 | ANTI SCALE INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 9 bar | No. | 1 | 43597164993 |  | 0 | 43597164993 | 0 |  | 85562096
42 | V | -601 | FLARE K.O. DRUM | 17.0 m³, T/T=7400 mm, ID=1600 mm | Kg | 6100 | 2111973 |  |  | 15980844496 |  |  | 85562096
43 | P | -601-A/B | FLARE K.O DRUM LIQUID PUMPS | 15m3/hr, 0.8 bar, 0.33 kw | No. | 2 | 14672969953 |  | 0 | 23383371606 | 0 | 0 | 2204077501
44 | PK | -602 | FLARE PACKAGE |  | No. | 1 | 229966487766 |  | 0 | 229966487766 | 0 |  | 85562096
45 | PK | -603 | COLD FLARE PACKAGE |  | No. | 1 | 65419741079 |  |  | 65419741079 |  |  | 85562096
46 | PK | -701 | BURN PIT IGNITION PACKAGE |  | No. | 1 |  |  | 0 |  | ردیف 44 |  | 85562096
47 | P | -701-A/B | HC CLOSED DRAIN TRANSFER PUMPS | 27.5m3/hr, 4.3 bar, 3.3 kw | No. | 2 | 32892372161 |  | 0 | 41080860040 | 0 | 0 | 2204077501
48 | P | -702A/B | HC CLOSED DRAIN DRUM SUMP PUMP | 5.5m3/hr, 7 bar. 0.11 kw | No. | 2 | 32892372161 |  | 0 | 41080860040 | 0 | 0 | 2204077501
49 | V | -701 | HC CLOSED DRAIN DRUM | 96.2 m³,T/T=10000 mm ID=3500 mm | Kg | 34097 | 3090411 |  |  | 64772674364 |  |  | 85562096
50 | P | -703-A/B | CLEAN WATER PUMPS | 11m3/hr, 1.8 bar, 0.54 kw | No. | 2 | 8189489299 |  | 0 | 30355601271 | 0 | 0 | 2204077501
51 | P | -704-A/B | RECOVERED WASTE OIL PUMPS | 11 m3/hr, 2.7 bar, 0.8 kw | No. | 2 | 17460888925 |  | 0 | 25352009756 | 0 | 0 | 2204077501
52 | P | -750 | OILY WATER SEPARATOR PUMP | 1m3/hr, 0.84 bar, 0.02kw | No. | 1 | 6263191680 |  | 0 | 6263191680 | 0 | 0 | 2204077501
53 | TK | -701 | DIRTY OILTANK | 21 m³,T/T=3000 mm, ID=3000 mm | Kg | 3600 | 530386 |  |  | 1532078218 |  |  | 85562096
54 | P | -705-A/B | DIRTY OIL PUMPS | 5m3/hr, 2bar, 0.3 kw | No. | 2 | 12456615012 |  | 0 | 36391728440 | 0 | 0 | 2204077501
55 | P | -706-A/B | RECOVERED WASTE WATER PUMPS | 33m3/hr, 1.5 bar, 1.35 kw | No. | 2 | 14672969953 |  | 0 | 23383371606 | 0 | 0 | 452499608
56 | V | -801 | DIESEL STORAGE TANK | 14.9 m³, T/T=4750mm ID=2000mm | Kg | 6100 | 530386 |  |  | 3331087949 |  |  | 85562096
57 | P | -801 | DIESEL OIL PUMP | 10m3/hr, 0.6 bar, 0.16 kw | No. | 1 | 6062783279 |  | 0 | 6062783279 | 0 | 0 | 2204077501
58 | P | -901A/B | FIRE WATER MAIN ELECTRICAL PUMP | 480m3/hr, 10 barg,133kw | No. | 2 | 36134010770 |  |  | 78213005853 |  |  | 155400299
59 | P | 902 | FIRE WATER MAIN DESEL PUMP | 480m3/hr, 10 barg,133kw | No. | 1 | 46483438699 |  |  | 46483438699 |  |  | 452499608
60 | P | -903-A/B | FIRE WATER JOCKEY PUMPS | 15m3/hr, 6 barg, 2.5 kw | No. | 2 | 2358123753 |  |  | 4211951555 |  |  | 151466801
60 | P | 108A/B | UNIT SUPPLY WATER PUMP | 15m3/hr, 6 barg, 2.5 kw | No. | 2 | 10521574010 |  | 0 | 17460888925 | 0 |  | 151466801
61 | TK | -901 | DISEL FUEL DAILY TANK | 2 m³ | Kg | 300 | 530386 |  |  | 146788743 |  |  | 2633972470
62 | TK | -902-A/B | FIRE WATER STORAGE TANK |  | Kg | 98646 | 530386 |  |  | 97347141564 |  |  | 85562096
63 | TK | -104 | SUPPLY WATER STORAGE TANK | 1717.2 m³, T/T=14000mm, ID=12500mm | Kg | 20889 | 530386 |  |  | 17735412625 |  |  | 85562096
64 | P | -904 | FIRE WATER LOADING PUMP | 30m3/hr, 3 bar, 2.5 kw | No. | 1 | 10218391469 |  | 0 | 10218391469 | 0 |  | 151466801
65 |  |  | CRANES | [6 empty] | طبق لیست زیر |  |  | 1558429746
65.1 | CR | 001 | AIR COMPRESSOR ROOM CRANE |  | No. | 1 | 18939429436 |  |  | 18939429436
65.2 | CR | 002 | CHEMICAL STORAGE SHELTER CRANE (ex) |  | No. | 1 | 44564946839 |  |  | 44564946839
65.3 | CR | 003 | CHEMICAL STORAGE SHELTER CRANE (ex) |  | No. | 1 | 44564946839 |  |  | 44564946839
65.4 | CR | 004 | CHEMICAL INJECTION PACKAGE SHELTER CRANE (ex) |  | No. | 1 | 24710948304 |  |  | 24710948304
65.5 | CR | 005 | CHEMICAL INJECTION PACKAGE SHELTER CRANE (ex) |  | No. | 1 | 24710948304 |  |  | 24710948304
65.6 | CR | 006 | WORK SHOP CRANE |  | No. | 1 | 18939429436 |  |  | 18939429436
65.7 | CR | 007 | PUMP SHELTER CRANE (ex) |  | No. | 1 | 24710948304 |  |  | 24710948304
65.8 | CR | 008 | FIRE WATER SHELTER CRANE |  | No. | 1 | 16417118056 |  |  | 16417118056
65.9 | CR | 009 | PROCESS PUMP SHELTER CRANE (ex) |  | No. | 1 | 60217002259 |  |  | 60217002259
65.10 | CR | 010 | DILUTION WATER PUMP SHELTER CRANE |  | No. | 1 | 16859965894 |  |  | 16859965894
65.11 | CR | 011 | DEARATOR WATER PUMP SHELTER CRANE |  | No. | 1 | 16859965894 |  |  | 16859965894
65.12 | CR | 012 | PU4 COMPRESSOR STATION CRANE |  | No. | 1 | 57512199921 |  |  | 57512199921
65.13 | CR | 013 | CHEMICAL STORAGE SHELTER CRANE(ex) |  | No. | 1 | 34059235213 |  |  | 34059235213
66 |  |  | HVAC | [6 empty] | طبق لیست زیر |  |  | 1321638459
66.1 |  |  | HVAC FOR ACCOMMODATION |  | SET | 1 | 1518677236 |  |  | 1518677236
66.2 |  |  | HVAC FOR DE4 SWITCHGERA ROOM |  | SET | 1 | 117450892713 |  |  | 117450892713
66.3 |  |  | HVAC FOR DE4 CONTROL ROOM |  | SET | 1 | 118461069946 |  |  | 118461069946
66.4 |  |  | HVAC FOR 33 KV STATION |  | SET | 1 | 106571104561 |  |  | 106571104561
66.5 |  |  | HVAC FOR 33/3.45 STATION |  | SET | 1 | 2387517586 |  |  | 2387517586
66.6 |  |  | HVAC FOR GUARD HOUSE |  | SET | 1 | 1518677236 |  |  | 1518677236
66.7 |  |  | HVAC FOR LABORATORY |  | SET | 1 | 3422602226 |  |  | 3422602226
66.8 |  |  | HVAC BULK |  | No. | 1 | 4168497024 |  |  | 4168497024 |  |  | 839755096
66.9 |  |  | Waste water treatment package |  | SET | 1 | 4493011461 |  |  | 4493011461 |  |  | 85562096
66.10 |  |  | Water treatment package |  | SET | 1 | 2353403858 |  |  | 2353403858 |  |  | 85562096
67 |  |  | SAFETY EQUIPMENT | طبق لیست زیر | No. |  |  |  |  | طبق لیست زیر
67.1 |  |  | WATER HYDRANT | 6" | No. | 13 | 515823531 |  |  | 4018827635
67.2 |  |  | WATER HYDRANT WITH MONITOR | 6" | No. | 27 | 805119134 |  |  | 15798478004
67.3 |  |  | DELUGE VALVE | 4" | No. | 2 | 6527315146 |  |  | 14976381668
67.4 |  |  | DRY POWDER PORTABLE FIRE EXTINGUISHER | 12 KG | No. | 32 | 46100720 |  |  | 1538168723
67.5 |  |  | DRY POWDER WHELEED FIRE EXTINGUISHER | 75 KG | No. | 12 | 323916475 |  |  | 5047171174
67.6 |  |  | CO2 PORTABLE FIRE EXTINGUISHER | 5 KG | No. | 42 | 37522309 |  |  | 2045423305
67.7 |  |  | CO2 WHEELD FIRE EXTINGUISHER | 30 KG | No. | 24 | 342821165 |  |  | 7754292285
67.8 |  |  | SAFETY SHOWER & EYE WASH | - | No. | 7 | 1068612681 |  |  | 5623670648
67.9 |  |  | FIRST AID KIT | - | No. | 4 | 103736041 |  |  | 721952057
67.11 |  |  | OS&Y GATE VALVE-ISOLATING VALVE, 12" |  | No. | 2 | 1952731692 |  |  | 4344365045
67.12 |  |  | OS&Y GATE VALVE-ISOLATING VALVE, 6" |  | No. | 19 | 719699583 |  |  | 11572146233
67.13 |  |  | 9 LIT WATER EXTINGUISHER | - | No. | 8 | 37522309 |  |  | 374871601
67.14 |  |  | EMERGANCY BREATHING APPARATUS WITH MASK |  | No. | 2 | 480783912 |  |  | 1172276581
67.15 |  |  | FIRE MAN CABINET |  | No. | 2 | 5699407176 |  |  | 14047815817
67.16 |  |  | FIRE SHED EQUIPMENT. 100 lit foam drums, 3% FP (5 NOS.), Fire Hose, 25 m (10 NOS.) Foam Nozzle 10X (2 NOS.) Water Nozzle, 450 lpm (Fog/Jet/Stop) (5 NOS.)) 12 kg portable powder fire extinguisher (6 NOS.) 75 kg Wheeled powder fire extinguisher (2 NOS.) 5 kg portable CO2 fire extinguisher (2 NOS.) In Line Inductor, 450 lpm with pick up tube (2 NOS.) Drum Wrench (1 NO.) Hose Bridge (1 NO.) | - | No. | 10 | 6527315146 |  |  | 42247721222
67.17 |  |  | WATER SPRAY SYSTEM |  | No. | 40 | 5287618 |  |  | 141200346
67.18 |  |  | SAFETY SIGN |  | No. | 200 | 2147504 |  |  | 446276395
67.19 |  |  | Bulks OS&Y GATE VALVE-ISOLATING VALVE;OS&Y GATE VALVE-ISOLATING VALVE; WIND SOCK; HOSE REEL; EMERGENCY EQUIPMENT BOX;EMERGENCY BREATING APPARATUS WITH MASK; FIRE MAN CABINET;STRETCHER; FIRE DOSE SYSTEM;WATER SPRAY SYSTEM;SAFETY SIGN;AXE;RECHARGEABLE FLASHLIGHT (EXPLOSION PROOF);EMERGENCY BREATHING APPARATUS WITH AIR MASTER;BREATHING RECOVERY DEVICE |  | a lot | 1 | 4949173166 |  |  | 4949173166 |  |  | 1321638459
68 |  |  | Pig Launcher & Receiver |  | SET | 1 | 92437172040 |  |  | 92437172040 |  |  | 233993633
69 |  |  | CLEANING IN PLATE FOR EXCHANGER |  | SET | 2 | 38014590580 |  |  | 40603966363 |  |  | 233993633

## P.EL
ITEM | DESCRIPTION | QUANTITY |  | هزینه واحد بدون ضریب |  |  | هزینه کل بدون ضریب
|  | QTY | UNIT | خرید |  |  | خرید |  | حمل
|  |  |  | Rls | Euro | Dollar | Rls | Euro | Rls
1 | SWITCHGEAR
1.1 | MV Switchgear, 33KV, 630A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 15 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010/Location:33KV station/DWG no. EL-SLD-21028 | 1 | SET | 165643524253 |  |  | 165643524253 | 0 | 947616999
1.2 | MV Switchgear, 3.3KV, 1250A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 9 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010. /Location: DE4 Outdoor station/ DWG no. M9003-EB-EL-SLD-21026 : OUT-SWG-01 | 1 | SET | 112232664212 |  |  | 112232664212 | 0 | یک قلم در ردیف 1.1
1.3 | MV Switchgear, 3.3KV, 630A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 12 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010./Location:DE4/ DWG no. M9003-EB-EL-SLD-21026 : DE4-SWG-01 | 1 | SET | 126188380302 |  |  | 126188380302 | 0 | یک قلم در ردیف 1.1
1.4 | LV Switchgear, 400V, 4000A, 3 phase + N+E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 50KA, 1Sec., in accordance with attached Specification No.: M9003-EB-EL-SPC-21008./Location: DE4 / / DWG no. M9003-EB-EL-SLD-21025 : (DE-MCC-001 | 1 | SET | 103881576111 |  |  | 103881576111 | 0 | یک قلم در ردیف 1.1
1.5 | 33 KV transformer bay, withdrawable, outdoor type with OCB and all protection and metering devises in accordance to Dwg no. M9003-EB-EL-SLD-21026 | 2 | SET | 43872736649 |  |  | 155366873143 | 0 | یک قلم در ردیف 1.1
1.6 | MV Switchgear, 3.3KV, 630A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 9 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010./Location:Production uni/ DWG no. M9003-EB-EL-SLD-21026 : PU4-SWG-01 | 1 | SET | 112232664212 |  |  | 112232664212 | 0 | یک قلم در ردیف 1
1.7 | SAMPLE 4-DESALTING UNIT EDP,400V SWITCHGEAR (EDP) / DWG no. M9003-EB-EL-SLD-21024 | 2 | SET | 14700142257 |  |  | 32921695228 | 0 | یک قلم در ردیف 2
1.8 | Capacitor Bank Set 400/230 V AC, 50Hz, 3Phase, 3-wires + N + PE , 425KVAR with min 5 Steps Regulator (50KVAR fixed step+375KVAR as variable steps), rapid discharge on contactor, free standing type, supplying from L V Switchgear, for indoor use, IP42. | 2 |  | 11526483683 |  |  | 11942945926 | 0
2 | TRANSFORMERS
2.1 | TR1 : Power Transformer 2500 KVA, 3.3 / 0.42 Kv 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral solidly earthed Complete with accessories. | 1 | SET | 20110296326 |  |  | 20110296326 |  | 244723206
2.2 | TR2 : Power Transformer 2500 KVA, 3.3 / 0.42 kV 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase, 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral solidly earthed Complete with accessories. | 1 | SET | 20110296326 |  |  | 20110296326 |  | 244723206
2.3 | PTR1 : Power Transformer6000 KVA, 33 / 3.45kV 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase, 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral earthed with NGR. | 1 | SET | 74686671845 |  |  | 74686671845 |  | 244723206
2.4 | PTR2 : Power Transformer 6000 KVA, 33 / 3.45kV 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase, 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral earthed with NGR. | 1 | SET | 74686671845 |  |  | 74686671845 |  | 244723206
3 | DIESEL GENERATOR EDG-1
3.1 | DIESEL GENERATOR EDG-1 0.4 kv, 550kva, 50Hz, 1500rpm | 1 |  | 33913151515 |  |  | 33913151515 |  | 666301589
3.2 | emergency diesel generator, 0.4 kv, 180KVA, 50Hz, 1500rpm,with automatic control panel | 1 |  | 10748873937 |  |  | 10748873937 |  | یک قلم در ردیف فوق

## P.IN
ITEM | DESCRIPTION | QUANTITY |  |  | هزینه واحد بدون ضریب |  | هزینه کل بدون ضریب
[5 empty] | خرید |  | خرید
|  | UNIT | QTY | Dollar | Rls | Euro | Rls | Euro
1 | ANALYZER
1.1 | BS&W ANALYZER TRANSMITTER / ELEMENT | NO. | 3 |  |  | 52603 |  | 146751
1.2 | DISSOLVED OXYGEN ANALYZER | NO. | 1 |  | 30999170005 | 0 | 30999170005 | 0
2 | CORROSION INSTRUMENTS
2.1 | CORROSION COUPON | NO. | 28 |  | 275011347 | 0 | 15498969486 | 0
2.2 | CORROSION PROBE | NO. | 15 |  | 2307549736 | 0 | 35356022076 | 0
2.3 | Local DATA LOGGER | NO. | 15 |  | 878130399 | 0 | 13424325434 | 0
2.4 | RETRIVER AND SERVICE VALVE and Handheld Data Logger + REQUIRED SOFTWARE | NO. | 1 |  | 41057708593 | 0 | 41057708593 | 0
3 | FLOW TRANSMITTER (DIFF. PRESSURE TYPE) WITH 5-VALVE MANIFOLD | NO. | 37 |  | 887145729 | 0 | 35429400194 | 0
4 | FLOW SWITCH (DIFF. PRESSURE SWITCH TYPE) WITH 5-VALVE MANIFOLD | NO. | 10 |  | 1044092139 | 0 | 8628038530 | 0
5 | FLOW GAGE (ROTAMETER) | NO. | 23 |  | 1282886455 | 0 | 20658559595 | 0
6 | ORIFICE PLATE WITH FLANGES | NO. | 37 |  | 442323480 | 0 | 18923236393 | 0

## P.PI
NO | ITEM | AREA | DESCRIPTION | [6 empty] | MATERIAL |  | هزینه واحد بدون ضریب | هزینه کل بدون ضریب
|  |  | TYPE | BORE 1 | BORE 2 | UNIT | QTY | CLASS | S.CH./thK | MATERIAL | MATERIAL REMARK |  | خرید | حمل و جنبي
[12 empty] | Euro | Euro | Rls
1 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 5/8" | 85 | No | 12 | AX01 | For flange:2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 14.5673 | 3041761
2 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 5/8" | 90 | No | 100 | AX01 | For flange:3"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 121.3943 | 29066957
3 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 5/8" | 90 | No | 256 | AX01 | For flange:4"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 310.7695 | 44578864
4 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 3/4" | 105 | No | 320 | AX01 | For flange:6"150# | A193 GR.B7/A194 GR.BH | GALVD | 2.0834 | 666.6846 | 125931128
5 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 3/4" | 110 | No | 64 | AX01 | For flange:8"150# | A193 GR.B7/A194 GR.BH | GALVD | 2.0834 | 133.3369 | 20471892
6 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 7/8" | 115 | No | 912 | AX01 | For flange:10"150# | A193 GR.B7/A194 GR.BH | GALVD | 3.1606 | 2882.4923 | 514709065
7 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 7/8" | 125 | No | 120 | AX01 | For flange:12"150# | A193 GR.B7/A194 GR.BH | GALVD | 3.3028 | 396.3361 | 83158346
8 | Fitting | Fire Water Lines(Non Metal) | 45deg.Elbow | 10 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 421.695 | 3373.5598 | 337149387
9 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 3 | - | No | 5 | AX01 | DR11 | HDPE 100 |  | 19.9043 | 99.5215 | 8159327
10 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 4 | - | No | 10 | AX01 | DR11 | HDPE 100 |  | 23.3766 | 233.7661 | 24925148
11 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 6 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 68.38 | 547.0401 | 84515395
12 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 8 | - | No | 6 | AX01 | DR11 | HDPE 100 |  | 187.8742 | 1127.2449 | 160275635
13 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 10 | - | No | 27 | AX01 | DR11 | HDPE 100 |  | 421.695 | 11964 | 1004118483
14 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 12 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 558.414 | 4467.3119 | 680945580
15 | Fitting | Fire Water Lines(Non Metal) | Pipe Nipple | 1 | - | No | 12 | AX01 | DR11 | HDPE 100 |  | 1.3671 | 16.4046 | 2217257
16 | Fitting | Fire Water Lines(Non Metal) | Reducer | 4 | 3 | No | 1 | AX01 | DR11 | HDPE 100 |  | 18.1545 | 18.1545 | 1493598
17 | Fitting | Fire Water Lines(Non Metal) | Reducer | 10 | 8 | No | 6 | AX01 | DR11 | HDPE 100 |  | 114.0806 | 684.4837 | 71116026
18 | Fitting | Fire Water Lines(Non Metal) | Olet | 3 | 1 | No | 3 | AX01 | DR11 | HDPE 100 |  | 36.0902 | 108.2706 | 13834470
19 | Fitting | Fire Water Lines(Non Metal) | Olet | 10 | 1 | No | 3 | AX01 | DR11 | HDPE 100 |  | 585.0989 | 1755.2966 | 265720074
20 | Fitting | Fire Water Lines(Non Metal) | Olet | 12 | 1 | No | 5 | AX01 | DR11 | HDPE 100 |  | 842.1049 | 4210.5246 | 624298209
21 | Fitting | Fire Water Lines(Non Metal) | Tee | 4 | 1 | No | 1 | AX01 | DR11 | HDPE 100 |  | 32.8913 | 32.8913 | 4448714
22 | Fitting | Fire Water Lines(Non Metal) | Tee | 4 | 4 | No | 5 | AX01 | DR11 | HDPE 100 |  | 32.8913 | 164.4565 | 24470141

## P.LAB
|  |  | هزینه واحد بدون ضریب |  | هزینه کل بدون ضریب
|  |  | خرید |  | خرید
| DESCRIPTION | Qty. | Rls | Euro | Rls | Euro
1 | Microwave Digestion System | 1 |  | 48403 |  | 48403
2 | Ion Meter | 1 |  | 24224 |  | 24224
3 | Oxygen Meter | 2 |  | 1722.4873 |  | 3444.9747
4 | Barometer | 2 |  | 3909.7728 |  | 7819.5457
5 | Oil Test Centrifuge | 2 |  | 37584 |  | 63130
6 | Dual Extraction Apparatus | 5 |  | 33215 |  | 106555
7 | Evaporator Mantless (500 cc) | 2 |  | 1640.4641 |  | 3280.9283
8 | Water Still For Douuble Distillation | 4 |  | 9159.258 |  | 44299
9 | Ph Meter | 2 |  | 3417.6336 |  | 6835.2672
10 | Balance | 2 |  | 8885.8473 |  | 14605
11 | R.V.P Automatic | 2 |  | 55567 |  | 107720
12 | Thermostatic Water Baths | 2 |  | 7382.0886 |  | 9342

## C.mECHANICAL
جدول 13 - برآورد اجراو نصب تجهیزات مکانیک بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | شماره تجهیز |  | شرح | ردیف |  |  | وزن واحد
[9 empty] | نصب دیسالترها و هیترها | 1
3949178670 | 2947971084 | 40027 | 13683 | کد 591111 ردیف 4 | 108555 | Kg | DE | -001-A/B | 1at TRAIN DESALTER | 1.1 |  |  | 90695
3949178670 | 2947971084 | 40027 | 13683 | کد 591111 ردیف 4 | 108555 | Kg | DE | -002-A/B | 2nd TRAIN DESALTER | 1.2 |  |  | 90695
5433051395 | 1209835918 | 54565853 | 17053448 | کد 591231 ردیف2 | 120 | TON | H | -001-A1/A2 | CRUDE OIL INDIRECT FIRED HEATER | 1.3 |  |  | 60
5433051395 | 1209835918 | 54565853 | 17053448 | کد 591231 ردیف 2 | 120 | TON | H | -001-B1/B2 | CRUDE OIL INDIRECT FIRED HEATER | 1.4 |  |  | 60
| 0 | [7 empty] | نصب مبدلهای حرارتی | 2 |  |  |  | منطقه ای نمونه. | 1.12
123595437 | 52536156 | 53497 | 19487 | کد 591111 ردیف 1 | 5000 | Kg | E | -001-A/B | SALTY CRUDE / DESALTED CRUDE HEAT EXCHANGER | 2.1 |  |  | 2500 | بالاسری | 1.48
219630285 | 62194380 | 53497 | 19487 | کد 591111 ردیف 1 | 4000 | Kg | E | -002-A/B | WATER / WATER HEAT EXCHANGER | 2.2 |  |  | 2000 | تجهیزکارگاه | 1
| 0 | [7 empty] | نصب پمپ ها | 3 |  |  |  | بروزرسانی | 1.515
460326687 | 193061837 | 71002 | 23209 | کد 591001 ردیف 04 | 8000 | Kg | P | -001-A/B | MAIN TRANSFER PUMPS | 3.1 |  |  | 4000
301226346 | 142355912 | 71002 | 23209 | کد 591001 ردیف 04 | 5600 | Kg | P | -002-A/B | AUXILLIARY TRANSFER PUMPS | 3.2 |  |  | 2800
225986937 | 142193775 | 96527 | 42286 | کد 591001 ردیف 03 | 3000 | Kg | P | -003-A/B | OFF-SPEC PUMPS | 3.3 |  |  | 1500
139681464 | 87651592 | 216633 | 72950 | کد 591001 ردیف 01 | 1000 | Kg | P | -005-A/B | DEGASSING WATER PUMPS | 3.4 |  |  | 500
95406274 | 44777617 | 158503 | 65583 | کد 591001 ردیف 02 | 1000 | Kg | P | -103 | DILUTION WATER PUMPS | 3.5 |  |  | 1000
190732388 | 63475553 | 158503 | 65583 | کد 591001 ردیف 02 | 1500 | Kg | P | -106-A1/A2 | DILUTION WATER PUMPS | 3.6 | ضریب | 2.511 | 750
108268389 | 39818605 | 216633 | 72950 | کد 591001 ردیف 01 | 500 | Kg | P | -601-A/B | FLARE K.O DRUM LIQUID PUMPS | 3.7 |  |  | 250

## E.Mechanic
Mechanical Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification, Criteria, Standard Drawing
1.1 | Mechanical Design Criteria |  |  |  | 10
1.2 | General Requirements for Welded Fabrication |  |  |  | 5
1.3 | Specification for Centrifugal Pumps for General Duty Services |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.4 | Specification for Centrifugal Pumps for Process Services |  |  |  | 8 | [6 empty] | 0.5 |  | 0.5
1.5 | Specification for Fire Water Pumps |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.6 | Specification for Indirect Fired Heaters |  |  |  | 8 | [6 empty] | 1 |  | 1
1.7 | Specification for Instrument Air Compressor Package |  |  |  | 8 | [6 empty] | 0.5 |  | 0.5
1.8 | Specification for Minimum Requirements for Packaged Equipment |  |  |  | 8
1.9 | Specification for Plate & Frame Heat Exchangers |  |  |  | 8 | [6 empty] | 0.5 |  | 0.5
1.10 | Specification for Pressure Vessels |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5