## عملكرد كلي
رديف | شرح | (هزار ريال)
(هزار دلار)
1 | هزينه هاي در تعهد كارفرما | 88895228
2 | هزينه انجام شده تاكنون طراحي و مهندسي | 54048717
3 | جمع هزينه شده | 94095222
4 | برآورد اعتبار بخش ريالي زير پروژه 002 | 53048195982
5 | برآورد اعتبار بخش ارزي زير پروژه 002 | 15771
6 | پیش بینی تعديل معادل 40 درصد برآورد بخش ريالي زيرپروژه 002 | 19648571858
7 | پيش بيني اضافه­كاري در سقف 25 درصد برآورد بخش ريالي زير پروژه 002 | 9147177302
8 | پيش بيني اضافه­كاري در سقف 25 درصد برآورد بخش ارزي زير پروژه 002 | 5848
9 | جمع كل درخواست بخش ريالي | 98653541717
10 | جمع كل درخواست بخش ارزي | 33208
11 | اعتبار مصوب بخش ريالي | 271361276
12 | اعتبار مصوب بخش ارزي | 22116
13 | مبلغ افزايش اعتبار بخش ريالي | 53646227585
14 | مبلغ افزايش اعتبار بخش ارزي | 14478

## EPC Summary
| برآورد هزينه هاي مستقيم |  |  |  |  | برآورد با اعمال بالاسري
بخش |  | بخش ريالي | بخش ارزي (دلار) | مجموع (ريال) | درصد از كل پروژه | بخش ريالي با اعمال سربار | بخش ارزي(دلار) با اعمال سربار | مجموع (ريال با اعمال سربار) | درصد از كل پروژه
E | مهندسي | 1148738203798 |  | 1148738203798 | 0.020546 | 1720717288953 |  | 1720717288953 | 0.020546
P | كالا | 20057906473315 | 30009013 | 36890083542856 | 0.69876 | 35447286264205 | 30009013 | 43212047838909 | 0.69876
C | اجرا | 11355183168297 |  | 11355183168297 | 0.2708 | 10513407318072 |  | 10513407318072 | 0.2708
Development | توسعه فناوري | 302936703055 |  | 302936703055 | 0.0099011 | 488003914050 |  | 488003914050 | 0.0099011
| جمع | 39942029203771 | 30009013 | 65478773284888 | 1 | 57002959939762 | 30009013 | 69631720910718 | 1
| FR(EPC Initial Capex) | ریال | ارز - دلار | مجموع (ريال + ارز تسعير شده) |  | Adjustment | Over Work | Elevated Price | 89205005
0.0214 | مهندسي -E | 825658738764 |  | 825658738764 |  | 316851629326 | 382543783293 | 2075013518378 | 52395538927
0.69815 | کالا- P | 35447286264205 | 30009013 | 43212047838909 |  | 15552458072105 | 6373157036633 | 35715336407960 | Expenditure
0.27056 | اجرا- C | 10513407318072 |  | 10513407318072 |  | 7568032571872 | 5030659740397 | 35670506247948 | 126668568954
0.0098925 | توسعه - De | 488003914050 |  | 488003914050 |  | 170652475821 | 91526408240 |  | Request
58346572894095 | مجموع | 67742640583824 | 30009013 | 58346572894095 |  | 16661415586082 | 9076898839913 | 67954853841113 | 112986239185917
|  |  |  | Bpd_Cost_rate |  |  | 7057579 | 67954853841113 | 30623786
فناوري سخت | 551182035079 |  |  | 1333.5171 |  |  |  |  | Approved Finance
توسعه مديريت | 22047891381 | [7 empty] | 286740463305
سهم داخل | 22047891381 | RFCS | [6 empty] | 14724420
|  | 67742640583824 | [6 empty] | Finance Increment
|  | 20419403 | [6 empty] | 96690273724484
نيروگاه خورشيدي | 129734587058 | [7 empty] | 8304329
تصفيه پساب | 538194132171

## PEP
ردیف | شرح |  |  | ريال | یورو
1 | خدمات مهندسی | الف | بازنگری و تائید مهندسی مقدماتی | 34855813285 | 0
|  | ب | انجام خدمات مهندسی تفصیلی | 671194558707 | 0
|  | ج | مطالعات ارزیابی اثرات زیست محیطی، پيوست سلامت، هزاپ، ژئوتكنيك تكميلي، و نقشه برداري تكميلي | 38346608851 | 0
|  | د | مديريت مهندسي | 163454561547
|  |  | جمع خدمات مهندسی | 1042479218935 | 0
2 | 2-1 تهیه و تامین کالا و تجهیزات خارجی بر مبنای DAP (تحويل در محل پروژه) | الف | هزینه تهیه و تامین کالا و تجهیزات خارجی | 0 | 27984795
|  |  | هزینه تهیه و تامین قطعات یدکی برای دوران راه اندازی و 2 ساله تعمیر و نگهداری | 0 | 3208415
|  | ب | هزینه حمل خارجی | 0 | در آيتم الف از 1-2 در نظر گرفته شده است
|  | ج | هزینه بیمه کالا و تجهیزات خارجی |  | در آيتم الف از 1-2 و ج از 2-2 در نظر گرفته شده است
|  | د | هزینه ترخیص شامل عوارض گمرکی و سود بازرگانی کالا و تجهیزات خارجی | 1134224764444 | 0
|  | ه‍ | هزینه حمل داخلی کالا و تجهیزات خرید خارج و هزينه حمل كالاي داخلي | 602216012292 | 0
|  | و | هزینه خدمات فنی سازندگان در دوران نصب و راه اندازی | 815086857062 | 0
|  | ز | هزینه بازرسی کالا و تجهیزات خارجی | 280708718347 | 0
| 2-2 تهیه و تامین کالا و تجهیزات داخلی برمبنای تحويل در محل پروژه | الف | هزینه تهیه و تامین کالا و تجهیزات داخلی | 14466759773977 | 0
|  |  | هزینه تهیه و تامین قطعات یدکی برای دوران راه اندازی و 2 ساله تعمیر و نگهداری | 1621132687361 | 0
|  | ب | هزینه حمل داخلی | در آيتم ه از 1-2 در نظر گرفته شده است | 0
|  | ج | هزینه بیمه کالا و تجهیزات داخلی و هزينه هاي داخلي بيمه كالا و تجهيزات خريد خارج | 280708718347 | 0
|  | د | هزینه خدمات فنی سازندگان در دوران نصب و راه اندازی | در آيتم و از 1-2 در نظر گرفته شده است | 0
|  | ه‍ | هزینه بازرسی کالا و تجهیزات داخلی | در آيتم ز از 1-2 در نظر گرفته شده است | 0
|  |  | جمع خدمات تهیه و تامین کالا و تجهیزات | 24588340638708 | 18940867
3 | عملیات ساختمانی و اجرا | الف | تجهیز و برچیدن | 374049037854 | 0
|  | ب | ساخت و نصب و راه اندازی | 6843028160904 | 0
|  | ج | تسهیلات مورد نیاز کارفرما | 1289533114269 | 0
|  | د | الزامات HSE (مقررات ایمنی، بهداشت و محیط زیست شرکت ملی نفت ایران) | 133894045982 | 0
|  | ه‍ | ه: هزینه دفتر فنی کارگاه | 70230265512
|  |  | جمع خدمات ساختمانی | 14144788668806 | 0
4 | توسعه فناوريهاي سخت، توسعه قابليتهاي مديريتي و توسعه سهم داخل | الف | يك درصد از كل برآورد | 444153142068
|  |  | جمع کل پروژه ( ردیف های 5 ، 4 ، 3 ، 2 ، 1) | 36012472276287 | 18940867

## basic data
per Euro | 1.085 |  | Year | ME0 | ME | IN | EL | ME0 | ME | IN | EL | درصد تغيير شاخص قيمت توليد كننده در بخش صنعت - طبق آمار منتشر شده در بهمن ماه 1401 در مركز آمار ايران | Year | Ind. PPI | Ind. PPI Variation | 1395=100
per $ | 393219 | ريال | 94 | -12.6 | -0.62 | -2.3 | -1.6 | 0.874 | 0.9938 | 0.977 | 0.984 | ME0: ساخت فلزات پايه | 1395 |  | 4.7
overhead factor (E,G,D) | 1.2713 |  | 95 | 1.9 | 3.4 | 2.7 | 2 | 1.019 | 1.034 | 1.027 | 1.02 | ME: ساخت محصولات فلزي ساخته شده به جز ماشين آلات و تجهيزات | 1396 |  | 13.3
overhead factor (P) | 1.2713 |  | 96 | 31.8 | 6.7 | 0.8 | 11.5 | 1.318 | 1.067 | 1.008 | 1.115 | IN: ساخت محصولات رايانه اي، الكترونيكي و نوري | 1397 |  | 58.6
overhead factor (C) | 1.2713 |  | 97 | 67.9 | 66.7 | 58.8 | 68.1 | 1.679 | 1.667 | 1.588 | 1.681 | EL: ساخت تجهيزات برقي | 1398 | 246.2 | 37.1
سال مبنا | تورم ريالي | تورم ارزي | 98 | 32.7 | 49.2 | 43.1 | 43 | 1.327 | 1.492 | 1.431 | 1.43 |  | 1399 | 386.1 | 56.8
1392 | 0.373 | 0.02 | 99 | 105.6 | 62.9 | 37.3 | 71 | 2.056 | 1.629 | 1.373 | 1.71 |  | 1400 | 605 | 56.7
1393 | 0.156 | 0.02 | 1400 | 54.9 | 53.4 | 37.6 | 46.9 | 1.549 | 1.534 | 1.376 | 1.469 |  | 99.2 | 355.6 | 23.9
1394 | 0.119 | 0.02 | 1400.2 | 98.2 | 71.5 | 53.3 | 79.3 | 1 | 1 | 1 | 1 |  | 99.3 | 433.1 | 37.4
1395 | 0.09 | 0.02 | 1400.3 | 72.3 | 61.9 | 45 | 60.9 | 1 | 1 | 1 | 1 |  | 99.4 | 485.8 | 56.8
1396 | 0.096 | 0.02 | 1400.4 | 54.9 | 53.4 | 37.6 | 46.9 | 1 | 1 | 1 | 1 |  | 1400.1 | 525.6 | 78.5
1397 | 0.312 | 0.02 | 1401.1 | 36.5 | 46 | 27.3 | 38.2 | 1.365 | 1.46 | 1.273 | 1.382 |  | 1400.2 | 577 | 80.4
1398 | 0.412 | 0.02 | 1401.2 | 21.6 | 41.6 | 21.2 | 35.4 | 1 | 1 | 1 | 1 |  | 1400.3 | 633.9 | 69.7
1399 | 0.471 | 0.012 | [5 empty] | 11.3692 | 9.9492 | 5.5276 | 9.339 | ضريب تغيير قيمت نسبت به سال مبنا (1395) | 1400.4 | 683.6 | 56.7
1400 | 0.462 | 0.047 | [10 empty] | 1401.1 | 768.9 | 48
1401 | 0.465 | 0.08 | [10 empty] | 1401.2 | 750.9 | 40.4
1402 | 0.5 | 0.04
| 18.576 | 1.3671

## Engineering
| لیست مدارک مهندسی تفصیلی پروژه احداث واحد نمکردایی نمونه-4 به روش EPC | [24 empty] | بهاي كل (ریال) | حق الزحمه (ریال به ازای یک نفرساعت) |  |  | نفرساعت نيروي انساني |  |  | شرح
[27 empty] | مهندس ارشد | مهندس طراح | نقشه کش | مهندس ارشد | مهندس طراح | نقشه کش
[26 empty] | 34855813285 | 8100090 |  |  | 4950 |  |  | بازنگری و صحه گذاری اسناد پایه
جدول نفر ساعت مهندسی مورد نیاز انجام مهندسی تفصیلی
[30 empty] | نفرساعت نيروي انساني |  |  | شرح | شرح | نفر ساعت مهندسی |  |  |  | حق الزحمه (ریال) نفر ساعت |  |  | بهای کل
[30 empty] | مهندس ارشد | مهندس طراح | نقشه کش |  |  | سال | نقشه کش | مهندس طراح | مهندس ارشد | نقشه کش | مهندس طراح | مهندس ارشد | (ریال)
| PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN |  |  |  |  | 1269 | 5210.65 | 624.75 | بخش فرآيند | بخش فرآيند | سال 1402 | 250 | 2084 | 508 | 7109060 | 7110330 | 7217722 | 25576313954
| Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | [5 empty] | 1171.6 | 4957.5 | 224.25 | بخش كارهاي مكانيكال |  | سال 1403 | 250 | 2084 | 508 | 8670942 | 9064679 | 7449768 | 32323556578
Endorsement | 0 | 600 | 0 | 600 | 0 | 400 | 0 | 500 | 0 | 400 | 0 | 400 | 0 | 500 | 0 | 400 | 0 | 400 | 0 | 400 | 0 | 350 | 0 | 0 | 0 |  |  |  |  | 292.4 | 1555.55 | 1380 | بخش كارهاي HVAC |  | سال 1404 | 125 | 1042 | 254 | 7688151 | 11614021 | 17671024 | 20049341284
Process | 4045.65 | 1109 | 161 | 23 | 0 | 1 | 5 | 2 | 425 | 73 | 162 | 109 | 77 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624.75 |  |  |  |  | 677.4 | 1665.55 | 368 | بخش ایمنی | بخش كارهاي مكانيكال | سال 1402 | 90 | 1983 | 469 | 7109060 | 7110330 | 7217722 | 12719443791
Mechanic | 604 | 77 | 4649 | 1070.6 | 0 | 0 | 6 | 1 | 62 | 0 | 562.5 | 74 | 193.5 | 37 | 0 | 0 | 0 | 0 | 95 | 5 | 0 | 0 | 0 | 0 | 224.25 |  |  |  |  | 2404.6 | 7970 | 4887.5 | بخش كارهاي لوله كشي و خطوط لوله |  | سال 1403 | 90 | 1983 | 469 | 8670942 | 9064679 | 7449768 | 21698640744
HVAC | 0 | 0 | 0 | 0 | 1543.55 | 287.4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380 |  |  |  |  | 5246.7 | 7618.9 | 1075.25 | بخش كارهاي ابزار دقيق |  | سال 1404 | 45 | 992 | 234 | 7688151 | 11614021 | 17671024 | 10735136912
HSE | 7 | 1 | 20 | 0 | 0 | 0 | 1624.55 | 628.4 | 4 | 0 | 8 | 2 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 |  |  |  |  | 2437.8 | 7549.56 | 3772 | بخش كارهاي برقي | بخش كارهاي HVAC | سال 1402 | 552 | 622 | 117 | 7109060 | 7110330 | 7217722 | 10283885207
Piping&Pipeline | 65 | 49 | 0 | 45 | 0 | 0 | 0 | 17 | 7365 | 2302.6 | 0 | 6 | 0 | 34 | 66 | 33 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 4887.5 |  |  |  |  | 696.4 | 3485.8 | 598 | بخش كارهاي مخابرات |  | سال 1403 | 552 | 622 | 117 | 8670942 | 9064679 | 7449768 | 10613934618
Instrument | 476 | 29 | 0 | 8 | 0 | 0 | 13 | 10 | 0 | 4 | 6833.4 | 5031.7 | 8 | 8 | 9 | 9 | 4 | 0 | 0 | 0 | 80 | 15 | 0 | 0 | 1075.25 |  |  |  |  | 296.2 | 1763.35 | 1919.35 | بخش كارهاي سيويل |  | سال 1404 | 276 | 311 | 58 | 7688151 | 11614021 | 17671024 | 8168758099
Electrical | 5 | 0 | 79 | 8 | 0 | 0 | 0 | 0 | 11 | 0 | 6 | 0 | 7161.06 | 2304.8 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3772 |  |  |  |  | 1008.5 | 4983.95 | 3254.5 | بخش كارهاي معماری | بخش ایمنی | سال 1402 | 147 | 666 | 271 | 7109060 | 7110330 | 7217722 | 9354541626
Telecom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1186.5 | 291.8 | 0 | 0 | 598 |  |  |  |  | 306.8 | 1266.5 | 3914.6 | بخش كارهاي سازه |  | سال 1403 | 147 | 666 | 271 | 8670942 | 9064679 | 7449768 | 12813402343
Civil | 6 | 3 | 8 | 4 | 0 | 0 | 4 | 2 | 72 | 10 | 19 | 9 | 53 | 16 | 3369.8 | 650.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.35 |  |  |  |  | 230 | 860 | 0 | کنترل پروژه |  | سال 1404 | 74 | 333 | 135 | 7688151 | 11614021 | 17671024 | 7448956908
Architectural | 2 | 1 | 14 | 1 | 12 | 4 | 5 | 13 | 14 | 0 | 14 | 5 | 22 | 8 | 0 | 0 | 1710.35 | 296.2 | 0 | 0 | 0 | 0 | 0 | 0 | 3254.5 |  |  |  |  | 18905 | 39375 | 19943 | مجموع | بخش كارهاي لوله كشي و خطوط لوله | سال 1402 | 1955 | 3188 | 962 | 7109060 | 7110330 | 7217722 | 45361439763
[35 empty] | سال 1403 | 1955 | 3188 | 962 | 8670942 | 9064679 | 7449768 | 49357173173
Structural | 0 | 0 | 26.5 | 12 | 0 | 0 | 8 | 4 | 15 | 15 | 14 | 10 | 13 | 13 | 0 | 0 | 30 | 0 | 4888.95 | 992.5 | 0 | 0 | 0 | 0 | 3914.6 | [5 empty] | مطالعات زیست محیطی و غیره |  |  |  | سال 1404 | 978 | 1524 | 481 | 7688151 | 11614021 | 17671024 | 27466001731
Project Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 860 | 230 | 0 | [5 empty] | حق الزحمه | شرح |  | بخش كارهاي ابزار دقيق | سال 1402 | 430 | 3048 | 2099 | 7109060 | 7110330 | 7217722 | 41398610704
Total | 5210.65 | 1869 | 4957.5 | 1771.6 | 1555.55 | 692.4 | 1665.55 | 1177.4 | 7970 | 2804.6 | 7618.9 | 5646.7 | 7549.56 | 2937.8 | 3485.8 | 1096.4 | 1763.35 | 696.2 | 4983.95 | 1408.5 | 1266.5 | 656.8 | 860 | 230 | 19943 | [5 empty] | 4211951555 | مطالعات FMEA, HAZID, HAZOP (فاز طرح و ساخت) |  |  | سال 1403 | 430 | 3048 | 2099 | 8670942 | 9064679 | 7449768 | 67058606417
[31 empty] | 2070334480 | مطالعات پیوست سلامت |  |  | سال 1404 | 215 | 1594 | 1049 | 7688151 | 11614021 | 17671024 | 37883745775
[31 empty] | 4371567647 | مطالعات ارزیابی اثرات زیست محیطی (فاز طرح و ساخت) |  | بخش كارهاي برقي | سال 1402 | 1509 | 3020 | 975 | 7109060 | 7110330 | 7217722 | 29047293086
[31 empty] | 8413976134 | مطالعات ژئوتکنیک تکمیلی مورد نیاز برای تهیه مدارک مهندسی |  |  | سال 1403 | 1509 | 3020 | 975 | 8670942 | 9064679 | 7449768 | 46092773075
[31 empty] | 4371567647 | مطالعات پدافند غیر عامل |  |  | سال 1404 | 754 | 1510 | 488 | 7688151 | 11614021 | 17671024 | 45456242646
[31 empty] | 4211951555 | عملیات نقشه برداری مورد نیاز برای تهیه مدارک مهندسی |  | بخش كارهاي مخابرات | سال 1402 | 239 | 1394 | 279 | 7109060 | 7110330 | 7217722 | 16441037830
[31 empty] | 4211951555 | عملیات مستند سازی و استقرار سیستم ارسال مدارک |  |  | سال 1403 | 239 | 1394 | 279 | 8670942 | 9064679 | 7449768 | 20421062253
[31 empty] | 4371567647 | مهندسی ارزش |  |  | سال 1404 | 120 | 697 | 139 | 7688151 | 11614021 | 17671024 | 13042855749
[31 empty] | 1463237657 | ماليات قرارداد شركتهاي ثالث بر عهده پيمانكار به ميزان 5 درصد |  | بخش كارهاي سيويل | سال 1402 | 768 | 705 | 118 | 7109060 | 7110330 | 7217722 | 6377346451
[31 empty] | 38346608851 | مجموع |  |  | سال 1403 | 768 | 705 | 118 | 8670942 | 9064679 | 7449768 | 10433855807
[35 empty] | سال 1404 | 384 | 353 | 59 | 7688151 | 11614021 | 17671024 | 12208357768
[34 empty] | بخش كارهاي معماری | سال 1402 | 1302 | 1994 | 403 | 7109060 | 7110330 | 7217722 | 15982620514
[31 empty] | مبلغ (ريال) | شرح |  |  | سال 1403 | 1302 | 1994 | 403 | 8670942 | 9064679 | 7449768 | 31966671815
[31 empty] | 34855813285 | بازنگری و صحه گذاری اسناد پایه |  |  | سال 1404 | 651 | 997 | 202 | 7688151 | 11614021 | 17671024 | 22769487893
[31 empty] | 500264437826 | مهندسی تفصیلی |  | بخش كارهاي سازه | سال 1402 | 1566 | 507 | 123 | 7109060 | 7110330 | 7217722 | 8813673103
[31 empty] | 38346608851 | مطالعات زیست محیطی و غیره |  |  | سال 1403 | 1566 | 507 | 123 | 8670942 | 9064679 | 7449768 | 18274748686
[31 empty] | 159562840084 | مديريت مهندسي |  |  | سال 1404 | 783 | 253 | 61 | 7688151 | 11614021 | 17671024 | 16078771731
[31 empty] | 1126039832355 | مجموع |  | کنترل پروژه | سال 1402 | 0 | 344 | 92 | 7109060 | 7110330 | 7217722 | 2142622612
[35 empty] | سال 1403 | 0 | 344 | 92 | 8670942 | 9064679 | 7449768 | 5003499507
[35 empty] | سال 1404 | 0 | 172 | 46 | 7688151 | 11614021 | 17671024 | 3939353005
[35 empty] | مجموع | 24286 | 34553 | 17190 |  |  |  | 500264437826

## Procurement
جدول 2.1 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي مکانیک و لوله و اتصالات مورد نياز پروژه بر اساس پیوست 1،2 و3 |  |  |  | ارز مرجع | 393219
رديف | شرح فعاليت ها | دلار | ريال | ضريب تورم عمومي ريالي | 18.576
1 | الكترواستاتيك ها و ادوات مربوطه | 10152685 | 0 | ضريب تورم ارزي دلار | 1.3671
2 | كوره ها و ادوات مربوطه | 4663098 | 0
3 | مبدل نفت / نفت و مبدل آب / آب | 0 | 508645912183
4 | تلمبه ها | 0 | 2494635482223
5 | شيرآلات و اتصالات ، رنگها و لوله های داخل سایت | 0 | 3243807684789
6 | خرید لوله های بیرون سایت | 0 | 2477897909125
7 | مخزن های اتمسفریک و تحت فشار | 0 | 492572895140
8 | سیستم پساب | 5125048 | 0
9 | air compressor Packages | 0 | 536273046912
10 | Flare & Ignitor | 0 | 491830659036
| بسته های تزریق مواد شیمیایی | 0 | 232942541372
12 | Vacuum Deaerator Package | 0 | 174968753515
13 | سیستم HVAC | 0 | 511942420507
14 | جرثقیلهای سقفی | 0 | 273200054599
15 | خرید اقلام ایمنی و آتش نشانی | 0 | 104966724045
16 | گیرنده و فرستنده توپک | 0 | 92437172040
17 | مواد شیمیایی مصرفی | 0 | 740415223179
| جمع كل | 12750596 | 7462351092867
جدول 2.4 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي برق و مخابرات مورد نياز پروژه بر اساس پیوست 4
رديف | شرح فعاليت ها | دلار | ريال
1 | تابلوها | 0 | 845776977386
2 | اتصالات برق (شامل گلندها، شرودها، جعبه هاي اتصال، مفصلها و ...) | 0 | 205204969998
3 | كابلهاي قدرت | 0 | 664916509784
4 | ترانس ها و UPS دیزل ژنراتور | 1854359 | 448333800823
5 | وسايل و تجهيزات مخابرات، و پیجینگ | 127815 | 7677451930
6 | پایه ها و برجهاي روشنائي و سایر ملحقات و ادوات روشنایی | 0 | 154851613835
7 | خط انتقال برق شامل کابل ، پایه ها و یراق آلات | 0 | 554666712274
| جمع كل | 1108309 | 4016230071338
جدول 2.5 -جدول خلاصه مالی تفكيكي تهيه و خريدادوات و تجهیزات ابزاردقیق و تجهیزات آزمایشگاه مورد نياز پروژه بر اساس پیوست 5و6
رديف | شرح فعاليت ها | دلار | ريال
1 | ادوات ابزار دقیق شامل : ترانسمیترها ، سوئیچ ها ، گیج ها و ... | 174878 | 613299426660
2 | شیرآلات ابزار شامل : شیر ON/OFF ، شیرهای کنترلی ، PSV ، PCV | 0 | 1044176003168
3 | سيستم كنترل ( DCS,FGS )، ESD | 0 | 551207838624
4 | ادوات F&G و CO2 Total Flooding و ابزار خاص | 0 | 828192794987
5 | اقلام بالک ابزار دقیق | 0 | 86887160480
6 | کابلهای ابزار دقیق و ملحقات شامل : گلند سینی و ... | 0 | 211021173445
7 | تجهیزات آزمایشگاه | 0 | 582463629079
8 | CCTV | 0 | 252729536874
| جمع كل | 174878 | 3080404255950
جدول 1.7 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي پروژه
رديف | شرح فعاليت ها | دلار | ريال
1 | مجموع قیمت خرید تجهیزات مطابق جداول 2.1، 2.4 و 2.5 و اعمال فاكتور تورم ريال و دلار از سال 1395 تا 1402 | 27984795 | 13163383602850
2 | لوازم يدكي (شامل لوازم يدكي براي راه اندازي و لوازم يدكي موردنياز براي كاركرد دو ساله) | 3208415 | 1621132687361 | ضريب
3 | ترخيص كالاي خارجي شامل هزينه هاي گمرك و بازرگاني ، عوارض موردنياز ماليات، هزينه‌هاي بانكي و ... |  | 1134224764444
4 | بیمه حمل کالاهای داخلی و خارجی، بیمه مسئولیت، تمام خطر نصب و سایر بیمه های مورد نیاز |  | 280708718347 | 0.01
5 | هزينه هاي بارگيري ، حمل و تخليه كالاي خارجي، هزينه هاي بارگيري، حمل و تخليه كالاي داخلي |  | 602216012292 | 0.03
6 | هزینه های بازرسی اشخاص ثالث |  | 280708718347 | 0.01
7 | خدمات فنی سازندگان در دوران نصب و راه اندازی |  | 815086857062 | 0.03
| جمع كل | 18940867 | 28150175133494

## Construction
:خلاصه براورد ساخت و اجرا مطابق تفکیک نرخ پیمان- پیوست یک قرارداد
|  | 370666133958 |  |  |  | الف:تجهیز و برچیدن مطابق جدول ب-1 |  |  | الف
|  | 13435428500560 |  |  |  | ب:ساخت و نصب و راه اندازی مطابق جدول ب-1 |  |  | ب
|  | 1132179656484 |  |  |  | ج:تسهیلات مورد نیاز کارفرما مطابق جدول ب-2 |  |  | ج
|  | 127898575135 |  |  |  | د: الزامات HSEمطابق جدول ب-3 |  |  | د
|  | 70230265512 |  |  |  | ه: هزینه دفتر فنی کارگاه |  |  | ه
|  | 10654005797245 |  |  |  | مجموع
شرح ردیف های الف و ب - برآورد هزینه ساخت و نصب و راه اندازی و تجهیز کارگاه - مطابق جداول
جمع کل | هزینه تجهیز کارگاه |  | هزینه اجرا پس از اعمال ضریب بروزرسانی | ضریب بروزرسانی به سه ماهه اول 1402 | هزینه اجرا پس از اعمال ضرایب فهرست بهای مربوطه |  | هزینه اجرامطابق فهرست بهای مربوطه | عنوان
491579382437 | 156488318616 |  | 191231233256 | 1.06 | 199740618673 |  | 195489127233 | اجرای فونداسیون تجهیزات
440245437999 | یک قلم در ردیف اول محاسبه گردید |  | 440245437999 | 1.06 | 453023321638 |  | 470240269188 | اجرای جاده های داخلی و خارجی
809128201396 | یک قلم در ردیف اول محاسبه گردید |  | 809128201396 | 1.06 | 581916120788 |  | 293833681014 | اجرای سایبانها
2247387556534 | یک قلم در ردیف اول محاسبه گردید |  | 2247387556534 | 1.06 | 1861057449237 |  | 832035297689 | اجرای ساختمانها
2452113061198 | یک قلم در ردیف اول محاسبه گردید |  | 2452113061198 | 1.06 | 2554055764105 |  | 1013563103618 | اجرای ابنیه و اقلام متفرقه
903684988705 | یک قلم در ردیف اول محاسبه گردید |  | 903684988705 | 1.06 | 638115136092 |  | 280859407682 | محوطه سازی واحدها
111319244111 | یک قلم در ردیف اول محاسبه گردید |  | 111319244111 | 1.062 | 182339590579 |  | 71626764788 | اجرای دیوار حایل و شیروانی دورواحد
213848900636 | یک قلم در ردیف اول محاسبه گردید |  | 213848900636 | 1.06 | 254112606966 |  | 116422454107 | دفن کابل و لوله های دفنی
1360158998329 | یک قلم در ردیف اول محاسبه گردید |  | 1360158998329 | 1.06 | 952015947575 |  | 405657590969 | نصب و اجرای سازه های فلزی متفرقه
6917339225 | یک قلم در ردیف اول محاسبه گردید |  | 6917339225 | 1.06 | 7257127901 |  | - | احداث فضای سبز
478811986295 | 17794045289 |  | 372119852605 | 1.061 | 247533580958 |  | 154959892728 | اجرا و نصب تجهیزات مکانیک
209304050892 | 21047291421 |  | 332553070916 | 1.061 | 232926597983 |  | 101076054246 | اجرای خطوط لوله
739539552189 | 42967458541 |  | 562848974768 | 1.06 | 1066671998559 |  | 242489881221 | اجرای پایپینگ درون واحدها
161275065358 | 8073631597 |  | 265487319048 | 1.058 | 171896245653 |  | 208294579081 | اجرای برق
134340597823 | 11652251354 |  | 214109426941 | 1.058 | 255222945166 |  | 75050113044 | اجرای ابزاردقیق
10539855406976 | 370666133958 |  | 11194507190837 |  | 11944524909137 |  | 7388452383817 | مجموع
شرح ردیف د - برآورد هزینه ایمنی کارگاه (HSE) | [6 empty] | شرح ردیف ج - برآورد تسهیلات کارفرما
86559430016 | لوازم حفاظت فردی و تجهیزات | [5 empty] | 924111311359 | تسهيلات رفاهي گروه نظارت
3394150075 | سدجش و اندازه گیری 1 | [5 empty] | 152830405314 | تسهیلات ماموریت داخل و خارج و آموزش
88142751 | سدجش و اندازه گیری 2
5684473657 | آموزش | [5 empty] | 1132179656484 | مجموع
20575804971 | نیروی انسانی
شرح ردیف ه: هزینه دفتر فنی کارگاه
127898575135 | مجموع | [5 empty] | 4 نفر طی بیست و چهار ماه هزینه نفر ماه : 750،000،000 ریال | پرسنل دفتر فنی کارگاه (طبق توضیح بند 6 صفحه قبل (صفحه 4)
[7 empty] | 70230265512 | مجموع

## C.CONTENT
فهرست
الف) مبانی محاسبات براورد
ب) خلاصه برآورد مالی بخش اجرا
پیوست یک - برآورد هزینه اجرای پروژه بر اساس فهارس بها
جدول 1 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث فونداسیون تجهیزات وادوات (بر اساس ریز متره مندرج در جدول الف پیوست 2) |  |  | -
جدول 2 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث سایبان تجهیزات(بر اساس ریز متره مندرج در جدول ب پیوست 2) |  |  | -
جدول 3 - برآورد اجرا بر اساس فهرست بهای ابنیه 140 - احداث جاده های دسترسی، جاده های داخل واحدها و پاترول(بر اساس ریز متره مندرج در جدول ج پیوست 2) |  |  | -
جدول 4 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث ابنیه متفرقه (بر اساس ریز متره مندرج در جدول د پیوست 2) |  |  | -
جدول 5 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 -محوطه سازی واحدها (بر اساس ریز متره مندرج در جدول ه پیوست 2) |  |  | -
جدول 6 - برآورد اجرا فضای سبز - خارج از فهرست بها |  |  | -
جدول7 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - دفن لوله ها (داخل و خارج واحد) و کابل های زیر زمینی (بر اساس ریز متره مندرج در جدول و پیوست 2) |  |  | -
جدول 8 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - سازه های فلزی متفرقه (بر اساس ریز متره مندرج در جدول ط پیوست 2) |  |  | -
جدول10 - برآورد اجرا بر اساس فهرست بهای باند و راه 1402 -ساخت دیوار حایل مجاور تپه و سطوح کوهبری شده و شیروانی دورتادور کارخانه |  |  | -
جدول 11 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 -تجهیز و برچیدن کارگاه |  |  | -
جدول 12 - برآورد اجرای لوله کشی وپایپینگ بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401 |  |  | -
جدول 13 - برآورد اجراو نصب تجهیزات مکانیک بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401 |  |  | -
جدول 14 - برآورد اجرا ی خطوط لوله بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته خطوط لوله روزمینی جریانی نفت و گاز1401 - |  |  | -
جدول 15 - برآورد اجرای عملیات برق و مخابرات و کابل کشی بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401 |  |  | -
جدول 16 - برآورد اجرا و نصب تجهیزات ابزاردقیق بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401 |  |  | -
جدول 17-1: هزینه تسهیلات کارفرما جهت ماموریت داخل کشور |  |  | -
جدول 17 -2: هزینه تسهیلات کارفرما جهت ماموریت خارج کشور |  |  | -
جدول 17-3: - هزینه آموزشی عملیاتی (اپراتوری) به میزان 192 نفر-روز |  |  | -
جدول 17-4: هزینه تسهیلات کارفرما مربوط به احداث کمپهای دستگاه نظارت کلیه بندهای اشاره شده در ذیل مربوط به مدرک "مشخصات فنی کمپهای دستگاه نظارت به شماره M9003-BD-GN-OTH-26011میباشد |  |  | -
جدول 18-1: براورد هزینه ایمنی کارگاه : لوازم حفاظت فردی و تجهیزات |  |  | -
جدول 18 -2: براورد هزینه ایمنی کارگاه : نیروی انسانی |  |  | -
جدول 18-3 - براورد هزینه ایمنی کارگاه : سنجش و اندازه گیری (1) - اندازه گیری آلاینده های فیزیکی،شیمیایی و ارگونومی در محیط کار |  |  | -
جدول 18-4: براورد هزینه ایمنی کارگاه : سنجش و اندازه گیری (2) |  |  | -
جدول 18-5: براورد هزینه ایمنی کارگاه : آموزش |  |  | -
پیوست دو - ریز متره و برآورد احجام بخش سیویل وسازه
جدول الف : ریز برآورد متره فونداسیون تجهیزات |  |  | -
جدول ب-1 : ریز برآورد متره سایبانها - فونداسیون و کف سازی |  |  | -
جدول ب-2 : ریز برآورد متره سایبانها - لسکلت فلزی |  |  | -
جدول ج : ریز برآورد متره جاده ها |  |  | -
جدول د : ریز برآورد متره ابنیه متفرقه |  |  | -
جدول ه : ریز برآورد متره محوطه سازی |  |  | -
جدول و : ریز برآورد کانال های لوله ها و کابل های دفنی |  |  | -
جدول ط : ریز برآورد متره سازه های فلزی متفرقه |  |  | -

## C.Note
[9 empty] | مبانی محاسبات براورد : | الف)
[9 empty] | جهت براورد هزینه اجرای بخش سیویل و سازه از "فهرست بهای واحد پایه رشته ابنیه" سال 1402 استفاده شده است. | -1
با توجه به آنکه این پروژه در حد مهندسی مقدماتی و پایه بوده و نقشه معماری فاز یک آن اماده گردیده لیکن نقشه های فاز 2 معماری، نقشه های اجرایی فونداسیون، سازه بتی و فولادی و نیز نقشه های تاسیسات آن تهیه نگردیده و میبایست در مرحله مهندسی تفصیلی انجام شود، لذا امکان تهیه ریز برآورد اقلام و استفاده از فهرست احاد بهای ابنیه در این مرحله از پروژه میسر نمیباشد. لذا برای برآورد هزینه ساخت و اجرای ساختمانها از ابلاغیه شماره 47855/ش م مورخ 1401/12/16شورای مرکزی سازمان نظام مهندسی ساختمان که بر مبنای متراژ ساخت بنا میباشد، استفاده گردیده است | [9 empty] | -2
جهت برآورد هزینه اجرای سایر بخشها از "فهرست بهای اختصاصی تاسیسات نفت و گاز - رشته نصب واحدهای بهره برداری نفت و گاز ایستگاه تراکم گاز" و "فهرست بهای اختصاصی تاسیسات نفت و گاز - رشته خطوط لوله روزمینی جریانی نفت و گاز" سال 1401 استفاده شده است. | [9 empty] | -3
[9 empty] | ضریب بالاسری بخش اجرا بر اساس فهرست بهای اختصاصی نصب واحدهای بهره برداری که در محاسبه هزینه پروژه منظور شده است معادل است با : | -4
[7 empty] | گروه لوله کشی |  | 1-4-
هزینه بالاسری برای کارهایی که از طریق مناقصات انجام میشود : 48%
ضریب هزینه تفاوت بیمه های تامین اجتماعی به میزان 1
ضریب منطقه ای : 1.12
ضریب بروزرسانی به سه ماهه چهارم 1401 : 1.51
| 2.503 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : =1.12*1.51 * 1.48 = | -
|  | 0.06 | [6 empty] | ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = | -
[7 empty] | گروه نصب تجهیزات |  | 2-4-
هزینه بالاسری برای کارهایی که از طریق مناقصات انجام میشود : 48%
ضریب هزینه تفاوت بیمه های تامین اجتماعی به میزان 1
ضریب منطقه ای : 1.12
ضریب بروزرسانی به سه ماهه چهارم 1401 : 1.515
| 2.5113 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : =1.12*1.515 * 1.48 = | -
|  | 0.06 | [6 empty] | ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = | -
[5 empty] | گروه نصب کارهای برقی و ابزار دقیق |  |  |  | 3-4-
هزینه بالاسری برای کارهایی که از طریق مناقصات انجام میشود : 48%
ضریب هزینه تفاوت بیمه های تامین اجتماعی به میزان 1
ضریب منطقه ای : 1.12
ضریب بروزرسانی به سه ماهه چهارم 1401 : 1.491
| 2.4715 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : =1.12*1.491 * 1.48 = | -
|  | 0.06 | [6 empty] | ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = | -
[9 empty] | ضریب بالاسری بخش اجرا بر اساس فهرست بهای اختصاصی خطوط لوله روزمینی که در محاسبه هزینه پروژه منظور شده است معادل است با : | -5
هزینه بالاسری برای کارهایی که از طریق مناقصات انجام میشود : 48%
ضریب هزینه تفاوت بیمه های تامین اجتماعی به میزان 1
ضریب منطقه ای : 1.11
ضریب بروزرسانی به سه ماهه چهارم 1401 : 1.469
| 2.4133 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : =1.11*1.469 * 1.48 = | -
|  | 0.06 | [6 empty] | ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = | -
[9 empty] | ضریب بالاسری بخش اجرا بر اساس فهرست رشته ابنیه که در محاسبه هزینه پروژه منظور شده است معادل است با | -5
|  |  | 1.41 | [5 empty] | ضریب بالاسری برای کارهایی که از طریق مناقصات انجام میشود :
[9 empty] | ضریب منطقه ای : 1.09 | -
[9 empty] | ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = 4% | -
| 1.5369 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : 1.09 * 1.41 = | -
[9 empty] | برای دفتر فنی کارگاه 4 نفر به شرح زیر برای مدت 20 ماه در نظر گرفته شده است: | -6
سرپرست دفتر فنی ، کنترل پروژه، دو نفر کارشناس فنی بر حسب نیاز
حقوق هر کارشناس سایت بر اساس تجربه این مشاور 50 ملیون تومان در نظر گرفته شده است که با احتساب مالیات و بیمه 75 ملیون تومان هزینه در نظر گرفته شده است.
[9 empty] | ضریب بالاسری بخش اجرا بر اساس فهرست رشته راه و باند که در محاسبه هزینه پروژه منظور شده است معادل است با | 7-
|  |  | 1.41 | [5 empty] | ضریب بالاسری برای کارهایی که از طریق مناقصات انجام میشود :
ضریب منطقه ای : 1.12
ضریب هزینه تجهیز و برچیدن کارگاه که مبلغ آن با مبلغ اجرا جمع میگردد = 4%
| 1.5792 | [7 empty] | ضریب اجرا که به صورت خطی در مبالغ محاسبه شده فهرست بها ضرب میگردد : 1.12 * 141 = | -
[8 empty] | با توجه به اینکه نرخ فهارس بها براساس 1402 براساس نرخ سه ماهه چهارم 1401 میباشد لذا جهت بروزرسانی مبالغ به سه ماهه اول 1402 از ضرایب بروزرسانی زیر استفاده شده است : | توضیحات
|  |  |  | 1.06 |  | 1- فهرست ابنیه
|  |  |  | 1.062 |  | 2- فهرست راه و باند
|  |  |  | 1.061 |  | 3- فهرست خطوط لوله روزمینی
|  |  |  | 1.061 | گروه نصب | 4- فهرست نصب واحدهای بهره برداری
|  |  |  | 1.06 | گروه لوله کشی
|  |  |  | 1.058 | گروه برق

## C.foundation-2
جدول 1 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث فونداسیون تجهیزات وادوات (بر اساس ریز متره مندرج در جدول الف پیوست 2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح | ردیف
[5 empty] | * | خاکبرداری و پی کنی با ماشین | * | 1.537
36345799378 | 21681244881 | 9664 | 2540524 | 2130152 | m3 | کندن زمین در صورت لزوم استفاده از چکش هیدرولیکی در زمین های سنگی و حمل و تخلیه مواد کنده شده تا فاصله ٢٠ متر از مرکز ثقل برداشت | 31584 | منطقه ای نمونه. | 1.09
| 0 |  |  |  | * | قالب بندی فلزی | * | بالاسری | 1.41
13215174982 | 6208676324 | 4501 | 1565852 | 1123678 | m2 | تهیه مصالح و قالب بندی فلزی در پی ها | 75489 | تجهیزکارگاه | 1
| 0 |  |  |  | * | تهیه مصالح و اجرای پی | * | بروزرسانی | 1
133544688913 | 109636811712 | 363170 | 307442 | 283934 | Kg | تهیه، بریدن، خم کردن و کار گذاشتن میلگرد آج دار به قطر ١٢ تا ١٨ میلی متر، برای بتن مسلح با سیم پیچی لازم. | 74449
67551830341 | 35484733397 | 4149 | 11374410 | 9803149 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با عیار 350 کیلو سیمان | 57821
380110706 | 260098696 | 4149 | 151494 | 76577 | m3 | اضافه بهایه ردیفهای بتنه ریزی در بتن مسلح | 108178
315354665 | 103573742 | 500 | 479555 | 301022 | kg | نهیه و نصب انکربولت، میل مهار با مهره مربوطه | 90148
| 0 |  |  |  | * | تهیه خاک مناسب از فاصله 15 کیلومتری | *
856808128 | 828119306 | 4472 | 284253 | 217449 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری | 38587
1089037435 | 122084632 | 4472 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 31285
789940204 | 95417459 | 4472 | 156833 | 17245 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر | 32798
| 0 |  |  |  | * | خاکریزی و آبپاشی و کوبیدن با ماشین | *
895237791 | 389927096 | 2680 | 289647 | 270404 | m3 | پخش و کوبیدن خاکریزیها با 100% تراکم | 38813
| 0 |  |  |  | * | آبپاشی و کوبیدن سطوح با دست | *
136992029 | 94661961 | 1792 | 83398 | 45335 | m2 | آبپاشی و کوبیدن سطوح با تراکم 95 درصد | 12771
| 0 |  |  |  | * | تهیه مصالح و اجرای بتن با عیار 150 کیلو سیمان | *
14443167982 | 6972572869 | 795.8 | 13804203 | 12282487 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با 150 کیلو سیمان | 77378
267830514 | 82281843 | 795.8 | 289224 | 166654 | m3 | اضافه بها برای بتن به ضخامت 15 سانتیمتر و کمتر | 61193
| 0 |  |  |  | * | حمل خاک تا km10 با ماشین | *
2065929810 | 1589770010 | 9664 | 202229 | 167754 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری | 26742
471746643 | 54745393 | 9664 | 32292 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایه ر 100 متر مازاد | 36914
4557843832 | 177884829 | 9664 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 31285
1079880115 | 790238504 | 1410 | 774582 | 274128 | مترمربع | تهیه و اجرای بتن آسفالتی با سنگ شکسته از مصالح رودخانه ای برای قشر رویه ( توپکا ) ، هر گاه دانه بندی مصالح صفر تا 12/5 میلی متر باشد ، به ازای هر سانتی متر ضخامت آسفالت | 211211
| 0 |  |  |  |  | اجرای لایه نفوذ ناپذیر زیر فونداسیون مخازن | *
1963618453 | 2165503488 | 2240 | 1779382 | 1062702 | m2 | تهیه و اجرای ژئوممبرین (زمین غشا) از جنس پلی اتیلن سنگین (High Density Poly Ethylene) به ضخامت یک میلی متر | 266390 | چهارم 91 | 481.9
1653989413 | 1653989413 | 2240 | 493086 | - | m2 | تهیه مصالح و اجرای ژئو تکستایل بافته | 231207* | چهارم 1401 | 5125.778
199740618673 | 195489127233 |  |  |  |  | مجموع |  | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366

## C.Shelters-2
جدول 2 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث سایبان تجهیزات(بر اساس ریز متره مندرج در جدول ب پیوست 2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح | ردیف
[5 empty] | * | خاکبرداری و پی کنی با ماشین | * | 1.537
18930680580 | 11942216058 | 6211.5 | 2540524 | 2130152 | m3 | کندن زمین در صورت لزوم استفاده از چکش هیدرولیکی در زمین های سنگی و حمل و تخلیه مواد کنده شده تا فاصله ٢٠ متر از مرکز ثقل برداشت | 31584 | منطقه ای نمونه. | 1.09
289364379 | 37429481 | 6211.5 | 32292 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد | 36914 | بالاسری | 1.41
2645149219 | 180893798 | 6211.5 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 31285 | تجهیزکارگاه | 1
| 0 |  |  |  | * | قالب بندی فلزی | * | بروزرسانی | 1
3210100373 | 2141440350 | 1476 | 1565852 | 1123678 | m2 | تهیه مصالح و قالب بندی فلزی در پی ها | 75489
173198798 | 77831549 | 4428 | 27846 | 22319 | dm3 | تعبیه انواع درز در مقطع عرضی قطعات بتنی بدون پر کرد آن بر حسب حجم درز. | 44713
| 0 |  |  |  | * | تهیه مصالح و اجرای پی | *
11469738158 | 6340734477 | 17730 | 669704 | 284231 | Kg | تهيه، بريدن، خم كردن و كار گذاشتن ميل گرد ساده به قطر تا 10 ميلي‌متر، براي بتن مسلح | 77967
14002655376 | 9193233364 | 46534 | 307442 | 283934 | Kg | تهیه، بریدن، خم کردن و کار گذاشتن میلگرد آج دار به قطر ١٢ تا ١٨ میلی متر، برای بتن مسلح با سیم پیچی لازم. | 74449
23949071117 | 8376464081 | 1380.15 | 11374410 | 9803149 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با عیار 350 کیلو سیمان | 57821
147205196 | 124683434 | 1380.15 | 151494 | 76577 | m3 | اضافه بهایه ردیفهای بتنه ریزی در بتن مسلح | 108178
20229282 | 15589146 | 519.15 | 45076 | 31176 | m4 | اضافه بها براي بتن كف‌سازي‌ها با هر وسيله و به هر ضخامت | 90288
504663456 | 509179519 | 1537.5 | 479555 | 301022 | kg | نهیه و نصب انکربولت، میل مهار با مهره مربوطه | 90148
| 0 |  |  |  | * | تهیه خاک مناسب از فاصله 15 کیلومتری | *
1517185355 | 568466990 | 3690 | 284253 | 217449 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری | 38587
1747439252 | 79930175 | 3690 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 31285
618427860 | 85894794 | 3690 | 156833 | 17245 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر | 32798
| 0 |  |  |  | * | خاکریزی و آبپاشی و کوبیدن با ماشین | * | چهارم 91 | 481.9
781702254 | 352776440 | 1845 | 289647 | 270404 | m3 | پخش و کوبیدن خاکریزیها با 100% تراکم | 38813 | چهارم 1401 | 5125.778
| 0 |  |  |  | * | آبپاشی و کوبیدن سطوح با دست | * | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
173643707 | 91704537 | 1845 | 83398 | 45335 | m2 | آبپاشی و کوبیدن سطوح با تراکم 95 درصد | 12771
| 0 |  |  |  | * | تهیه مصالح و اجرای بتن با عیار 150 کیلو سیمان | *
9567672810 | 4516903135 | 726.55 | 13804203 | 12282487 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با 150 کیلو سیمان | 77378
256749195 | 82009563 | 726.55 | 289224 | 166654 | m3 | اضافه بها برای بتن به ضخامت 15 سانتیمتر و کمتر | 61193
| 0 |  |  |  | * | حمل خاک تا km10 با ماشین | *
1518396733 | 1063135609 | 6211.5 | 202229 | 167754 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری | 26742
289364379 | 37429481 | 6211.5 | 32292 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایه ر 100 متر مازاد | 36914
304760720 | 180893798 | 6211.5 | 46707 | 30506 | m3 | حمل از 500 متر تا 10 کیلومتر | 31285
| 0 |  |  |  |  | عملیات بنایی | *
10464079461 | 5891068155 | 1038.3 | 7815551 | 4241143 | m3 | سنگ چيني دركف ساختمان (بلوكاژ) با سنگ لاشه. | 43161
| 0 |  |  |  |  | ساخت سازه فلزی | *
66825425900 | 55326029962 | 134943 | 510722 | 215561 | Kg | تهیه ، ساخت و نصب ستون از یک تیرآهن | 73509
35484241335 | 32554240344 | 175895 | 548294 | 309194 | Kg | تهیه و نصب تیرحمال با جوشکاریهای لازم در محل اتصال | 68554
63882606360 | 36511576038 | 323276 | 244415 | 149646 | Kg | اضافه بها در صورت مصرف تیراهن پهن | 120787
21824602136 | 17810145403 | 68422 | 353388 | 239924 | Kg | تهیه و نصب پرلین روی سطح شیبدار اسکلت فلزی از پروفیلZ | 73372
16172108898 | 17339955931 | 49856 | 654653 | 397348 | Kg | تهیه ونصب بادبندبا تمام قطعات اتصال | 109119
42107352659 | 26090247815 | 69498 | 353388 | 239924 | Kg | تهیه و نصب پرلین روی سطح شیبدار اسکلت فلزی با قطعات اتصال | 68664
2251019601 | 1000622813 | 69498 | 13110 | 18517 | Kg | اضافه بها به ردیف 90204 برای پرلین افقی | 110759
39365264112 | 31249280535 | 64086 | 923008 | 725893 | Kg | تهیه مصالح و پوشش سقف با ورق گالوانیزه با وسایل و لوازم نصب | 182146
| 0 |  |  |  |  | زنگ زدایی و رنگ آمیزی اسکلت فلزی | *
211401203849 | 162757787990 | 274563 | 463412 | 537069 | Kg | زنگ زدايي اسكلت‌هاي فلزي، به روش ساچمه پاشي (شات بلاست). | 329444
8869596128 | 4761586106 | 9690.8 | 948918 | 982053 | m2 | تهيه مصالح و اجراي رنگ اپوكسي برايساير كارهاي فلزي، شامل دوقشر ضد زنگ براي اپوكسي، يك قشرآستر و يك قشر رويه. | 155043
581916120788 | 293833681014 |  |  |  |  | جمع :

## C.ROAD-2
جدول 3 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث جاده های دسترسی، جاده های داخل واحدها و پاترول(بر اساس ریز متره مندرج در جدول ج پیوست2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح | ردیف
45925599774 | 25166699456 | 8260.4 | 3191360 | 3646829 | m3 | تهیه مصالح زیر اساس از مصالح رودخانه ای با دانه بندی صفر تا 50 میلی متر | 176689 | 1.537
57161585746 | 29382233966 | 8260.4 | 7371703 | 2948168 | m3 | تهیه مصالح اساس از مصالح رودخانه ای با دانه بندی صفر تا 38 میلی متر ، وقتی که حداقل 50 درصد مصالح مانده روی الک نمره 4 در یک وجه شکسته باشد | 194683 | منطقه ای نمونه. | 1.09
2313870311 | 1600772130 | 8260.4 | 217556 | 159196 | m3 | پخش ، آب پاشی ، تسطیح و کوبیدن قشرهای زیر اساس به ضخامت تا 15 سانتی متر ، با حداقل 95 درصد تراکم به روش آشو اصلاحی | 282901 | بالاسری | 1.41
7266161971 | 2605457158 | 8260.4 | 680041 | 420321 | m3 | پخش ، آب پاشی ، تسطیح و کوبیدن قشرهای اساس به ضخامت بیش از 10 سانتی متر تا 15، با حداقل 100 درصد تراکم به روش آشو اصلاحی | 255581 | تجهیزکارگاه | 1
13171835074 | 9171177313 | 68158 | 280100 | 127815 | kg | تهیه مصالح و اجرای اندود نفوذی ( پریمکت ) با قیر محلول | 311126 | بروزرسانی | 1
4682152727 | 5134126797 | 11155 | 286665 | 181295 | kg | تهیه مصالح و اجرای اندود سطحی ( تک کت ) با قیر محلول | 314794
363829350116 | 168574517630 | 6608.32 | 50702286 | 20402641 | مترمربع | تهیه و اجرای بتن آسفالتی با سنگ شکسته از مصالح رودخانه ای برای قشر آستر ( بیندر ) ، هرگاه دانه بندی مصالح صفر تا 19 میلی متر باشد ، به ازای هر سانتی متر ضخامت آسفالت | 360153
3488964006 | 1571422472 | 5526.24 | 774582 | 274128 | مترمربع | تهیه و اجرای بتن آسفالتی با سنگ شکسته از مصالح رودخانه ای برای قشر رویه ( توپکا ) ، هر گاه دانه بندی مصالح صفر تا 12/5 میلی متر باشد ، به ازای هر سانتی متر ضخامت آسفالت | 211211
5217629502 | 1716352306 | 950 | 5297591 | 2922225 | m2 | هيه مصالح رودخانه‌اي (تونان) براي تحكيم بستر راه و محوطه، يا اجراي قشر تقويتي در زير سازي راه و محوطه | 363750
| 0 |  |  |  | * | تهیه خاک مناسب از فاصله 15 کیلومتری | *
3018672242 | 1790549233 | 13791 | 284253 | 217449 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری | 38587
5587404435 | 239606419 | 13791 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 31285
1168082805 | 328900358 | 13791 | 156833 | 17245 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر | 32798
| 0 |  |  |  | * | خاکریزی و آبپاشی و کوبیدن با ماشین | *
349123301 | 226211523 | 950 | 289647 | 270404 | m3 | پخش و کوبیدن خاکریزیها و تونان با 100% تراکم | 38813
3952975193 | 1265775600 | 13791 | 280288 | 195934 |  | پخش و کوبیدن خاکریزیها و تونان با 90% تراکم | 24928 | چهارم 91 | 481.9
0 | 0 |  |  |  | * | حمل خاک تا km10 با ماشین | * | چهارم 1401 | 5125.778
2050945766 | 1664576409 | 7200 | 313407 | 195870 | m3 | کانال کنی در زمینهای نرم تا عمق 2 متر | 24806 | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
9611803952 | 3819366377 | 29400 | 247610 | 232447 | m3 | کانال کنی در زمینهای سخت با وسیله مکانیکی تا عمق 2 متر | 41326
75017958360 | 45275469131 | 3600 | 18794612 | 15420358 | m3 | کانال کنی در زمینهایسنگی با چکش هیدرولیکی تا عمق 2 متر | 31584
1036518216 | 517251702 | 35686 | 38159 | 21835 | m3 | اضافه بها برای فاصله حمل بیش از 20 متر و حداکثر 50متر | 39686
4219259319 | 3573935972 | 35686 | 202229 | 167754 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری | 26742
900779342 | 132338383 | 35686 | 32292 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد | 36914
10140567246 | 767653906 | 35686 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 31285
453023321638 | 470240269188 |  |  |  |  | جمع :

## C.OTHERS-2
جدول 4 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - احداث ابنیه متفرقه (بر اساس ریز متره مندرج در جدول د پیوست 2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح |  | ردیف
[5 empty] | * | خاکبرداری و پی کنی با ماشین |  | * | 1.537 | ضریب =
1194360698522 | 715053047897 | 249609 | 2540524 | 2130152 | m3 | کندن زمین در صورت لزوم استفاده از چکش هیدرولیکی در زمین های سنگی و حمل و تخلیه مواد کنده شده تا فاصله ٢٠ متر از مرکز ثقل برداشت |  | 31584 | منطقه ای نمونه. | 1.09
0 |  |  |  |  | * | حمل خاک تا km10 با ماشین |  | * | بالاسری | 1.41
78540529108 | 53745153035 | 249609 | 202229 | 167754 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری |  | 26742 | تجهیزکارگاه | 1
8608608025 | 1997661691 | 249609 | 32292 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد |  | 36914 | بروزرسانی | 1
156820284524 | 9888504277 | 249609 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول |  | 31285
[5 empty] | * | قالب بندی فلزی |  | *
92117621955 | 57839175334 | 38140 | 1565852 | 1123678 | m2 | تهیه مصالح و قالب بندی فلزی در پی ها |  | 75489
[5 empty] | * | تهیه مصالح و اجرای پی |  | *
256232182693 | 148368354812 | 850530 | 307442 | 283934 | Kg | تهیه، بریدن، خم کردن و کار گذاشتن میلگرد آج دار به قطر ١٢ تا ١٨ میلی متر، برای بتن مسلح با سیم پیچی لازم. |  | 74449
275963272243 | 160266715630 | 16929 | 11374410 | 9803149 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با عیار 350 کیلو سیمان |  | 57821
2697763598 | 899652419 | 16929 | 151494 | 76577 | m3 | اضافه بهایه ردیفهای بتنه ریزی در بتن مسلح |  | 108178
[5 empty] | * | تهیه خاک مناسب از فاصله 15 کیلومتری |  | *
8835661395 | 9561511822 | 50970 | 284253 | 217449 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری |  | 38587
12499947042 | 627566871 | 50970 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول |  | 31285
4083951425 | 605033864 | 50970 | 156833 | 17245 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر |  | 32798
0 |  |  |  |  | * | خاکریزی و آبپاشی و کوبیدن با ماشین |  | *
41857367776 | 28221900448 | 84516 | 289647 | 270404 | m3 | پخش و کوبیدن خاکریزیها با 100% تراکم |  | 38813
0 |  |  |  |  | * | آبپاشی و کوبیدن سطوح با دست |  | *
2844580727 | 1648056085 | 50970 | 83398 | 45335 | m2 | آبپاشی و کوبیدن سطوح با تراکم 95 درصد |  | 12771
0 |  |  |  |  | * | تهیه مصالح و اجرای بتن با عیار 150 کیلو سیمان |  | *
43639069859 | 19909433089 | 2284.88 | 13804203 | 12282487 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با 150 کیلو سیمان |  | 77378
788403525 | 272074185 | 2284.88 | 289224 | 166654 | m3 | اضافه بها برای بتن به ضخامت 15 سانتیمتر و کمتر |  | 61193
0 | [6 empty] | فنس | *
78445352644 | 64819255335 | 84516 | 679766 | 712895 | Kg | تهیه و ساخت و کارگذاری پایه با دستک فلزی از لوله گالوانیزه برای نصب تور یا مشابه |  | 120362
41895900974 | 15130595232 | 65601 | 734573 | 430143 | Kg | تهیه و نصب تور سیمی گالوانیزه حصاری با لوازم اتصال |  | 199516
0 | [5 empty] | اجرای لایه نفوذ ناپذیر |  | *
21285321359 | 6321960506 | 13588 | 1654449 | 1062702 | m2 | تهیه و اجرای ژئوممبرین (زمین غشا) از جنس پلی اتیلن سنگین (High Density Poly Ethylene) به ضخامت یک میلی متر |  | 266390 | چهارم 91 | 481.9
5819582413 | 5819582413 | 7738 | 493086 | - | m2 | تهیه مصالح و اجرای ژئو تکستایل بافته |  | 231207* | چهارم 1401 | 5125.778
32665948796 | 32665948796 | 200 | 145599508 | خارج فهرست بها | m2 | تهیه و اجرای آجر نسوز برای گودال های سوزا |  | * | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
2554055764105 | 1013563103618 |  |  |  |  | جمع :

## C.SITE-2
جدول 5 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 -محوطه سازی واحدها (بر اساس ریز متره مندرج در جدول ه پیوست2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح |  | ردیف
[5 empty] | * |  | خاکبرداری و پی کنی با ماشین و حمل تا فاصله 10 کیلومتری | * | 1.537 | ضریب =
68128332863 | 37371745569 | 414350 | 103685 | 95641 | m3 | خاکبرداری در زمین های سخت با هر وسیله مکانیکی و حمل تا فاصله 20 متری |  | 29789 | منطقه ای نمونه. | 1.09
137116883992 | 76066503744 | 138396 | 574740 | 376189 | m3 | خاکبرداری در زمین های سنگی با هر وسیله مکانیکی و حمل تا فاصله 20 متری |  | 21612 | بالاسری | 1.41
39254175947 | 34225245443 | 93883 | 601105 | 383719 | m3 | خاکبرداری در زمین های سنگی با استفاده از چکش هیدرولیکی و حمل تا فاصله 20 متری |  | 34384 | تجهیزکارگاه | 1
27134792605 | 21478577847 | 733558 | 42557 | 53614 | m3 | اضافه بها برای فاصله حمل بیش از 20 متر و حداکثر 50متر |  | 39686 | بروزرسانی | 1
87989228406 | 69716958265 | 733558 | 202229 | 167754 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری |  | 26742
27021541124 | 4674364503 | 733558 | 32292 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد |  | 36914 |  | چهارم 91 | 481.9
224293178009 | 11194039911 | 733558 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول |  | 31285 |  | چهارم 1401 | 5125.778
0 |  |  |  |  | * | تهیه خاک مناسب از فاصله 15 کیلومتری |  | * |  | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
31065439034 | 23601093616 | 162769 | 284253 | 217449 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری |  | 38587
27204068634 | 2659738414 | 162769 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول |  | 31285
18326310527 | 2238712037 | 162769 | 156833 | 17245 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر |  | 32798
0 |  |  |  |  | * |  | خاکریزی و آبپاشی و کوبیدن با ماشین | *
34922724867 | 17718971948 | 162769 | 280288 | 195934 | m3 |  | پخش و کوبیدن خاکریزیها با 90% تراکم | 24928
0 |  |  |  |  | * |  | حمل خاک تا km10 با ماشین | *
18980903376 | 15700925608 | 414350 | 46707 | 30506 | m3 |  | حمل از 500 متر تا 10 کیلومتر | 31285
0 | [6 empty] | محوطه سازی | *
10525089752 | 8192350574 | 346.5 | 30198667 | 12285545 | m3 |  | تهيه و نصب جدول هاي بتني پيش ساخته با سطح مقطع بيش از 0/05 تا 0/1 مترمربع با بتن به عيار250 كيلو گرم سيمان در مترمكعب | 126281
135566692564 | 93884621521 | 23266 | 6545026 | 4421386 | m3 |  | تهيه، حمل و ريختن شن طبيعي در داخل كانال‌ها، اطراف پي‌ها و لوله‌ها، كف ساختمان‌ها، معابر محوطه‌ها يا هر محل ديگري كه لازم باشد، به‌انضمام پخش و تسطيح آن‌ها در ضخامت‌هاي لازم. | 43759
638115136092 | 280859407682 |  |  |  |  | جمع :
|  |  |  | 126281 | تهيه و نصب جدول هاي بتني پيش ساخته با سطح مقطع بيش از 0/05 تا 0/1 مترمربع با بتن به عيار250 كيلو گرم سيمان در مترمكعب و ملات ماسه سيمان 1:5. | مترمكعب | 1331125

## C.SITE-3
جدول 6 - برآورد اجرا فضای سبز - خارج از فهرست بها
توضیحات | هزینه نهایی | مقدار | هزینه واحد | واحد | شرح | ردیف
| - | - | 62792 | متر مربع | اختصاص حداقل 10 درصد از محدوده تعیین شده کارخانه و تاسیسات به فضای سبز | * |  |  | چهارم 91 | 481.9
%60 سطح فضای سبز برای کاشت چمن و مابقی برای کاشت گیاهان در نظر گرفته شده است. | 277089377 | 4500 | 62792 | متر مکعب | تهیه خاک مناسب مخلوط رسی-شنی با PH مناسب | 1 | 30804 | 164503 | چهارم 1401 | 5125.778
| 1086223660 | 9000 | 62792 | مترمربع | خاکریزی به میزان تقریبی 40سانتی متر | 2 |  | 164503 | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.637
| 86520109 | 900 | 62792 | متر مکعب | خاک رس سرندی به میزان 10 سانتی متری | 3 |  | 164503
| 1086223660 | 9000 | 62792 | متر مکعب | تسطیح و رگلاژ | 4 |  | 164503
| 1086223660 | 9000 | 62792 | مترمربع | کودپاشی | 5 |  | 164503
| 626111391 | 7000 | 62792 | مترمربع | بذر پاشی چمن | 6 |  | 164503
| 626111391 | 7000 | 62792 | مترمربع | اجرت کاشت چمن | 7 |  | 164503
| 626111391 | 7000 | 62792 | مترمربع | نگهداری چمن به مدت یک ماه | 8 |  | 164503
در هر متربع دو عدد | 493861329 | 4000 | 62792 | عدد | تهیه گیاهان پوششی | 9 |  | 164503
| 123952021 | 2000 | 62792 | متر مربع | کندوکوهی و کود دهی گیاهان پوششی | 10 |  | 164503
| 123952021 | 2000 | 62792 | مترمربع | نگهداری گیاهان پوششی به مدت یک ماه | 11 |  | 164503
| 1396265623 | مطابق مشخصات فنی فضای سبز پروژه | یک قلم | یک قلم | احداث سیستم آبیاری پروژه به صورت مکانیزه و تحت فشار ( بارانی- قطره ای ) | *
| 196899296 |  | یک قلم | یک قلم | تهیه لوازم کشاورزی | *
| 7257127901 |  |  |  | مجموع

## C.UG CIVIL-2
جدول7 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - دفن لوله ها (داخل و خارج واحد) و کابل های زیر زمینی (بر اساس ریز متره مندرج در جدول و پیوست2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح | ردیف
[5 empty] | * | کانال کنس با ماشین | * | 1.537 | ضریب =
80919514992 | 25239225649 | 28658 | 2540524 | 2130152 | m3 | کندن زمین در صورت لزوم استفاده از چکش هیدرولیکی در زمین های سنگی و حمل و تخلیه مواد کنده شده تا فاصله ٢٠ متر از مرکز ثقل برداشت | 31584
[5 empty] | * | حمل خاک تا km10 با ماشین | *
3398314635 | 3292374182 | 28658 | 202229 | 167754 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری | 26742 | منطقه ای نمونه. | 1.09
526274359 | 94253371 | 28658 | 32292 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد | 36914 | بالاسری | 1.41
10489054071 | 622676846 | 28658 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 31285 | تجهیزکارگاه | 1
[5 empty] | * | قالب بندی فلزی | * | بروزرسانی | 1
4135145305 | 1976690222 | 1400 | 1565852 | 1123678 | m2 | تهیه مصالح و قالب بندی فلزی در پی ها | 75489
20679545 | 9899797 | 450 | 27846 | 22319 | dm3 | تعبیه انواع درز در مقطع عرضی قطعات بتنی بدون پر کرد آن بر حسب حجم درز. | 44713
[5 empty] | * | تهیه مصالح و اجرای پی | *
15600606449 | 9367189245 | 39975 | 307442 | 283934 | Kg | تهیه، بریدن، خم کردن و کار گذاشتن میلگرد آج دار به قطر ١٢ تا ١٨ میلی متر، برای بتن مسلح با سیم پیچی لازم. | 74449
18551569771 | 8109578280 | 986 | 11374410 | 9803149 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با عیار 350 کیلو سیمان | 57821
54782905 | 25772806 | 1800 | 45076 | 31176 | m4 | اضافه بها براي بتن كف‌سازي‌ها با هر وسيله و به هر ضخامت | 90288
[5 empty] | * | تهیه خاک مناسب از فاصله 15 کیلومتری | * |  | چهارم 91 | 481.9
4165056396 | 1871886549 | 12952 | 284253 | 217449 | m3 | تهیه خاک مناسب از داخل یا خارج از کارگاه شامل کندن و حمل تا 500 متری | 38587 |  | چهارم 1401 | 5125.778
4784359379 | 229919704 | 12952 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول | 31285 |  | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
1370160292 | 206723848 | 12952 | 156833 | 17245 | m3-Km | حمل مواد حاصل از عمليات خاكي،فاصله حمل بيش از10 كيلومتر تا30 كيلومتر باشد، براي هر كيلومتر مازاد بر10 كيلومتر | 32798
[5 empty] | * | تهیه مصالح و اجرای بتن با عیار 150 کیلو سیمان | *
1838477848 | 1132565436 | 156 | 13804203 | 12282487 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با 150 کیلو سیمان | 77378
[6 empty] | ماسه/خاک نرم ریزی در کانال | *
73062565945 | 41678418073 | 9100 | 6271725 | 4521487 | m3 | تهیه، حمل و ریختن ماسه کفی خاکدار در داخل کانال | 34678
[6 empty] | عملیات بنایی | *
2958358698 | 2194510336 | 540 | 7815551 | 4241143 | m3 | سنگ چيني دركف ساختمان (بلوكاژ) با سنگ لاشه. | 43161
[5 empty] | * | کانال کنی با ماشین | * | 1.642 | ضریب =
9971767448 | 4184440087 | 1000 | 14254183 | 4377068 | مترمكعب | بنايي با سنـگ لاشه و ملات ماسه سيمان 1:3 در پي. | 81115 | منطقه ای نمونه. | 1.12
2745343733 | 2009745900 | 1000 | 3666001 | 2092983 | مترمكعب | اضافه بها به رديف‌هاي بنايي با سنـگ لاشه در پي، براي بنايي در ديوار. | 41297 | بالاسری | 1.41
338303158 | 187556639 | 1000 | 231066 | 193559 | مترمربع | اضافه بها به رديف‌هاي خشکه‌چيني و بنايي با سنـگ لاشه، براي سطوح شيب‌دار. | 46282 | تجهیزکارگاه | 1.04
254112606966 | 116422454107 |  |  |  |  | مجموع |  | بروزرسانی | 1

## C.STEEL STRUCTURE (2)
جدول 8 - برآورد اجرا بر اساس فهرست بهای ابنیه 1402 - سازه های فلزی متفرقه (بر اساس ریز متره مندرج در جدول ط پیوست 2)
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست ابنیه 1402 | واحـد | شــــــــرح |  | ردیف
[5 empty] | * | خاکبرداری و پی کنی با ماشین |  | * | 1.537 | ضریب =
8818135502 | 6049342911 | 4410 | 2540524 | 2130152 | m3 | پکندن زمین در صورت لزوم استفاده از چکش هیدرولیکی در زمین های سنگی و حمل و تخلیه مواد کنده شده تا فاصله ٢٠ متر از مرکز ثقل برداشت |  | 31584
0 |  |  |  |  | * | حمل خاک تا km10 با ماشین |  | * |  | منطقه ای نمونه. | 1.09
951477637 | 392074935 | 4410 | 202229 | 167754 | m3 | بارگیری موادحاصل عملیات خاکی و حمل تا فاصله 100 متری |  | 26742 |  | بالاسری | 1.41
109643987 | 23768205 | 4410 | 32292 | 4750 | m3-Km | حمل مواد حاصل از عمليات خاكي برای فاصله حمل بیش از 100متر تا 500متر، به ازایهر 100 متر مازاد |  | 36914 |  | تجهیزکارگاه | 1
1210366708 | 106126213 | 4410 | 278015 | 30506 | m3-Km | حمل مواد حاصل از عمليات خاكي، فاصله حمل بيش از500 متر تا10 كيلومتر ، براي هر كيلومتر مازاد بر500 متر اول |  | 31285 |  | بروزرسانی | 1
[5 empty] | * | قالب بندی فلزی |  | *
19924133989 | 14226812250 | 9754 | 1565852 | 1123678 | m2 | تهیه مصالح و قالب بندی فلزی در پی ها |  | 75489
[5 empty] | * | تهیه مصالح و اجرای پی |  | *
112296527056 | 134316274277 | 444019 | 307442 | 283934 | Kg | تهیه، بریدن، خم کردن و کار گذاشتن میلگرد آج دار به قطر ١٢ تا ١٨ میلی متر، برای بتن مسلح با سیم پیچی لازم. |  | 74449
45056120840 | 32065665837 | 3038 | 11374410 | 9803149 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با عیار 350 کیلو سیمان |  | 57821
383507474 | 279498341 | 3038 | 151494 | 76577 | m3 | اضافه بهایه ردیفهای بتنه ریزی در بتن مسلح |  | 108178
0 |  |  |  |  | * | تهیه مصالح و اجرای بتن با عیار 150 کیلو سیمان |  | *
18131976598 | 13472155378 | 1082.8 | 13804203 | 12282487 | m3 | تهیه و اجرای بتن با شن و ماسه طبیعی با 150 کیلو سیمان |  | 77378
340146613 | 136087791 | 1082.8 | 289224 | 166654 | m3 | اضافه بها برای بتن به ضخامت 15 سانتیمتر و کمتر |  | 61193
[7 empty] | نصب برجها و پایه های روشنایی | *
76781960 | 47170292 | 144 | 604488 | 464471 | Kg | (تهیه ، ساخت و) نصب ستون از یک قوطی و یا لوله(توضیح : با توجه به انکه پایه ها و برجها جداگانه خرید میگردندو در براورد اجرا فقط نصب آن منظور میگردد، از هزینه فهرست بها10،000 ریال /کیلوگرم بابت تامین مواد پایه ها کم شده است) |  | *90102
[6 empty] | تهیه ونصب استند پایپ مخازن |  | *
49246750049 | 31243328983 | 44111 | 812569 | 411891 | Kg | تهیه و ساخت . نصب برجهای فلزی مرتفع (آب) (توضیح : با توجه به مشخصات مشابه استند پایپها با سازه فلزی مخازن مرتفع آب ، از این بند استفاده گردید) |  | 120425
[6 empty] | نصب دکلهای انتقال برق 66 کیلوولت |  | *
152157088851 | 174939866588 | 499996 | 577341 | 233075 | Kg | تهیه، ساخت و نصب ستون های خرپایی به اشکال مختلف ا ز تیرآهن ، ناودانی ، نبش ی و مانن د آن، ب ا اتصا ل اعضای خرپا بدون استفاده از ورق. |  | 67612
[6 empty] | ساخت و نصب پلترمها و سایر سازه های فلزی |  | *
173266089304 | 70748944596 | 178372 | 857246 | 420284 | Kg | تهیه ، ساخت و نصب قاب ها (تا دهانه 30 متر) |  | 87849
[6 empty] | زنگ زدایی و رنگ آمیزی اسکلت فلزی |  | *
170261231181 | 175943428234 | 464729 | 463412 | 537069 | Kg | زنگ زدايي اسكلت‌هاي فلزي، به روش ساچمه پاشي (شات بلاست). |  | 329444 |  | چهارم 91 | 481.9
7075297396 | 3666675948 | 5600 | 948918 | 982053 | m2 | تهيه مصالح و اجراي رنگ اپوكسي برايساير كارهاي فلزي، شامل دوقشر ضد زنگ براي اپوكسي، يك قشرآستر و يك قشر رويه. |  | 155043 |  | چهارم 1401 | 5125.778
952015947575 | 405657590969 |  |  |  |  | جمع : |  |  |  | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366

## C.Buildings
جدول 9- برآورد اجرا بر اساس ابلاغیه شماره 47855 مورخ 1401/12/16 شورای مرکزی سازمان نظام مهندسی ساختمان -احداث ساختمانها
|  |  | هزینه اجرا |  | متراژ بر حسب متر |  | ردیف
|  | 257651255393 |  |  | 936 | احداث اتاق کنترل و مخابرات | 1 | 126998974
|  | 390020013469 |  | 790+ | 480 | احداث پست برق | 2 | 3.3814
|  | 16156193085 |  |  | 56 | احداث نگهبانی | 3
|  | 94729073372 |  |  | 233 | احداث کارگاه مهندسی | 4
|  | 57247066487 |  |  | 260 | احداث ساختمان کمپرسور و دیزل ژنراتور | 5 | منطقه ای نمونه. | 1.09
|  | 5174263231 |  |  | 25 | توسعه پست برق بهره برداری | 6 | بالاسری | 1.41
|  | 24816167999 |  |  | 66 | ساختمان رفاهی بهره برداری | 7 | تجهیزکارگاه | 1
|  | 25433541986 |  |  | 133 | توسعه اتاق کنترل بهره برداری | 8 | بروزرسانی | 1
|  | 62613144433 |  |  | 197 | احداث ساختمان کمپرسور واحد بهره برداری | 9 | ضريب تطبيق | 2
|  | 85618998885 |  |  | 425 | ایستگاه برق 33 کیلو ولت | 10 | چهارم 91 | 481.9
|  | 108282283844 |  |  | 297 | پست برق 3.45/33 کیلوولت | 11 | چهارم 1401 | 5125.778
|  | 13837890853 |  |  | 48 | احداث دیزل ژنراتور پست برق | 12 | ضریب بروزرسانی اعمال شده براساس فهرست ابنیه | 10.6366
|  | 8681063311 |  |  | 29 | احداث نگهبانی پست برق | 13
|  | 99273408551 |  |  | 228 | احداث آزمایشگاه مرکزی | 14
|  | 26822499584 |  |  | 68 | احداث انبار فوم | 15
|  | 26822499584 |  |  | 68 | ساختمان انبار مصرفی | 16
1861057449237
نحوه محاسبه اجرای ساختمانها با توجه به آنکه این پروژه در حد مهندسی مقدماتی و پایه بوده و نقشه معماری فاز یک آن اماده گردیده لیکن نقشه های فاز 2 معماری، نقشه های اجرایی فونداسیون، سازه بتی و فولادی و نیز نقشه های تاسیسات آن تهیه نگردیده و میبایست در مرحله مهندسی تفصیلی انجام شود، لذا امکان تهیه ریز برآورد اقلام و استفاده از فهرست احاد بهای اببنیه در این مرحله از پروژه میسر نمیباشد. لذا برای برآورد هزینه ساخت و اجرای ساختمانها از ابلاغیه شماره 47855/ش م مورخ 1401/12/16شورای مرکزی سازمان نظام مهندسی ساختمان که بر مبنای متراژ ساخت بنا میباشد، استفاده گردیده است که در ذیل ابلاغیه مذکور درج گردیده است:

## C.RETAINING WAL
جدول10 - برآورد اجرا بر اساس فهرست بهای باند و راه 1402 -ساخت دیوار حایل مجاور تپه و سطوح کوهبری شده و شیروانی دورتادور کارخانه
ارزش کار | مبلغ بدون اعمال ضرایب | مقـدار | واحد بــها با اعمال ضریب | واحد بــهامطابق فهرست راه و باند 1402 | واحـد | شــــــــرح | ردیف
[5 empty] | * | کانال کنی با ماشین | * | 1.579 | ضریب =
162901993986 | 56494302793 | 12117 | 9970187 | 4377068 | مترمكعب | بنايي با سنـگ لاشه و ملات ماسه سيمان 1:3 در پي. | 81115 |  |  | منطقه ای نمونه. | 1.12
23194833254 | 21647546714 | 12117 | 1700865 | 2092983 | مترمكعب | اضافه بها به رديف‌هاي بنايي با سنـگ لاشه در پي، براي بنايي در ديوار. | 41297 |  |  | بالاسری | 1.41
2416468851 | 1523606630 | 9000 | 153535 | 193559 | مترمربع | اضافه بها به رديف‌هاي خشکه‌چيني و بنايي با سنـگ لاشه، براي سطوح شيب‌دار. | 46282 |  |  | تجهیزکارگاه | 1
182339590579 | 71626764788 |  |  |  |  | مجموع |  |  |  | بروزرسانی | 1
جدول 11 - برآورد اجرا بر اساس فهرست بهای راه و باند 1402 -تجهیز و برچیدن کارگاه
توضیحات (ارقام بر اساس اطلاعات برداشت شده از پروژه مشابه درج شده است) |  |  |  | مبلغ | واحد | شرح | ردیف |  |  | 4/91 | 469.7
اجاره 400مترمربع مسکونی |  |  |  | 9025202687 | مقطوع | تامين و تجهيز محل سكونت كارمندان و افراد متخصص پيمانكار. | 333830 |  |  | 4/1401 | 5610.6444
احداث 200 متر مربع و تجهیز |  |  |  | 12545318165 | مقطوع | تامين و تجهيز ساختمان‌هاي اداري و دفاتر كار پيمانكار. | 452923 |  |  |  | 11.9452
طبخ روزانه 100 وعده غذا |  |  |  | 121429347323 | مقطوع | تامين كمك هزينه يا تسهيلات لازم براي تهيه غذاي كارگران. | 385806
|  |  |  | 3962643 | مقطوع | تامين وتجهيزساختمانهاي اداري و دفاتركاركارفرما،مهندس مشاورو .آزمايشگاه | 266588
احداث 500 متر انبار سرپوشیده |  |  |  | 18490140343 | مقطوع | تامين ساختمان‌هاي پشتيباني و هزينه تجهيز انبارهاي سرپوشيده، آزمايشگاه پيمانكار و موارد مشابه. | 317038
|  |  |  | 3605047218 | مقطوع | تامين و تجهيز ساختمان‌هاي عمومي، بجز ساختمان‌هاي مسکوني و اداري و دفاتر کار. | 475506
2000 متر مربع |  |  |  | 1660640274 | مقطوع | محوطه سازي. | 552346
ماهیانه 2،000،000 ریال |  |  |  | 83992023 | مقطوع | تامين آب كارگاه و شبكه آب رساني داخل كارگاه. | 300484
ماهیانه 30،000،000 ریال |  |  |  | 10395331262 | مقطوع | تامين برق كارگاه و شبكه برق رساني داخل كارگاه. | 527976
|  |  |  | 462089523 | مقطوع | تامين سيستم‌هاي مخابراتي داخل كارگاه. | 424297
ماهیانه 30،000،000 ریال |  |  |  | 10395331262 | مقطوع | تامين سيستم سوخت رساني كارگاه. | 351048
[5 empty] | مقطوع | تامين راه دسترسي. | 308465
[5 empty] | مقطوع | بيمه تجهيز كارگاه. | 352395
|  |  |  | 9025202687 | مقطوع | برچيدن کارگاه. | 547809
|  |  |  | 156488318616 |  | جمع :

## C.PIPING
جدول 12 - برآورد اجرای لوله کشی وپایپینگ بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | فصل | شرح عمليات
15331497705 | 6989529138 | 4704101 | 1447212 | 1.01 | 824120317 | 5775 | تن | فصل اول-لوله کشی-حمل و جابجایی مصالح | حمل و جابجايي مصالح در محدوده سايت |  |  |  | 8662.5
13926022011 | 5380092880 | 2555482 | 1094007 | 1.02 | 697154863 | 5775 | تن | فصل اول-لوله کشی-حمل و جابجایی مصالح | بخشی که در محل ساخته و نصب می شود | 2.503 | منطقه ای نمونه. | 1.12 | 8662.5
25443170679 | 21642034368 | 21931 | 9500 | 1.03 | 644019960 | 2325036 | تن/کیلومتر | فصل اول-لوله کشی-حمل و جابجایی مصالح | اضافه بهای حمل بیش از 5 کیلومتر |  | بالاسری | 1.48 | 2106706
80301599669 | 29240927931 | 20301198 | 4086617 | 3.01 | 640995554 | 6958.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 2 اينچ با ضخامت كوچكتر يا مساوي 375/0 اينچ |  | تجهیزکارگاه | 1 | 6390
46706040759 | 16674394126 | 18398325 | 9829710 | 3.02 | 769050204 | 1857 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 3 اينچ با ضخامت كوچكتر يامساوي 375/. اينچ |  | بروزرسانی | 1.51 | 2785.5
21334582493 | 11569557042 | 20451784 | 6931475 | 3.03 | 491323179 | 1248 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 4 اينچ با ضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 1872
43115035668 | 19300121418 | 19854980 | 7617972 | 3.04 | 496245744 | 1341 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 6 اينچ با ضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 2011.5
37971803921 | 7097879494 | 47762962 | 18197372 | 3.05 | 811607555 | 823.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 8 اينچ با ضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 1235.25
43310862963 | 11491290353 | 38413433 | 23835163 | 3.06 | 779811856 | 1035 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 10 اينچ با ضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 1552.5
30648434773 | 15081010965 | 50129135 | 16624581 | 3.07 | 378063526 | 856.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 12 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 1284.75
469936313 | 255099355 | 71879909 | 26713922 | 3.08 | 434829041 | 12 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 14 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 18
30446751819 | 9289230640 | 40853133 | 19389597 | 3.09 | 430485675 | 372 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 16 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 558
638250225 | 312999586 | 96883131 | 21239254 | 3.1 | 789743965 | 12 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 18 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 18
32972984729 | 13950394362 | 74032656 | 39222964 | 3.11 | 815021773 | 634.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 20 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ | 1.529 |  |  | 951.75
238983480 | 115061517 | 135057272 | 56907872 | 3.12 | 424821787 | 3 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، كربن استيل با قطر 26 اينچ باضخامت كوچكتر يا مساوي 375/0 اينچ |  |  |  | 4.5
97320204 | 40320233 | 967370 | 194643 | 3.13 | 713062631 | 96 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 1 اینچ |  |  |  | 144
45769086 | 20174066 | 1363646 | 775828 | 3.14 | 737680124 | 33 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 2 اینچ |  |  |  | 49.5
185849817 | 60525149 | 2053842 | 1003812 | 3.15 | 546628233 | 111 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 3 اینچ |  |  |  | 166.5
1298814974 | 804852291 | 2707859 | 1027127 | 3.16 | 707611200 | 726 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 4 اینچ |  |  |  | 1089
188069428 | 66502235 | 2318345 | 1638601 | 3.17 | 812749956 | 48 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 5 اینچ |  |  |  | 72
1198919971 | 515211152 | 5973668 | 1763906 | 3.18 | 561229797 | 228 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 6 اینچ |  |  |  | 342
1017253482 | 436301308 | 3478010 | 1541971 | 3.19 | 524296300 | 234 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 8 اینچ |  |  |  | 351
2365116436 | 915345002 | 5985949 | 2856056 | 3.2 | 701605206 | 297 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 10 اینچ |  |  |  | 445.5
238720356 | 111960525 | 8951189 | 3438489 | 3.21 | 530946603 | 33 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، ساختو نصب در محل، فایبر گلاس ،رزینی قطر 12 اینچ |  |  |  | 49.5
175444214 | 113252550 | 375894 | 142084 | 3.22 | 647098039 | 714 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 2 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 1071
251294682 | 152841075 | 675632 | 221021 | 3.23 | 593108696 | 556.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 3 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 834.75
370717233 | 81281879 | 476133 | 303174 | 3.24 | 686698459 | 442.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 4 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 663.75
52505774 | 13514263 | 1031242 | 483680 | 3.25 | 804744846 | 48 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 5 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 72
282306836 | 116898710 | 1151165 | 462859 | 3.26 | 402680576 | 274.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 6 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 411.75
189271689 | 143949818 | 1947309 | 571024 | 3.27 | 412226525 | 196.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 8 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 294.75
477716513 | 282919899 | 1433220 | 477224 | 3.28 | 788293756 | 378 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 10 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 567
295250141 | 234326809 | 1625196 | 1102921 | 3.29 | 697180780 | 229.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 12 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 344.25
19512000 | 3619795 | 2798539 | 1274224 | 3.3 | 592703712 | 6 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 14 اينچ با كلاس كوچكتر يا مساوي 600 |  |  |  | 9
96687400 | 46867925 | 3217520 | 1344251 | 3.31 | 772438866 | 39 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 16 اينچ با كلاس كوچكتر يا مساوي600 |  |  |  | 58.5
24069658 | 8106233 | 2019571 | 1159472 | 3.32 | 397559304 | 6 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 18 اينچ با كلاس كوچكتر يا مساوي600 |  |  |  | 9
146737012 | 92746707 | 4634615 | 1653320 | 3.33 | 804462055 | 51 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 20 اينچ با كلاس كوچكتر يا مساوي600 |  |  |  | 76.5
7337819 | 3805180 | 5529892 | 2128470 | 3.34 | 608547803 | 1.5 | سرجوش | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب و جوشكاري، بستن فلنجها با قطر 26 اينچ با كلاس كوچكتر يا مساوي600 |  |  |  | 2.25
359470140 | 250141856 | 706156 | 261312 | 3.35 | 436815806 | 922.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 2 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 1383.75
180792268 | 59673894 | 1021707 | 300802 | 3.36 | 458336026 | 219 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 3 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 328.5
187065395 | 81572412 | 1411847 | 437173 | 3.37 | 783860630 | 178.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 4 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 267.75
34126230 | 7398360 | 1286740 | 352730 | 3.38 | 520013419 | 18 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 5 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 27
177437138 | 55653560 | 1409662 | 770285 | 3.39 | 694328048 | 76.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 6 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 114.75
177520711 | 97418082 | 2967489 | 2062892 | 3.4 | 477497346 | 54 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 8 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 81
748911950 | 247789300 | 5397916 | 2113162 | 3.41 | 413679632 | 139.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 10 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 209.25
458297535 | 131345067 | 8032672 | 2262873 | 3.42 | 779717414 | 78 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 12 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 117
8136059 | 2607251 | 5406376 | 2187950 | 3.43 | 704719718 | 1.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 14 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 2.25
92165179 | 33784487 | 5995868 | 3177824 | 3.44 | 484704920 | 13.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 16 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 20.25
9411363 | 6358094 | 7739578 | 3004342 | 3.45 | 405069644 | 1.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 18 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 2.25
117102301 | 88678931 | 8108754 | 2558175 | 3.46 | 510339847 | 19.5 | عدد | فصل سوم-گروه لوله كشي-لوله كشي روزميني ( ادامه..) | لوله كشي روزميني، نصب شيرآلات و سايرملحقات، شير/صافي/مفصل انبساط وقطر 20 اينچ و كلاس مساوي يا كوچكتر از 600 |  |  |  | 29.25
79129097 | 20114735 | 565325 | 348978 | 4.01 | 410931142 | 90 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 40 میلیمتر |  |  |  | 135
342875097 | 181649027 | 640521 | 232619 | 4.02 | 766704231 | 664.5 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 63 میلیمتر |  |  |  | 996.75
693049789 | 184750313 | 1018012 | 425079 | 4.03 | 446141512 | 636 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 90 میلیمتر |  |  |  | 954
734284457 | 249921830 | 1256978 | 312264 | 4.04 | 700771711 | 717 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 110 میلیمتر |  |  |  | 1075.5
119119460 | 68846657 | 1531718 | 333642 | 4.05 | 770630182 | 108 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 125 میلیمتر |  |  |  | 162
265098410 | 101816089 | 1132162 | 451932 | 4.06 | 666597083 | 217.5 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 160 میلیمتر |  |  |  | 326.25
86311005 | 34542906 | 1234890 | 559376 | 4.07 | 637749415 | 63 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 200 میلیمتر |  |  |  | 94.5
1113148741 | 754209502 | 1372336 | 430214 | 4.08 | 448871283 | 1083 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 250 میلیمتر |  |  |  | 1624.5
247877030 | 53684217 | 1883561 | 703355 | 4.09 | 766170383 | 135 | سرجوش | فصل چهارم-گروه لوله كشي- لوله كشي زیر زمینی | لوله كشي زیر زمینی-در محدوده واحد -پلی اتیلن-قطر 315 میلیمتر |  |  |  | 202.5
23089334077 | 5341760016 | 1168658 | 381070 | 5.01 | 477263117 | 9867 | اينچ-قطر | فصل پنجم-گروه لوله كشي- عمليات تكميلي لوله كشي | عمليات تكميلي لوله كشي ، آزمايشات پرتو نگاری |  |  |  | 23176
55447697631 | 20637641783 | 187804 | 85960 | 5.02 | 543799075 | 189750 | اينچ-متر | فصل پنجم-گروه لوله كشي- عمليات تكميلي لوله كشي | عمليات تكميلي لوله كشي ، آزمايشات هیدرو استاتیک |  |  |  | 276407
17717217458 | 6934157856 | 91601 | 26414 | 6.01 | 694988151 | 189750 | اینچ-متر | فصل ششم– گروه لوله کشی- عملیات پیش ساخت راه اندازی لوله کشی | پیش راه اندازی خطوط لوله کشی در همه سایزها |  |  |  | 276407
2985214102 | 1124185185 | 140252 | 59449 | 15.01 | 656576586 | 18300 | کیلوگرم | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-ساخت قطعات-10 تا 50 کیلوگرم |  |  |  | 32254
2365870852 | 1251797369 | 157219 | 50188 | 15.02 | 375106055 | 38551 | کیلوگرم | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-ساخت قطعات-سنگینتر از 50 کیلوگرم |  |  |  | 40531
3661609399 | 1723399551 | 110842 | 57766 | 15.03 | 818032799 | 18300 | کیلوگرم | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-نصب قطعات-10 تا 50 کیلوگرم |  |  |  | 32254
4113715000 | 1129508011 | 154260 | 70210 | 15.04 | 800667467 | 38551 | کیلوگرم | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-نصب قطعات-سنگینتر از 50 کیلوگرم |  |  |  | 40531
1590113625 | 549649520 | 1415553 | 829929 | 15.05 | 381012658 | 855 | عدد | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-ساخت و نصب تکیه گاه های سبکتر از 5 کیلوگرم |  |  |  | 1282.5
2644638751 | 748051982 | 3967393 | 1358872 | 15.06 | 579686148 | 855 | عدد | فصل پانزدهم-ساخت و نصب سازه های فلزی و تکیه گاه ها | ساخت و نصب سازه های فلزی و تکیه گاه ها-ساخت و نصب تکیه گاه های 5 تا 10 کیلوگرم |  |  |  | 1282.5
57660953497 | 18115579537 | 1235523 | 412780 | 17.01 | 568767093 | 45123 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | رنگ آميزي، كارهاي لوله كشي، سند بلاست |  |  |  | 47619
8874446477 | 5336720405 | 223756 | 144493 | 17.02 | 596511653 | 37502 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | رنگ آميزي، كارهاي لوله كشي، رنگ در کارگاه |  |  |  | 51366
2431920765 | 1317332834 | 526589 | 340638 | 17.03 | 518221197 | 3960 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | رنگ آميزي، كارهاي لوله كشي، رنگ در محل نصب- قطر زیر 2اينچ |  |  |  | 5940
27293024238 | 11350007132 | 555706 | 286296 | 17.04 | 729812946 | 55866 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | رنگ آميزي، كارهاي لوله كشي، رنگ در محل نصب قطر بزرگتر يا مساوي 2 اينچ |  |  |  | 65623
35323929542 | 8060366086 | 1093331 | 440985 | 17.05 | 609596773 | 40679 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | مصالح رنگ آمیزی |  |  |  | 72453
80553715034 | 39967971727 | 790186 | 628129 | 17.06 | 376429030 | 79600 | متر مربع | فصل هفدهم- گروه نصب تجهيزات، رنگ وعايق-عمليات زنگ زدايي و رنگ آميزي | مصالح رنگ آمیزی |  |  |  | 130202
92978967 | 32018903 | 1151483 | 512841 | 18.01 | 716697323 | 68.1 | متر | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم لوله های راسته-2 تا 6 اینچ |  |  |  | 102.15
1145495204 | 272151979 | 1588168 | 521475 | 18.02 | 797144784 | 728.1 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم لوله های راسته-8 تا 12 اینچ |  |  |  | 1092.15
119337026 | 56689075 | 1341555 | 711952 | 18.03 | 443655598 | 135 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم شیرآلات و فیتینگ ها-زیر 2 اینچ |  |  |  | 202.5
177940271 | 99766132 | 2386550 | 1175246 | 18.04 | 590752752 | 84 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم شیرآلات و فیتینگ ها- 2 تا 6 اینچ |  |  |  | 126
1226264413 | 347000079 | 4139752 | 1855406 | 18.05 | 681964102 | 315 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم شیرآلات و فیتینگ ها-8 تا 12 اینچ |  |  |  | 472.5
23871775 | 16641680 | 813991 | 205986 | 18.06 | 709478915 | 48 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم فلنجها-زیر 2 اینچ |  |  |  | 72
36647538 | 17541758 | 1338051 | 359450 | 18.07 | 578998265 | 33 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم فلنجها-2 تا 6 اینچ |  |  |  | 49.5
559633087 | 154221081 | 2603614 | 777833 | 18.08 | 780067279 | 246 | عدد | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | عایقکاری گرم فلنجها-8 تا 12 اینچ |  |  |  | 369
3215767445 | 1140146522 | 444601 | 189363 | 18.09 | 528310053 | 8137.5 | اینچ/متر | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | مصالح عایقکاری گرم لوله های راسته |  |  |  | 10940
3128131740 | 1713843121 | 1065504 | 429558 | 18.1 | 693598410 | 3700.5 | اینچ/قطر | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | مصالح عایقکاری گرم شیرآلات و فیتینگ ها |  |  |  | 5550.75
600017108 | 155917592 | 279006 | 90060 | 18.11 | 817690429 | 2646 | اینچ/قطر | فصل هجدهم - نصب تجهيزات، رنگ و عایق - عمليات عایقکاری حرارتی، رطوبتی، ضدحریق و خوردگی | مصالح عایقکاری گرم فلنجها |  |  |  | 3969
1066671998559 | 242489881221 | [7 empty] | مجموع

## C.mECHANICAL
جدول 13 - برآورد اجراو نصب تجهیزات مکانیک بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | شماره تجهیز |  | شرح | ردیف |  |  |  | وزن واحد
[9 empty] | نصب دیسالترها و هیترها | 1
3949178670 | 2947971084 | 40027 | 13683 | کد 591111 ردیف 4 | 108555 | Kg | DE | -001-A/B | 1at TRAIN DESALTER | 1.1 |  |  |  | 90695
3949178670 | 2947971084 | 40027 | 13683 | کد 591111 ردیف 4 | 108555 | Kg | DE | -002-A/B | 2nd TRAIN DESALTER | 1.2 |  |  |  | 90695
5433051395 | 1209835918 | 54565853 | 17053448 | کد 591231 ردیف2 | 120 | TON | H | -001-A1/A2 | CRUDE OIL INDIRECT FIRED HEATER | 1.3 |  |  |  | 60
5433051395 | 1209835918 | 54565853 | 17053448 | کد 591231 ردیف 2 | 120 | TON | H | -001-B1/B2 | CRUDE OIL INDIRECT FIRED HEATER | 1.4 |  |  |  | 60
| 0 | [7 empty] | نصب مبدلهای حرارتی | 2 |  |  |  |  | منطقه ای نمونه. | 1.12
123595437 | 52536156 | 53497 | 19487 | کد 591111 ردیف 1 | 5000 | Kg | E | -001-A/B | SALTY CRUDE / DESALTED CRUDE HEAT EXCHANGER | 2.1 |  |  |  | 2500 | بالاسری | 1.48
219630285 | 62194380 | 53497 | 19487 | کد 591111 ردیف 1 | 4000 | Kg | E | -002-A/B | WATER / WATER HEAT EXCHANGER | 2.2 |  |  |  | 2000 | تجهیزکارگاه | 1
| 0 | [7 empty] | نصب پمپ ها | 3 |  |  |  |  | بروزرسانی | 1.515
460326687 | 193061837 | 71002 | 23209 | کد 591001 ردیف 04 | 8000 | Kg | P | -001-A/B | MAIN TRANSFER PUMPS | 3.1 |  |  |  | 4000
301226346 | 142355912 | 71002 | 23209 | کد 591001 ردیف 04 | 5600 | Kg | P | -002-A/B | AUXILLIARY TRANSFER PUMPS | 3.2 |  |  |  | 2800
225986937 | 142193775 | 96527 | 42286 | کد 591001 ردیف 03 | 3000 | Kg | P | -003-A/B | OFF-SPEC PUMPS | 3.3 |  |  |  | 1500
139681464 | 87651592 | 216633 | 72950 | کد 591001 ردیف 01 | 1000 | Kg | P | -005-A/B | DEGASSING WATER PUMPS | 3.4 |  |  |  | 500
95406274 | 44777617 | 158503 | 65583 | کد 591001 ردیف 02 | 1000 | Kg | P | -103 | DILUTION WATER PUMPS | 3.5 |  |  |  | 1000
190732388 | 63475553 | 158503 | 65583 | کد 591001 ردیف 02 | 1500 | Kg | P | -106-A1/A2 | DILUTION WATER PUMPS | 3.6 |  | ضریب | 2.511 | 750
108268389 | 39818605 | 216633 | 72950 | کد 591001 ردیف 01 | 500 | Kg | P | -601-A/B | FLARE K.O DRUM LIQUID PUMPS | 3.7 |  |  |  | 250
102734026 | 43539121 | 216633 | 72950 | کد 591001 ردیف 01 | 600 | Kg | P | -102-A/B | DEAERATED WATER PUMPS | 3.8 |  |  |  | 300
82279586 | 33720862 | 216633 | 72950 | کد 591001 ردیف 01 | 400 | Kg | P | -105 | DEAERATED WATER PUMPS | 3.9 |  |  |  | 400
42171692 | 15231510 | 216633 | 72950 | کد 591001 ردیف 01 | 300 | Kg | P | -104 | POTABLE WATER FILLING PUMP | 3.10 |  |  |  | 300
287382852 | 143183044 | 96527 | 42286 | کد 591001 ردیف 03 | 4200 | Kg | P | -201-A/B | WATER INJECTION MAIN PUMPS | 3.11 |  |  |  | 2100
299277065 | 103029909 | 96527 | 42286 | کد 591001 ردیف 03 | 2800 | Kg | P | -206-A/B/C | WATER INJECTION BOOSTER PUMPS | 3.12 |  |  |  | 1400
108268389 | 39818605 | 216633 | 72950 | کد 591001 ردیف 01 | 500 | Kg | P | -501-A/B/C | CHEMICAL INJECTION PORTABLE PUMPS | 3.13 |  |  |  | 250
119567466 | 79627362 | 216633 | 72950 | کد 591001 ردیف 01 | 900 | Kg | P | -701-A/B | HC CLOSED DRAIN TRANSFER PUMPS | 3.14 |  |  |  | 450
51565829 | 17085700 | 216633 | 72950 | کد 591001 ردیف 01 | 250 | Kg | P | -702 | HC CLOSED DRAIN DRUM SUMP PUMP | 3.15 |  |  |  | 250
108268389 | 39818605 | 216633 | 72950 | کد 591001 ردیف 01 | 500 | Kg | P | -703-A/B | CLEAN WATER PUMPS | 3.16 |  |  |  | 250
102734026 | 43539121 | 216633 | 72950 | کد 591001 ردیف 01 | 600 | Kg | P | -704-A/B | RECOVERED WASTE OIL PUMPS | 3.17 |  |  |  | 300
51565829 | 17085700 | 216633 | 72950 | کد 591001 ردیف 01 | 250 | Kg | P | -750 | OILY WATER SEPARATOR PUMP | 3.18 |  |  |  | 250
108268389 | 39818605 | 216633 | 72950 | کد 591001 ردیف 01 | 500 | Kg | P | -705-A/B | DIRTY OIL PUMPS | 3.19 |  |  |  | 250
102734026 | 43539121 | 216633 | 72950 | کد 591001 ردیف 01 | 600 | Kg | P | -706-A/B | RECOVERED WASTE WATER PUMPS | 3.2 |  |  |  | 300
51565829 | 17085700 | 216633 | 72950 | کد 591001 ردیف 01 | 250 | Kg | P | -801 | DIESEL OIL PUMP | 3.21 |  |  |  | 250
498970598 | 97109815 | 96527 | 42286 | کد 591001 ردیف 03 | 4000 | Kg | P | -901 | FIRE WATER MAIN ELECTRICAL PUMP | 3.22 |  |  |  | 2000
263072014 | 106215887 | 69238 | 20045 | کد 591001 ردیف 05 | 5500 | Kg | P | 902 | FIRE WATER MAIN DESEL PUMP | 3.23 |  |  |  | 5500
132878838 | 45401083 | 216633 | 72950 | کد 591001 ردیف 01 | 800 | Kg | P | -903-A/B | FIRE WATER JOCKEY PUMPS | 3.24 |  |  |  | 400
132878838 | 45401083 | 216633 | 72950 | کد 591001 ردیف 01 | 800 | Kg | P | -904 | FIRE WATER LOADING PUMP | 3.25 |  |  |  | 400
| 0 | [7 empty] | نصب بسته های فرایندی | 4
1769463498 | 672818006 | 56813 | 15220 | کد 591101 -ردیف 3 | 23825 | No. | PK | -101 | VACUUM DEAERATOR PACKAGE | 4.1 |  |  |  | 23825
3896945615 | 778817575 | 56813 | 15220 | کد 591101 -ردیف 3 | 32514 | Kg | PK | -201-A/B | IGF PACKAGE | 4.2 |  |  |  | 32514
1769463498 | 672818006 | 56813 | 15220 | کد 591101 -ردیف 3 | 23825 | Kg | PK | -202 | NUTSHELL FILTER PACKAGE | 4.3 |  |  |  | 23825
1054364187 | 257225494 | 69757 | 24942 | کد 591011 ردیف 02 | 8338 | Kg | PK | -401-A/B | AIR COMPRESSOR PACKAGE | 4.4 |  |  |  | 5300
75831376 | 31555706 | 46964 | 34070 | کد 591101 ردیف 01 | 1000 | Kg | PK | -402 | AIR DRYER PACKAGE | 4.5 |  |  |  | 1000
1216708533 | 403720608 | 158690 | 34968 | کد 591011 ردیف 01 | 7600 | Kg | PK | -002-A/B | AIR COMPRESSOR PACKAGE | 4.6 |  |  |  | 3800
75831376 | 31555706 | 46964 | 34070 | کد 591101 ردیف 01 | 1000 | Kg | PK | -003 | AIR DRYER PACKAGE | 4.7 |  |  |  | 1000
221918094 | 77015806 | 57534 | 35860 | کد 591101 -ردیف 2 | 3000 | Kg | PK | -501 | DEMULSIFIER INJECTION PACKAGE | 4.8 |  |  |  | 3000
352134505 | 217976095 | 57534 | 35860 | کد 591101 -ردیف 2 | 6000 | Kg | PK | -502-A/B | DEMULSIFIER INJECTION PACKAGE | 4.9 |  |  |  | 3000
184276964 | 78752017 | 46964 | 34070 | کد 591101 ردیف 01 | 2000 | Kg | PK | -503 | OXYGEN SCAVENGER INJECTION PACKAGE | 4.10 |  |  |  | 2000
221918094 | 77015806 | 57534 | 35860 | کد 591101 -ردیف 2 | 3000 | Kg | PK | -504 | CORROSION INHIBITOR INJECTION PACKAGE | 4.11 |  |  |  | 3000
221918094 | 77015806 | 57534 | 35860 | کد 591101 -ردیف 2 | 3000 | Kg | PK | -505 | REVERSE DEMULSIFIER INJECTION PACKAGE | 4.12 |  |  |  | 3000
402475471 | 146869491 | 56813 | 15220 | کد 591101 -ردیف 3 | 6000 | Kg | PK | -506-A | BIOCIDE INJECTION PACKAGE (TYPE A) | 4.13 |  |  |  | 3000
402475471 | 146869491 | 56813 | 15220 | کد 591101 -ردیف 3 | 6000 | Kg | PK | -506-B | BIOCIDE INJECTION PACKAGE (TYPE B) | 4.14 |  |  |  | 3000
221918094 | 77015806 | 57534 | 35860 | کد 591101 -ردیف 2 | 3000 | Kg | PK | -507 | ANTI SCALE INJECTION PACKAGE | 4.15 |  |  |  | 3000
| 0 | [7 empty] | نصب مخازن تحت فشار | 5
211849061 | 136878549 | 53497 | 19487 | کد 591111 ردیف 1 | 6100 | Kg | V | -601 | FLARE K.O. DRUM | 5.1 |  |  |  | 6100
64881251 | 15949927 | 31283 | 27455 | کد 591112 ردیف 1 | 1000 | Kg | V | -301 | FUEL GAS K.O. DRUM | 5.2 |  |  |  | 1000
859531340 | 379720788 | 75307 | 20410 | کد 591112 ردیف 2 | 8140 | Kg | V | -401 | AIR RECIEVER | 5.3 |  |  |  | 8140
10784680958 | 6047572801 | 40027 | 13683 | کد 591111 ردیف 4 | 305647 | Kg | V | -001-A/B | FREE WATER K.O DRUM | 5.4 |  |  |  | 305647
754851937 | 526460793 | 49296 | 12065 | کد 591111 ردیف 2 | 34097 | Kg | V | -701 | HC CLOSED DRAIN DRUM | 5.5 |  |  |  | 34097
175522191 | 44817474 | 35538 | 14507 | کد 581113 ردیف 1 | 6100 | Kg | V | -801 | DIESEL STORAGE TANK | 5.6 |  |  |  | 6100
690403018 | 213566354 | 49296 | 12065 | کد 591111 ردیف 2 | 30477 | Kg |  |  | LUNCHER AND RECEIVER | 5.7
| 0 | [7 empty] | نصب فلرها | 6
315541632 | 150086092 | 126518292 | 30487235 | کد 591241 ردیف 01 | 3 | Kg | PK | -602 | FLARE PACKAGE | 6.1 |  |  |  | 3000
317546587 | 56619451 | 126518292 | 30487235 | کد 591241 ردیف 01 | 2.5 | Kg | PK | -603 | COLD FLARE PACKAGE | 6.2 |  |  |  | 2500
| 0 | [7 empty] | نصب جرثقیلهای سقفی | 7
4168325234 | 1173245115 | 59994751 | 25387020 | کد 591401 - ردیف 1 | 12x5 تن | TON | CR | 001~0012 | CRANES | 7.1 |  |  |  | 40
| 0 | [7 empty] | نصب مخازن اتمسفریک | 8
| 0 | [5 empty] | TK | -003 | OFF-SPEC TANK : نصب و اجرای مخزن | 8.1 | ID= | 25 | 142134
570721219 | 338670300 | 4771235 | 1766151 | کد 591301 - ردیف 2 | 216.5 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.1.1 | HEIGHT= | 15
3823923661 | 1616477496 | 167198804 | 59602225 | کد 591302 - ردیف 2 | 38.5325 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.1.2 |  |  | 45958
27730724898 | 11365116792 | 268054752 | 114621399 | کد 591303 - ردیف 2 | 116.3156 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.1.3 |  |  | 73772
4582691895 | 2139448457 | 153367341 | 81362047 | کد 591304 - ردیف 2 | 30.826 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.1.4 |  |  | 37086
4606927870 | 1932107438 | 325830 | 115609 | کد 591308 | 37086 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.1.5 |  |  | 37086
1112400070 | 249999106 | 392454 | 104340 | کد 591307 | 3000 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.1.6
442730758 | 346466211 | 1525127 | 368398 | کد 591741 - ردیف 1 | 490.8594 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.1.7
3083823796 | 891409258 | 1505393 | 766092 | کد 591741 - ردیف 3 | 1767.0938 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.1.8 |  |  | 0
100731609 | 81681319 | 284539 | 78548 | کد 591741 - ردیف 4 | 785.375 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.1.9
2574881683 | 992334485 | 1505393 | 766092 | کد 591741 - ردیف 3 | 1668.9219 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.1.10 |  |  | 0
100731609 | 81681319 | 284539 | 78548 | کد 591741 - ردیف 4 | 785.375 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.1.11 |  |  | 0
905410514 | 595013396 | 220766 | 150439 | کد 591742 - ردیف 2 | 3926.875 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.1.12 |  |  | 0
69412409 | 27567582 | 42156 | 19728 | کد 591742 - ردیف 3 | 1570.75 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.1.13 |  |  | 0
1771310475 | 764165208 | 1092026 | 440985 | کد 591731- ردیف 3 | 1767.0938 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.1.14
4013568617 | 1350142493 | 1380967 | 628129 | کد 591731- ردیف 12 | 3534.1875 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.1.15
4365298055 | 3194135430 | 1380967 | 628129 | کد 591731- ردیف 12 | 5006.7656 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (سه لایه پرایمر،میانی و نهایی) | 8.1.16
1560162869 | 380796064 | 251535 | 75851 | کد591901ردیف 2 | 7362.8906 | M3 |  |  | تست هیدرواستاتیک | 8.1.17
40154145 | 10331132 | 38457 | 18063 | کد591921 | 744.5156 | CM |  |  | آزمایش پرتو نگاری | 8.1.18
0 | 0 | [5 empty] | TK | -101 | DILUTION WATER TANK : نصب و اجرای مخزن | 8.2 |  | 12.5 | 75997
319048836 | 140303258 | 5241240 | 1979728 | کد 591301 - ردیف 1 | 62 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.2.1 |  | 12
1407312062 | 757230724 | 135595388 | 80962652 | کد 591302 - ردیف 1 | 9.6331 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.2.2 |  |  | 9633.1152
10920905456 | 3864913193 | 281690806 | 124603271 | کد 591303 - ردیف 1 | 36.9539 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.2.3 |  |  | 48888
1308245204 | 451530738 | 249345872 | 57199201 | کد 591304 - ردیف 1 | 7.7065 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.2.4 |  |  | 7706.4922
1264643452 | 493055609 | 325830 | 115609 | کد 591308 | 7706.4922 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.2.5 |  |  | 7706.4922
921319359 | 214514463 | 392454 | 104340 | کد 591307 | 2500 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.2.6
137866079 | 74536039 | 1525127 | 368398 | کد 591741 - ردیف 1 | 122.7148 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.2.7
871167948 | 471416455 | 1505393 | 766092 | کد 591741 - ردیف 3 | 618.4828 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.2.8 |  |  | 0
78491892 | 30362206 | 284539 | 78548 | کد 591741 - ردیف 4 | 274.8813 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.2.9
1096713201 | 500879849 | 1505393 | 766092 | کد 591741 - ردیف 3 | 593.9398 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.2.10 |  |  | 0
78491892 | 30362206 | 284539 | 78548 | کد 591741 - ردیف 4 | 274.8813 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.2.11 |  |  | 0
412129845 | 134192951 | 220766 | 150439 | کد 591742 - ردیف 2 | 1335.1375 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.2.12 |  |  | 0
22517099 | 10072167 | 42156 | 19728 | کد 591742 - ردیف 3 | 549.7625 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.2.13 |  |  | 0
615046440 | 161466167 | 1092026 | 440985 | کد 591731- ردیف 3 | 618.4828 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.2.14
1205921395 | 707221552 | 1380967 | 628129 | کد 591731- ردیف 12 | 1236.9656 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.2.15
1794639657 | 1151155693 | 1380967 | 628129 | کد 591731- ردیف 12 | 1781.8195 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (سه لایه پرایمر،میانی و نهایی) | 8.2.16
471360953 | 185050935 | 381634 | 128133 | کد591901ردیف 1 | 1472.5781 | M3 |  |  | تست هیدرواستاتیک | 8.2.17
30760157 | 11997437 | 38457 | 18063 | کد591921 | 507.2578 | CM |  |  | آزمایش پرتو نگاری | 8.2.18
0 | 0 | [5 empty] | TK | -102 | POTABLE WATER TANK : نصب و اجرای مخزن | 8.3 |  | 4 | 16620
139017896 | 57699804 | 5241240 | 1979728 | کد 591301 - ردیف 1 | 25.5 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.3.1 |  | 2.6
160831867 | 80499645 | 135595388 | 80962652 | کد 591302 - ردیف 1 | 0.98643 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.3.2 |  |  | 986.431
1032744487 | 611867410 | 281690806 | 124603271 | کد 591303 - ردیف 1 | 5.7244 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.3.3 |  |  | 5724.4242
157639170 | 61464932 | 249345872 | 57199201 | کد 591304 - ردیف 1 | 0.78914 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.3.4 |  |  | 789.1448
1910468121 | 788921328 | 72170 | 36901 | کد 90501 فهرست ابنیه | 22116 | Kg |  |  | نصب و جوشکاری سازه نگهدارنده مخزن مخزن | 8.3.5 |  |  | 22116
279419305 | 105894159 | 72170 | 36901 | کد 90501 فهرست ابنیه | 4000 | Kg |  |  | نصب و جوشکاری پله بدنه و سایر متعلقات | 8.3.6
13689579 | 4345692 | 1525127 | 368398 | کد 591741 - ردیف 1 | 12.566 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.3.7
78679045 | 31587299 | 1505393 | 766092 | کد 591741 - ردیف 3 | 47.7508 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.3.8 |  |  | 0
0 | 0 | 284539 | 78548 | کد 591741 - ردیف 4 | 0 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.3.9
84993642 | 18603747 | 1505393 | 766092 | کد 591741 - ردیف 3 | 45.2376 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.3.10 |  |  | 0
0 | 0 | 284539 | 78548 | کد 591741 - ردیف 4 | 0 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.3.11 |  |  | 0
27290958 | 12725985 | 220766 | 150439 | کد 591742 - ردیف 2 | 105.5544 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.3.12 |  |  | 0
0 | 0 | 42156 | 19728 | کد 591742 - ردیف 3 | 0 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.3.13 |  |  | 0
45821305 | 21003800 | 1092026 | 440985 | کد 591731- ردیف 3 | 47.7508 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.3.14
134183640 | 30686194 | 1380967 | 628129 | کد 591731- ردیف 12 | 95.5016 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.3.15
151601139 | 90252415 | 1380967 | 628129 | کد 591731- ردیف 12 | 135.7128 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (سه لایه پرایمر،میانی و نهایی) | 8.3.16
7933602 | 4706040 | 381634 | 128133 | کد591901ردیف 1 | 32.6716 | M3 |  |  | تست هیدرواستاتیک | 8.3.17
5194016 | 2636073 | 38457 | 18063 | کد591921 | 125.1225 | CM |  |  | آزمایش پرتو نگاری | 8.3.18
0 | 0 | [5 empty] | TK | -201 | DISPOSAL TANK : نصب و اجرای مخزن | 8.4 |  | 10 | 39559
269742942 | 93507411 | 5241240 | 1979728 | کد 591301 - ردیف 1 | 40 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.4.1 |  | 12
890111130 | 259225218 | 135595388 | 80962652 | کد 591302 - ردیف 1 | 6.1652 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.4.2 |  |  | 6165.1938
6310768793 | 1819437765 | 281690806 | 124603271 | کد 591303 - ردیف 1 | 23.9705 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.4.3 |  |  | 15499
679671692 | 266725160 | 249345872 | 57199201 | کد 591304 - ردیف 1 | 4.9322 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.4.4 |  |  | 4932.155
1619479906 | 446242469 | 325830 | 115609 | کد 591308 | 4932.155 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.4.5 |  |  | 4932.155
921319359 | 214514463 | 392454 | 104340 | کد 591307 | 2500 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.4.6
102415925 | 42863297 | 1525127 | 368398 | کد 591741 - ردیف 1 | 78.5375 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.4.7
539620107 | 251656923 | 1505393 | 766092 | کد 591741 - ردیف 3 | 471.225 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.4.8 |  |  | 0
34026766 | 24531857 | 284539 | 78548 | کد 591741 - ردیف 4 | 219.905 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.4.9
796310770 | 373824640 | 1505393 | 766092 | کد 591741 - ردیف 3 | 455.5175 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.4.10 |  |  | 0
34026766 | 24531857 | 284539 | 78548 | کد 591741 - ردیف 4 | 219.905 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.4.11 |  |  | 0
258113843 | 90998219 | 220766 | 150439 | کد 591742 - ردیف 2 | 1005.28 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.4.12 |  |  | 0
14023887 | 6868689 | 42156 | 19728 | کد 591742 - ردیف 3 | 439.81 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.4.13 |  |  | 0
323082718 | 104241829 | 1092026 | 440985 | کد 591731- ردیف 3 | 471.225 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.4.14
1313029335 | 377725702 | 1380967 | 628129 | کد 591731- ردیف 12 | 942.45 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.4.15
1335595788 | 523162884 | 1237585 | 420321 | خارج از فهرست بها | 1366.5525 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (EPOXY GLASS FLAKE) | 8.4.16
181627831 | 101783660 | 381634 | 128133 | کد591901ردیف 1 | 942.45 | M3 |  |  | تست هیدرواستاتیک | 8.4.17
31555034 | 12943428 | 38457 | 18063 | کد591921 | 477.8062 | CM |  |  | آزمایش پرتو نگاری | 8.4.18
0 | 0 | [5 empty] | OS | -201 | OIL SKIMMER TANK : نصب و اجرای مخزن | 8.5 |  | 10 | 40625
271041285 | 111518131 | 5241240 | 1979728 | کد 591301 - ردیف 1 | 45.9 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.5.1 |  | 12
890111130 | 259225218 | 135595388 | 80962652 | کد 591302 - ردیف 1 | 6.1652 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.5.2 |  |  | 6165.1938
4723933866 | 2804888600 | 281690806 | 124603271 | کد 591303 - ردیف 1 | 29.8705 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.5.3 |  |  | 32154
679671692 | 266725160 | 249345872 | 57199201 | کد 591304 - ردیف 1 | 4.9322 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.5.4 |  |  | 4932.155
1619479906 | 446242469 | 325830 | 115609 | کد 591308 | 4932.155 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.5.5 |  |  | 4932.155
921319359 | 214514463 | 392454 | 104340 | کد 591307 | 2500 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.5.6
102415925 | 42863297 | 1525127 | 368398 | کد 591741 - ردیف 1 | 78.5375 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.5.7
539620107 | 251656923 | 1505393 | 766092 | کد 591741 - ردیف 3 | 471.225 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.5.8 |  |  | 0
34026766 | 24531857 | 284539 | 78548 | کد 591741 - ردیف 4 | 219.905 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.5.9
796310770 | 373824640 | 1505393 | 766092 | کد 591741 - ردیف 3 | 455.5175 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.5.10 |  |  | 0
34026766 | 24531857 | 284539 | 78548 | کد 591741 - ردیف 4 | 219.905 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.5.11 |  |  | 0
258113843 | 90998219 | 220766 | 150439 | کد 591742 - ردیف 2 | 1005.28 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.5.12 |  |  | 0
14023887 | 6868689 | 42156 | 19728 | کد 591742 - ردیف 3 | 439.81 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.5.13 |  |  | 0
323082718 | 104241829 | 1092026 | 440985 | کد 591731- ردیف 3 | 471.225 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.5.14
1313029335 | 377725702 | 1380967 | 628129 | کد 591731- ردیف 12 | 942.45 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.5.15
733252549 | 523162884 | 420321 | - | خارج از فهرست بها | 1366.5525 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (EPOXY GLASS FLAKE) | 8.5.16
181627831 | 101783660 | 381634 | 128133 | کد591901ردیف 1 | 942.45 | M3 |  |  | تست هیدرواستاتیک | 8.5.17
31555034 | 12943428 | 38457 | 18063 | کد591921 | 477.8062 | CM |  |  | آزمایش پرتو نگاری | 8.5.18
2023895755 | 2023895755 | 273127 | - | خارج از فهرست بها | 6000 | Kg |  |  | نصب اجزا داخلی اسکیمر | 8.5.19
0 | 0 | [5 empty] | TK | -701 | DIRTY OILTANK : نصب و اجرای مخزن | 8.6 |  | 3 | 3600
13684487 | 8882143 | 5241240 | 1979728 | کد 591301 - ردیف 1 | 3.6 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.6.1 |  | 3
60686619 | 21918288 | 135595388 | 80962652 | کد 591302 - ردیف 1 | 0.55487 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.6.2 |  |  | 554.8674
432461160 | 146313567 | 281690806 | 124603271 | کد 591303 - ردیف 1 | 2.1573 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.6.3 |  |  | 2157.3447
110012750 | 36463659 | 249345872 | 57199201 | کد 591304 - ردیف 1 | 0.44389 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.6.4 |  |  | 443.894
74643003 | 56074130 | 325830 | 115609 | کد 591308 | 443.894 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.6.5 |  |  | 443.894
73527 | 33790 | 392454 | 104340 | کد 591307 | 0.3 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.6.6
12529729 | 2912873 | 1525127 | 368398 | کد 591741 - ردیف 1 | 7.0684 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.6.7
41785490 | 25147999 | 1505393 | 766092 | کد 591741 - ردیف 3 | 36.7555 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.6.8 |  |  | 0
0 | 0 | 284539 | 78548 | کد 591741 - ردیف 4 |  | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.6.9
44993674 | 26483919 | 1505393 | 766092 | کد 591741 - ردیف 3 | 35.3419 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.6.10 |  |  | 0
0 | 0 | 284539 | 78548 | کد 591741 - ردیف 4 |  | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.6.11 |  |  | 0
17489085 | 9419439 | 220766 | 150439 | کد 591742 - ردیف 2 | 79.1658 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.6.12 |  |  | 0
0 | 0 | 42156 | 19728 | کد 591742 - ردیف 3 | 0 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.6.13 |  |  | 0
35326744 | 10510232 | 1092026 | 440985 | کد 591731- ردیف 3 | 36.7555 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.6.14
73725826 | 30931472 | 1380967 | 628129 | کد 591731- ردیف 12 | 73.5111 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.6.15
112777258 | 31532254 | 1237585 | 420321 | خارج از فهرست بها | 106.0256 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (EPOXY GLASS FLAKE) | 8.6.16
5740280 | 2411691 | 381634 | 128133 | کد591901ردیف 1 | 21.2051 | M3 |  |  | تست هیدرواستاتیک | 8.6.17
4282011 | 2212040 | 38457 | 18063 | کد591921 | 125.3419 | CM |  |  | آزمایش پرتو نگاری | 8.6.18
0 | [6 empty] | TK | -902-A/B | FIRE WATER STORAGE: نصب و اجرای مخزن | 8.7 |  | 11 | 98646
574771706 | 184178777 | 5241240 | 1979728 | کد 591301 - ردیف 1 | 144.6 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.7.1 |  | 12
2308596421 | 1043955614 | 135595388 | 80962652 | کد 591302 - ردیف 1 | 14.9198 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.7.2 |  |  | 17436
43525520006 | 26623949446 | 281690806 | 124603271 | کد 591303 - ردیف 1 | 238.4728 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.7.3 |  |  | 277545
2320116086 | 1205184901 | 249345872 | 57199201 | کد 591304 - ردیف 1 | 11.9358 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.7.4 |  |  | 8992
4639180726 | 2817366244 | 325830 | 115609 | کد 591308 | 17215 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.7.5 |  |  | 17215
921319359 | 214514463 | 392454 | 104340 | کد 591307 | 2500 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.7.6
121407836 | 31806961 | 1525127 | 368398 | کد 591741 - ردیف 1 | 95.0304 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.7.7
724320831 | 349549137 | 1505393 | 766092 | کد 591741 - ردیف 3 | 528.7144 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.7.8
67922426 | 14596706 | 284539 | 78548 | کد 591741 - ردیف 4 | 241.8955 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.7.9
921557572 | 423159909 | 1505393 | 766092 | کد 591741 - ردیف 3 | 509.7084 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.7.10
67922426 | 14596706 | 284539 | 78548 | کد 591741 - ردیف 4 | 241.8955 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.7.11
420933548 | 138886421 | 220766 | 150439 | کد 591742 - ردیف 2 | 1133.4532 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.7.12
19975665 | 5542576 | 42156 | 19728 | کد 591742 - ردیف 3 | 483.791 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.7.13
517134715 | 207581681 | 1092026 | 440985 | کد 591731- ردیف 3 | 528.7144 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.7.14
1244195035 | 634742886 | 1380967 | 628129 | کد 591731- ردیف 12 | 1057.4289 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.7.15
2346973804 | 590868429 | 1380967 | 628129 | کد 591731- ردیف 12 | 1529.1251 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (سه لایه پرایمر،میانی و نهایی) | 8.7.16
258951446 | 89785169 | 381634 | 128133 | کد591901ردیف 1 | 1140.3645 | M3 |  |  | تست هیدرواستاتیک | 8.7.17
26580304 | 11692655 | 38457 | 18063 | کد591921 | 489.5869 | CM |  |  | آزمایش پرتو نگاری | 8.7.18
[7 empty] | TK | 104 | SUPPLY WATER TANK : نصب و اجرای مخزن | 8.8 |  | 8 | 20889
128784043 | 41514761 | 5241240 | 1979728 | کد 591301 - ردیف 1 | 32 | Ton |  |  | تخلیه ، بار اندازی و صفافی مصالح | 8.8.1 |  | 10
466895671 | 179929310 | 135595388 | 80962652 | کد 591302 - ردیف 1 | 3.9457 | Ton |  |  | نصب و جوشکاری کف مخزن | 8.8.2 |  |  | 3945.724
4614610674 | 2391304002 | 281690806 | 124603271 | کد 591303 - ردیف 1 | 21.7411 | Ton |  |  | نصب و جوشکاری بدنه مخزن | 8.8.3 |  |  | 14568
734087863 | 293634570 | 249345872 | 57199201 | کد 591304 - ردیف 1 | 3.1566 | Ton |  |  | نصب و جوشکاری سقف ثابت مخزن | 8.8.4 |  |  | 3156.5792
963664043 | 292994445 | 325830 | 115609 | کد 591308 | 3156.5792 | Kg |  |  | نصب و جوشکاری سازه سقف ثابت مخزن | 8.8.5 |  |  | 3156.5792
| 214514463 | 392454 | 104340 | کد 591307 | 2500 | Kg |  |  | نصب و جوشکاری پله بدنه | 8.8.6
80999621 | 19163637 | 1525127 | 368398 | کد 591741 - ردیف 1 | 50.264 | M2 |  |  | سند بلاست کف مخازن سقف ثابت | 8.8.7
381013431 | 239316763 | 1505393 | 766092 | کد 591741 - ردیف 3 | 311.6368 | M2 |  |  | سند بلاست بدنه خارجی مخازن و سقف ثابت | 8.8.8 |  |  | 0
17917507 | 14414713 | 284539 | 78548 | کد 591741 - ردیف 4 | 125.66 | M2 |  |  | اضافه بهای سند بلاست بابت ارتفاع بیش از 5 متر | 8.8.9
548354420 | 250572216 | 1505393 | 766092 | کد 591741 - ردیف 3 | 301.584 | M2 |  |  | سند بلاست بدنه داخلی مخازن و کف | 8.8.10 |  |  | 0
17917507 | 14414713 | 284539 | 78548 | کد 591741 - ردیف 4 | 125.66 | M2 |  |  | اضافه بهای سند بلاست داخلی بابت ارتفاع بیش از 5 متر | 8.8.11 |  |  | 0
233838719 | 107368124 | 220766 | 150439 | کد 591742 - ردیف 2 | 663.4848 | M2 |  |  | رنگ امیزی سطوح داخل و خارج مخزنها | 8.8.12 |  |  | 0
9009604 | 4978434 | 42156 | 19728 | کد 591742 - ردیف 3 | 251.32 | M2 |  |  | اضافه بهای رنگ امیزی بابت ارتفاع بیش از 5 متر | 8.8.13 |  |  | 0
350210547 | 95466555 | 1092026 | 440985 | کد 591731- ردیف 3 | 311.6368 | M2 |  |  | مصالح رنگ خارجی پرایمر | 8.8.14 | [5 empty] | 4/1400 | 3296.3 | 5257 | 3323.285
837898556 | 370106150 | 1380967 | 628129 | کد 591731- ردیف 12 | 623.2736 | M2 |  |  | مصالح رنگ خارجی بدنه نهایی و میانی | 8.8.15 | [5 empty] | 4/1391 | 429.7 | 597 | 402.315
1084223599 | 566712843 | 1380967 | 628129 | کد 591731- ردیف 12 | 904.752 | M2 |  |  | مصالح رنگ داخلی بدنه و کف (سه لایه پرایمر،میانی و نهایی) | 8.8.16
179455769 | 60477150 | 381634 | 128133 | کد591901ردیف 1 | 502.64 | M3 |  |  | تست هیدرواستاتیک | 8.8.17 | [7 empty] | 8.26
18813845 | 11021341 | 38457 | 18063 | کد591921 | 394.245 | CM |  |  | آزمایش پرتو نگاری | 8.8.18
25802143512 | 25802143512 | 0 |  | خارج از فهرست بها |  | No. |  |  | نصب سیستم HVAC ساختمانها | 9 |  |  |  | 1
18378668292 | 18378668292 | 0 |  | خارج از فهرست بها |  | No. |  |  | نصب تجهیزات سیستم CO2 | 10
1102906342 | 1102906342 | 0 |  | خارج از فهرست بها |  | No. |  |  | نصب تجهیزات اطفا حریق | 11 |  |  |  | 13
[6 empty] | No. |  |  | WATER HYDRANT WITH MONITOR | 65.3
[6 empty] | No. |  |  | DELUGE VALVE | 65.4
[6 empty] | No. |  |  | DRY POWDER PORTABLE FIRE EXTINGUISHER | 65.5
[6 empty] | No. |  |  | DRY POWDER WHELEED FIRE EXTINGUISHER | 65.6
[6 empty] | No. |  |  | CO2 PORTABLE FIRE EXTINGUISHER | 65.7
[6 empty] | No. |  |  | CO2 WHEELD FIRE EXTINGUISHER | 65.8
[6 empty] | No. |  |  | SAFETY SHOWER & EYE WASH | 65.9
[6 empty] | No. |  |  | FIRST AID KIT | 65.10
[6 empty] | No. |  |  | CO2 TOTAL FLOODING SYSTEM | 65.11
[6 empty] | No. |  |  | FIRE SHED EQUIPMENT. 100 lit foam drums, 3% FP (5 NOS.), Fire Hose, 25 m (10 NOS.) Foam Nozzle 10X (2 NOS.) Water Nozzle, 450 lpm (Fog/Jet/Stop) (5 NOS.)) 12 kg portable powder fire extinguisher (6 NOS.) 75 kg Wheeled powder fire extinguisher (2 NOS.) 5 kg portable CO2 fire extinguisher (2 NOS.) In Line Inductor, 450 lpm with pick up tube (2 NOS.) Drum Wrench (1 NO.) Hose Bridge (1 NO.) | 65.12
[6 empty] | No. |  |  | FIRE DOSE SYSTEM | 65.13
[6 empty] | No. |  |  | 9 LIT WATER EXTINGUISHER | 65.14
[9 empty] | نصب تجهیزات مکانیک (غیر از مخازن ذخیره) | 67
247533580958 | 154959892728 | [7 empty] | مجموع

## C.PIPELINE
جدول 14 - برآورد اجرا ی خطوط لوله بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته خطوط لوله روزمینی جریانی نفت و گاز 1401 -
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | شرح |  | ردیف
[10 empty] | 2.413 | ضریب
[5 empty] | 400 | متر | احداث خط لوله انتقال نفت نمکی 20 اینچ روزمینی با جنسAPI 5L GR.X52/SCH.30/NACE از واحد بهره برداری نمونه 4 به واحد نمک زدایی نمونه 4 به طول تقریبی 1500 متر و شامل الکترود و تست هیدرواستاتیک |  | 1 | منطقه ای نمونه. | 1.11
[5 empty] | 400 | متر | احداث خط لوله انتقال نفت نمک زدایی شده 20 اینچ روزمینی با جنس API 5L GR.X52/SCH.30/NACE از واحد نمک زدایی نمونه 4 به واحد بهره برداری نمونه 4 به طول تقریبی 1500 متر. |  | 2 | بالاسری | 1.48
321652217 | 107104839 | 331838 | 174649 | 540758719 | 800 | متر |  | عملیات ریسه کردن | 2.1 | تجهیزکارگاه | 1
3926644151 | 1326567923 | 33127628 | 15213810 | 379021619 | 135 | سرجوش |  | عملیات خم زدن و جوشکاری لوله 20" با ضخامت 0.5" | 2.2 | بروزرسانی | 1.469
1066110393 | 596331679 | 9592634 | 3970390 | 64726395 | 135 | سرجوش |  | پرتو نگاری از جوش لوله، شیر واتصالات فولادی 20" | 2.3
1141889779 | 660080620 | 1907597 | 1120611 | 533490308 | 800 | متر |  | زنگ زدایی و پرایمر زنی لوله 20" با ماسه پاشی در کارگاه پابت | 2.4
1309595850 | 367325917 | 1902038 | 759457 | 524804751 | 800 | متر |  | اجرای یک لایه ضد زنگ و دولایه رنگ روی قطر 20" | 2.5
351804701 | 103491870 | 79909358 | 38687562 | 397768335 | 4 | عدد |  | نصب شیر 20" تا کلاس 600در هر نقطه از طول خط لوله | 2.6
68531106 | 23718083 | 15257485 | 9115104 | 695292837 | 4 | جفت |  | اتصال یک جفت فلنج 20" تا کلاس 600 در هر نقطه از خط | 2.7
1087220508 | 308061695 | 383899606 | 230281036 | 763404983 | 2 | عدد |  | اتصال گرم خط لوله به قطر 20" به لوله اصلی | 2.8
706536760 | 138385981 | 496383 | 345550 | 392564795 | 800 | متر |  | آزمایش هیدرواستیتک خط لوله به قطر 20" | 2.9
| 0 |  |  |  | 19647 | m |  | تعویض خط لوله انتقال نفت از واحد بهره برداری پازنان به واحد بهره برداری نمونه 3 با سایز 12 اینچ | 3
4052251921 | 2106095428 | 259700 | 95123 | 544830998 | 19647 | متر |  | عملیات ریسه کردن | 3.1
39478935760 | 25318845350 | 10927256 | 9126363 | 733485360 | 2850 | سرجوش |  | عملیات خم زدن و جوشکاری لوله 12" تا ضخامت 0.5" | 3.2
23814339666 | 4931349609 | 4062888 | 3683331 | 741480852 | 2850 | سرجوش |  | پرتو نگاری از جوش لوله، شیر واتصالات فولادی 12" | 3.3
20658816658 | 8126481230 | 872832 | 351616 | 713313784 | 19647 | متر |  | زنگ زدایی و پرایمر زنی لوله 12" با ماسه پاشی در کارگاه پابت | 3.4
13382007833 | 8618020645 | 884977 | 364989 | 521582351 | 19647 | متر |  | اجرای یک لایه ضد زنگ و دولایه رنگ روی قطر 12" | 3.5
216244455 | 75670678 | 45134893 | 11221735 | 591083558 | 4 | عدد |  | نصب شیر 12" تا کلاس 600در هر نقطه از طول خط لوله | 3.6
56997784 | 16464035 | 7217891 | 2879822 | 618789207 | 4 | جفت |  | اتصال یک جفت فلنج 12" تا کلاس 600 در هر نقطه از خط | 3.7
885062908 | 277778654 | 371209599 | 112776371 | 560499796 | 2 | عدد |  | اتصال گرم خط لوله به قطر 12" به لوله اصلی | 3.8
5319449523 | 2817402323 | 339059 | 141671 | 629422770 | 12117 | متر |  | آزمایش هیدرواستیتک خط لوله به قطر 12" | 3.9
| 0 |  |  |  | 1000 | m | جابجایی حدود 1900 متر از خط لوله 4 اینچ فشار بالای گاز موجود در سمت شرق سایت و احداث مجدد آن در فاصله حداقل 200 متر از حصار تسهیلات بیرون واحد. لازم به ذکر است در این زمینه حریمهای مجاز فاصله از خطوط لوله و تاسیسات مطابق با ضوابط اغلام شده در آیین نامه مناطق نفتخیز جنوب باید مد نظر قرار گیرد. |  | 4
470777335 | 147485155 | 284973 | 57634 | 620275970 | 1900 | متر |  | عملیات ریسه کردن | 4.1
2331179747 | 1580842754 | 10450896 | 2534916 | 746817044 | 350 | سرجوش |  | عملیات خم زدن و جوشکاری لوله 4" تا ضخامت0.674" | 4.2
852860445 | 682675876 | 3545218 | 1730773 | 357187641 | 350 | سرجوش |  | پرتو نگاری از جوش لوله، شیر واتصالات فولادی 4" | 4.3
969883626 | 257441600 | 571671 | 237355 | 549623603 | 1900 | متر |  | زنگ زدایی و پرایمر زنی لوله 4" با ماسه پاشی در کارگاه پابت | 4.4
861299580 | 190116749 | 383461 | 176190 | 337379455 | 1900 | متر |  | اجرای یک لایه ضد زنگ و دولایه رنگ روی قطر 4" | 4.5
30197259 | 7967698 | 14677149 | 6233293 | 607284468 | 2 | عدد |  | نصب شیر 4" تا کلاس 600در هر نقطه از طول خط لوله | 4.6
25804988 | 6412578 | 6849751 | 2948171 | 461755959 | 4 | جفت |  | اتصال یک جفت فلنج 4" تا کلاس 600 در هر نقطه از خط | 4.7
444946406 | 194497415 | 120093357 | 70895661 | 458935055 | 2 | عدد |  | اتصال گرم خط لوله به قطر 4" به لوله اصلی | 4.8
470976781 | 124584232 | 433576 | 155244 | 633747925 | 1000 | متر |  | آزمایش هیدرواستیتک خط لوله به قطر 4" | 4.9
| 0 |  |  |  | 500 | m | احداث خط لوله انتقال گاز 6 اینچ فلزی با جنس API5L GR.X52/SCH.80/NACE به صورت روزمینی از واحد بهره برداری نمونه 4 به واحد نمک زدایی نمونه 4 |  | 5
| 0 |  |  |  | 500 |  | ·احداث خط انتقال آب 6 اینچ فلزی با جنس API 5L0 به صورت رو زمینی از تصفیه خانه خیر آباد به واحدنمکزدایی نمونه-4 |  | 6
295752589 | 109795805 | 293225 | 75081 | 753674248 | 1000 | متر |  | عملیات ریسه کردن | 6.1
2952799333 | 1238327912 | 12193147 | 5850679 | 605887902 | 200 | سرجوش |  | عملیات خم زدن و جوشکاری لوله 6"تاا ضخامت 0.5" | 6.2
1039033100 | 360088654 | 2731719 | 1094607 | 456770419 | 200 | سرجوش |  | پرتو نگاری از جوش لوله، شیر واتصالات فولادی 6" | 6.3
694676012 | 179328126 | 939039 | 364174 | 735497907 | 1000 | متر |  | زنگ زدایی و پرایمر زنی لوله 6" با ماسه پاشی در کارگاه پابت | 6.4
341923449 | 216399475 | 520152 | 244925 | 492410956 | 1000 | متر |  | اجرای یک لایه ضد زنگ و دولایه رنگ روی قطر 6" | 6.5
0 | 0 | 20004502 | 9383852 | 456647036 |  | عدد |  | نصب شیر 6" تا کلاس 600در هر نقطه از طول خط لوله | 6.6
0 | 0 | 4310050 | 3068638 | 441150010 |  | جفت |  | اتصال یک جفت فلنج 6" تا کلاس 600 در هر نقطه از خط | 6.7
215577309 | 91667783 | 253184689 | 91667783 | 448174346 | 1 | عدد |  | اتصال گرم خط لوله به قطر 6" به لوله اصلی | 6.8
382619071 | 173890341 | 396077 | 145930 | 370630831 | 1000 | متر |  | آزمایش هیدرواستیتک خط لوله به قطر 6" | 6.9
66691770430 | 13502307926 | 8815517 | 4101683 | خارج از فهرست بها | 6000 | m | احداث دو خط لوله انتقال پساب غیر فلزی با جنس RTP زیر زمینی از واحدنمکزدایی نمونه-4 به چاههای تزریق در فاصله تقریبی 3 کیلومتر برای هر خط لوله. |  | 7 |  | 4/1400 | 4356.5
3457062470 | 1668401505 | 8815517 | 4101683 | خارج از فهرست بها | 500 | m | احداث خط لوله انتقال آب ازاد غیر فلزی با جنس RTP زیر زمینی از واحد بهره برداری نمونه-4 به واحدنمکزدایی نمونه-4 |  | 8 |  | 4/1391 | 500 | 8.713
20804962014 | 15532169267 | 2732868 | 1016558 | خارج از فهرست بها | 8500 | m | خط لوله آب "6 از چاههای لیشتر با جنس PE-100 به طول تقریبی |  | 9
28323903209 | 23022615438 | 4216512 | 2699158 | خارج از فهرست بها | 8500 | m | خط لوله "10 آب آتش نشانی اتصال بین دو واحد با جنس PE-100 به طول تقریبی 500متر |  | 10
232926597983 | 101076054246 | [5 empty] | مجموع |  | 11
82992686564

## C.ELECTRICAL
جدول 15 - برآورد اجرای عملیات برق و مخابرات و کابل کشی بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | شرح | ردیف
891492558 | 176719368 | 164103 | 37947 | کد 592401 - ردیف 04 | 5000 | Kg | نصب پنل برق MV Switchgear, 33KV, 630A, 3 (with approximately 15 cell)/Location:33KV station | 1 |  |  |  |  | 1 | SET
227160287 | 114173116 | 142779 | 32710 | کد 592401 - ردیف 06 | 3500 | Kg | نصب پنل برق MV Switchgear, 3.3KV, 1250A,(with approximately 9 cell) /Location: DE4 Outdoor station | 2 | ضریب = | 2.471 |  |  | 1 | SET
318770624 | 212456046 | 142779 | 32710 | کد 592401 - ردیف 06 | 4000 | Kg | نصب پنل برق MV Switchgear, 3.3KV, 630A, 3 phase +E, (with approximately 12 cell)/Location:DE4 | 3 |  |  |  |  | 1 | SET
819241687 | 252683339 | 164103 | 37947 | کد 592401 - ردیف 04 | 5500 | Kg | LV Switchgear, 400V, 4000A/Location: DE4 | 4 | منطقه ای نمونه. | 1.12 |  |  | 1 | SET
224051248 | 161295532 | 142779 | 32710 | کد 592401 - ردیف 06 | 3000 | Kg | نصب پنل برق 33 KV transformer bay,(2 SET) | 5 | بالاسری | 1.48 |  |  | 2 | SET
227160287 | 114173116 | 142779 | 32710 | کد 592401 - ردیف 06 | 3500 | Kg | نصب پنل برق MV Switchgear, 3.3KV, 630A, (with approximately 9 cell). /Location:Production un | 6 | تجهیزکارگاه | 1 |  |  | 1 | SET
241654271 | 110724479 | 164103 | 37947 | کد 592401 - ردیف 04 | 2000 | Kg | نصب پنل برق SAMPLE 4-DESALTING UNIT EDP,400V SWITCHGEAR (EDP) | 7 | بروزرسانی | 1.491 |  |  | 2 | SET
0 |  | 0 |  |  | 1 | Kg | MV Switchgear, 3.3KV, 1000A, نصب تابلو | 8 |  | 33 KV transformer bay, withdrawable, outdoor type with OCB and all protection and metering devises in accordance to Dwg no. M9003-EB-EL-SLD-21026
190166196 | 110747925 | 61873 | 23412 | کد 592411 - ردیف 01 | 2500 | Kg | نصب تابلو روشنایی 37 عدد | 8
2049098038 | 690582181 | 3236825 | 826424 | کد 592841 ردیف 1 | 700 | Kg | NGRنصب | 9
2495076970 | 738343442 | 11216259 | 3701430 | کد 592451 ستون 1 | 200 | Kg | نصب 62 عدد تابلوی محلی | 10
1481469740 | 487148678 | 7876724 | 4073742 | کد 592451 ستون 2 | 200 |  | نصب 62 عدد تابلوی محلی ضد انفجار
85007709 | 40042703 | 23154 | 6850 | کد 592801 - ردیف 01 - ستون 2 | 5000 | Kg | پیش راه اندازی و راه اندازی پنل برق MV Switchgear, 33KV, 630A, 3 (with approximately 15 cell)/Location:33KV station | 11
47067224 | 30172837 | 11937 | 6340 | کد 592801 - ردیف 01 - ستون 1 | 3500 | Kg | پیش راه اندازی و راه اندازی پنل برق MV Switchgear, 3.3KV, 1250A,(with approximately 9 cell) /Location: DE4 Outdoor station | 12
40943212 | 15970365 | 11937 | 6340 | کد 592801 - ردیف 01 - ستون 1 | 4000 | Kg | پیش راه اندازی و راه اندازی پنل برق MV Switchgear, 3.3KV, 630A, 3 phase +E, (with approximately 12 cell)/Location:DE4 | 13
511846000 | 173490674 | 2327004 | 1848921 | کد 592812 | 200 | OUTGOING | LV Switchgear, 400V, 4000A/Location: DE4 | 14
58069053 | 15728253 | 23154 | 6850 | کد 592801 - ردیف 01 - ستون 2 | 3000 | Kg | پیش راه اندازی و راه اندازی پنل برق 33 KV transformer bay,(2 SET) | 15
47067224 | 30172837 | 11937 | 6340 | کد 592801 - ردیف 01 - ستون 1 | 3500 | Kg | پیش راه اندازی و راه اندازی پنل برق MV Switchgear, 3.3KV, 630A, (with approximately 9 cell). /Location:Production un | 16
100975237 | 56803795 | 2327004 | 1848921 | کد 592812 | 30 | OUTGOING | پیش راه اندازی و راه اندازی پنل برق SAMPLE 4-DESALTING UNIT EDP,400V SWITCHGEAR (EDP) | 17
274586777 | 87335255 | 52417 | 30563 | کد 592813 | 2500 | Kg | پیش راه اندازی و راه اندازی تابلو روشنایی 37 عدد | 18
2154040 | 561033 | 6597.57 | 2670 | کد 592801 - ردیف 03 - ستون 1 | 300 | Kg | پیش راه اندازی و راه اندازی 62 عدد تابلوی محلی | 19
363172284 | 146206108 | 56529 | 15861 | کد 592411 - ردیف 04 | 6000 | Kg | TR1 : Power Transformer 2500 KVA, 3.3 / 0.42 Kv - TR1 نصب تارنسفورماتور | 20
363172284 | 146206108 | 56529 | 15861 | کد 592411 - ردیف 04 | 6000 | Kg | 2500 KVA, 3.3 / 0.42 kV - TR2 نصب ترانسفورماتور | 21
346445801 | 151398061 | 56529 | 15861 | کد 592411 - ردیف 04 | 8000 | Kg | 6000 KVA, 33 / 3.45kV- PTR1 نصب ترانسفورماتور | 22
346445801 | 151398061 | 56529 | 15861 | کد 592411 - ردیف 04 | 8000 | Kg | 6000 KVA, 33 / 3.45kV - PRT2 نصب ترانسفورماتور | 23
47116661 | 24777362 | 7907.2 | 3200 | کد 592821 - ردیف 02- ستون 1 | 6000 | Kg | TR1 : Power Transformer 2500 KVA, 3.3 / 0.42 Kv - TR1 پیش راه اندازی و راه اندازی تارنسفورماتور | 24
47116661 | 24777362 | 7907.2 | 3200 | کد 592821 - ردیف 02- ستون 1 | 6000 | Kg | 2500 KVA, 3.3 / 0.42 kV - TR2 پیش راه اندازی و راه اندازی ترانسفورماتور | 25
71623349 | 27892332 | 7091.77 | 2870 | کد 592821 - ردیف 03- ستون 03 | 8000 | Kg | 6000 KVA, 33 / 3.45kV- PTR1 پیش راه اندازی و راه اندازی ترانسفورماتور | 26
71623349 | 27892332 | 7091.77 | 2870 | کد 592821 - ردیف 03- ستون 03 | 8000 | Kg | 6000 KVA, 33 / 3.45kV - PRT2 پیش راه اندازی و راه اندازی ترانسفورماتور | 27
310216304 | 75653515 | 53255 | 34326 | کد 591034 - ردیف 01 | 4000 | Kg | 0.4 kv, 550 KVA- نصب ژنراتور دیزل | 28
79700977 | 35334996 | 53255 | 34326 | کد 591034 - ردیف 01 | 2000 | Kg | 0.4 kv, 180 KVA- نصب ژنراتور دیزل | 29
79700977 | 35334996 | 53255 | 34326 | کد 591034 - ردیف 01 | 2000 | Kg | 0.4 kv, 180 KVA- نصب ژنراتور دیزل | 30
0 |  | 0 |  |  | 1 |  | UNINTERRUPTIBLE POWER SUPPLY (UPS) | 32
5285623 | 2033485 | 9888 | 4760 | کد 592821 - ردیف 01- ستون 1 | 500 | Kg | UPS-1, 110V AC UPS, 80KW - نصب پکیج برق | 31
4721900 | 998431 | 9888 | 4760 | کد 592821 - ردیف 01- ستون 1 | 300 | Kg | DC-01, 110V DC UPS,13 KW - نصب پکیج برق | 32
4721900 | 998431 | 9888 | 4760 | کد 592821 - ردیف 01- ستون 1 | 300 | Kg | DC-02, 24V DC UPS, 18KW - نصب پکیج برق | 33
4721900 | 998431 | 9888 | 4760 | کد 592821 - ردیف 01- ستون 1 | 300 | Kg | DC-03, 110V DC UPS, 9 KW - نصب پکیج برق | 34
4721900 | 998431 | 9888 | 4760 | کد 592821 - ردیف 01- ستون 1 | 300 | Kg | DC-04, 110V DC UPS, 7.5 KW - نصب پکیج برق | 35
4721900 | 998431 | 9888 | 4760 | کد 592821 - ردیف 01- ستون 1 | 300 | Kg | DC-05, 110V DC UPS, 13 KW - نصب پکیج برق | 36
675935651 | 478590177 | 61873 | 23412 | کد 592411 - ردیف 01 | 11739 | Kg | نصب باتری | 37
53673111 | 16486173 | 61873 | 23412 | کد 592411 - ردیف 01 | 500 | Kg | UPS-1, 110V AC UPS, 80KW - پیش راه اندازی و راه اندازی پکیج برق | 38
15655910 | 9249203 | 61873 | 23412 | کد 592411 - ردیف 01 | 300 | Kg | DC-01, 110V DC UPS,13 KW - پیش راه اندازی و راه اندازی پکیج برق | 39
15655910 | 9249203 | 61873 | 23412 | کد 592411 - ردیف 01 | 300 | Kg | DC-02, 24V DC UPS, 18KW - پیش راه اندازی و راه اندازی پکیج برق | 40
15655910 | 9249203 | 61873 | 23412 | کد 592411 - ردیف 01 | 300 | Kg | DC-03, 110V DC UPS, 9 KW - پیش راه اندازی و راه اندازی پکیج برق | 41
15655910 | 9249203 | 61873 | 23412 | کد 592411 - ردیف 01 | 300 | Kg | DC-04, 110V DC UPS, 7.5 KW - پیش راه اندازی و راه اندازی پکیج برق | 42
15655910 | 9249203 | 61873 | 23412 | کد 592411 - ردیف 01 | 300 | Kg | DC-05, 110V DC UPS, 13 KW - پیش راه اندازی و راه اندازی پکیج برق | 43
432468567 | 275681855 | 27231533 | 17007317 | کد 592421 - ردیف 03- ستون 1 | 15 | متر | نصب باسداکت | 44
0 |  | 0 |  |  | 1 |  | Earting | 45
85549240 | 66623517 | 13823 | 6080 | کد 592101 ردیف 1 | 9400 | متر | نصب اتصال زمین -سیم کشی | 45
0 |  | 0 |  |  | 500 |  | نصب اتصال زمین -سیم کشی | 49
0 |  | 0 |  |  |  |  | 70 mm2 BARE STRANDED COPPER CONDUCTOR | 50
0 |  | 0 |  |  | 2850 |  | 70 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 51
0 |  | 0 |  |  | 350 |  | 35 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 52
0 |  | 0 |  |  | 400 |  | 16 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 53
15889336 | 6455305 | 704883 | 403392 | کد 592615 ردیف 1 | 22 | عدد | نصب اتصال زمین تسمه مسی | 46
336515790 | 130807072 | 2531557 | 1502489 | کد 592612 ردیف 3 | 79 | عدد | نصب اتصال زمین کدولد مسی | 47
964308503 | 304630175 | 2701550 | 983446 | کد 592612 ردیف 2 | 280 | عدد | نصب اتصال زمین کدولد مسی | 48
0 |  | 0 |  |  | 160 | عدد | CADWELD,CARTRIDGE, FOR CROSS CONNECTION OF 70x70 mm2 | 57
0 |  | 0 |  |  | 40 | عدد | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 70x35 mm2 | 58
0 |  | 0 |  |  | 40 | عدد | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 70x16 mm2 | 59
0 |  | 0 |  |  | 40 | عدد | CADWELD,CARTRIDGE, FOR CONNECTION OF 70 mm2 COPPER CONDUCTOR TO COPPER EARTH PLATE | 60
0 |  | 0 |  |  | 68 | عدد | 10-WAY COPPER EARTH BAR,6mm THICKNESS,50 mm WIDE,700 mm LENGTH AND TWO WASHERS AND ONE NUT FOR EACH HOLE | 61
1716951543 | 1361968394 | 16693299 | 5315751 | کد 592613 | 156 | عدد | نصب اتصال زمین- الکنرود (میله) زمین | 49
0 |  | 0 |  |  | 64 | NO | "U" bolt rod to cable clamp for nominal rod dia. 20 mm | 63
0 |  | 0 |  |  | 24 | NO | TINNED COPPER COMPRESSION CABLE LUG FOR CABLE SIZE 120 mm2 | 64
41635801 | 21548864 | 662450 | 222998 | کد 592614 ردیف 1 | 70 | عدد | نصب اتصال زمین- اتصال به تجهیزات | 50
338285795 | 93168065 | 1777752 | 381228 | کد 592614 ردیف 2 | 195 | عدد | نصب اتصال زمین- اتصال به تجهیزات | 51
0 |  | 0 |  |  | 121 | عدد | نصب اتصال زمین- اتصال به تجهیزات | 67
0 |  | 0 |  |  | 49 | عدد | CONDUIT , HEAVY GUAGE HOT DIP GALVANIZED ,RIGID STEEL,DOUBLE SIDE ISO THREADED, LENGTH 3000mm, size: M50 | 68
0 |  | 0 |  |  | 147 | عدد | Conduit clamp, m50 | 69
0 |  | 0 |  |  | 1 | عدد | Spark gap | 70
73480913 | 29378062 | 306436 | 100487 | کد 592616 | 400 | Kg | نصب اتصال زمین- مخلوط ذغال
29538846 | 25575585 | 11492715 | 4550304 | کد 592621 ردیف 1 | 5 | عدد | نصب صاعقه گیر | 52
0 |  | 0 |  |  |  | 1 | cable | 64.3333
0 |  | 0 |  |  |  |  | 0.6/1 KV, Stranded Annealed Copper Conductor, PVC Insulated, Lead Sheath, Extruded PVC Bedding, Galvanized Steel Wire Armored, PVC Sheathed, Cu-PVC-Lsh-Bd-SWA-PVC Power Cable | 64.7619
10353047948 | 4806373168 | 144648 | 90071 | کد 592103 - ستون 1- ردیف 1 | 31200 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی -زره دار باغلاف سربی-0.6/1 KV | 53
1502517480 | 360810004 | 184639 | 109057 | کد 592103 - ستون 1- ردیف 2 | 5380 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی -زره دار باغلاف سربی-0.6/1 KV | 54
158899632 | 70752485 | 239239 | 94695 | کد 592103 - ستون 1- ردیف 3 | 750 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی -زره دار باغلاف سربی-0.6/1 KV | 55
0 |  | 0 |  |  | 8200 | M | 3C4 | 56
0 |  | 0 |  |  |  | M | 3C6 | 57
0 |  | 0 |  |  | 2100 | M | 3C10 | 58
0 |  | 0 |  |  | 4100 | M | 3C16 | 59
0 |  | 0 |  |  | 550 | M | 3C25 | 60
0 |  | 0 |  |  | 250 | M | 3C95 | 61
0 |  | 0 |  |  |  | M | 3C150 | 62
0 |  | 0 |  |  |  | M | 3C25+16 | 63
0 |  | 0 |  |  | 200 | M | 3C150+70 | 64
0 |  | 0 |  |  | 750 | M | 3C240+120 | 65
0 |  | 0 |  |  | 280 | M | 3C95+50 | 66
0 |  | 0 |  |  | 3900 | M | 3C70 | 67
0 |  | 0 |  |  | 750 | M | 3C50 | 68
0 |  | 0 |  |  | 1100 | M | 4C4 | 69
0 |  | 0 |  |  | 1500 | M | 4C10 | 70
0 |  | 0 |  |  | 300 | M | 4C16 | 71
0 |  | 0 |  |  |  |  | 0.6/1 KV, Stranded Annealed Copper Conductor, PVC Insulated, Galvanized Steel Wire Armored, PVC Sheathed, Cu-PVC-SWA-PVC Power Cable | 72
6444905946 | 3302087960 | 254917 | 66368 | کد 592102 - ستون 1- ردیف 1 | 43626 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی - زره دار-0.6/1 KV | 56
339533503 | 124595854 | 266566 | 95335 | کد 592102 - ستون 1- ردیف 2 | 1350 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی - زره دار-0.6/1 KV | 57
2943622233 | 1286130370 | 216417 | 92390 | کد 592102 - ستون2 - ردیف 2 | 25481 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی - زره دار-3/6 KV | 58
806925500 | 455753971 | 333715 | 116600 | کد 592102 - ستون2 - ردیف 3 | 3500 | M | کابل کشی کابل قدرت و کنترل - زیرزمینی - زره دار-3/6 KV | 59
0 |  | 0 |  |  | 2000 | M | 1C300 | 60
0 |  | 0 |  |  | 150 | M | 3C4 | 61
0 |  | 0 |  |  | 250 | M | 3C6 | 62
0 |  | 0 |  |  | 300 | M | 3C16 | 63
0 |  | 0 |  |  | 650 | M | 3C25 | 64
0 |  | 0 |  |  | 500 | M | 3C25+16 | 65
0 |  | 0 |  |  | 100 | M | 3C150+70 | 66
0 |  | 0 |  |  | 400 | M | 4C4 | 67
0 |  | 0 |  |  | 600 | M | 4C16 | 68
0 |  | 0 |  |  | 150 | M | 4C10 | 69
0 |  | 0 |  |  | 50 | M | 3C95+50 | 70
0 |  | 0 |  |  | 100 | M | 3C50+25 | 71
0 |  | 0 |  |  | 1100 | M | 3C50 | 72
0 |  | 0 |  |  |  | M | 3/6 KV, Stranded Annealed Copper Conductor, XLPE Insulated, Galvanized Steel Wire Armored, PVC Sheathed, Cu-XLPE-SWA-PVC Power Cable | 73
0 |  | 0 |  |  | 11974 | M | 1C95 | 74
0 |  | 0 |  |  | 2000 | M | 3C70 | 75
0 |  | 0 |  |  | 1400 | M | 3C95 | 76
0 |  | 0 |  |  | 2500 | M | 3C300 | 77
0 |  | 0 |  |  | 1000 | M | 3C240+120 | 78
439612636 | 239559127 | 551816 | 253593 | کد 592141 ردیف 1 | 1100 | M2 | ماسه ریزی داخل ترانشه | 60
544926608 | 393217940 | 671845 | 420268 | کد 592141 ردیف 2 | 1100 | M2 | آجر چینی داخل ترانشه | 61
485923882 | 258389832 | 656284 | 200567 | کد 592201 ردیف 2 - ستون 2 | 600 | سر | سر سیم بندی کابل های کنترل- 5 تا 12 CORE | 62
366672351 | 128945269 | 254519 | 149091 | کد 592213 ردیف 2 - ستون 3 | 800 | سر | سر سیم بندی کابل فشار ضعیف - زره داربا غلاف سربی-3 CORE | 63
150881301 | 43407361 | 471574 | 217440 | کد 592213 ردیف 3 - ستون 3 | 200 | سر | سر سیم بندی کابل فشار ضعیف - زره داربا غلاف سربی-3 CORE | 64
210915525 | 71930925 | 1006576 | 711952 | کد 592213 ردیف 4 - ستون 4 | 200 | سر | سر سیم بندی کابل فشار ضعیف - زره داربا غلاف سربی-3 CORE | 65
124081296 | 34536503 | 387059 | 105761 | کد 592212 ردیف 2 - ستون 3 | 400 | سر | سر سیم بندی کابل فشار ضعیف - زره دار-3 CORE | 66
213545334 | 150636849 | 585480 | 129993 | کد 592212 ردیف 3 - ستون 3 | 600 | سر | سر سیم بندی کابل فشار ضعیف - زره دار-3 CORE | 67
138446253 | 59673319 | 1314919 | 592675 | کد 592212 ردیف 4 - ستون 4 | 100 | سر | سر سیم بندی کابل فشار ضعیف - زره دار-4.5 CORE | 68
623052969 | 433662982 | 9103457 | 3945713 | کد 592222 ردیف 1 - ستون 3 | 120 | سر | سر سیم بندی کابل فشارمتوسط - 3 CORE - تا 6KV | 69
289276075 | 151376717 | 7982593 | 4126500 | کد 592222 ردیف 2 - ستون 3 | 30 | سر | سر سیم بندی کابل فشار متوسط - 3 CORE - تا 6KV | 70
297955505 | 88766642 | 16917933 | 4910378 | کد 592224 ردیف 3 - ستون 3 | 15 | سر | سر سیم بندی کابل فشار متوسط - تا 33KV | 71
7158214 | 3387393 | 153467 | 62752 | کد 592231 ردیف 6 | 50 | عدد | نصب گلند ضد گردوغبارM20 | 72
42948200 | 17189023 | 243611 | 160978 | کد 592231 ردیف 7 | 200 | عدد | نصب گلند ضد گردوغبارM25 | 73
45148975 | 19704880 | 452490 | 213162 | کد 592231 ردیف 8 | 100 | عدد | نصب گلند ضد گردوغبارM33 | 74
27085012 | 16778208 | 575059 | 417439 | کد 592231 ردیف 9 | 35 | عدد | نصب گلند ضد گردوغبارM40 | 75
16676212 | 4635636 | 1181054 | 455733 | کد 592231 ردیف 10 | 20 | عدد | نصب گلند ضد گردوغبارM50 | 76
222088694 | 82312762 | 1824539 | 416345 | کد 592231 ردیف 11 | 150 | عدد | نصب گلند ضد گردوغبارM63 | 77
637067841 | 186900743 | 16664637 | 4619073 | کد 592232 ردیف 12 | 30 | عدد | نصب گلند ضد گردوغبارM75 | 78
695605 | 529302 | 144434 | 99160 | کد 592231 ردیف 6 | 5 | عدد | نصب گلند ضدانفجارM20 | 79
3641790 | 1658111 | 444171 | 104437 | کد 592231 ردیف 7 | 10 | عدد | نصب گلند ضدانفجارM25 | 80
27402538 | 12050061 | 598775 | 220440 | کد 592231 ردیف 8 | 50 | عدد | نصب گلند ضدانفجارM33 | 81
29334801 | 22817819 | 1540187 | 462930 | کد 592231 ردیف 9 | 40 | عدد | نصب گلند ضدانفجارM40 | 82
4914623 | 2460855 | 1628038 | 551626 | کد 592231 ردیف 10 | 5 | عدد | نصب گلند ضدانفجارM50 | 83
8143633 | 4547956 | 1443273 | 627426 | کد 592231 ردیف 11 | 5 | عدد | نصب گلند ضدانفجارM63 | 84
0 |  | 0 |  |  | 31 | SET | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator.(L4-T12,L2-T12 Schematic code). | 73
0 |  | 0 |  |  | 8 | SET | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be explosion proof type, IP55, EExd, IIB, T3 and supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator.(L4-T12,L2-T12 Schematic code). | 74
0 |  | 0 |  |  | 13 | SET | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch and remote position indicator.(L1-T12 Schematic code). | 75
0 |  | 0 |  |  | 9 | SET | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be explosion proof type, IP55, EExd, IIB,T3 and supplied with stop push Button, start push button, Local / Remote Selector Switch and remote position indicator.(L1-T12 Schematic code). | 76
0 |  | 0 |  |  | 1 | SET | Local Control Stations for remote operation of the fire water pump.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator. | 77
485886487 | 120413638 | 11984343 | 4173290 | کد 592501 ردیف 1 ستون 2 | 46 | عدد | 1x250W HIGH PRESSURE MERCURY نصب نورافکن و چراغ های صنعتی محوطه | 85
854271936 | 208165960 | 11984343 | 4173290 | کد 592501 ردیف 1 ستون 2 | 80 | عدد | نصب نورافکن و چراغ های صنعتی محوطه CORROSION RESISTANT OUTDOOR AREA FLOOD LIGHT,1x400W METAL HALIDE LAMP | 87
164016243 | 75426036 | 3236825 | 826424 | کد 592831 ردیف 1 | 62 | دستگاه | پیش راه اندازی و راه اندازی موتورها تا یک KV - زیر 50 KW | 88
47195861 | 20047189 | 3337785 | 2094237 | کد 592831 ردیف 2 | 10 | دستگاه | پیش راه اندازی و راه اندازی موتورها تا یک KV -بالای 50 KW | 89
44604004 | 30899250 | 5802471 | 1573281 | کد 5ردیف82832 ردیف 1 | 11 | دستگاه | پیش راه اندازی و راه اندازی موتورها بیش از یک KV -زیر 500 KW | 90
[7 empty] | Power Transition Line | 79
135971495876 | 135971495876 | 1065114808 |  | خارج از فهرست بها | 108 | km | Cable ACSR -33KV –LYNX | 91 |  | 4/1400 | 3296.3 | 5257 | 3492.37
8650529109 | 8650529109 | 1065114808 |  | خارج از فهرست بها | 6 | m | Cable ACSR -66KV –HORSE | 92 |  | 4/1391 | 429.7 | 597 | 446.43
586722053 | 407451321 | 26355052 | 13593823 | کد 592721 ردیف 1 | 30 | دستگاه | نصب دوربین مدار بسته | 93
218717000 | 82370405 | 53190141 | 17851116 | کد 592721 ردیف 2 | 4 | دستگاه | نصب مونیتور های سیتم تلویزیون مدار بسته | 94 |  |  |  | 7.823
46585880 | 18443819 | 57172261 | 18443819 | کد 592721 ردیف 3 | 1 | دستگاه | نصب سیستم کنترل تلویزیون مدار بسته | 95
4422919192 | 4422919192 | - | یک قلم | خارج از فهرست بها | - | - | نصب سیستم محافظت پیرامونی ، مخابرات و فراخوان (غیر از داخل ساختمانها و کابل) | 96
4422919192 | 4422919192 | - | یک قلم | خارج از فهرست بها | 34 | عدد | نصب کلیه سوکتهای صنعتی محوطه
2053119027 | 2053119027 | - | یک قلم | خارج از فهرست بها | - | - | نصب کلیه سوییچهای روشنایی
171896245653 | 208294579081 | [5 empty] | مجموع | 97

## C.INSTRUMENT
جدول 16 - برآورد اجرا و نصب تجهیزات ابزاردقیق بر اساس فهرست بهای اختصاصی تاسیسات نفت و گاز، رشته نصب واحدهای بهره برداری نفت و گاز -1401 | [10 empty] | منطقه ای نمونه. | 1.12
هزینه تمام شده مطابق فهرست بها | مبلغ بدون اعمال ضرایب | بهای واحد بــها با اعمال ضریب | بهای واحد بــها بدون اعمال ضریب | ردیف فهرست بهای نفت سال 1401 | مقدار | واحد | شرح | ردیف |  | وزن واحد | بالاسری | 1.48
[11 empty] | تجهیزکارگاه | 1
[11 empty] | بروزرسانی | 1.491
5037258822 | 2815864670 | 13075404 | 6382915 | کد 593133 ردیف 02 | 600 | کیلوگرم | نصب سیستم های آنالایزر- بیشتر از 10 کیلوگرم | 1 | 2.471
1934029025 | 667179532 | 7230291 | 2381856 | کد 593133 ردیف 01 | 280 | کیلوگرم | نصب سیستم های آنالایزر-تا 10 کیلوگرم | 2 | 2.471
584696596 | 272484280 | 19555085 | 4112294 | کد 593101 ردیف 02 | 37 | دستگاه | نصب انتقال دهنده جریان | 3 | 2.471
120129033 | 87045156 | 8669460 | 7007406 | کد 593102 ردیف 04 | 14 | دستگاه | نصب سوییچ جریان | 4 | 2.471
299862118 | 120419864 | 15914844 | 4009843 | کد 593111 ردیف 09 | 22 | دستگاه | نصب نمایشگر جریان | 5 | 2.471
90717862 | 73279179 | 8698911 | 2007185 | کد 593119 ردیف 01 | 22 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات جریان سنجهای در طول خط سایز تا 4" | 6 | 2.471
57714959 | 19299669 | 5135625 | 2350239 | کد 593118 ردیف 01 | 13 | عدد | نصب/ کنترل مشخصات صفحه اوریفیس سایز تا 4" | 7 | 2.471
81093147 | 34379260 | 4567481 | 1400963 | کد 593118 ردیف 02 | 15 | عدد | نصب/ کنترل مشخصات صفحه اوریفیس سایز از 4" تا 8" | 8 | 2.471
119854230 | 25083709 | 6591829 | 2815610 | کد 593118 ردیف 03 | 17 | عدد | نصب/ کنترل مشخصات صفحه اوریفیس سایز از 8" تا 12" | 9 | 2.471
26055303 | 5612918 | 8721211 | 2066392 | کد 593118 ردیف 04 | 3 | عدد | نصب/ کنترل مشخصات صفحه اوریفیس سایز از 12" تا 20" | 10 | 2.471
243368279 | 113226792 | 16157347 | 7519043 | کد 593111 ردیف01 | 14 | دستگاه | نصب نمایشگر سطح مغناطیسی | 11 | 2.471
53576930 | 27627993 | 35588599 | 10894456 | کد 593111 ردیف02 | 2 | دستگاه | (FLOAT-CABLE) نصب نمایشگر سطح | 12 | 2.471
777699293 | 242038642 | 20568348 | 8509262 | کد 593102 ردیف 01 | 30 | دستگاه | نصب سوییچ سطح EXTERNAL | 13 | 2.471
127522987 | 59609211 | 14856835 | 10978153 | کد 593102 ردیف 02 | 7 | دستگاه | نصب سوییچ سطح INTERNAL | 14 | 2.471
32275391 | 10449454 | 32275391 | 10449454 | کد 593101 ردیف 06 | 1 | دستگاه | نصب انتقال دهنده سطح EXT. DIS. TYPE تا 32 اینچ | 15 | 2.471
96061824 | 63874377 | 22505510 | 15965826 | کد 593101 ردیف 07 | 4 | دستگاه | نصب انتقال دهنده سطح EXT. DIS. TYPE از 32 تا 72 اینچ | 16 | 2.471
134814722 | 57534826 | 47037520 | 18463021 | کد 593101 ردیف 08 | 3 | دستگاه | نصب انتقال دهنده سطح EXT. DIS. TYPE بزرگتر از 72 اینچ | 17 | 2.471
120353389 | 39741694 | 19555085 | 4112294 | کد 593101 ردیف 02 | 6 | دستگاه | DIFF. PRESSURE TYPE نصب انتقال دهنده سطح | 18 | 2.471
1337052556 | 362606889 | 11104883 | 2763079 | کد 593111 ردیف 03 | 138 | دستگاه | نصب نمایشگر فشار | 19 | 2.471
313206771 | 138663046 | 11104883 | 2763079 | کد 593111 ردیف 03 | 30 | دستگاه | نصب نمایشگر اختلاف فشار | 20 | 2.471
857745657 | 380688265 | 8669460 | 7007406 | کد 593102 ردیف 04 | 94 | دستگاه | نصب سوییچ فشار | 21 | 2.471
1477311546 | 463556067 | 19555085 | 4112294 | کد 593101 ردیف 02 | 77 | دستگاه | نصب انتقال دهنده فشار | 22 | 2.471
279777790 | 140808714 | 19555085 | 4112294 | کد 593101 ردیف 02 | 17 | دستگاه | نصب انتقال دهنده اختلاف فشار | 23 | 2.471
584696596 | 272484280 | 19555085 | 4112294 | کد 593101 ردیف 02 | 37 | دستگاه | نصب انتقال دهنده دما | 24 | 2.471
108965207 | 38673504 | 8669460 | 7007406 | کد 593102 ردیف 04 | 8 | دستگاه | نصب سوییچ دما | 25 | 2.471
681458392 | 200658298 | 8408365 | 2833160 | کد 593111 ردیف 07 | 59 | دستگاه | نصب نمایشگر دما (BIMETAL) | 26 | 2.471
616072743 | 280346595 | 7170644 | 1475434 | کد 593104 ردیف 06 | 104 | دستگاه | نصب THERMOWELL - طول بیشتر از 60 سانتی متر | 27 | 2.471
277399685 | 114031694 | 8064792 | 4736624 | کد 593114 ردیف 1 | 29 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر کنترل سایز تا 4" | 28 | 2.471
124698879 | 65468200 | 10659851 | 5618829 | کد 593114 ردیف 2 | 9 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر کنترل سایز از 4" تا 8" | 29 | 2.471
54364458 | 13510716 | 17759826 | 7696910 | کد 593114 ردیف 3 | 3 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر کنترل سایز از 4" تا 8" | 30 | 2.471
54969292 | 16286930 | 23681459 | 10658723 | کد 593114 ردیف 4 | 2 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر کنترل سایز از 12" تا 20" | 31 | 2.471
130570087 | 43841514 | 9286831 | 5421938 | کد 593116 ردیف 1 | 10 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر قطع و وصل سایز تا 4" | 32 | 2.471
78780382 | 30082856 | 15664537 | 7320925 | کد 593116 ردیف 2 | 8 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر قطع و وصل سایز از 4" تا 8" | 33 | 2.471
310244726 | 186980050 | 12013955 | 6637879 | کد 593116 ردیف 3 | 24 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر قطع و وصل سایز از 8" تا 12" | 34 | 2.471
107646845 | 42073457 | 19875670 | 10644036 | کد 593116 ردیف 4 | 4 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیر قطع و وصل سایز از 12" تا 20" | 35 | 2.471
352715091 | 152628755 | 15094432 | 3462507 | کد 593117 ردیف 1 | 29 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیراطمینان سایز تا 4" | 36 | 2.471
153700824 | 55428658 | 12587277 | 3384771 | کد 593117 ردیف 2 | 10 | عدد | نصب/ کالیبراسیون/ کنترل مشخصات شیراطمینان سایز از 4" تا 8" | 37 | 2.471
1991025959 | 523850111 | 241767 | 60736 | کد 593171- ردیف 1-ستون 1 | 7310 | متر | کابل کشی و اتصالات- خواباندن کابلها-زیر زمینی و ...-کابل سیگنال-2~10 core | 38 | 2.471
2625856251 | 1679929577 | 250943 | 77921 | کد 593171- ردیف 2-ستون 1 | 16613 | متر | کابل کشی و اتصالات- خواباندن کابلها-زیر زمینی و ...-کابل سیگنال-12~20 core | 39 | 2.471
177808276 | 102831312 | 283186 | 77355 | کد 593171- ردیف 3-ستون 1 | 1020 | متر | کابل کشی و اتصالات- خواباندن کابلها-زیر زمینی و ...-کابل سیگنال-22~30 core | 40 | 2.471
1347692298 | 1165162138 | 207037 | 103968 | کد 593171- ردیف 4-ستون 1 | 8840 | متر | کابل کشی و اتصالات- خواباندن کابلها-زیر زمینی و ...-کابل سیگنال-32~40 core | 41 | 2.471
1842814969 | 618274145 | 250943 | 77921 | کد 593173- ردیف 1-ستون 1 | 11522 | متر | کابل کشی و اتصالات- خواباندن کابلها-زیر زمینی و ...-کابل سیستم اعلان خطر-S<16 mm2 | 42 | 2.471
5471009400 | 1360373794 | 187955 | 115078 | کد 593174- ردیف 1-ستون 1 | 23556 | متر | کابل کشی و اتصالات- خواباندن کابلها-سینی و ...-کابل سیگنال-2~10 core | 43 | 2.471
3157090469 | 1233857596 | 166674 | 88035 | کد 593176- ردیف 1-ستون 1 | 20078 | متر | کابل کشی و اتصالات- خواباندن کابلها-سینی و ...-کابل سیستم اعلان خطر-S<16 mm2 | 44 | 2.471
671317875 | 209565825 | 129391 | 86312 | کد 593176- ردیف 1-ستون 2 | 3060 | متر | کابل کشی و اتصالات- خواباندن کابلها-سینی و ...-کابل سیستم اعلان خطر-S<16 mm2 | 45 | 2.471
1132166651 | 435815021 | 326039 | 64519 | کد 593183- ردیف 1-ستون 1 | 4930 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیگنال-2~4 core | 46 | 2.471
1238701184 | 534676477 | 602259 | 163070 | کد 593183- ردیف 2-ستون 1 | 2380 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیگنال-5~10 core | 47 | 2.471
17347098477 | 5027847279 | 622556 | 373096 | کد 593183- ردیف 3-ستون 1 | 16613 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیگنال-12~20 core | 48 | 2.471
760204976 | 364539926 | 1255668 | 336191 | کد 593183- ردیف 4-ستون 1 | 1020 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیگنال-22~30 core | 49 | 2.471
11750057440 | 3193376078 | 1562246 | 456157 | کد 593183- ردیف 5-ستون 1 | 8840 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیگنال-32~40 core | 50 | 2.471
767898093 | 478310138 | 323612 | 286031 | کد 593183- ردیف 1-ستون 3 | 2210 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیستم اعلان خطر-2~4 core | 51 | 2.471
7049275895 | 2884138717 | 1154760 | 959093 | کد 593183- ردیف 3-ستون 3 | 3570 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیستم اعلان خطر-12~20 core | 52 | 2.471
8397776698 | 4650658233 | 1858198 | 739052 | کد 593183- ردیف 4-ستون 3 | 4760 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار با غلاف سربی-سیستم اعلان خطر-22~30 core | 53 | 2.471
5163174101 | 2221540990 | 258777 | 82445 | کد 593184- ردیف 1-ستون 1 | 23556 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار-سیگنال-2~4 core | 54 | 2.471
5523072844 | 2999194409 | 606142 | 215982 | کد 593184- ردیف 1-ستون 3 | 20078 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-زره دار-سیستم اعلان خطر-2~4 core | 55 | 2.471
998224037 | 617351240 | 516153 | 193131 | کد 593185- ردیف 1-ستون 3 | 3060 | متر | کابل کشی و اتصالات-سر سیم بندی اتصالات-بدون زره-سیستم اعلان خطر-2~4 core | 56 | 2.471
5103549562 | 1096374409 | 984707 | 364843 | کد 593191- ردیف 1-ستون 1 | 5355 | متر | مسیرهای عبور کابل-سینی ها-W<=10cm-STRAIGHT | 57 | 2.471
826494329 | 520923370 | 1844871 | 1071481 | کد 593191- ردیف 1-ستون 2 | 544 | متر | مسیرهای عبور کابل-سینی ها-W<=10cm-TEE | 58 | 2.471
1367995704 | 476310012 | 157259 | 53153 | کد 593191- ردیف 1-ستون 3 | 5899 | متر | مسیرهای عبور کابل-سینی ها-W<=10cm-COVER | 59 | 2.471
2424095776 | 954435946 | 967374 | 290542 | کد 593191- ردیف 2-ستون 1 | 2040 | متر | مسیرهای عبور کابل-سینی ها-W<=30cm , W>10-STRAIGHT | 60 | 2.471
568104463 | 336115109 | 2097306 | 872381 | کد 593191- ردیف 2-ستون 2 | 204 | متر | مسیرهای عبور کابل-سینی ها-W<=30cm , W>10-TEE | 61 | 2.471
450546308 | 246578153 | 213906 | 87155 | کد 593191- ردیف 2-ستون 3 | 2244 | متر | مسیرهای عبور کابل-سینی ها-W<=30cm , W>10-COVER | 62 | 2.471
764480401 | 410486372 | 735495 | 476613 | کد 593191- ردیف 3-ستون 1 | 935 | متر | مسیرهای عبور کابل-سینی ها-W<=60cm , W>30-STRAIGHT | 63 | 2.471
239621673 | 196513267 | 3798026 | 1788888 | کد 593191- ردیف 3-ستون 2 | 102 | متر | مسیرهای عبور کابل-سینی ها-W<=60cm , W>30-TEE | 64 | 2.471
212889327 | 174804171 | 432609 | 130544 | کد 593191- ردیف 3-ستون 3 | 1037 | متر | مسیرهای عبور کابل-سینی ها-W<=60cm , W>30-COVER | 65 | 2.471
84566159 | 34450680 | 758963 | 261258 | کد 593194- ردیف 12 | 170 | متر | مسیرهای عبور کابل-کاندویت ها-پی وی سی | 66 | 2.471
3704533076 | 1830771027 | 1132526 | 713336 | کد 593182- ردیف 6 | 3077 | عدد | کابل کشی و اتصالات-نصب گلندها-ضد انفجار-فلزی-M20 | 67 | 2.471
520270692 | 136355119 | 5210870 | 2226179 | کد 593182- ردیف 8 | 85 | عدد | کابل کشی و اتصالات-نصب گلندها-ضد انفجار-فلزی-M32 | 68 | 2.471
294603156 | 180589991 | 9840042 | 2840218 | کد 593182- ردیف 9 | 51 | عدد | کابل کشی و اتصالات-نصب گلندها-ضد انفجار-فلزی-M40 | 69 | 2.471
433007025 | 177287532 | 8460037 | 5640879 | کد 593182- ردیف 10 | 42.5 | عدد | کابل کشی و اتصالات-نصب گلندها-ضد انفجار-فلزی-M50 | 70 | 2.471
597079845 | 254818142 | 360592 | 77274 | کد 593125- ردیف 1 | 1834.3 | کیلوگرم | جعبه تقسیم - وزن تا 25 کیلوگرم | 71 | 2.471
7676495475 | 2633371193 | 69794973 | 27026443 | کد 593141- ردیف 2 | 125.8 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-لوله کشی (هوک آپ) ادوات PD - جنس SS | 72 | 2.471
8130090928 | 3886531768 | 48080304 | 20179866 | کد 593142- ردیف 2 | 290.7 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-لوله کشی (هوک آپ) ادوات P - جنس SS | 73 | 2.471
3870882686 | 1993764267 | 20024785 | 8150666 | کد 593143- ردیف 2 | 285.6 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-لوله کشی (هوک آپ) فشار سنج ها - جنس SS | 74 | 2.471
2109459626 | 932180791 | 14823212 | 6045053 | کد 593144- ردیف 1 | 125.8 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-تیوبینگ ها (هوک آپ) ادوات PD - جنس SS | 75 | 2.471
3747560940 | 1372505650 | 8587632 | 5585550 | کد 593145- ردیف 1 | 290.7 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-تیوبینگ ها (هوک آپ) ادوات P - جنس SS | 76 | 2.471
583565152 | 222532618 | 10645279 | 2657809 | کد 593146- ردیف 1 | 51 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-تیوبینگ ها (هوک آپ) فشار سنج ها - جنس SS | 77 | 2.471
14748080667 | 2886185756 | 16203603 | 8575878 | کد 593147- ردیف 2 | 525.3 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-دو راهه-جنس SS | 78 | 2.471
5016813321 | 3386666158 | 22317180 | 11309894 | کد 593148- ردیف 2 | 176.8 | مجموعه | لوله کشی های فرآیندی ابزاردقیق-پنج راهه-جنس SS | 79 | 2.471
1317186527 | 670065843 | 1071116 | 467284 | کد 593153- ردیف 1 | 1088 | متر | شبکه هوای ابزار دقیق-نصب تیوبهای فولاد زنگ نزن | 80 | 2.471
1553699886 | 581861605 | 243500 | 132801 | کد 593201- ردیف 2 | 5780 | کیلوگرم | تجهیزات اتاق کنترل- پنلها - وزن 101 تا 250 کیلو گرم | 81 | 2.471
56912897 | 26015428 | 10954084 | 4438279 | کد 593211- ردیف 1 | 5.1 | دستگاه | تجهیزات اتاق کنترل- سایر ادوات نصب شده | 82 | 2.471
173088334 | 45568816 | 10225941 | 2979517 | کد 593221- ردیف 1 | 17 | دستگاه | تجهیزات جانبی سیستم کنترل | 83 | 2.471
1156883149 | 218690454 | 11007570 | 6666110 | کد 593103- ردیف 2 | 66 | دستگاه | ادوات F&G واقع در محوطه - GAS DETECTOR | 84 | 2.471
1615065072 | 750566207 | 10017861 | 7020504 | کد 593103- ردیف 3 | 122 | دستگاه | ادوات F&G واقع در محوطه - HEAT DETECTOR | 85 | 2.471
297236844 | 135541999 | 8146320 | 2315552 | کد 593103- ردیف 5 | 48 | دستگاه | ادوات F&G واقع در محوطه - FLAME DETECTOR (UV/IR) | 86 | 2.471
59430068 | 17840675 | 14953769 | 6059089 | کد 593103- ردیف 7 | 3 | دستگاه | ادوات F&G واقع در محوطه - LINEAR HEAT DETECTOR | 87 | 2.471
455855738 | 122324727 | 6776848 | 2375931 | کد 593103- ردیف 8 | 73 | دستگاه | ادوات F&G واقع در محوطه - MANUAL CALL POINT | 88 | 2.471
396397482 | 171678588 | 11081541 | 4412627 | کد 593103- ردیف 9 | 36 | دستگاه | ادوات F&G واقع در محوطه - BEACON | 89 | 2.471
330825266 | 72413546 | 8143942 | 5278521 | کد 593103- ردیف 10 | 21 | دستگاه | ادوات F&G واقع در محوطه - SIREN | 90 | 2.471
1810387827 | 585905959 | 24774470 | 10963990 | کد 593301- ردیف 1 | 80 | لوپ | عملیات لوپ چک-لوپ حلقه بسته | 91 | 2.471
13554110366 | 4292035716 | 14314136 | 5726797 | کد 593301- ردیف 2 | 950 | لوپ | عملیات لوپ چک-لوپ حلقه باز | 92 | 2.471
255222945166 | 75050113044 | [5 empty] | مجموع

## C.tashilat
جدول 17-1: هزینه تسهیلات کارفرما جهت ماموریت داخل کشور
| هزینه | تعداد | هزینه واحد | شرح
| 11174209658 | 300 | 38745780 | بلیط رفت و برگشت داخلی (با محوریت اهواز)
| 1088540808 | 300 | 7318600 | ترانسفر فرودگاهی
| 18000920852 | 865 | 11672719 | ایاب و ذهاب در سطح شهر واسطه و مقصد
| 25202841293 | 865 | 26890408 | اقامت در هتل پنج ستاره در اتاق تک تخته به ازای هر نفر- شب
| 15410443697 | 865 | 15609625 | خورد و خوراک 3 وعده در روز
| 90550334155 |  |  | مجموع
توضیح جدول 1-17 : تعداد تقریبی ماموریتهای داخل کشورپرسنل کارفرما معادل 865 نفر-روز مطابق مدرک شرح خدمات و تسهیلات کارفرما به شرح ذیل: 250 نفر -روز جهت شرکت در جلسات و 255 نفر-روز جهت دوره اموزشی و360 نفر روز برای بازدید از مراحل ساخت کالا در تهران یا سایر نقاط کشور (مبدا : اهواز). هر ماموریت بطور متوسط 3 روز منظور شده است. لذا جمعا 300 سفر و به مدت 865 شب اقامت منظور شده است.
جدول 17 -2: هزینه تسهیلات کارفرما جهت ماموریت خارج کشور
| هزینه | تعداد | هزینه واحد | شرح
| 28326 | 40 | 600 | بلیط رفت و برگشت خارجی و بیمه (متوسط قیمت)
| 2000 | 40 | 50 | ترانسفر فرودگاهی
| 14766 | 160 | 100 | ایاب و ذهاب در سطح شهر واسطه و مقصد
| 14273 | 160 | 120 | اقامت در هتل پنج ستاره در اتاق تک تخته به ازای هر نفر- شب
| 8892 | 160 | 80 | خورد و خوراک 3 وعده در روز
| 6000 | 40 | 150 | هزینه امور کنسولی و ویزا
| 53078 |  | 1100 | مجموع
| 45330206822 |  |  | معادل ریالی
توضیح جدول 2-17 : تعداد تقریبی ماموریتهای خارج کشورپرسنل کارفرما مطابق مدرک شرح خدمات و تسهیلات کارفرما معادل است با: 120 نفر شرکت در مراحل ساخت و 40 نفر-روز جهت حضور احتمالی در آزمایشات هر ماموریت بطور متوسط 4 روز منظور شده است. لذا جمعا 40 سفر و به مدت 160 شب اقامت منظور شده است.
جدول 17-3: - هزینه آموزشی عملیاتی (اپراتوری) به میزان 192 نفر-روز
| هزینه | تعداد | هزینه واحد | شرح
| 3415577894 | 192 | 15609625 | خورد و خوراک 3 وعده در روز در سایت
| 2204077501 | - | یک قلم | امکانات سخت افزاری و نرم افزاری
| 603083628 | - | یک قلم | تدارک مواد آموزشی شامل تکثیر جزوه و کتاب
| 2894576908 | - | یک قلم | برگزاری دوره نقشه برداری
| 5834889198 |  |  | مجموع
مرجع : مدرک شرح خدمات و تسهیلات مورد نیاز کارفرما به شماره M9003-BD-GN-OTH-26010

## C.tashilat (2)
جدول 17-4: هزینه تسهیلات کارفرما مربوط به احداث کمپهای دستگاه نظارت کلیه بندهای اشاره شده در ذیل مربوط به مدرک "مشخصات فنی کمپهای دستگاه نظارت به شماره M9003-BD-GN-OTH-26011میباشد
هزینه (ریال) | توضیحات | شرح
311287462345 | به مساحت 900 متر با هزینه محاسبه شده برای احداث ساختمان | کمپ اصلی استقرار کارفرما مطابق مشخصات منرج در بند 4
223856849990 | توضیح : طبق استعلام مشخصات درخواستی | کمپ فرعی استقرار کارفرمامندرج در بند 5.1
132463946525 | حراست فيزيكي و سيستم دوربين مدار بسته، روشنايي، فضاي سبز | محوطه سازی کمپ اصلی و فرعی مطابق مشخصات منرج در بند 4.2و5.2
12745072038 | یک نفر آبدارچی به صورت شبانه‌روزی. یک نفر آشپز بصورت روزانه. یک نفر نظافتچی به صورت روزانه. یک نفر نگهبان به صورت شبانه روزی | تامین نیروی خدماتی برای طول مدت پروژه مطابق بند 6.1
361809267977 | سه وعده غذاي گرم، میوه فصل، دسر ، آب معدنی ، نوشیدنی و غیره در روز به طور ميانگين براي 20 نفر نمایندگان کارفرما در طي زمان قرارداد در تمام روزها | تهيه و تأمين و سرو خورد و خوراک کادر نظارت کارفرما مطابق بند6.3
21615995735 | پذیرایی سرد/گرم | پذیرایی از شرکت کنندگان جلسات کارفرما
14258311614 | تجهيزات لازم و متعارف براي پرسنل کادر نظارت | تجهیز دفاتر کار، سالنها و اتاقهاي خواب مطابق بند 6.5
2773543697 |  | سيستم اعلان حريق خودكار
4542244594 | شامل كپسول آبي و پودري و گازي و غيره | تجهیزات ایمنی و آتش‌نشانی به تعداد كافي
2964498483 |  | جعبه كمكهاي اوليه .
7429729044 | (کولرهاي گازي نو تركيبي از پنجره اي و دو تكه، بخاري از نوع رادياتور روغني برقي. سه دستگاه آبگرمكن برقي با مخزن 200 ليتري ) | تجهيزات سرمايشي و گرمايشي در كليه فضاها مطابق بند 7.4
9451928325 | ( مبلمان دفتری و مبلمان پذيرايي، کابینت نگهداری نقشه ها و مدارک پروژه، کابینت پرونده و كابينت بايگاني به تعداد كافي، نوشت‌افزار و غيره.) | لوازم و تجهيزات اداري مطابق بند5، 6 و 7.6
13598965742 | (تلويزيون رنگي 48 اينچ از نوع LEDبه تعداد 2 دستگاه، تلويزيون رنگي 32 اينچ از نوع LED به تعداد 8 دستگاه، يخچال كوچك در هر اتاق خواب، مبلمان نشيمن، خواب و راحتي و مطالعه.) | لوازم و تجهيزات رفاهي: مطابق بند 7.7 | 2 | 0
4441456906 | يخچال، اجاق و فر گاز، مايكروفر، ماشين لباسشويي، میز و لوازم غذاخوري،تجهيزات آبدارخانه، كابينت‌بندي و تجهيزات و ظروف آشپزخانه، فريزر، كباب‌پز، هود، اگزوزفن، دستگاه تصفيه آب جهت آشپزخانه و غيره | . لوازم و تجهيزات آشپزخانه مطابق بند 7.8:
60761820669 | هفت دستگاه كامپيوتر روميزي كامل با لوازم جانبي؛ چهار دستگاه چاپگر ليزري، سه دستگاه چاپگر ليزري رنگي؛ چهار دستگاه نمابر؛ چهار دستگاه كپي؛ چهار دستگاه اسكنر؛ پنج دستگاه كامپيوتر لپ‌تاپ؛ سه خط تلفن ثابت؛ گوشي تلفن سيار | . لوازم و تجهيزات كامپيوتري مطابق بند 7.9
9073015899 | كمپ اصلي و كمپ فرعي | 7.10. لوازم و تجهيزات ورزشي متناسب با فضاهاي پيش‌بيني‌شده
60887721329 | سه دستگاه خودرو شاسي استيشن | وسيله اياب و ذهاب
7348934918 | آب و برق و گاز و خطوط تلفن و اشتراك اينترنت در كمپهاي كارفرما | تأمين و پرداخت كليه هزينه‌هاي انشعاب و هزينه جاري
740793186 | به تعداد مورد نیاز کارفرما | تکثیر نسخ نرم و سخت و اسکن اسناد قرارداد
7954303485 | به ظرفيت 5 متر مكعب در روز | بسته تصفيه فاضلاب بهداشتي
924111311359 |  | مجموع

## C.HSE(1)
جدول 18-1: براورد هزینه ایمنی کارگاه : لوازم حفاظت فردی و تجهیزات
بهای کل (ریال) |  | تعداد کل | بهای واحد (ریال) |  | زمان کل پروژه(ماه) | زمان استفاده در هر دوره (ماه) | تعداد | شرح | ردیف |  | بهای واحد (ریال)Min | بهای واحد (ریال)Max | فاکتور
17651395361 |  | 2400 | 7318600 |  | 36 | 3 | 200 | لباس کار | 1 | 12 | 222638 | 523063 | 4207776
2168818315 |  | 300 | 14629573 |  | 36 | 6 | 50 | لباس جوشکار و تجهیزات مربوطه | 2 | 6 | 614108 | 614108 | 14629573
287371525 |  | 40 | 6083532 |  | 36 | 42 | 40 | لباس سند بلاست کار و تجهیزات مربوطه | 3 | 1 | 3632475 | 31042605 | 6083532
10536162206 |  | 1500 | 6791346 |  | 36 | 6 | 250 | کفش ایمنی | 4 | 6 | 334362 | 523063 | 4666069
306817795 |  | 35 | 15655987 |  | 36 | 42 | 35 | کمربند ایمنی | 5 | 1 | 122438 | 1409678 | 7450148
1146462756 |  | 400 | 3362768 |  | 36 | 21 | 200 | کلاه ایمنی | 6 | 2 | 32514 | 523063 | 1228630
13662175794 |  | 19807 | 799833 |  | 36 | 0.5 | 200 | دستکش کارگر ساده | 7 | 72 | 26887 | 44111 | 279063
1297855031 |  | 1080 | 1130656 |  | 36 | 1 | 30 | دستکش ورق کار | 8 | 36 | 44111 | 44111 | 6083532
1741745671 |  | 540 | 4474962 |  | 36 | 2 | 30 | دستکش مواد شیمیایی | 9 | 18 | 108555 | 222638 | 3220746
11694174146 |  | 360 | 25758838 |  | 36 | 3 | 30 | دستکش برق کار | 10 | 12 | 1036432 | 2614271 | 1966764
5929427910 |  | 19807 | 292475 |  | 36 | 0.5 | 200 | ماسک گرد و غبار استاندارد فیلتر دار | 11 | 72 | 11739 | 32216 | 1966764
2861163859 |  | 300 | 7332239 |  | 36 | 6 | 50 | ماسک فیلتردار جهت رنگ آمیزی مخازن | 12 | 6 | 119689 | 476116 | 7217722
18510962 |  | 3 | 5353912 |  | 36 | 42 | 3 | زنگ اعلام شرایط اضطراری | 13 | 1 | 271809 | 469579
4115304526 |  | 3600 | 934408 |  | 36 | 1 | 100 | علائم و تابلوهای هشدار دهنده ایمنی و آموزشی | 14 | 36 | 2500 | 79214
484556864 |  | 90 | 7911657 |  | 36 | 6 | 15 | لباس کار،کلاه و چکمه برای کارکنان آشپزخانه و آبدارخانه ها | 15 | 6 | 523063 | 469579
6080766589 |  | 288 | 20431931 |  | 36 | 1 | 8 | جعبه کمکهای اولیه با تجهیزات کامل | 16 | 36 | 90695 | 1966764
10055071 |  | مقطوع | 1076152 |  | 36 | 1 |  | نوار محدوده خطر | 17 | 36 | 54149 | 66541
2336193418 |  | 60 | 52638110 |  | 36 | 42 | 60 | کپسول اطفاء حریق 12Kg (نوعC) (مربوط به دوران شروع تا پایان پروژه) | 18 | 1 | 3672594 | 2945052
152368928 |  | 10 | 21471415 |  | 36 | 42 | 10 | کپسول اطفاء حریق 12Kg (نوعB) (مربوط به دوران شروع تا پایان پروژه) | 19 | 1 | 637623 | 637623
19417767 |  | 2 | 9952441 |  | 36 | 42 | برای کلیه ی اتاقها و اماکن سرپوشیده | سیستم دودیاب و حسگرهای آن (مربوط به دوران شروع تا پایان پروژه) | 20 | 1 | 766478 | 766478
1822468236 |  | 3 | 425202954 |  | 36 | 42 | برای تمام ساختمانها و کانکس ها | سیتم ارتینگ (مربوط به دوران شروع تا پایان پروژه) زمین شن زار | 21 | 1 | 26474806 | 26474806
2894576908 |  | 6 | 328087117 |  | 36 | 42 | برای 6 ساختمان | صاعقه گیر (مربوط به دوران شروع تا پایان پروژه) | 22 | 1 | 34483486 | 34483486
86559430016 | [7 empty] | مجموع | 23
جدول 18 -2: براورد هزینه ایمنی کارگاه : نیروی انسانی
| جمع (ریال) |  | زمان کل پروژه(ماه) | مقدار حقوق ماهیانه(ریال) |  |  | واحد / نفر | عنوان | ردیف
| 11379858165 |  | 30 | 488503596 |  |  | 1 | کارشناس HSE جهت سایت ویزیتو نظارت برانجام ایمن کارها | 1
| 11379858165 |  | 30 | 488503596 |  |  | 1 | کارشناس IMS جهت مستندسازی فرآیندهای مربوطه و کارهای داکیومنتی | 2
| 20575804971 | [6 empty] | مجموع | 3

## C.HSE(2)
جدول 18-3 - براورد هزینه ایمنی کارگاه : سنجش و اندازه گیری (1) - اندازه گیری آلاینده های فیزیکی،شیمیایی و ارگونومی در محیط کار
بهای کل ریال | تعداد دفعات اندازه گیری در هر سال | کل زمان پروژه |  | بهای اندازه گیری در هر دوره |  |  | عنوان | ردیف
15348257 | 30 | 36ماه |  | 259108 |  |  | نور | 1
166561149 | 30 | 36ماه |  | 2310558 |  |  | صدا(اکتاو،دزیمتری،محیط کار) | 2
560192254 | 10 | 36ماه |  | 12637427 |  |  | هوا | 3
112521872 | 10 | 36ماه |  | 7318600 |  |  | سنجش غبار زیست محیطی | 4
148990404 | 10 | 36ماه |  | 7423460 |  |  | سنجش گازهای محیط کار | 5
205089330 | 30 | 36ماه |  | 1574357 |  |  | ارتعاش | 6
27554971 | 10 | 36ماه |  | 799833 |  |  | استرس گرمایی | 7
86711530 | 30 | 36ماه |  | 799833 |  |  | اشعهX,UV,IR | 8
308730939 | 20 | 36ماه |  | 7318600 |  |  | گرد و غبار | 9
761775851 | 30 | 36ماه |  | 5317582 |  |  | فیوم جوشکاری | 10
377790336 | 30 | 36ماه |  | 3605315 |  |  | گازهای خروجی ماشین آلات | 11
277455687 | 3 | 36ماه |  | 39145313 |  |  | آب آشامیدنی | 12
20065164 | 3 | 36ماه |  | 6945658 |  |  | کارشناسی | 13
3394150075 | [6 empty] | مجموع | 14
جدول 18-4: براورد هزینه ایمنی کارگاه : سنجش و اندازه گیری (2)
بهای کل(ریال) | دفعات انجام آزمایش در کل پروژه | کل زمان پروژه | بهای انجام آزمایشات برای هر نفر(ریال) |  |  | تعداد نفرات | عنوان | ردیف
88142751 | 3 | 36 | 10709736 |  |  | 3 | انجام آزمایشات دوره ای طب صنعتی برای پرسنل آبدارخانه و آشپزخانه | 1
جدول 18-5: براورد هزینه ایمنی کارگاه : آموزش
بهای کل (ریال) | بهای دوره (ریال) | زمان دوره(روز) | تعداد دوره در کل زمان پروژه | زمان کل پروژه (سال) | زمان استفاده در هر دوره (ماه) | تعداد دوره در سال | سرفصل دوره ها | ردیف
358306718 | 284778206 | 1 | 2 | 3 | 18 | 2 | MSDS کار با مواد شیمیایی و | 1
901847233 | 284778206 | 1 | 3 | 3 | 12 | 2 | ایمنی داربستها،کار در ارتفاع،بالابرها،جرثقیل و لیفتراکها | 2
284778206 | 284778206 | 1 | 1 | 3 | 36 | 2 | ایمنی برق و برق صنعتی،صاعقه و رعد و برق و سیستمهای ارتینگ | 3
901847233 | 284778206 | 1 | 3 | 3 | 12 | 3 | آتش نشانی و اطفاء حریق | 4
151466801 | 151466801 | 1 | 1 | 3 | 36 | 1 | آشنایی با استانداردهای Iso9001و TS29001 | 5
151466801 | 151466801 | 1 | 1 | 3 | 36 | 1 | آشنایی با استانداردهای Iso 14001 | 6
151466801 | 151466801 | 1 | 1 | 3 | 36 | 2 | آشنایی باOHSAS18001 | 7
452499608 | 151466801 | 1 | 2 | 3 | 18 | 2 | کنترل عملیاتHSE،IMS و پرمیتها | 8
901847233 | 284778206 | 1 | 3 | 3 | 12 | 1 | ایمنی کار با پرتوها و اشعه ها | 9
603083628 | 151466801 | 1 | 3 | 3 | 12 | 3 | اورژانس ،کمکهای اولیه و ارگونومی و مدیریت بحران | 10
901847233 | 284778206 | 1 | 3 | 3 | 12 | 2 | ایمنی جوشکاری، برشکاری و عملیات سند بلاست | 11
284778206 | 284778206 | 1 | 1 | 3 | 36 | 2 | انبارداری و رعایت اصول مربوطه | 12
5684473657 | [6 empty] | مجموع | 13
ردیف
1

## C.Foundation-1
جدول الف : ریز برآورد متره فونداسیون تجهیزات
| حجم خاکبرداري | حجم خاکریزی | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد | کوبیدن خاک | ASPHALT | Geotextile | Geomembrane
فونداسیون های تجهیزات | متر مکعب | متر مکعب | متر مربع | متر مکعب | متر مکعب | کيلو گرم | متر مکعب | متر مربع | متر مربع | متر مربع
FOUNDATION OF OFF-SPEC TANK | 1960 | 1480 | 340 | 100 | 320 | 32514 | 1480 | 1000 | 1340 | 1340
FOUNDATION OF DILUTION WATER TANK | 480 | 100 | 100 | 40 | 240 | 22116 |  | 160 | 280 | 280
FOUNDATION OF POTABLE WATER TANK | 90 | 40 | 100 | 5 | 80 | 5800
FOUNDATION OF DISPOSAL TANK | 360 | 300 | 260 | 20 | 240 | 25592 | 200 | 20 | 280 | 280
FOUNDATION OF DIRTY OILTANK | 90 |  | 50 | 120 | 20 | 3600 |  | 20 | 60 | 60
FOUNDATION OF FIRE WATER STORAGE TANK | 1080 | 200 | 240 | 80 | 500 | 45534 | 180 | 50
FOUNDATION OF SKIMMER TANK | 720 | 560 | 480 | 40 | 480 | 39559 | 400 | 160 | 280 | 280
FOUNDATION OF FREE WATER K.O DRUM | 1500 | 700 | 900 | 100 | 0 | 46879 | 60
FOUNDATION OF FUEL GAS K.O. DRUM | 64 | 8 |  | 2 | 50 | 600
FOUNDATION OF AIR RECIEVER | 30 | 16 | 15 | 3 | 20 | 1500
FOUNDATION OF FLARE K.O. DRUM | 28 |  | 44 | 3 | 20 | 2600
FOUNDATION OF HC CLOSED DRAIN DRUM | 16 |  | 26 | 2 | 12 | 1800
FOUNDATION OF DIESEL oil STORAGE TANK | 80 | 34 | 30 | 30 | 5 | 3600
FOUNDATION OF DESALTER FOUNDATION | 900 | 500 | 400 | 40 | 500 | 32216 | 100
FOUNDATION OF HEATERS FOUNDATION | 380 | 160 | 280 | 32 | 280 | 22116 | 100
FOUNDATION OF EXCHANGER FOUNDATION | 24 |  | 36 | 4 | 24 | 2400
FOUNDATION OF DEARATOR FOUNDATION | 38 | 18 | 70 | 26 | 42 | 2140 | 20
FOUNDATION OF IGF FOUNDATION | 240 | 120 | 840 | 30 | 80 | 5600 | 40
FOUNDATION OF NUTSHELL FILTER | 110 | 20 | 84 | 12 | 60 | 5200 | 20
FOUNDATION OF COLD FLARE | 32 | 4 |  | 2 | 30 | 500
FOUNDATION OF HOT FLARE | 28 | 4 |  | 2 | 30 | 440
FOUNDATION OF COMPRESSOR (4no.) | 12 |  | 20 | 4 | 20 | 800
FOUNDATION OF PROCESS PUMPS (~ 40NO.) | 960 | 120 |  | 60 | 900 | 11974 | 80
FOUNDATION OF FIREWATER PUMP(5 no.) | 50 |  | 80 | 12 | 36 | 3400
FOUNDATION OF AIR DRYER | 64 | 8 |  | 2 | 50 | 600
FOUNDATION OF DIESEL GENERATOR | 288 | 80 | 46 | 4.8 | 40 | 3500
FOUNDATION OF INJECTION PACKAGE (9 NO.) | 40 |  | 60 | 20 | 70 | 5160
TOTAL : | 9664 | 4472 | 4501 | 795.8 | 4149 | 363170 | 2680 | 1410 | 2240 | 2240

## C.Shelters-1
جدول ب-1 : ریز برآورد متره سایبانها - فونداسیون و کف سازی
مشخصات سایبان |  | فونداسیون | [7 empty] | کف سازی
شرح سایبان | متراژ | حجم خاکبرداري | حجم خاکریزی | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد | کوبیدن خاک | انکربولت | بلوکاژ (30سانتیمتر) | بتن با عيار150 | بتن با عيار300 | ميلگرد | درزبندی کف
| متر مربع | متر مکعب | متر مکعب | متر مربع | متر مکعب | متر مکعب | کيلو گرم | متر مکعب | کیلو گرم | متر مکعب | متر مکعب | متر مکعب | کيلو گرم | دسی متر مکعب
احداث سایبان پمپ 1 نمکزدایی (ناحیه 8) | 600 | 1010 | 600 | 240 | 90 | 140 | 6500 | 300 | 250 | 180 | 30 | 90 | 3000 | 720 | 10
احداث سایبان پمپ 2 نمکزدایی (ناحیه 9) | 180 | 303 | 180 | 72 | 27 | 42 | 1950 | 90 | 75 | 54 | 9 | 27 | 900 | 216 | 3
احداث سایبان پمپ 3 نمکزدایی (ناحیه 5) | 90 | 151.5 | 90 | 36 | 13.5 | 21 | 975 | 45 | 37.5 | 27 | 4.5 | 13.5 | 450 | 108 | 1.5
احداث سایبان پمپ 4 نمکزدایی (ناحیه 4) | 240 | 404 | 240 | 96 | 36 | 56 | 2600 | 120 | 100 | 72 | 12 | 36 | 1200 | 288 | 4
احداث سایبان پمپ 5 نمکزدایی (ناحیه 1) | 60 | 101 | 60 | 24 | 9 | 14 | 650 | 30 | 25 | 18 | 3 | 9 | 300 | 72 | 1
احداث سایبان پمپ آب آتش نشانی | 420 | 707 | 420 | 168 | 63 | 98 | 4550 | 210 | 175 | 126 | 21 | 63 | 2100 | 504 | 7
احداث سایبان پمپ بهره برداری | 425 | 808 | 480 | 192 | 72 | 112 | 5200 | 240 | 200 | 127.5 | 21.25 | 63.75 | 2125 | 576 | 8
احداث سایبان پکیج تزریق 1 نمکزدایی | 240 | 505 | 300 | 120 | 45 | 70 | 3250 | 150 | 125 | 72 | 12 | 36 | 1200 | 360 | 5
احداث سایبان پکیج تزریق 2 نمکزدایی | 180 | 303 | 180 | 72 | 27 | 42 | 1950 | 90 | 75 | 54 | 9 | 27 | 900 | 216 | 3
احداث انبار مواد1 شیمیایی | 250 | 505 | 300 | 120 | 45 | 70 | 3250 | 150 | 125 | 75 | 12.5 | 37.5 | 1250 | 360 | 5
احداث انبار مواد2 شیمیایی | 150 | 303 | 180 | 72 | 27 | 42 | 1950 | 90 | 75 | 45 | 7.5 | 22.5 | 750 | 216 | 3
توسعه سایبان پکیج تزریق بهره داری | 36 | 101 | 60 | 24 | 9 | 14 | 650 | 30 | 25 | 10.8 | 1.8 | 5.4 | 180 | 72 | 1
احداث انبار مواد شیمیایی بهره برداری نمونه-4 | 90 | 101 | 60 | 24 | 9 | 14 | 650 | 30 | 25 | 27 | 4.5 | 13.5 | 450 | 72 | 1
احداث پارکینگ | 310 | 505 | 300 | 120 | 45 | 70 | 3250 | 150 | 125 | 93 | 15.5 | 46.5 | 1550 | 360 | 5
احداث پارکینگ پست برق 33 کیلولت | 70 | 202 | 120 | 48 | 18 | 28 | 1300 | 60 | 50 | 21 | 3.5 | 10.5 | 350 | 144 | 2
احداث سایبان آتش نشانی (13 عدد) | 120 | 202 | 120 | 48 | 18 | 28 | 1300 | 60 | 50 | 36 | 6 | 18 | 600 | 144 | 2
مجموع |  | 6211.5 | 3690 | 1476 | 553.5 | 861 | 46534 | 1845 | 1537.5 | 1038.3 | 173.05 | 519.15 | 17730 | 4428
میزان واحد |  | 101 | 60 | 24 | 9 | 14 | 650 | 30 | 25 | 0.3 | 0.5 | 0.15 | 5 | 72

## C.Shelters-1 (2)
جدول ب-2 : ریز برآورد متره سایبانها - لسکلت فلزی
مشخصات سایبان |  | سازه فلزی
شرح سایبان | متراژ | ستون | سازه سقف | Girt | Strut | Purlin | پوشش سقف | سطح رنگ خور
| متر مربع | کیلو گرم | کیلو گرم | کیلو گرم | کیلو گرم | کیلو گرم | کیلو گرم | متر مربع
احداث سایبان پمپ 1 نمکزدایی (ناحیه 8) | 600 | 17960 | 19845 | 12122 | 7620 | 9144 | 9000 | 1680
احداث سایبان پمپ 2 نمکزدایی (ناحیه 9) | 180 | 6172.2 | 7086.6 | 4572 | 2286 | 2743.2 | 2700 | 504
احداث سایبان پمپ 3 نمکزدایی (ناحیه 5) | 90 | 3086.1 | 3543.3 | 2286 | 1143 | 1371.6 | 1350 | 252
احداث سایبان پمپ 4 نمکزدایی (ناحیه 4) | 240 | 8229.6 | 9448.8 | 6096 | 3048 | 3657.6 | 3600 | 672
احداث سایبان پمپ 5 نمکزدایی (ناحیه 1) | 60 | 2057.4 | 2362.2 | 1524 | 762 | 914.4 | 900 | 168
احداث سایبان پمپ آب آتش نشانی | 420 | 11656 | 12531 | 8080 | 5334 | 6400.8 | 6300 | 1176
احداث سایبان پمپ بهره برداری | 425 | 10478 | 14807 | 12617 | 5397.5 | 6477 | 6375 | 1190
احداث سایبان پکیج تزریق 1 نمکزدایی | 240 | 8229.6 | 9448.8 | 6096 | 3048 | 3657.6 | 3600 | 672
احداث سایبان پکیج تزریق 2 نمکزدایی | 180 | 6172.2 | 7086.6 | 4572 | 2286 | 2743.2 | 2700 | 504
احداث انبار مواد1 شیمیایی | 250 | 8572.5 | 9842.5 | 6350 | 3175 | 3810 | 3750 | 700
احداث انبار مواد2 شیمیایی | 150 | 5143.5 | 5905.5 | 3810 | 1905 | 2286 | 2250 | 420
توسعه سایبان پکیج تزریق بهره داری | 36 | 1234.44 | 1417.32 | 914.4 | 457.2 | 548.64 | 540 | 100.8
احداث انبار مواد شیمیایی بهره برداری نمونه-4 | 90 | 3086.1 | 3543.3 | 2286 | 1143 | 1371.6 | 1350 | 252
احداث پارکینگ | 310 | 8433 | 16697 | 7874 | 3937 | 4724.4 | 4650 | 868
احداث پارکینگ پست برق 33 کیلولت | 70 | 2400.3 | 2755.9 | 1778 | 889 | 1066.8 | 1050 | 196
احداث سایبان آتش نشانی (13 عدد) | 120 | 4114.8 | 4724.4 | 3048 | 1524 | 1828.8 | 1800 | 336
مجموع |  | 134943 | 175895 | 69498 | 49856 | 68422 | 64086 | 9690.8
میزان واحد |  | 34.29 | 39.37 | 25.4 | 12.7 | 15.24 | 15 | 2.8
|  | 0.27 | 0.31 | 0.2 | 0.1 | 0.12

## C.ROAD-1
جدول ج : ریز برآورد متره جاده ها
|  | مساحت | خاکبرداری | زیر اساس | اساس | پریمکت | تک کت | بیندر با لایه 4 cm | توپکا با لایه 4 cm | خاکریزی با تراکم 100% | خاکریزی با تراکم 95% | تونان
ردیف | شرح | متر مربع |  | متر مکعب | متر مکعب | متر مکعب | کیلو گرم | متر مربع | متر مربع | متر مکعب | متر مکعب | متر مکعب
1 | جاده های داخل واحد نمکزدایی | 1900 x 7.5 |  | 3300 | 3300 | 17245 | 7425 | 660 | 495 |  |  |  | 2200 | 7.5 | 11358
2 | جاده های داخل واحد بهره برداری | 210x6 |  | 300 | 300 | 1800 | 675 | 60 | 45 |  |  |  | 250 | 6 | 1500
3 | حاده و محوطه اسفالته پست برق نمونه-3 | 1300 |  | 230 | 230 | 1380 | 517.5 | 46 | 34.5 | [5 empty] | 1150
4 | حاده و محوطه اسفالته پست برق نمونه-4 | 1050 |  | 196 | 196 | 1176 | 441 | 39.2 | 29.4 | [5 empty] | 980
5 | جاده های دسترسی بین واحدهای جانبی | 400x6 |  | 720 | 720 | 4320 | 1620 | 144 | 108 |  |  |  | 600 | 6 | 3600
6 | جاده های دسترسی اصلی به واحد نمکزدایی | 500x6 |  | 986.4 | 986.4 | 5918.4 | 2219.4 | 197.28 | 147.96 |  |  |  | 822 | 6 | 4932
7 | جاده های پاترول | 1500x6 |  | 2400 | 2400 | 19807 | 5400 | 480 | 360 |  |  |  | 2000 | 6 | 12117
8 | جاده های داخلی حوضچه تبخیر | 500x6 |  |  |  | 5040 |  |  | 126 | 840 | 1680 | 840 | 700 | 6 | 4200
9 | جاده های داخلی فلرها | 450 |  |  |  | 360 |  |  | 9 | 60 | 120 | 60 |  |  | 300
10 | جاده های داخلی گودال های سوزا | 300 |  |  |  | 300 |  |  | 7.5 | 50 | 100 | 50 |  |  | 250
11 | احداث جاده خطوط لوله نفت 12" | 12000x6 | 26887 | [7 empty] | 7500 |  | 11974 | 6 | 119689
12 | احداث جاده خطوط لوله پساب | 3200x6 | 6000 | [7 empty] | 2250 |  | 4500 | 6 | 16624
13 | پارکینگ واحد نمکزدایی | 600 |  | 88 | 88 | 528 | 198 | 17.6 | 13.2 | [5 empty] | 440
14 | پارکینگ پست برق نمونه-3 | 200 |  | 40 | 40 | 240 | 90 | 8 | 6 | [5 empty] | 200
15 | مجموع |  | 41285 | 8260.4 | 8260.4 | 68158 | 11155 | 1652.08 | 1381.56 | 950 | 11652 | 950
توضیح : برای میزان خاکبرداریجاده های خطوط لوله با نظر مشاور ژئوتکنیک، 70% زمین از نوع سخت، 20% از نوع نرم و 10% سنگی در نظر گرفته شده است.
فنس ها
[14 empty] | متراژ بر حسب متر |  | عنوان | ردیف
[13 empty] | 1160 |  |  | فنس واحد نمکزدایی | 1
[13 empty] | 500 |  |  | فنس واحد بهره برداری | 2
[13 empty] | 170 |  |  | فنس پست برق نمونه-3 | 3
[13 empty] | 150 |  |  | فنس پست برق نمونه-4 | 4
[13 empty] | 200 |  |  | فنس واحدهای جانبی | 5
[13 empty] | 700 |  |  | فنس حوضچه تبخیر | 5

## C.OTHERS-1
جدول د : ریز برآورد متره ابنیه متفرقه
| حجم خاکبرداري | حجم خاکریزی | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد | پایه گالوانیزه برای نصب فنس | فنس گالوانیزه برای نصب فنس | Geotextile | Geomembrane (1.5mm) | آجر نسوز
فونداسیون ها | متر مکعب | متر مکعب | متر مربع | متر مکعب | متر مکعب | کیلو گرم | کیلو گرم | کیلو گرم | متر مربع | متر مربع | تن | M2 | M2 | M2
Cable Trench
Culvert
Sump Pit (H/C Drain & KNOCK Out Drain) | 8400 | 500 | 2800 | 100 | 1900 | 95761
Sump Pit (IGF) | 2600 | 900 | 2200 | 200 | 2000 | 62036
Bound Wall | 800 | 300 | 2200 | 320 | 800 | 124787
PIPEWAY | 15583 | 3000 | 0 | 240 | 0 | 0
هزینه ساخت پل دسترسی داخل واحد (6 عدد در نمکزدایی و 1 عدد درحوضچه تبخیر) | 5600 | 0 | 6000 | 140 | 2100 | 100059
هزینه ساخت پل دسترسی خارج واحد (4 عدد) | 3200 | 0 | 3600 | 80 | 1300 | 84874
هزینه ساخت پل ورودی واحد با دهانه حداقل 40 متر | 2200 | 0 | 2800 | 60 | 1000 | 59191
API SEPARATOR | 2400 | 60 | 500 | 16 | 280 | 7227 | 30 |  |  | 180
احداث حوضچه تبخیربا در نظر گرفتن خاکریزهای میانی وپیرامونی وحوضچه آرامش | 400803 | 23825 | 440 | 10 | 220 | 19647 |  |  | 7800 | 7800 |  | 8900 | 1200
BURN PIT | 1200 | 0 | 0 | 120 | 0 | 1600 |  |  | 750 | 750 | 50 |  |  | 240
احداث سه گودال سوزا چاههای 58 و 58 الف | 1800 | 0 | 0 | 360 | 0 | 4800 |  |  | 2250 | 2250 | 150 |  |  | 240
برچیدن سه گودال سوزا چاههای 58 و 58 الف | 4000 | 7000 | 0 | 0 | 0 | 0
فنس واحد نمکزدایی (طول تقریبی 1150متر) | 1290.24 | 0 | 4480 | 161.28 | 1484 | 13046 | 21030 | 10863 |  |  |  | 1120
فنس محوطه فلرها، گودالهای سوز(4 منطقه با طول تقریبی 800 متر) | 921.6 | 0 | 3200 | 115.2 | 1060 | 9469.7376 | 25592 | 12117 |  |  |  | 800
فنس محوطه حوضچه تبخیر(طول تقریبی 700متر) | 806.4 | 0 | 2800 | 100.8 | 927.5 | 8286.0204 | 15989 | 12236 |  |  |  | 700
فنس پیرامونی منطقه نمکزدایی (طول تقریب 960 متر) | 1105.92 | 0 | 3840 | 138.24 | 1272 | 7271 | 28326 | 19807 |  |  |  | 960
فنس محوطه پست های برق 33 کیلو ولت نمونه-3 و 3.45 نمونه-4(جمعاطول تقریبی220 2x متر) | 506.88 | 0 | 1760 | 63.36 | 583 | 5208.3557 | 8382 | 6600 |  |  |  | 440
کارهای متفرقه : کالورتها ، منهولها، چاله شیرها، و غیره | 6000 | 0 | 0 | 60 | 800 | 44111
مجموع | 249609 | 50970 | 38140 | 2284.88 | 16929 | 850530 | 84516 | 65601 | 13588 | 7738 | 200

## C.SITE-1
جدول ه : ریز برآورد متره محوطه سازی
| حجم خاکبرداری | [6 empty] | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد
| زمین سخت | زمین سنگی | زمین سنگی (با پیکور) | حجم خاکریزی | جدول بندی | شن ریزی
[8 empty] | متر مربع | متر مکعب | متر مکعب | کيلو گرم
فونداسیون ها | متر مکعب | متر مکعب | متر مکعب | متر مکعب | متر مکعب | متر مربع
محوطه سازی واحد نمکزدایی | 647109 | 156777 | 97313 | 81823 | 285 | 25592 | [5 empty] | 913989 | 989392
محوطه سازی واحد بهره برداری | 0 | 0 | 0 |  | 31.5 | 500 | [5 empty] | 0 | 0
محوطه سازی پست برق نمونه-3 | 15989 | 5000 | 2500 | 2300 | 15 | 400 | [5 empty] | 23825 | 32514
محوطه سازی پست برق نمونه-4 | 3500 | 1000 | 500 | 1200 | 15 | 400 | [5 empty] | 5000 | 11739
محوطه سازی حوضچه تبخیر | 560 | 160 | 80 | [5 empty] | Cut (m3) | Fill (m3) |  | 800 | 1600
محوطه سازی محدوده فلرها | 7000 | 2000 | 1000 | 2000 |  |  |  | Flare-1 | 3940 | 3963 |  | 11739 | 25592
محوطه سازی محدوده گودالهای سوزا | 7000 | 2000 | 1000 | 1500 |  |  |  | Flare-2 | 3496 | 2781 |  | 11739 | 25592
ترانشه تپه مجاور | [7 empty] | Burn pit | 25401 | 0 |  | 0 | 0
کارهای متفرقه : منهولها، چاله شیرها، و غیره | 200 | [6 empty] | Evaporation pond | 109557 | 11 |  | 400 | 800
مجموع | 414350 | 138396 | 93883 | 162769 | 346.5 | 23266 | [5 empty] | 545898
توضیح : با توجه به مشخصات مندرج در مدرک مکانیک خاک و استعلام از مشاور ژئو تکنینک، 30% زمین ، از نوع سنگی و 70% آن از نوع سخت
در نظر گرفته شده است.

## C.UG CIVIL-1
جدول و : ریز برآورد کانال های لوله ها و کابل های دفنی
| حجم خاکبرداری | حجم خاکریزی | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد | ماسه ریزی | بلوکاژ (30سانتیمتر) | درزبندی کف | سنگچین کانال
فونداسیون ها | متر مکعب | متر مکعب | متر مربع | متر مکعب | متر مکعب | کیلو گرم | متر مکعب | متر مکعب | دسی متر مکعب
کانال کابلهای برق و ابزاردقیق | 4600 | 2500 | 500 | 50 | 440 | 15914 | 2100
کانال کابلهای برق ارتباط واحدها دفنی | 2000 | 1200 | 180 | 6 | 40 | 3600 | 800
کانال لوله های زیر زمینی آتش نشانی | 4400 | 2440 | 300 | 12 | 96 | 6000 | 1960
کانال خط لوله زیرزمینی پساب | 800 | 360 | 100 | 6 | 40 | 1600 | 440
کانال کنی خط لوله پساب | 8000 | 3800 | 320 | 12 | 100 | 7000 | 3800 | [5 empty] | 8900 | 1200
روسازی پیاده روهای بتونی |  |  |  | 70 | 270 | 5400 |  | 540 | 450 | [5 empty] | 240
کانال جمع آوری سیلاب بیرون محوطه (طول تقریبی 1000متر و عرض متوسط و عمق یک متر) | 2600 | 400 | [7 empty] | 1000
مجموع | 28658 | 12952 | 1400 | 156 | 986 | 39975 | 9100 | 540 | 450 | 1000 |  | 900
1120
800
700
960

## C.STEEL STRUCTURE-1
جدول ط : ریز برآورد متره سازه های فلزی متفرقه
| حجم خاکبرداري | حجم خاکریزی | قالب بندي | بتن با عيار150 | بتن با عيار300 | ميلگرد | ساخت سازه فلزی | نصب سازه فلزی | سطح رنگ خور
فونداسیون ها | متر مکعب | متر مکعب | متر مربع | متر مکعب | متر مکعب | کیلو گرم | تن | تن | متر مربع
STANDPIPES (7 NO.) | 200 | 5 | 250 | 10 | 180 | 3520 | 60 | 60 | 336
ACCESS PLATFORMS(ABOUT 30 NO.) | 80 |  | 320 | 80 | 8 | 11739 | 200 | 200 | 448
ساخت سازه گنتری درایستگاه های برق | 50 |  | 80 | 6 | 44 | 1600 | 4 | 4 | 280
اجرای فونداسیون و نصب پایه های انتقال برق 66 کیلوولت(80 عدد) | 1900 |  | 4400 | 2400 | 80 | 152557 | هزینه ساخت در خرید دیده شده است | 480
اجرای فونداسیون و نصب برجهای روشنایی | 240 |  | 640 | 160 | 8 | 8000 |  | 64
اجرای فونداسیون و نصب پایه های روشنایی | 320 |  | 512 | 256 | 12.8 | 8892 |  | 80
نصب واجرای پلکان دسترسی چاله | 20 |  | 60 | 6 | 30 | 1400 | 4 | 4 | 56
ساپورت خطوط لوله و لوله کشی | 1600 |  | 7200 | 120 | 720 | 162769 | 84 | 84 | 4480
مجموع | 4410 | 5 | 9754 | 3038 | 1082.8 | 444019 | 352 | 976 | 5600

## P.ME
ITEM | TAG. NO. |  | SERVICE | SPECIFICATION | UNIT | Quantity | هزینه واحد بدون ضریب |  |  | هزینه کل بدون ضریب
[7 empty] | خرید |  |  | خرید |  | ترخیص | حمل
[7 empty] | Rls | Dollar | Euro | Rls | Euro | Rls
1 | DE | -001-A/B | 1at TRAIN DESALTER | 536 m3/hr , 19.5 bar D.P. T/T=18000 mm , ID=5300 mm | SET | 1 |  |  | 2823626 |  | 2823626 | 214189659684 | 4436260201
2 | DE | -002-A/B | 2nd TRAIN DESALTER | 537 m3/hr , 19.5 bar D.P. T/T=18000 mm , ID=5300 mm | SET | 1 |  |  | 2823626 |  | 2823626 | 214189659684 | 4436260201
3 | E | -001-A/B | SALTY CRUDE / DESALTED CRUDE HEAT EXCHANGER | COLD = 527 m³/h, HOT = 421 m³/h , D.P.=19.5barg, 5275 kw | No. | 2 | 363348092985 |  | 0 | 384253410187 | 0 | 0 | 2964498483
4 | E | -002-A/B | WATER / WATER HEAT EXCHANGER | COLD = 21 m³/h, HOT = 136.5 m³/h , D.P.=19.5barg, 1250 kw | No. | 2 | 8189489299 |  | 0 | 30355601271 | 0 | 0 | 1100642431
5 | H | -001-A1/A2 | CRUDE OIL INDIRECT FIRED HEATER | 245.4 m³/h (each) , D.P.=19.5barg 7155 kw | No. | 2 |  |  | 2089832 |  | 3981891 | 86050183905 | 4436260201
6 | H | -001-B1/B2 | CRUDE OIL INDIRECT FIRED HEATER | 245.4 m³/h (each) , D.P.=19.5barg 7155 kw | No. | 2 |  |  | 2089832 |  | 3981891 | 86050183905 | 4436260201
7 | TK | -003 | OFF-SPEC TANK | 7363 m³,H=15000mm.D=25000mm | Kg | 142134 | 530386 |  |  | 90340713883 |  |  | 2633972470
8 | P | -001-A/B | MAIN TRANSFER PUMPS | 500m3/hr, 15.2 bar, 216.3 kw | No. | 2 | 150436748608 |  | 0 | 390095441611 | 0 | 0 | 2773543697
9 | P | -002-A/B | AUXILLIARY TRANSFER PUMPS | 250m3/hr, 15.2 bar, 108.1 kw | No. | 2 | 72089205351 |  | 0 | 157260661232 | 0 | 0 | 2773543697
10 | P | -003-A/B | OFF-SPEC PUMPS | 100 m3/hr , 15.5 bar,44.2 kw | No. | 2 | 42048791743 |  | 0 | 167769172093 | 0 | 0 | 2773543697
11 | P | -005-A/B | DEGASSING WATER PUMPS | 30m3/hr, 3bar, 2.7 kw | No. | 2 | 19192788063 |  | 0 | 21004899388 | 0 | 0 | 2773543697
12 | V | -001-A/B | FREE WATER K.O DRUM | 340 m³, L=21250mm, ID=4250mm | Kg | 305647 | 1225516 |  |  | 246329473078 |  |  | 85562096
13 | TK | -101 | DILUTION WATER TANK | 1472 m³,H=12000mm, ID=12500mm | Kg | 75997 | 530386 |  |  | 41224119728 |  |  | 1321638459
14 | P | -103 | DILUTION WATER PUMPS | 40m3/hr , 10.4 bar, 12 kw | No. | 1 | 16533883040 |  | 0 | 16533883040 | 0 | 0 | 2204077501
15 | P | -106-A1/A2 | DILUTION WATER PUMPS | 20 m3/hr, 10.4 bar, 6 kw | No. | 2 | 14736900931 |  | 0 | 28807064335 | 0 | 0 | 2204077501
16 | PK | -101 | VACUUM DEAERATOR PACKAGE | 41 m³/h | No. | 1 | 174968753515 |  | 0 | 174968753515 | 0 | 0 | 308991054
17 | P | -102-A/B | DEAERATED WATER PUMPS | 20m3/hr, 2.4 bar, 1.35 kw | No. | 2 | 7367999377 |  | 0 | 13856186213 | 0 | 0 | 2204077501
18 | P | -105 | DEAERATED WATER PUMPS | 40m3/hr, 2.4 bar, 2.7 kw | No. | 1 | 6910171822 |  | 0 | 6910171822 | 0 | 0 | 2204077501
19 | TK | -102 | POTABLE WATER TANK | 32.6 m³,H=2600mm, D=4000mm | Kg | 16620 | 530386 |  |  | 18150667293 |  |  | 308991054
20 | P | -104 | POTABLE WATER FILLING PUMP | 20m3/hr, 2.5 bar, 1.4 kw | No. | 1 | 6483446849 |  | 0 | 6483446849 | 0 | 0 | 2204077501
21 | P | -201-A/B/C | WATER INJECTION MAIN PUMPS | 73m3/hr (each),36.3 bar, 73.6 kw | No. | 3 | 176769586356 |  | 0 | 660173385528 | 0 | 0 | 2773543697
22 | P | -206-A/B/C | WATER INJECTION BOOSTER PUMPS | 36.5m3/hr (each),36.3 bar, 36.5 kw | No. | 3 | 123693742350 |  | 0 | 450681034846 | 0 | 0 | 2773543697
23 | OS | -201 | OIL SKIMMER TANK | 392.5 m³,H=5000mm, D=10000mm | Kg | 40625 | 530386 |  |  | 31224404086 |  |  | 1558429746
24 | PK | -201-A/B | IGF PACKAGE | 18105 SBPD (each) | SET | 1 |  |  | 3551860 |  | 3551860 | 121851525406 | 4436260201
25 | PK | -202 | NUTSHELL FILTER PACKAGE | 36100 SBPD | SET | 1 |  |  | 1077590 |  | 1077590 | 42048791743 | 4436260201
26 | TK | -201 | DISPOSAL TANK | 942 m³,H=12000mm,D=10000mm | Kg | 39559 | 530386 |  |  | 35041294556 |  |  | 2122665422
27 | V | -301 | FUEL GAS K.O. DRUM | 1.5 m³ , T/T=2810 mm, D=860 mm | Kg | 1000 | 2111973 |  |  | 2968249503 |  |  | 85562096
28 | V | -401 | AIR RECIEVER | 30 m³, T/T=7000mm, ID=2335mm | Kg | 8140 | 762977 |  |  | 7568028429 |  |  | 85562096
29 | PK | -401-A/B | AIR COMPRESSOR PACKAGE | 553 N m³/h, 10barg | No. | 2 | 154627286732 |  | 0 | 152151580125 | 0 |  | 4436260201
30 | PK | -402 | AIR DRYER PACKAGE | 453 N m³/h | No. | 1 | 5676890635 |  | 0 | 5676890635 | 0 |  | 4436260201
31 | PK | -002-A/B | AIR COMPRESSOR PACKAGE | 300 N m³/h, 10barg | No. | 2 | 123409872698 |  | 0 | 189150877635 | 0 |  | 4436260201
32 | PK | -003 | AIR DRYER PACKAGE | 525 N m³/h | No. | 1 | 2829621352 |  | 0 | 2829621352 | 0 |  | 4436260201
33 | P | -501-A/B/C | CHEMICAL INJECTION PORTABLE PUMPS | .8m³/h, 2bar, 0.45 kw | No. | 3 | 3787165926 |  | 0 | 10899544261 | 0 | 0 | 2204077501
34 | PK | -501 | DEMULSIFIER INJECTION PACKAGE | 10-20 LIT/HR Injection Pressure = 5 barg | No. | 1 | 38330117771 |  | 0 | 38330117771 | 0 |  | 85562096
35 | PK | -502-A/B | DEMULSIFIER INJECTION PACKAGE | 10-20 LIT/HR Injection Pressure = 15 bar | No. | 2 | 39685809784 |  | 0 | 69302779250 | 0 |  | 85562096
36 | PK | -503 | OXYGEN SCAVENGER INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 4.5 bar | No. | 1 | 42943850358 |  | 0 | 42943850358 | 0 |  | 85562096
37 | PK | -504 | CORROSION INHIBITOR INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 3 bar | No. | 1 | 38330117771 |  | 0 | 38330117771 | 0 |  | 85562096
38 | PK | -505 | REVERSE DEMULSIFIER INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 3 bar | No. | 1 | 38330117771 |  | 0 | 38330117771 | 0 |  | 85562096
39 | PK | -506-A | BIOCIDE INJECTION PACKAGE (TYPE A) | 20-70 LIT/HR Injection Pressure = 3 bar | No. | 1 | 23425473998 |  | 0 | 23425473998 | 0 |  | 85562096
40 | PK | -506-B | BIOCIDE INJECTION PACKAGE (TYPE B) | 20-70 LIT/HR Injection Pressure = 3 bar | No. | 1 | 43597164993 |  | 0 | 43597164993 | 0 |  | 85562096
41 | PK | -507 | ANTI SCALE INJECTION PACKAGE | 2-10 LIT/HR Injection Pressure = 9 bar | No. | 1 | 43597164993 |  | 0 | 43597164993 | 0 |  | 85562096
42 | V | -601 | FLARE K.O. DRUM | 17.0 m³, T/T=7400 mm, ID=1600 mm | Kg | 6100 | 2111973 |  |  | 15980844496 |  |  | 85562096
43 | P | -601-A/B | FLARE K.O DRUM LIQUID PUMPS | 15m3/hr, 0.8 bar, 0.33 kw | No. | 2 | 14672969953 |  | 0 | 23383371606 | 0 | 0 | 2204077501
44 | PK | -602 | FLARE PACKAGE |  | No. | 1 | 229966487766 |  | 0 | 229966487766 | 0 |  | 85562096
45 | PK | -603 | COLD FLARE PACKAGE |  | No. | 1 | 65419741079 |  |  | 65419741079 |  |  | 85562096
46 | PK | -701 | BURN PIT IGNITION PACKAGE |  | No. | 1 |  |  | 0 |  | ردیف 44 |  | 85562096
47 | P | -701-A/B | HC CLOSED DRAIN TRANSFER PUMPS | 27.5m3/hr, 4.3 bar, 3.3 kw | No. | 2 | 32892372161 |  | 0 | 41080860040 | 0 | 0 | 2204077501
48 | P | -702A/B | HC CLOSED DRAIN DRUM SUMP PUMP | 5.5m3/hr, 7 bar. 0.11 kw | No. | 2 | 32892372161 |  | 0 | 41080860040 | 0 | 0 | 2204077501
49 | V | -701 | HC CLOSED DRAIN DRUM | 96.2 m³,T/T=10000 mm ID=3500 mm | Kg | 34097 | 3090411 |  |  | 64772674364 |  |  | 85562096
50 | P | -703-A/B | CLEAN WATER PUMPS | 11m3/hr, 1.8 bar, 0.54 kw | No. | 2 | 8189489299 |  | 0 | 30355601271 | 0 | 0 | 2204077501
51 | P | -704-A/B | RECOVERED WASTE OIL PUMPS | 11 m3/hr, 2.7 bar, 0.8 kw | No. | 2 | 17460888925 |  | 0 | 25352009756 | 0 | 0 | 2204077501
52 | P | -750 | OILY WATER SEPARATOR PUMP | 1m3/hr, 0.84 bar, 0.02kw | No. | 1 | 6263191680 |  | 0 | 6263191680 | 0 | 0 | 2204077501
53 | TK | -701 | DIRTY OILTANK | 21 m³,T/T=3000 mm, ID=3000 mm | Kg | 3600 | 530386 |  |  | 1532078218 |  |  | 85562096
54 | P | -705-A/B | DIRTY OIL PUMPS | 5m3/hr, 2bar, 0.3 kw | No. | 2 | 12456615012 |  | 0 | 36391728440 | 0 | 0 | 2204077501
55 | P | -706-A/B | RECOVERED WASTE WATER PUMPS | 33m3/hr, 1.5 bar, 1.35 kw | No. | 2 | 14672969953 |  | 0 | 23383371606 | 0 | 0 | 452499608
56 | V | -801 | DIESEL STORAGE TANK | 14.9 m³, T/T=4750mm ID=2000mm | Kg | 6100 | 530386 |  |  | 3331087949 |  |  | 85562096
57 | P | -801 | DIESEL OIL PUMP | 10m3/hr, 0.6 bar, 0.16 kw | No. | 1 | 6062783279 |  | 0 | 6062783279 | 0 | 0 | 2204077501
58 | P | -901A/B | FIRE WATER MAIN ELECTRICAL PUMP | 480m3/hr, 10 barg,133kw | No. | 2 | 36134010770 |  |  | 78213005853 |  |  | 155400299
59 | P | 902 | FIRE WATER MAIN DESEL PUMP | 480m3/hr, 10 barg,133kw | No. | 1 | 46483438699 |  |  | 46483438699 |  |  | 452499608
60 | P | -903-A/B | FIRE WATER JOCKEY PUMPS | 15m3/hr, 6 barg, 2.5 kw | No. | 2 | 2358123753 |  |  | 4211951555 |  |  | 151466801
60 | P | 108A/B | UNIT SUPPLY WATER PUMP | 15m3/hr, 6 barg, 2.5 kw | No. | 2 | 10521574010 |  | 0 | 17460888925 | 0 |  | 151466801
61 | TK | -901 | DISEL FUEL DAILY TANK | 2 m³ | Kg | 300 | 530386 |  |  | 146788743 |  |  | 2633972470
62 | TK | -902-A/B | FIRE WATER STORAGE TANK |  | Kg | 98646 | 530386 |  |  | 97347141564 |  |  | 85562096
63 | TK | -104 | SUPPLY WATER STORAGE TANK | 1717.2 m³, T/T=14000mm, ID=12500mm | Kg | 20889 | 530386 |  |  | 17735412625 |  |  | 85562096
64 | P | -904 | FIRE WATER LOADING PUMP | 30m3/hr, 3 bar, 2.5 kw | No. | 1 | 10218391469 |  | 0 | 10218391469 | 0 |  | 151466801
65 |  |  | CRANES | [6 empty] | طبق لیست زیر |  |  | 1558429746
65.1 | CR | 001 | AIR COMPRESSOR ROOM CRANE |  | No. | 1 | 18939429436 |  |  | 18939429436
65.2 | CR | 002 | CHEMICAL STORAGE SHELTER CRANE (ex) |  | No. | 1 | 44564946839 |  |  | 44564946839
65.3 | CR | 003 | CHEMICAL STORAGE SHELTER CRANE (ex) |  | No. | 1 | 44564946839 |  |  | 44564946839
65.4 | CR | 004 | CHEMICAL INJECTION PACKAGE SHELTER CRANE (ex) |  | No. | 1 | 24710948304 |  |  | 24710948304
65.5 | CR | 005 | CHEMICAL INJECTION PACKAGE SHELTER CRANE (ex) |  | No. | 1 | 24710948304 |  |  | 24710948304
65.6 | CR | 006 | WORK SHOP CRANE |  | No. | 1 | 18939429436 |  |  | 18939429436
65.7 | CR | 007 | PUMP SHELTER CRANE (ex) |  | No. | 1 | 24710948304 |  |  | 24710948304
65.8 | CR | 008 | FIRE WATER SHELTER CRANE |  | No. | 1 | 16417118056 |  |  | 16417118056
65.9 | CR | 009 | PROCESS PUMP SHELTER CRANE (ex) |  | No. | 1 | 60217002259 |  |  | 60217002259
65.10 | CR | 010 | DILUTION WATER PUMP SHELTER CRANE |  | No. | 1 | 16859965894 |  |  | 16859965894
65.11 | CR | 011 | DEARATOR WATER PUMP SHELTER CRANE |  | No. | 1 | 16859965894 |  |  | 16859965894
65.12 | CR | 012 | PU4 COMPRESSOR STATION CRANE |  | No. | 1 | 57512199921 |  |  | 57512199921
65.13 | CR | 013 | CHEMICAL STORAGE SHELTER CRANE(ex) |  | No. | 1 | 34059235213 |  |  | 34059235213
66 |  |  | HVAC | [6 empty] | طبق لیست زیر |  |  | 1321638459
66.1 |  |  | HVAC FOR ACCOMMODATION |  | SET | 1 | 1518677236 |  |  | 1518677236
66.2 |  |  | HVAC FOR DE4 SWITCHGERA ROOM |  | SET | 1 | 117450892713 |  |  | 117450892713
66.3 |  |  | HVAC FOR DE4 CONTROL ROOM |  | SET | 1 | 118461069946 |  |  | 118461069946
66.4 |  |  | HVAC FOR 33 KV STATION |  | SET | 1 | 106571104561 |  |  | 106571104561
66.5 |  |  | HVAC FOR 33/3.45 STATION |  | SET | 1 | 2387517586 |  |  | 2387517586
66.6 |  |  | HVAC FOR GUARD HOUSE |  | SET | 1 | 1518677236 |  |  | 1518677236
66.7 |  |  | HVAC FOR LABORATORY |  | SET | 1 | 3422602226 |  |  | 3422602226
66.8 |  |  | HVAC BULK |  | No. | 1 | 4168497024 |  |  | 4168497024 |  |  | 839755096
66.9 |  |  | Waste water treatment package |  | SET | 1 | 4493011461 |  |  | 4493011461 |  |  | 85562096
66.10 |  |  | Water treatment package |  | SET | 1 | 2353403858 |  |  | 2353403858 |  |  | 85562096
67 |  |  | SAFETY EQUIPMENT | طبق لیست زیر | No. |  |  |  |  | طبق لیست زیر
67.1 |  |  | WATER HYDRANT | 6" | No. | 13 | 515823531 |  |  | 4018827635
67.2 |  |  | WATER HYDRANT WITH MONITOR | 6" | No. | 27 | 805119134 |  |  | 15798478004
67.3 |  |  | DELUGE VALVE | 4" | No. | 2 | 6527315146 |  |  | 14976381668
67.4 |  |  | DRY POWDER PORTABLE FIRE EXTINGUISHER | 12 KG | No. | 32 | 46100720 |  |  | 1538168723
67.5 |  |  | DRY POWDER WHELEED FIRE EXTINGUISHER | 75 KG | No. | 12 | 323916475 |  |  | 5047171174
67.6 |  |  | CO2 PORTABLE FIRE EXTINGUISHER | 5 KG | No. | 42 | 37522309 |  |  | 2045423305
67.7 |  |  | CO2 WHEELD FIRE EXTINGUISHER | 30 KG | No. | 24 | 342821165 |  |  | 7754292285
67.8 |  |  | SAFETY SHOWER & EYE WASH | - | No. | 7 | 1068612681 |  |  | 5623670648
67.9 |  |  | FIRST AID KIT | - | No. | 4 | 103736041 |  |  | 721952057
67.11 |  |  | OS&Y GATE VALVE-ISOLATING VALVE, 12" |  | No. | 2 | 1952731692 |  |  | 4344365045
67.12 |  |  | OS&Y GATE VALVE-ISOLATING VALVE, 6" |  | No. | 19 | 719699583 |  |  | 11572146233
67.13 |  |  | 9 LIT WATER EXTINGUISHER | - | No. | 8 | 37522309 |  |  | 374871601
67.14 |  |  | EMERGANCY BREATHING APPARATUS WITH MASK |  | No. | 2 | 480783912 |  |  | 1172276581
67.15 |  |  | FIRE MAN CABINET |  | No. | 2 | 5699407176 |  |  | 14047815817
67.16 |  |  | FIRE SHED EQUIPMENT. 100 lit foam drums, 3% FP (5 NOS.), Fire Hose, 25 m (10 NOS.) Foam Nozzle 10X (2 NOS.) Water Nozzle, 450 lpm (Fog/Jet/Stop) (5 NOS.)) 12 kg portable powder fire extinguisher (6 NOS.) 75 kg Wheeled powder fire extinguisher (2 NOS.) 5 kg portable CO2 fire extinguisher (2 NOS.) In Line Inductor, 450 lpm with pick up tube (2 NOS.) Drum Wrench (1 NO.) Hose Bridge (1 NO.) | - | No. | 10 | 6527315146 |  |  | 42247721222
67.17 |  |  | WATER SPRAY SYSTEM |  | No. | 40 | 5287618 |  |  | 141200346
67.18 |  |  | SAFETY SIGN |  | No. | 200 | 2147504 |  |  | 446276395
67.19 |  |  | Bulks OS&Y GATE VALVE-ISOLATING VALVE;OS&Y GATE VALVE-ISOLATING VALVE; WIND SOCK; HOSE REEL; EMERGENCY EQUIPMENT BOX;EMERGENCY BREATING APPARATUS WITH MASK; FIRE MAN CABINET;STRETCHER; FIRE DOSE SYSTEM;WATER SPRAY SYSTEM;SAFETY SIGN;AXE;RECHARGEABLE FLASHLIGHT (EXPLOSION PROOF);EMERGENCY BREATHING APPARATUS WITH AIR MASTER;BREATHING RECOVERY DEVICE |  | a lot | 1 | 4949173166 |  |  | 4949173166 |  |  | 1321638459
68 |  |  | Pig Launcher & Receiver |  | SET | 1 | 92437172040 |  |  | 92437172040 |  |  | 233993633
69 |  |  | CLEANING IN PLATE FOR EXCHANGER |  | SET | 2 | 38014590580 |  |  | 40603966363 |  |  | 233993633
[5 empty] | 607052624678 | 1196581 | 6259334310817 | 14446040 | 1176130247062 | 310549825767
[5 empty] | IRR | Euro | Rls | Euro | Rls | Rls
[5 empty] | لوازم یدکی |  | خرید |  | ترخیص | حمل
هزینه کل بدون ضریب
جدول 2.1 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي مکانیک و لوله و اتصالات مورد نياز پروژه بر اساس پیوست 1،2 و3
[6 empty] | رديف | شرح فعاليت ها | دلار | یورو | ريال
[6 empty] | 1 | الكترواستاتيك ها و ادوات مربوطه | 10152685 | 4918605 | 0
[6 empty] | 2 | كوره ها و ادوات مربوطه | 4663098 | 5303818 | 0
[6 empty] | 3 | مبدل نفت / نفت و مبدل آب / آب | 0 | 0 | 508645912183
[6 empty] | 4 | تلمبه ها | 0 | 0 | 2494635482223
[6 empty] | 5 | شيرآلات و اتصالات ، رنگها و لوله های داخل سایت | 0 | 0 | 3243807684789
[6 empty] | 6 | خرید لوله های بیرون سایت | 0 | 0 | 2477897909125
[6 empty] | 7 | مخزن های اتمسفریک و تحت فشار | 0 |  | 492572895140
[6 empty] | 8 | سیستم پساب | 5125048 | 3035837 | 0
[6 empty] | 9 | کمپرسور و خشک کن هوا | 0 | 0 | 536273046912
[6 empty] | 10 | Flare & Ignitor | 0 | 0 | 491830659036
[7 empty] | بسته های تزریق مواد شیمیایی | 0 | 0 | 232942541372
[6 empty] | 12 | Vacuum Deaerator Package | 0 | 0 | 174968753515
[6 empty] | 13 | سیستم HVAC | 0 |  | 511942420507
[6 empty] | 14 | جرثقیلهای سقفی | 0 |  | 273200054599
[6 empty] | 15 | خرید اقلام ایمنی و آتش نشانی | 0 |  | 104966724045
[6 empty] | 16 | گیرنده و فرستنده توپک | 0 |  | 92437172040
[6 empty] | 17 | مواد شیمیایی مصرفی | 0 |  | 740415223179
[6 empty] | 18 | جمع كل | 12750596 | 14776042 | 7462351092867

## P.EL
ITEM | DESCRIPTION | QUANTITY |  | هزینه واحد بدون ضریب |  |  | هزینه کل بدون ضریب
|  | QTY | UNIT | خرید |  |  | خرید |  | حمل
|  |  |  | Rls | Euro | Dollar | Rls | Euro | Rls
1 | SWITCHGEAR
1.1 | MV Switchgear, 33KV, 630A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 15 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010/Location:33KV station/DWG no. EL-SLD-21028 | 1 | SET | 165643524253 |  |  | 165643524253 | 0 | 947616999
1.2 | MV Switchgear, 3.3KV, 1250A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 9 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010. /Location: DE4 Outdoor station/ DWG no. M9003-EB-EL-SLD-21026 : OUT-SWG-01 | 1 | SET | 112232664212 |  |  | 112232664212 | 0 | یک قلم در ردیف 1.1
1.3 | MV Switchgear, 3.3KV, 630A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 12 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010./Location:DE4/ DWG no. M9003-EB-EL-SLD-21026 : DE4-SWG-01 | 1 | SET | 126188380302 |  |  | 126188380302 | 0 | یک قلم در ردیف 1.1
1.4 | LV Switchgear, 400V, 4000A, 3 phase + N+E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 50KA, 1Sec., in accordance with attached Specification No.: M9003-EB-EL-SPC-21008./Location: DE4 / / DWG no. M9003-EB-EL-SLD-21025 : (DE-MCC-001 | 1 | SET | 103881576111 |  |  | 103881576111 | 0 | یک قلم در ردیف 1.1
1.5 | 33 KV transformer bay, withdrawable, outdoor type with OCB and all protection and metering devises in accordance to Dwg no. M9003-EB-EL-SLD-21026 | 2 | SET | 43872736649 |  |  | 155366873143 | 0 | یک قلم در ردیف 1.1
1.6 | MV Switchgear, 3.3KV, 630A, 3 phase +E, withdrawable type, free floor standing, metal clad for indoor use, IP42, 25KA, 1Sec(with approximately 9 cell). In accordance with Specification No.: M9003-EB-EL-SPC-21010./Location:Production uni/ DWG no. M9003-EB-EL-SLD-21026 : PU4-SWG-01 | 1 | SET | 112232664212 |  |  | 112232664212 | 0 | یک قلم در ردیف 1
1.7 | SAMPLE 4-DESALTING UNIT EDP,400V SWITCHGEAR (EDP) / DWG no. M9003-EB-EL-SLD-21024 | 2 | SET | 14700142257 |  |  | 32921695228 | 0 | یک قلم در ردیف 2
1.8 | Capacitor Bank Set 400/230 V AC, 50Hz, 3Phase, 3-wires + N + PE , 425KVAR with min 5 Steps Regulator (50KVAR fixed step+375KVAR as variable steps), rapid discharge on contactor, free standing type, supplying from L V Switchgear, for indoor use, IP42. | 2 |  | 11526483683 |  |  | 11942945926 | 0
2 | TRANSFORMERS
2.1 | TR1 : Power Transformer 2500 KVA, 3.3 / 0.42 Kv 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral solidly earthed Complete with accessories. | 1 | SET | 20110296326 |  |  | 20110296326 |  | 244723206
2.2 | TR2 : Power Transformer 2500 KVA, 3.3 / 0.42 kV 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase, 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral solidly earthed Complete with accessories. | 1 | SET | 20110296326 |  |  | 20110296326 |  | 244723206
2.3 | PTR1 : Power Transformer6000 KVA, 33 / 3.45kV 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase, 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral earthed with NGR. | 1 | SET | 74686671845 |  |  | 74686671845 |  | 244723206
2.4 | PTR2 : Power Transformer 6000 KVA, 33 / 3.45kV 50 Hz , Z= 6%, (secondary voltage at full load shall be 0.4KV) Oil immersed & conservator type, 3-phase, 2-winding Primary taps at nominal voltage +/-2 x 2.5 % with off-circuit tap changer Dyn11, ONAN, IP 54, Neutral earthed with NGR. | 1 | SET | 74686671845 |  |  | 74686671845 |  | 244723206
3 | DIESEL GENERATOR EDG-1
3.1 | DIESEL GENERATOR EDG-1 0.4 kv, 550kva, 50Hz, 1500rpm | 1 |  | 33913151515 |  |  | 33913151515 |  | 666301589
3.2 | emergency diesel generator, 0.4 kv, 180KVA, 50Hz, 1500rpm,with automatic control panel | 1 |  | 10748873937 |  |  | 10748873937 |  | یک قلم در ردیف فوق
4 | UNINTERRUPTIBLE POWER SUPPLY (UPS)
4.1 | UPS-001/ 110V AC | 2 | [6 empty] | 244723206
4..1.1 | INVERTER: 20 KVA inverter with all metering and protective devices. | 2 |  | 29134645575 |  |  | 76069874868
4.1.2 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (100%) with respective rack, Battery Back Up Duration : 2 Hours capacity, with fuse box EXD -IIC ,automatic switch 200 A | 2 |  |  | 94473 |  |  | 182678
4.2 | DC-001/110V DC | 2 | [6 empty] | یک قلم در ردیف 4.1
4.2.1 | CHARGERS :Suitable to feed 13KW UPS load and charge batteries simultaneity, as per manufacturer standard battery chargers with all metering and protective devices. | 2 |  | 17127806744 |  |  | 28192907033
4.2.2 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (50%) with respective rack, Battery Back Up Duration : 8Hours capacity, with fuse box EXD -IIC ,automatic switch 160 A | 2 |  |  | 105941 |  |  | 111394
4.3 | DC-002/24V DC | 2 | [6 empty] | 244723206
4.3.1 | CHARGERS :Suitable to feed 18KW UPS load and charge batteries simultaneity, as per manufacturer standard battery chargers with all metering and protective devices. | 2 |  | 125651873496 |  |  | 237677270198
4.3.3 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (50%) with respective rack, Battery Back Up Duration :24Hours capacity, with fuse box EXD -IIC ,automatic switch400 A | 2 |  |  | 308642 |  |  | 556948
4.4 | DC-003/110V DC | 2 | [6 empty] | یک قلم در ردیف 4.3
4.4.1 | CHARGERS :Suitable to feed 11KW UPS load and charge batteries simultaneity, as per manufacturer standard battery chargers with all metering and protective devices. | 2 |  | 10760059007 |  |  | 32491771134
4.4.2 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (50%) with respective rack, Battery Back Up Duration : 8Hours capacity , with fuse box EXD -IIC ,automatic switch160 A | 2 |  |  | 90695 |  |  | 108555
4.5 | DC-004/ 110V DC | 2 | [6 empty] | 244723206
4.5.1 | CHARGERS :Suitable to feed 11KW UPS load and charge batteries simultaneity, as per manufacturer standard battery chargers with all metering and protective devices. | 2 |  | 10760059007 |  |  | 32491771134
4.5.2 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (50%) with respective rack, Battery Back Up Duration : 8Hours capacity ,with fuse box EXD -IIC ,automatic switch160 A | 2 |  |  | 90695 |  |  | 108555
4.6 | DC-005/ 110V DC | 2 | [6 empty] | یک قلم در ردیف 4.5
4.6.1 | CHARGERS :Suitable to feed 13KW UPS load and charge batteries simultaneity, as per manufacturer standard battery chargers with all metering and protective devices. | 2 |  | 17127806744 |  |  | 28192907033
4.6.2 | BATTERY BANKS AS FOLLOW:Nickel-cadmium battery bank (50%) with respective rack, Battery Back Up Duration : 8Hours capacity ,with fuse box EXD -IIC ,automatic switch 160 A | 2 |  |  | 105941 |  |  | 111394
5 | Earthing
5.1 | 120 mm2 BARE STRANDED COPPER CONDUCTOR | 1200 | m | 8492968 |  |  | 9955326105 |  | 666301589
5.2 | 120 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 500 | m | 5006762 |  |  | 3034376662 |  | یک قلم در ردیف 5.1
5.3 | 70 mm2 BARE STRANDED COPPER CONDUCTOR | 4630 | m | 5415747 |  |  | 24238720652 |  | یک قلم در ردیف 5.1
5.4 | 70 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 2850 | m | 3349730 |  |  | 11272223466 |  | یک قلم در ردیف 5.1
5.5 | 35 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 350 | m | 1462889 |  |  | 669938377 |  | یک قلم در ردیف 5.1
5.6 | 16 mm2 INSULATED STRANDED COPPER, GREEN/YELLOW PVC COVERED | 400 | m | 1013966 |  |  | 446258490 |  | یک قلم در ردیف 5.1
5.7 | FLEXIBLE COPPER BRAID STRIP, 20x3 mm, HOLE=11mm,HOLE CENTERS= 250 mm | 22 | NO | 2894712 |  |  | 71614863 |  | یک قلم در ردیف 5.1
5.8 | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 120x120 mm2 | 72 | NO | 2029378 |  |  | 146891684 |  | یک قلم در ردیف 5.1
5.9 | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 120x70 mm2 | 7 | NO | 1013966 |  |  | 7580720 |  | یک قلم در ردیف 5.1
5.10 | CADWELD,CARTRIDGE, FOR CROSS CONNECTION OF 70x70 mm2 | 160 | NO | 928281 |  |  | 212254681 |  | یک قلم در ردیف 5.1
5.11 | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 70x35 mm2 | 40 | NO | 848813 |  |  | 40194683 |  | یک قلم در ردیف 5.1
5.12 | CADWELD,CARTRIDGE, FOR TEE CONNECTION OF 70x16 mm2 | 40 | NO | 848813 |  |  | 40194683 |  | یک قلم در ردیف 5.1
5.13 | CADWELD,CARTRIDGE, FOR CONNECTION OF 70 mm2 COPPER CONDUCTOR TO COPPER EARTH PLATE | 40 | NO | 928281 |  |  | 48908761 |  | یک قلم در ردیف 5.1
5.14 | 10-WAY COPPER EARTH BAR,6mm THICKNESS,50 mm WIDE,700 mm LENGTH AND TWO WASHERS AND ONE NUT FOR EACH HOLE | 68 | NO | 31707745 |  |  | 2275651373 |  | یک قلم در ردیف 5.1
5.15 | EARTHING ROD, SOLID COPPER, 3000mm LONG x 20 mm DIA. WITH ALL FITTINGS & ACC. | 64 | NO | 60305360 |  |  | 3262368074 |  | یک قلم در ردیف 5.1
5.16 | "U" bolt rod to cable clamp for nominal rod dia. 20 mm | 64 | NO | 363221 |  |  | 20466140 |  | یک قلم در ردیف 5.1
5.17 | TINNED COPPER COMPRESSION CABLE LUG FOR CABLE SIZE 120 mm2 | 24 | NO | 835641 |  |  | 34518746 |  | یک قلم در ردیف 5.1
5.18 | TINNED COPPER COMPRESSION CABLE LUG FOR CABLE SIZE 70 mm2 | 46 | NO | 569780 |  |  | 26317751 |  | یک قلم در ردیف 5.1
5.19 | TINNED COPPER COMPRESSION CABLE LUG FOR CABLE SIZE 35 mm2 | 74 | NO | 368047 |  |  | 33428371 |  | یک قلم در ردیف 5.1
5.20 | TINNED COPPER COMPRESSION CABLE LUG FOR CABLE SIZE 16 mm2 | 121 | NO | 173625 |  |  | 25231292 |  | یک قلم در ردیف 5.1
5.21 | CONDUIT , HEAVY GUAGE HOT DIP GALVANIZED ,RIGID STEEL,DOUBLE SIDE ISO THREADED, LENGTH 3000mm, size: M50 | 49 | NO | 526167 |  |  | 28486680 |  | یک قلم در ردیف 5.1
5.22 | Conduit clamp, m50 | 147 | NO | 29400 |  |  | 4592216 |  | یک قلم در ردیف 5.1
5.23 | Spark gap | 1 | NO | 81364417 |  |  | یک قلم در ردیف 5 |  | یک قلم در ردیف 5.1
6 | CABLE
6.1 | 0.6/1 KV, Stranded Annealed Copper Conductor, PVC Insulated, Lead Sheath, Extruded PVC Bedding, Galvanized Steel Wire Armored, PVC Sheathed, Cu-PVC-Lsh-Bd-SWA-PVC Power Cable
6.2 | 3C4 | 8200 | m | 2646274 |  |  | 24049635655 |  | 6252271816
6.3 | 3C10 | 2100 | m | 2720520 |  |  | 8434923758 |  | یک قلم در ردیف 6.2
6.4 | 3C16 | 4100 | m | 5604043 |  |  | 11239142173 |  | یک قلم در ردیف 6.2
6.5 | 3C25 | 550 | m | 7731967 |  |  | 2023736932 |  | یک قلم در ردیف 6.2
6.6 | 3C95 | 250 | m | 16696748 |  |  | 5550758980 |  | یک قلم در ردیف 6.2
6.7 | 3C240+120 | 750 | m | 60072589 |  |  | 42957355923 |  | یک قلم در ردیف 6.2
6.8 | 4C4 | 1100 | m | 2462218 |  |  | 1614918058 |  | یک قلم در ردیف 6.2
6.9 | 4C6 | 4100 | m | 2012940 |  |  | 8268100304 |  | یک قلم در ردیف 6.2
6.10 | 4C10 | 1500 | m | 3763375 |  |  | 4930848246 |  | یک قلم در ردیف 6.2
6.11 | 4C16 | 300 | m | 4032845 |  |  | 1575142306 |  | یک قلم در ردیف 6.2
6.12 | 3C95+50 | 280 | m | 21641319 |  |  | 4656610629 |  | یک قلم در ردیف 6.2
6.13 | 3C70 | 3900 | m | 12461800 |  |  | 65858061496 |  | یک قلم در ردیف 6.2
6.14 | 3C50 | 750 | m | 11676717 |  |  | 6312952711 |  | یک قلم در ردیف 6.2
6.15 | 3C120+70 | 200 | m | 21166512 |  |  | 5603825669 |  | یک قلم در ردیف 6.2
6.16 | 4C25 | 300 | m | 7028920 |  |  | 2189581866 |  | یک قلم در ردیف 6.2
6.17 | 3C240 | 1000 | m | 49451609 |  |  | 53399332753 |  | یک قلم در ردیف 6.2
6.18 | 0.6/1 KV, Stranded Annealed Copper Conductor, PVC Insulated, Galvanized Steel Wire Armored, PVC Sheathed, Cu-PVC-SWA-PVC Power Cable
6.19 | 1C300 | 2000 | m | 16647946 |  |  | 22775131947 |  | یک قلم در ردیف 6.2
6.20 | 3C4 | 150 | m | 657052 |  |  | 158252534 |  | یک قلم در ردیف 6.2
6.21 | 3C6 | 250 | m | 1083389 |  |  | 252400335 |  | یک قلم در ردیف 6.2
6.22 | 3C16 | 300 | m | 2150957 |  |  | 579519741 |  | یک قلم در ردیف 6.2
6.23 | 3C25 | 650 | m | 3114904 |  |  | 2427921530 |  | یک قلم در ردیف 6.2
6.24 | 3C25+16 | 500 | m | 5722742 |  |  | 3027140576 |  | یک قلم در ردیف 6.2
6.25 | 3C150+70 | 100 | m | 29386606 |  |  | 3303915892 |  | یک قلم در ردیف 6.2
6.26 | 4C4 | 500 | m | 676587 |  |  | 456870792 |  | یک قلم در ردیف 6.2
6.27 | 4C16 | 600 | m | 2697474 |  |  | 2000213211 |  | یک قلم در ردیف 6.2
6.28 | 4C10 | 150 | m | 2203075 |  |  | 376141030 |  | یک قلم در ردیف 6.2
6.29 | 3C95+50 | 500 | m | 15875781 |  |  | 4883299221 |  | یک قلم در ردیف 6.2
6.30 | 3C50+25 | 100 | m | 8403124 |  |  | 518089345 |  | یک قلم در ردیف 6.2
6.31 | 3C50 | 1100 | m | 5343075 |  |  | 10410798850 |  | یک قلم در ردیف 6.2
6.32 | 4C6 | 200 | m | 1777199 |  |  | 215514185 |  | یک قلم در ردیف 6.3
6.33 | 3/6 KV, Stranded Annealed Copper Conductor, XLPE Insulated, Galvanized Steel Wire Armored, PVC Sheathed, Cu-XLPE-SWA-PVC Power Cable
6.34 | 3C50 | 600 | m | 11081750 |  |  | 7487855035 |  | یک قلم در ردیف 6.2
6.35 | 3C70 | 1800 | m | 9837032 |  |  | 25798211231 |  | یک قلم در ردیف 6.2
6.36 | 3C95 | 400 | m | 14961407 |  |  | 5024841127 |  | یک قلم در ردیف 6.2
6.37 | 3C240 | 3800 | m | 47210576 |  |  | 162511989768 |  | یک قلم در ردیف 6.2
6.38 | 3C240+120 | 1000 | m | 60072589 |  |  | 30113705692 |  | یک قلم در ردیف 6.2
6.39 | 33 KV, Stranded Annealed Copper Conductor, XLPE Insulated, Galvanized Steel Wire Armored, PVC Sheathed, Cu-XLPE-SWA-PVC Power Cable
6.35 | 1C95 | 16325 | m | 9011399 |  |  | 120772714997 |  | یک قلم در ردیف 6.2
6.36 | CONTROL CABLE | 19647 | m | 2834471 |  |  | 50057165175 |  | یک قلم در ردیف 6.2
7 | LOCAL CONTROL STATION
7.1 | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator.(L4-T12,L2-T12 Schematic code). | 31 | SET | 185604086 |  |  | 5346952699 |  | 2945937341
7.2 | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be explosion proof type, IP55, EExd, IIB, T3 and supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator.(L4-T12,L2-T12 Schematic code). | 8 | SET | 527118159 |  |  | 5462295986 |  | یک قلم در ردیف 7.1
7.3 | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch and remote position indicator.(L1-T12 Schematic code). | 13 | SET | 185604086 |  |  | 2585304375 |  | یک قلم در ردیف 7.1
7.4 | Local Control Stations for remote operation of the Motor through Starter.Local Control Stations shall be explosion proof type, IP55, EExd, IIB,T3 and supplied with stop push Button, start push button, Local / Remote Selector Switch and remote position indicator.(L1-T12 Schematic code). | 9 | SET | 341462372 |  |  | 2861357420 |  | یک قلم در ردیف 7.1
7.5 | Local Control Stations for remote operation of the fire water pump.Local Control Stations shall be supplied with stop push Button, start push button, Local / Remote Selector Switch, ammeter and remote position indicator. | 1 | SET | 185604086 |  |  | 185604086 |  | یک قلم در ردیف 7.1
8 | Power Transition Line
8.1 | Cable ACSR -33KV –LYNX | 87958 | m | 695854 |  |  | 79180934262 |  | 11424510583
8.2 | Cable ACSR -66KV –HORSE | 6000 | m | 423929 |  |  | 3326356504 |  | 2826390859
8.3 | Shield wire -Horse | 28326 | m | 423929 |  |  | 17947229739
8.4 | Double Circuit 66 kv Overhead Line tower with accessories | 80 | no. | 6747277052 |  |  | 545596187447 |  | 12492928556
9 | Lighting
9.1 | Lighting Fixture
9.1.1 | INDUSTRIAL FLUORESCENT LIGHTING FIXTURE, FOR 2x36W TUBES, BODY OF GALVANIZED SHEET STEEL , CORROSION RESISTANT , INJECTED MOULDED BOWL OF IMPACT RESISTANT OPAL PATTERNED POLYCARBONATE, 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2, DEGREE OF PROTECTION: IP55, WITH FULL SUPPORTING ACCESSORIES FOR: SURFACE MOUNTING, WITH TWO BI PIN LAMPS, TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2 , AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 6 | SET | 20263801 |  |  | 244635204 |  | 666301589
9.1.2 | INTERIOR FLUORESCENT LIGHTING FIXTURE WITH SYMMETRICAL LIGHT DISTRIBUTION, FOR 2x36 TUBES HOUSING OF STEEL SHEET SYMMETRICAL REFLECTOR AND LOUVRE, DEGREE OF PROTECTION: IP41, SURFACE MOUNTED, 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2, WITH TWO BI PIN LAMPS,TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 9 | SET | 20263801 |  |  | 264072998 |  | یک قلم در ردیف 9.1.1
9.1.3 | INDUSTRIAL FLUORESCENT LIGHTING FIXTURE, FOR 2x36W TUBES,BODY AND REFLECTOR OF WHITE SHEET STEEL WITHOUT DIFFUSER, SURFACE MOUNTED, DEGREE OF PROTECTION IP41, 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2,WITH BI PIN LAMPS, TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 121 | SET | 20263801 |  |  | 4201287700 |  | یک قلم در ردیف 9.1.1
9.1.4 | INTERIOR FLUORESCENT LIGHTING FIXTURE WITH SYMMETRICAL LIGHT DISTRIBUTION, FOR 2x36 TUBES HOUSING OF STEEL SHEET SYMMETRICAL REFLECTOR AND LOUVRE WEATHER PROOF, DEGREE OF PROTECTION: IP55, SURFACE MOUNTED, 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2, WITH TWO BI PIN LAMPS,TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 18 | SET | 20263801 |  |  | 641300395 |  | یک قلم در ردیف 9.1.1
9.1.5 | INDUSTRIAL LIGHTING FIXTURE SUITABLE FOR MOUNTING ON HAZARDOUS AREA ,ZONE 2 , 2x36W FLUORESCENT TUBES,BODY OF GALVANIZED SHEET STEEL , INJECTED MOULDED BOWL OF IMPACT RESISTANT OPAL .DEGREE OF PROTECTION :IP55 , PATTERNED POLYCARBONATE, PROTECTION CLASS : EEX de IIB T3 , 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2 , WITH SUPPORTING ACCESSORIES FOR SURFACE MOUNTED ,WITH TWO LAMPS,TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 40 | SET | 257673812 |  |  | 7919804519 |  | یک قلم در ردیف 9.1.1
9.1.6 | INTERIOR FLUORESCENT LIGHTING FIXTURE WITH OPAL DIFFUSER, 4x20W TUBES , BODY OF STEEL SHEET, OPAL DIFFUSER, DEGREE OF PROTECTION: IP41, SURFACE MOUNTED TYPE,6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2,WITH FOUR LAMPS, TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. DIMENSION:590x590x82mm | 160 | SET | 41538322 |  |  | 7387123354 |  | یک قلم در ردیف 9.1.1
9.1.7 | INTERIOR LIGHTING FIXTURE, 2x20W FLUORESCENT TUBES, BODY OF: STEEL SHEET,OPAL DIFFUSER, DEGREE OF PROTECTION IP41, SURFACE MOUNTED, WITH LAMP, COMPLETE WITH ON-OFF (KNOT TYPE) SWITCH, WITH BATTERY BACK UP FOR MAX. 1/2 HOUR, TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 35 | SET | 79701081 |  |  | 2240342831 |  | یک قلم در ردیف 9.1.1
9.1.8 | INTERIOR LIGHTING FIXTURE, EMERGENCY WHITE EXIT SIGN ON GREEN BACKGROUND, FLUORESCENT FIXTURE, 1x8WATTS,BODY OF STEEL SHEET, DEGREE OF PROTECTION IP41, SURFACE MOUNTED, 6-POLE TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2, WITH LAMP, WITH BACKUP BATTERY FOR 1/2 HOUR , TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG, LAMP HOLDER : BI-PIN, WITH POWER FACTOR CORRECTION CAPACITOR. | 4 | SET | 71241562 |  |  | 237308310 |  | یک قلم در ردیف 9.1.1
9.1.9 | STREET LIGHTING,1x250W HIGH PRESSURE MERCURY VAPOUR LAMP,WEATHER PROOF BODY OF PRESSED ALUMINIUM SHEET WHICH IS CHROMATED AND ELECTROSTATICALLY STOVE-ENAMELLED, REFLECTOR OF ANODISED PURE ALUMINIUM AND BOWL OF GLASS, POLE MOUNTED, ON 44~60mm PIPE ANGELED AT 10 DEGREE TO HORIZONTAL, DEGREE OF PROTECTION: IP55, WITH CONTROL GEAR AND TERMINAL BLOCK SIZE 2.5 mm2,WITH LAMP AND POWER FACTOR CORRECTION CAPACITOR. | 46 | SET | 129813577 |  |  | 7991767679 |  | یک قلم در ردیف 9.1.1
9.1.10 | CORROSION RESISTANT HIGH-BAY LUMINAIRE FOR 1x250W MERCURY VAPOUR LAMP, WIDE BEAM LIGHT DISTRIBUTION, WITH CONTROL GEAR BOX INCLUDING TERMINAL BLOCKS AND THROUGH WIRING 3x2.5mm2, HOT DIPPED GALVANIZED STEEL OR ALUMINIUM SHEET HOUSING , SYMMETRICAL REFLECTOR OF ANODISED ALUMINIUM. DEGREE OF PROTECTION IP55, M20 HOLE SUITABLE FOR CONNECTING FLEXIBLE CONDUIT SIZE M20 , HANG TYPE MOUNTING, WITH LAMP.WIRING BETWEEN CONTROL GEAR AND FIXTURE SHALL BE PROVIDED BY VENDOR.WITH POWER FACTOR CORRECTION CAPACITOR. | 72 | SET | 55912739 |  |  | 6559679906 |  | یک قلم در ردیف 9.1.1
9.1.11 | CORROSION RESISTANT OUTDOOR AREA FLOOD LIGHT,1x400W METAL HALIDE LAMP, SYMMETRIC WIDE ANGLE BEAM LIGHT DISTRIBUTION, HIGH INTENSITY TYPE, BODY OF DIE CAST ALUMINIUM, DUST-PROOF SEALING, REFLECTOR OF PURE ALUMINIUM, DEGREE OF PROTECTION: IP 55, M20 HOLE AND CABLE GLANDS SUITABLE FOR CABLE PVC/PVC 3x4mm2 ,CONTROL GEAR WITH 3x4mm2 TERMINAL BLOCKS,WITH LAMP AND MOUNTING BRACKET WHICH HAVING ADJUSTABLE VERTICAL AND HORIZENTAL ANGLES , WITH POWER FACTOR CORRECTION CAPACITOR. | 75 | SET | 54926406 |  |  | 2537794951 |  | یک قلم در ردیف 9.1.1
9.1.12 | INDOOR LIGHTING FITTING FOR 1x36W LOW CONSUMPTION LAMP, BODY OF PORCELAIN, DUST AND WEATHER-PROOF SEALING BY GASKET BETWEEN BODY AND BOWL, BOWL OF PRISMATIC GLASS, 3 POLE TERMINAL BLOCKS FOR 3x2.5mm2 WIRING,WALL MOUNTED, DEGREE OF PROTECTION IP41,WITH LAMP , TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG. | 9 | SET | 20263801 |  |  | 264072998 |  | یک قلم در ردیف 9.1.1
9.1.13 | OUTDOOR LIGHTING FITTING FOR 1x36W LOW CONSUMPTION LAMP, BULKHEAD TYPE , BODY OF DIE-CAST ALUMINUM,WITH GLASS AND CORROSION PROOF ,STEEL PROTECTIVE MESH, 3 POLE TERMINAL BLOCKS FOR 3x2.5mm2 WIRING,SURFACE MOUNTED, DEGREE OF PROTECTION IP55,WITH LAMP, TWO M25 HOLES SUITABLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2, AND ONE END PLUG. | 11 | SET | 9054508 |  |  | 93637781 |  | یک قلم در ردیف 9.1.1
9.2 | Socket Outlet
9.2.1 | SOCKET OUTLET , OUTDOOR, LOCKABLE PLUG, SURFACE MOUNTING, GALVANIZED CAST IRON , THERMOPLASTIC ENCLOSURE, WEATHER PROOF, 230 V, 16 A, 3 PIN (PH+N+PE) DEGREE OF PROTECTION IP 55, WITH M25 HOLE AT TOP FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 4mm2 | 56 | NO | 99193030 |  |  | 5140142442 |  | یک قلم در ردیف 9.1.1
9.2.2 | SOCKET OUTLET, INDOOR , RECESSED MOUNTING, 230 V, 16 A, EQUIPED WITH ON-OFF SWITCH , DEGREE OF PROTECTION IP 23, TWO POLES PLUS EARTH LUG, WITH M25 HOLE AT TOP FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 4mm2, WITH SUITABLE GALVANIZED METAL FLUSH MOUNTING BOX WITH EARTH CONNECTION SCREW. METAL BOX HOLE SIZE PROPER FOR CONDUIT SIZE: M25 WITH DEPTH 35 mm. | 5 | NO | 7180294 |  |  | 45372460 |  | یک قلم در ردیف 9.1.1
9.2.3 | SOCKET OUTLET, INDOOR , RECESSED MOUNTING, 230 V, 16 A, DEGREE OF PROTECTION IP 23, TWO POLES PLUS EARTH LUG, WITH M25 HOLE AT TOP FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 4mm2 , WITH SUITABLE GALVANIZED METAL FLUSH MOUNTING BOX WITH EARTH CONNECTION SCREW. METAL BOX HOLE SIZE PROPER FOR CONDUIT SIZE: M25 WITH DEPTH 35 mm. | 58 | NO | 4406676 |  |  | 392955740 |  | یک قلم در ردیف 9.1.1
9.2.4 | WELDING SOCKET OUTLET, INDUSTRIAL , SURFACE MOUNTING METAL CLAD OR THERMO PLASTIC ENCLOSURE, HINGED FLAP, 400 V, 60 A, 4 POLES (3PH+PE) , LOCKABLE PLUG, DEGREE OF PROTECTION IP55. WITH M32 CABLE GLAND FOR SWA CABLE AT BOTTOM. | 3 | NO | 80903334 |  |  | 306024705 |  | یک قلم در ردیف 9.1.1
9.2.5 | SOCKET OUTLET, EXPLOSION PROOF, LOCKABLE, SURFACE MOUNTING, CAST IRON ENCLOUSURE OR THERMOPLASTIC ENCLOSURE, HOT DIP GALVANIZED IF METAL, PROTECTION CLASS: EEX de IIB T3, FLAME PROOF, 230 V, 16 A, 2 POLES , PLUS EARTH LUG. EXPLOSION PROOF CABLE GLAND FOR NON-SWA FIRE RESISTANCE CABLE SIZE 3x4MM2 AT TOP OF SOCKET. | 17 | NO | 110147492 |  |  | 2194825017 |  | یک قلم در ردیف 9.1.1
9.2.6 | WELDING SOCKET OUTLET, EXPLPSION PROOF,WEATHER PROOF , SURFACE MOUNTING METAL CLAD OR THERMOPLASTIC ENCLOSURE, HINGED FLAP, 400 V, 60 A, 4 POLES (3PH+PE) , LOCKABLE PLUG, DEGREE OF PROTECTION IP55. WITH M32 CABLE GLAND FOR SWA CABLE AT BOTTOM. | 4 | NO | 351534371 |  |  | 892689856 |  | یک قلم در ردیف 9.1.1
9.3 | Lighting Switch
9.3.1 | ON-OFF SWITCH FOR LIGHTING LUMINAIRES, RECESSED MOUNTED, 230V,10A, DEGREE OF PROTECTION IP23 , SINGLE POLE, WITH SUITABLE GALVANIZED METAL FLUSH MOUNTING BOX WITH EARTH CONNECTION SCREW. METAL BOX HOLE SIZE PROPER FOR CONDUIT SIZE: M25 WITH DEPTH 35 mm. | 38 | NO | 3989242 |  |  | 159358881 |  | 666301589
9.3.2 | OUT DOOR ONE POLE SWITCH FOR LIGHTING PURPOSE, 230V,10A, DEGREE OF PROTECTION IP55 MIN.,SURFACE MOUNTING,MADE OF DIE-CAST ALUMINIUM ALLOY OR THERMOPLASTIC ENCLOSURE,HIGH RESISTANT AGAINST IMPACTS, WITH ONE M25 HOLE FOR CONNECTING CONDUIT SIZE M25, CONNECTED PVC WIRE SIZE 2.5mm2 | 20 | NO | 9766733 |  |  | 180975295 |  | 740793186
9.3.3 | ON-OFF SWITCH FOR LIGHTING LUMINAIRS , 230V,10A, RECESSED MOUNTED, MULTIPOSITION TYPE ( FOR DISCONNECTING TWO SEPARATE LINE OF ONE FEEDER : (TWO POLE ), DEGREE OF PROTECTION IP23 , WITH SUITABLE GALVANIZED METAL FLUSH MOUNTING BOX, WITH EARTH CONNECTION SCREW. METAL BOX HOLE SIZE PROPER FOR CONDUIT SIZE: M25 , WITH DEPTH 35 mm. | 9 | NO | 3989242 |  |  | 20185396 |  | 244723206
9.3.4 | ON-OFF SWITCH FOR LIGHTING LUMINAIRS , 230V,10A, RECESSED MOUNTED, TWO WAY TYPE, DEGREE OF PROTECTION IP23 , WITH SUITABLE GALVANIZED METAL FLUSH MOUNTING BOX, WITH EARTH CONNECTION SCREW. METAL BOX HOLE SIZE PROPER FOR CONDUIT SIZE: M25 , WITH DEPTH 35 mm. | 51 | NO | 3989242 |  |  | 95809838 |  | 740793186
9.3.5 | ONE POLE SWITCH FOR LIGHTING PURPOSE, EXPLOSION PROOF, PROTECTION CLASS: EEX de IIB T3, WALL SURFACE MOUNTING, MADE OF DIE-CAST ALUMINIUM ALLOY OR THERMOPLASTIC ENCLOSURE,HIGH RESISTANT AGAINST IMPACTS, VIBRATION AND AGGRESSIVE CHEMICAL SUBSTANCES,WITH M20 EXP-CABLE GLAND FOR NON-SWA FIRE RESISTENCE CABLE SIZE:3x2.5MM2 , HOLE AT TOP | 5 | NO | 45372460 |  |  | 127445320 |  | 244723206
9.4 | Lighting Pole
9.4.1 | STREET LIGHTING POLE, HEIGHT :10m , DETAIL AS BELOW: PIPE SIZE 6" ,168.28mm OD x 7.11mm THK, LENGTH:2700mm , PIPE SIZE 5" ,141.3mm OD x 6.55mm THK, LENGTH:2300mm , PIPE SIZE 4" ,114.3mm OD x 6.02mm THK, LENGTH:2300mm , PIPE SIZE 3" ,88.9mm OD x 5.5mm THK, LENGTH:2700mm, CARBON-STEEL PIPE,SAND BLOST,ANTI CORROSION COATED,SILVER COLORED FINISHING PAINT. | 44 | NO | 123538621 |  |  | 7170120912
9.4.2 | FLOODLIGHTING TOWER, HEIGHT: 15m, LATTICE TYPE WITH TOP PLATFORM (As per attached drawing), CARBONSTEEL PIPE,SAND BLOST,ANTICORROSION COATED,SILVER COLORED FINISHING PAINT. | 22 | NO | 1242280420 |  |  | 48206284251
9.4.3 | POLE MOUNTED FLUORESCENT LIGHTING,2.5m EXPLOSION PROOF, PROTECTION CLASS: EEX de IIB T3, IP55, WITH FLOURECENT LAMP 2x36W EXPLOSION PROOF TYPE. | 20 | NO | 265474398 |  |  | 3984786674
9.5 | Lighting panels | 1 |  |  |  |  | 0
9.5.1 | LIGHTING PANEL- 3PH + N + PE, 400/230V, 50HZ, 10KA, 1SEC, - OUTDOOR USE, IP55, SUPPORT MOUNTING TYPE,INCOMING FEERDE MCCB 63A 4P WITH CONTACTOR 50A AC3 AND MCB 50A,ALSO 10 OUTGOING FEEDER 10A. MCCB,4P FOR INCOMING FEERDER VOLTMETER ,AMMETER AND PHOTOCELL SHALL BE CONSIDERED. | 4 | NO | 1417458572 |  |  | 5641162718
9.5.2 | LIGHTING PANEL- 3PH + N + PE, 400/230V, 50HZ, 10KA, 1SEC, INDOOR USE, IP42, WALL / RECESSED MOUNTING TYPE, INCOMING FEERDE MCCB 80A 4P WITH 12 OUTGOING FEEDER 10A 1PH AND 11 OUTGOING FEEDER FOR SOCKET OUTLET 16A 1PH WITH EARTH LEAKAGE PROTECTION. FOR INCOMING FEERDER VOLTMETER ,AMMETER SHALL BE CONSIDERED. | 21 | NO | 1417458572 |  |  | 44564946839
9.5.3 | LIGHTING PANEL- 3PH + N + PE, 400/230V, 50HZ, 15KA, 1SEC, - EXPLOSION PROOF , PROTECTION CLASS : ZONE2, IIB, T3,- OUTDOOR USE, IP55, WALL / SURFACE MOUNTING TYPE, INCOMING FEERDE MCCB 25A 4P WITH 3 OUTGOING FEEDER 16A 1PH AND 2 OUTGOING FEEDER FOR SOCKET OUTLET 16A 1PH WITH EARTH LEAKAGE PROTECTION. FOR INCOMING FEERDER VOLTMETER ,AMMETER SHALL BE CONSIDERED. | 12 | NO | 2930047212 |  |  | 42643120704
10 | Comunication
10.1 | Telephone System | 1 | SET |  | 80040 |  | 0 | 80040 | 244723206
10.2 | Telephone cable Outdoor(2500mX2pair, 350mX10pair, 300mX15pair) | 1 | r(2500mX2pair, 350mX10pair, 300mX15pair) | 6200497193 |  |  | 6200497193 |  | یک قلم در ردیف فوق
10.3 | Paging | 1 | SET |  | 84674 |  |  | 84674 | 244723206
10.4 | Paging Cable | 1200 | m | 1799841 |  |  | 2193772096 |  | یک قلم در ردیف فوق
10.5 | Radio System | 1 | SET |  | 29015 |  |  | 29015 | 244723206
| Radio Cable | 300 | m |  | 5 |  | 0 | 1500 | یک قلم در ردیف فوق
11 | Neutral Earthing Resistor | 2 | set | 2886036620 |  |  | 4079039197 | 0
12 | Gland & Tray | 1 |  | 20804690866 |  |  | 20804690866 |  | 244723206
13 | BUS DUCT | 80 | m | 2585304375 |  |  | 120389942597 |  | 244723206
14 | BULK MATERIALS | 1 |  | 57105875060 |  |  | 57105875060 |  | 2826390859
|  |  |  | 80312 | 117069500505 | 24762734988 | 2785415212451 | 1708197 | 127337453059
|  |  |  | Euro | Rls |  | Rls | Euro | Rls
|  |  |  | لوام یدکی |  | ترخيص | خرید |  | حمل
هزینه کل بدون ضریب
جدول 2.4 -جدول خلاصه مالی تفكيكي تهيه و خريد كالاي برق و مخابرات مورد نياز پروژه بر اساس پیوست 4
|  |  |  | رديف | شرح فعاليت ها | دلار | ريال | يورو
|  |  |  | 1 | تابلوها | 0 | 845776977386 | 0
|  |  |  | 2 | اتصالات برق (شامل گلندها، شرودها، جعبه هاي اتصال، مفصلها و ...) | 0 | 395480707882 | 0
|  |  |  | 3 | كابلهاي قدرت | 0 | 821371356270
|  |  |  | 4 | ترانسفورماتورها، دستگاههاي شارژر صنعتي، UPS صنعتي و دیزل ژنراتور | 1449998 | 448333800823 | 1487857
|  |  |  | 5 | وسايل و تجهيزات مخابرات، و پیجینگ | 251841 | 9935164448 | 139147
|  |  |  | 6 | پایه ها و برجهاي روشنائي و سایر ملحقات و ادوات روشنایی | 0 | 103808523217
|  |  |  | 7 | خط انتقال برق شامل کابل ، پایه ها و یراق آلات | 0 | 352749137304
[5 empty] | جمع كل بدون حمل و يدكي | 1663318 | 3034004525203 | 1338543

## P.IN
ITEM | DESCRIPTION | QUANTITY |  |  | هزینه واحد بدون ضریب |  | هزینه کل بدون ضریب
[5 empty] | خرید |  | خرید
|  | UNIT | QTY | Dollar | Rls | Euro | Rls | Euro
1 | ANALYZER
1.1 | BS&W ANALYZER TRANSMITTER / ELEMENT | NO. | 3 |  |  | 52603 |  | 146751
1.2 | DISSOLVED OXYGEN ANALYZER | NO. | 1 |  | 30999170005 | 0 | 30999170005 | 0
2 | CORROSION INSTRUMENTS
2.1 | CORROSION COUPON | NO. | 28 |  | 275011347 | 0 | 15498969486 | 0
2.2 | CORROSION PROBE | NO. | 15 |  | 2307549736 | 0 | 35356022076 | 0
2.3 | Local DATA LOGGER | NO. | 15 |  | 878130399 | 0 | 13424325434 | 0
2.4 | RETRIVER AND SERVICE VALVE and Handheld Data Logger + REQUIRED SOFTWARE | NO. | 1 |  | 41057708593 | 0 | 41057708593 | 0
3 | FLOW TRANSMITTER (DIFF. PRESSURE TYPE) WITH 5-VALVE MANIFOLD | NO. | 37 |  | 887145729 | 0 | 35429400194 | 0
4 | FLOW SWITCH (DIFF. PRESSURE SWITCH TYPE) WITH 5-VALVE MANIFOLD | NO. | 10 |  | 1044092139 | 0 | 8628038530 | 0
5 | FLOW GAGE (ROTAMETER) | NO. | 23 |  | 1282886455 | 0 | 20658559595 | 0
6 | ORIFICE PLATE WITH FLANGES | NO. | 37 |  | 442323480 | 0 | 18923236393 | 0
7 | RESTRICTION ORIFICE (WITHOUT FLANGES) | NO. | 6 |  | 393046738 | 0 | 4081372303 | 0
8 | LEVEL GAUGE (MAGNETIC) | NO. | 14 |  | 2273738664 | 0 | 29130738051 | 0
9 | LEVEL GAGE (FLOAT-CABLE) | NO. | 2 |  | 3518033112 | 0 | 13166698551 | 0
10 | LEVEL SWITCH (FLOAT; EXTERNAL WITH CHAMBER, SIDE/SIDE) | NO. | 31 |  | 1972374855 | 0 | 56919412890 | 0
11 | LEVEL SWITCH (DISPLACER; INTERNAL, TOP MOUNTED) | NO. | 7 |  | 2330053955 | 0 | 20815571511 | 0
12 | LEVEL TRANSMITTER (DISPLACER; EXTERNAL WITH CHAMBER, SIDE/SIDE) | NO. | 8 |  | 7334548878 | 0 | 61875964995 | 0
13 | LEVEL TRANSMITTER (DIFF. PRESSURE TYPE) WITH 5-VALVE MANIFOLD | NO. | 7 |  | 1208985521 | 0 | 10074211186 | 0
14 | PRESSURE GAUGE WITH 2-VALVE MANIFOLD | NO. | 134 |  | 271784397 | 0 | 26326615480 | 0
15 | DIFF. PRESSURE GAUGE WITH 5-VALVE MANIFOLD | NO. | 28 |  | 829284845 | 0 | 16224522241 | 0
16 | PRESSURE SWITCH WITH 2-VALVE MANIFOLD | NO. | 97 |  | 841830359 | 0 | 93289989374 | 0
17 | PRESSURE TRANSMITTER WITH 2-VALVE MANIFOLD | NO. | 82 |  | 1143187359 | 0 | 62525991668 | 0
18 | DIFF. PRESSURE TRANSMITTER WITH 5-VALVE MANIFOLD | NO. | 17 |  | 887145729 | 0 | 19487082048 | 0
19 | TEMPERATURE TRANSMITTER WITH THERMOWELL | NO. | 34 |  | 1592053245 | 0 | 44846429558 | 0
20 | TEMPERATURE SWITCH WITH THERMOWELL | NO. | 8 |  | 953809520 | 0 | 10405902765 | 0
21 | BIMETAL THERMOMETER WITH THERMOWELL | NO. | 57 |  | 599212817 | 0 | 35129792234 | 0
22 | DENSITY TRANSMITTER | NO. | 1 |  | 5522220898 | 0 | 5522220898 | 0
23 | FLOW COMPUTER | NO. | 1 |  | 110320512055 | 0 | 110320512055 | 0
24 | CONTROL VALVES
24.1 | 1" (300#) | NO. | 3 |  | 3295137688 | 0 | 6625297958 | 0
24.2 | 1 1/2" (300#) | NO. | 1 |  | 3647293814 | 0 | 3647293814 | 0
24.3 | 2" (300#) | NO. | 8 |  | 4619705390 | 0 | 29936291378 | 0
24.4 | 3" (300#) | NO. | 8 |  | 4529834205 | 0 | 22619167312 | 0
24.5 | 3" (600#) | NO. | 2 |  | 8828589260 | 0 | 10408611104 | 0
24.6 | 4" (300#) | NO. | 4 |  | 7030760114 | 0 | 28945164517 | 0
24.7 | 4" (600#) | NO. | 6 |  | 8493777908 | 0 | 37850934852 | 0
24.8 | 6" (300#) | NO. | 7 |  | 8537925796 | 0 | 44899452289 | 0
24.9 | 8" (300#) | NO. | 1 |  | 13157621578 | 0 | 13157621578 | 0
24.10 | 10" (300#) | NO. | 4 |  | 13661745947 | 0 | 38419194102 | 0
24.11 | 12" (300#) | NO. | 2 |  | 11972913636 | 0 | 31625062483 | 0
24.12 | 16" (300#) | NO. | 2 |  | 25585557380 | 0 | 36612972861 | 0
25 | SELF ACTUATED PRESSURE REGULATOR VALVE (1 1/2", 300#) | NO. | 1 |  | 2890340238 | 0 | 2890340238
26 | ON/OFF VALVE
26.1 | 1" (300#) | NO. | 1 |  | 1217989000 | 0 | 1217989000 | 0
25.2 | 2" (300#) | NO. | 5 |  | 2273738664 | 0 | 9639634746 | 0
25.3 | 4" (300#) | NO. | 5 |  | 2141955251 | 0 | 15693221690 | 0
25.4 | 6" (300#) | NO. | 7 |  | 3496306057 | 0 | 34434829033 | 0
25.5 | 6" (600#) | NO. | 2 |  | 6346171229 | 0 | 9220592439 | 0
25.6 | 10" (300#) | NO. | 18 |  | 11227798862 | 0 | 187482911201 | 0
25.7 | 12" (300#) | NO. | 6 |  | 12012712624 | 0 | 86131479846 | 0
25.8 | 20" (300#) | NO. | 5 |  | 33143394205 | 0 | 107510950915 | 0
27 | SAFETY / RELIEF VALVES
27.1 | 3/4" / 1" (300#) | NO. | 6 |  | 1893199342 | 0 | 9640152867 | 0
27.2 | 3/4" / 1" (600#) | NO. | 4 |  | 1972374855 | 0 | 5933630260 | 0
27.3 | 1" / 2" (300#) | NO. | 4 |  | 1217989000 | 0 | 6621298696 | 0
27.4 | 1 1/2" / 2" (300#) | NO. | 4 |  | 2833959782 | 0 | 8579432258 | 0
27.5 | 2" / 3" (300#) | NO. | 2 |  | 2752792693 | 0 | 3522100353 | 0
27.6 | 3" / 4" (300#) | NO. | 8 |  | 4529834205 | 0 | 22619167312 | 0
27.7 | 4" / 6" (300#) | NO. | 12 |  | 6370312823 | 0 | 64492536585 | 0
27.8 | 6" / 8" (300#) | NO. | 2 |  | 8828589260 | 0 | 10408611104 | 0
27.9 | 8" (300#; emergency relief) | NO. | 11 |  | 6168733551 | 0 | 119245255674 | 0
28 | PRESSURE & VACUUM RELIEF VALVE
28.1 | 2" (300#) | NO. | 4 |  | 6168733551 | 0 | 30396786461 | 0
28.2 | 4" (300#) | NO. | 1 |  | 6168733551 | 0 | 6168733551 | 0
29 | LINE BREAK VALVE (12", 300#) | NO. | 4 |  | 25585557380 | 0 | 154551322683 | 0
30 | CABLE
● | 1×2×2.5 mm2, PVC/OSCR/SWA/PVC (FLAME RETARDANT) | m | 4500 |  | 589866 |  | 2645512153
● | 1×2×AWG18 (FF CABLE), PVC/OSCR/SWA/PVC (FLAME RETARDANT) | m | 6100 |  | 198141 |  | 2353572163
● | 10×2×AWG18 (FF CABLE), PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 900 |  | 4149024 |  | 3301644186
● | 1×2×1.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 2900 |  | 1496653 |  | 3334476256
● | 1×2×1.5 mm2, PVC/OSCR/SWA/PVC (FLAME RETARDANT) | m | 4700 |  | 290583 |  | 2740932279
● | 20×1.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 6200 |  | 4431092 |  | 18952516413
● | 20×2.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 2800 |  | 3941448 |  | 16951894410
● | 1×3×1.5 mm2, MT-XLPE/OSCR/LC/SWA/LSFH (FIRE RESISTANT) | m | 800 |  | 2338284 |  | 900461923
● | 1×3×1.5 mm2, MT-XLPE/OSCR/SWA/LSFH (FIRE RESISTANT) | m | 4000 |  | 789828 |  | 2227276358
● | 10×3×1.5 mm2, MT-XLPE/OSCR/ISCR/LC/SWA/LSFH (FIRE RESISTANT) | m | 2800 |  | 10887074 |  | 27092521803
● | 1×2×1.5 mm2, MT-XLPE/OSCR/LC/SWA/LSFH (FIRE RESISTANT) | m | 500 |  | 1988536 |  | 1046739391
● | 1×2×1.5 mm2, MT-XLPE/OSCR/SWA/LSFH (FIRE RESISTANT) | m | 4700 |  | 711686 |  | 2414149171
● | 1×2×1.5 mm2, MT-XLPE/OSCR/LSFH (FIRE RESISTANT) | m | 1800 |  | 233684 |  | 403619362
● | 20×1.5 mm2, MT-XLPE/OSCR/LC/SWA/LSFH (FIRE RESISTANT) | m | 2100 |  | 4375125 |  | 11881944020
● | 40×1.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 4100 |  | 4759154 |  | 24654229112
● | 7×2×1.5 mm2, PVC/ISCR/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 300 |  | 4346935 |  | 1649810863
● | 28×2.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 600 |  | 9086197 |  | 5979124756
● | 6×1.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 1400 |  | 2522918 |  | 4118531890
● | 34×1.5 mm2, PVC/OSCR/LC/SWA/PVC (FLAME RETARDANT) | m | 1100 |  | 4327385 |  | 6308250489
31 | Bulk (Gland, Junction Box, hook-up,…) | Lot | 1 |  | 88640473774 |  | 88640473774
32 | CONTROL SYSTEMS
32.1 | DCS (CONTROL SYSTEM OF DESALTING UNIT) | set | 1 |  | 202402662265 | 0 | 202402662265 | 0
32.2 | PLC BASED ESD SYSTEM (FOR DESALTING UNIT) | set | 1 |  | 97064465766 | 0 | 97064465766 | 0
32.3 | PLC (CONTROL SYSTEM OF PRODUCTION UNIT) | set | 1 |  | 29323763741 | 0 | 29323763741 | 0
32.4 | RELAY BASED ESD SYSTEM (FOR PRODUCTION UNIT) | set | 1 |  | 15314851982 | 0 | 15314851982 | 0
32.5 | PLC BASED F&G SYSTEM (OF DESALTING UNIT) | set | 1 |  | 153823129031 | 0 | 153823129031 | 0
32.6 | SIL3 ADDRESSABLE FIRE ALARM PANEL (OF DESALTING UNIT & 33KV STATION) | set | 2 |  | 15314851982 | 0 | 45048048487 | 0
33 | F&G EQUIPMENT (OF DESALTING UNIT & 33 KV STATION)
33.1 | HEAT DETECTORS
● | EX, ADDRESSABLE | NO. | 3 |  | 717799924 | 0 | 1798203086 | 0
● | NON EX, ADDRESSABLE | NO. | 4 |  | 77647877 | 0 | 175689417 | 0
33.2 | COMBUSTIBLE GAS DETECTORS | [5 empty] | 0
● | EX | NO. | 32 |  | 1436028602 | 0 | 45330206822 | 0
● | NON EX | NO. | 5 |  | 1436028602 | 0 | 4241808343 | 0
33.3 | TOXIC GAS DETECTORS | [5 empty] | 0
● | EX | NO. | 24 |  | 1023793131 | 0 | 35873624398 | 0
● | NON EX | NO. | 5 |  | 1261799569 | 0 | 7837339826 | 0
33.4 | SIREN | [5 empty] | 0
● | EX | NO. | 14 |  | 867067274 | 0 | 6461523732 | 0
● | NON EX, ADDRESSABLE | NO. | 6 |  | 97378238 | 0 | 437833741 | 0
33.5 | BEACON | [5 empty] | 0
● | EX | NO. | 24 |  | 754629296 | 0 | 24087349397 | 0
● | NON EX, ADDRESSABLE | NO. | 10 |  | 97378238 | 0 | 697967469 | 0
33.6 | UV/IR FLAME DETECTOR (EX) | NO. | 48 |  | 1849398473 | 0 | 71272747487 | 0
33.7 | COMBINED HEAT & SMOKE DETECTOR (NON EX, ADDRESSABLE) | NO. | 115 |  | 77647877 | 0 | 4295517472 | 0
33.8 | LINEAR HEAT DETECTOR (WITH BOX & CABLE) | NO. | 3 |  | 1257673027 | 0 | 4068006023 | 0
33.9 | MANUAL CALL POINT | [5 empty] | 0
● | EX | NO. | 34 |  | 265207073 | 0 | 6813044081 | 0
● | NON EX, ADDRESSABLE | NO. | 39 |  | 170049271 | 0 | 5806679189 | 0
33.10 | SPECIAL TOOLS + HHC HART | SET | 1 |  | 22647103985 | 0 | 22647103985 | 0
34 | CCTV | SET | 1 |  | 183738708697 | 0 | 183738708697 | 0
35 | CCTV Accessory | SET | 1 |  | 35046100120 | 0 | 35046100120 | 0
36 | CO2 TOOTAL FLOODING SYSTEM | SET | 5 |  | 71082084551 | 0 | 495703129973 | 0
37 | SPARE PARTS | [5 empty] | 516810905362 | 19464
|  | 19464 | 3293694571060 | 146751 | 17294651802 | 15753483779
|  | Euro | Rls | Euro | Rls | Rls
|  | لوازم یدکی | خرید |  | ترخیص | حمل
جدول 2.5 -جدول خلاصه مالی تفكيكي تهيه و خريدادوات و تجهیزات ابزاردقیق و تجهیزات آزمایشگاه مورد نياز پروژه بر اساس پیوست 5و6
|  | رديف | شرح فعاليت ها | دلار | یورو | ريال
|  | 1 | ادوات ابزار دقیق شامل : ترانسمیترها ، سوئیچ ها ، گیج ها و ... | 237820 | 146751 | 1041490563598
|  |  | كاهش قيمت ابزاردقيق به دليل تغيير از FCS به DCS | -17727 | -29358 | -116267747717
|  | 2 | شیرآلات ابزار شامل : شیر ON/OFF ، شیرهای کنترلی ، PSV ، PCV | 0 | 0 | 1279131411040
|  | 3 | سيستم كنترل ( DCS,FGS )، ESD | 0 | 0 | 551207838624
|  | 4 | ادوات F&G و CO2 Total Flooding و ابزار خاص | 0 | 0 | 818932595111
|  | 5 | اقلام بالک ابزار دقیق | 0 |  | 88640473774
|  | 6 | کابلهای ابزار دقیق و ملحقات شامل : گلند سینی و ... | 0 |  | 88686150068
|  |  | افزايش كابلهاي ابزاردقيق به دليل تغيير FCS به DCS |  |  | 121675153930
|  | 7 | تجهیزات آزمایشگاه | 0 | 0 | 379120539510
|  | 8 | Security CCTV | 0 | 0 | 178856132493
|  |  | جمع كل | 174878 | 254076 | 5001270906517

## P.PI
NO | ITEM | AREA | DESCRIPTION | [6 empty] | MATERIAL |  | هزینه واحد بدون ضریب | هزینه کل بدون ضریب
|  |  | TYPE | BORE 1 | BORE 2 | UNIT | QTY | CLASS | S.CH./thK | MATERIAL | MATERIAL REMARK |  | خرید | حمل و جنبي
[12 empty] | Euro | Euro | Rls
1 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 5/8" | 85 | No | 12 | AX01 | For flange:2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 14.5673 | 3041761
2 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 5/8" | 90 | No | 100 | AX01 | For flange:3"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 121.3943 | 29066957
3 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 5/8" | 90 | No | 256 | AX01 | For flange:4"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 310.7695 | 44578864
4 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 3/4" | 105 | No | 320 | AX01 | For flange:6"150# | A193 GR.B7/A194 GR.BH | GALVD | 2.0834 | 666.6846 | 125931128
5 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 3/4" | 110 | No | 64 | AX01 | For flange:8"150# | A193 GR.B7/A194 GR.BH | GALVD | 2.0834 | 133.3369 | 20471892
6 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 7/8" | 115 | No | 912 | AX01 | For flange:10"150# | A193 GR.B7/A194 GR.BH | GALVD | 3.1606 | 2882.4923 | 514709065
7 | StudBolt&nuts | Fire Water Lines(Non Metal) | - | 7/8" | 125 | No | 120 | AX01 | For flange:12"150# | A193 GR.B7/A194 GR.BH | GALVD | 3.3028 | 396.3361 | 83158346
8 | Fitting | Fire Water Lines(Non Metal) | 45deg.Elbow | 10 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 421.695 | 3373.5598 | 337149387
9 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 3 | - | No | 5 | AX01 | DR11 | HDPE 100 |  | 19.9043 | 99.5215 | 8159327
10 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 4 | - | No | 10 | AX01 | DR11 | HDPE 100 |  | 23.3766 | 233.7661 | 24925148
11 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 6 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 68.38 | 547.0401 | 84515395
12 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 8 | - | No | 6 | AX01 | DR11 | HDPE 100 |  | 187.8742 | 1127.2449 | 160275635
13 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 10 | - | No | 27 | AX01 | DR11 | HDPE 100 |  | 421.695 | 11964 | 1004118483
14 | Fitting | Fire Water Lines(Non Metal) | 90deg.Elbow | 12 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 558.414 | 4467.3119 | 680945580
15 | Fitting | Fire Water Lines(Non Metal) | Pipe Nipple | 1 | - | No | 12 | AX01 | DR11 | HDPE 100 |  | 1.3671 | 16.4046 | 2217257
16 | Fitting | Fire Water Lines(Non Metal) | Reducer | 4 | 3 | No | 1 | AX01 | DR11 | HDPE 100 |  | 18.1545 | 18.1545 | 1493598
17 | Fitting | Fire Water Lines(Non Metal) | Reducer | 10 | 8 | No | 6 | AX01 | DR11 | HDPE 100 |  | 114.0806 | 684.4837 | 71116026
18 | Fitting | Fire Water Lines(Non Metal) | Olet | 3 | 1 | No | 3 | AX01 | DR11 | HDPE 100 |  | 36.0902 | 108.2706 | 13834470
19 | Fitting | Fire Water Lines(Non Metal) | Olet | 10 | 1 | No | 3 | AX01 | DR11 | HDPE 100 |  | 585.0989 | 1755.2966 | 265720074
20 | Fitting | Fire Water Lines(Non Metal) | Olet | 12 | 1 | No | 5 | AX01 | DR11 | HDPE 100 |  | 842.1049 | 4210.5246 | 624298209
21 | Fitting | Fire Water Lines(Non Metal) | Tee | 4 | 1 | No | 1 | AX01 | DR11 | HDPE 100 |  | 32.8913 | 32.8913 | 4448714
22 | Fitting | Fire Water Lines(Non Metal) | Tee | 4 | 4 | No | 5 | AX01 | DR11 | HDPE 100 |  | 32.8913 | 164.4565 | 24470141
23 | Fitting | Fire Water Lines(Non Metal) | Tee | 8 | 4 | No | 2 | AX01 | DR11 | HDPE 100 |  | 225.0853 | 450.1707 | 33636016
24 | Fitting | Fire Water Lines(Non Metal) | Tee | 10 | 6 | No | 32 | AX01 | DR11 | HDPE 100 |  | 586.0695 | 15293 | 2312788938
25 | Fitting | Fire Water Lines(Non Metal) | Tee | 10 | 10 | No | 17 | AX01 | DR11 | HDPE 100 |  | 586.0695 | 9963.1811 | 1527909119
26 | Fitting | Fire Water Lines(Non Metal) | Tee | 12 | 10 | No | 14 | AX01 | DR11 | HDPE 100 |  | 842.3373 | 8401 | 1838510059
27 | Fitting | Fire Water Lines(Non Metal) | Tee | 12 | 12 | No | 2 | AX01 | DR11 | HDPE 100 |  | 842.3373 | 1684.6746 | 224437096
28 | Fitting | Fire Water Lines(Non Metal) | Olet | 3 | 1/2" | No | 120 | AX01 | DR11 | HDPE 100 |  | 36.0902 | 4330.8253 | 537891487
29 | Fitting | Fire Water Lines(Non Metal) | Olet | 6 | 3 | No | 12 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 976.2402 | 115647225
30 | Fitting | Fire Water Lines(Non Metal) | Olet | 10 | 2 | No | 3 | AX01 | DR11 | HDPE 100 |  | 585.0989 | 1755.2966 | 265720074
31 | Fitting | Fire Water Lines(Non Metal) | Olet | 12 | 2 | No | 2 | AX01 | DR11 | HDPE 100 |  | 842.1049 | 1684.2098 | 246938310
32 | Fitting | Fire Water Lines(Non Metal) | Olet | 12 | 3 | No | 2 | AX01 | DR11 | HDPE 100 |  | 842.1049 | 1684.2098 | 246938310
33 | Flange | Fire Water Lines(Non Metal) | Flange | 2 | - | No | 3 | AX01 | DR11 | ASTM A105 |  | 11.2372 | 33.7115 | 3793966
34 | Flange | Fire Water Lines(Non Metal) | Flange | 3 | - | No | 25 | AX01 | DR11 | ASTM A105 |  | 22.9392 | 573.4789 | 44163309
35 | Flange | Fire Water Lines(Non Metal) | Flange | 4 | - | No | 26 | AX01 | DR11 | ASTM A105 |  | 30.4306 | 791.1958 | 61458077
36 | Flange | Fire Water Lines(Non Metal) | Flange | 6 | - | No | 40 | AX01 | DR11 | ASTM A105 |  | 46.7396 | 1869.5823 | 294433660
37 | Flange | Fire Water Lines(Non Metal) | Flange | 8 | - | No | 8 | AX01 | DR11 | ASTM A105 |  | 73.3014 | 586.4112 | 42088114
38 | Flange | Fire Water Lines(Non Metal) | Flange | 10 | - | No | 72 | AX01 | DR11 | ASTM A105 |  | 98.0314 | 7058.2609 | 550142243
39 | Flange | Fire Water Lines(Non Metal) | Flange | 12 | - | No | 13 | AX01 | DR11 | ASTM A105 |  | 136.7053 | 1777.1695 | 265845657
40 | Gasket | Fire Water Lines(Non Metal) | - | 2 | - | No | 3 | AX01 | DR11 | FLAT |  | 1.4081 | 4.2242 | 1028750
41 | Gasket | Fire Water Lines(Non Metal) | - | 3 | - | No | 25 | AX01 | DR11 | FLAT |  | 2.0916 | 52.2898 | 11306978
42 | Gasket | Fire Water Lines(Non Metal) | - | 4 | - | No | 34 | AX01 | DR11 | FLAT |  | 3.3766 | 114.8051 | 13388805
43 | Gasket | Fire Water Lines(Non Metal) | - | 6 | - | No | 40 | AX01 | DR11 | FLAT |  | 4.0328 | 161.3123 | 24556310
44 | Gasket | Fire Water Lines(Non Metal) | - | 8 | - | No | 8 | AX01 | DR11 | FLAT |  | 5.728 | 45.8236 | 10639666
45 | Gasket | Fire Water Lines(Non Metal) | - | 10 | - | No | 76 | AX01 | DR11 | FLAT |  | 30.2939 | 2302.3367 | 270154800
46 | Gasket | Fire Water Lines(Non Metal) | - | 12 | - | No | 11 | AX01 | DR11 | FLAT |  | 41.4764 | 456.2404 | 89937184
47 | Pipe | Fire Water Lines(Non Metal) | - | 3 | - | m | 467 | AX01 | SDR11 | HDPE 100 |  | 4.6602 | 2176.3276 | 186048222
48 | Pipe | Fire Water Lines(Non Metal) | - | 4 | - | m | 147 | AX01 | SDR11 | HDPE 100 |  | 6.9024 | 1014.6553 | 60492650
49 | Pipe | Fire Water Lines(Non Metal) | - | 6 | - | m | 80 | AX01 | SDR11 | HDPE 100 |  | 14.6621 | 1172.9712 | 53047264
50 | Pipe | Fire Water Lines(Non Metal) | - | 8 | - | m | 40 | AX01 | SDR11 | HDPE 100 |  | 22.8615 | 914.4603 | 80674998
51 | Pipe | Fire Water Lines(Non Metal) | - | 10 | - | m | 1734 | AX01 | SDR11 | HDPE 100 |  | 35.6112 | 69229 | 5105285157
52 | Pipe | Fire Water Lines(Non Metal) | - | 12 | - | m | 130 | AX01 | SDR11 | HDPE 100 |  | 56.2745 | 7315.6826 | 608930436
53 | Special | Fire Water Lines(Non Metal) | Filter | 4 | - | No | 1 | AX01 | - | ASTM A216-GR.WCB |  | 527.6826 | 527.6826 | 54773679
54 | Special | Fire Water Lines(Non Metal) | Filter | 10 | - | No | 3 | AX01 | - | ASTM A216-GR.WCB |  | 929.5963 | 2788.789 | 419168444
55 | Special | Fire Water Lines(Non Metal) | Orifice Flange | 4 | - | No | 4 | AX01 | DR11 | ASTM A105 |  | 30.4306 | 121.7224 | 14408819
56 | Special | Fire Water Lines(Non Metal) | Orifice Flange | 12 | - | No | 2 | AX01 | DR11 | ASTM A105 |  | 191.3875 | 382.775 | 43754486
57 | Special | Fire Water Lines(Non Metal) | Quick Coupling | 3 | - | No | 6 | AX01 | DR11 | ASTM A105 |  | 150.3759 | 902.2553 | 125650514
58 | Special | Fire Water Lines(Non Metal) | Quick Coupling | 4 | - | No | 1 | AX01 | DR11 | ASTM A105 |  | 205.058 | 205.058 | 14489264
59 | Valve | Fire Water Lines(Non Metal) | Check | 4 | - | No | 4 | AX01 | - | ASTM B148 |  | 1460.1498 | 5840.5991 | 302008484
60 | Valve | Fire Water Lines(Non Metal) | Check | 6 | - | No | 2 | AX01 | - | ASTM B148 |  | 2678.1944 | 5356.3888 | 228963155
61 | Valve | Fire Water Lines(Non Metal) | Check | 10 | - | No | 3 | AX01 | - | ASTM B148 |  | 4101.1603 | 7450 | 1026311784
62 | Valve | Fire Water Lines(Non Metal) | Gate | 1 | - | No | 12 | AX01 | - | ASTM B148 |  | 355.4339 | 4265.2067 | 353745472
63 | Valve | Fire Water Lines(Non Metal) | Gate | 2 | - | No | 3 | AX01 | - | ASTM B148 |  | 697.1973 | 2091.5918 | 188616733
64 | Valve | Fire Water Lines(Non Metal) | Gate | 3 | - | No | 6 | AX01 | - | ASTM B148 |  | 1107.3133 | 6643.8797 | 319907682
65 | Valve | Fire Water Lines(Non Metal) | Gate | 4 | - | No | 7 | AX01 | - | ASTM B148 |  | 1435.4061 | 12236 | 645474850
66 | Valve | Fire Water Lines(Non Metal) | Gate | 6 | - | No | 2 | AX01 | - | ASTM B148 |  | 2050.5802 | 4101.1603 | 287474464
67 | Valve | Fire Water Lines(Non Metal) | Gate | 10 | - | No | 32 | AX01 | - | ASTM B148 |  | 3896.1023 | 101526 | 6847416048
68 | Valve | Fire Water Lines(Non Metal) | Gate | 12 | - | No | 2 | AX01 | - | ASTM B148 |  | 5276.8263 | 7268 | 854711448
69 | Valve | Fire Water Lines(Non Metal) | Globe | 4 | - | No | 2 | AX01 | - | ASTM B148 |  | 1345.8641 | 2691.7282 | 243026203
70 | StudBolt&nuts | In Production Unit4 | - | 5/8" | 85 | No | 4 | AN01 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 3.6418 | 766895
71 | StudBolt&nuts | In Production Unit4 | - | 5/8" | 85 | No | 20 | AN06 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 18.2092 | 2841221
72 | StudBolt&nuts | In Production Unit4 | - | 5/8" | 85 | No | 4 | AN16 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 3.6418 | 766895
73 | StudBolt&nuts | In Production Unit4 | - | 7/8" | 115 | No | 24 | AN16 | For flange:10"150# | A193 GR.B7/A194 GR.BH |  | 2.3705 | 56.8913 | 9407461
74 | StudBolt&nuts | In Production Unit4 | - | 7/8" | 125 | No | 120 | AN16 | For flange:12"150# | A193 GR.B7/A194 GR.BH |  | 2.4771 | 297.2521 | 69587697
75 | StudBolt&nuts | In Production Unit4 | - | 1" | 135 | No | 128 | AN16 | For flange:16"150# | A193 GR.B7/A194 GR.BH |  | 3.5024 | 448.306 | 77194862
76 | StudBolt&nuts | In Production Unit4 | - | 1 1/8" | 160 | No | 120 | AN16 | For flange:20"150# | A193 GR.B7/A194 GR.BH |  | 5.0444 | 605.3313 | 84207833
77 | StudBolt&nuts | In Production Unit4 | - | 3/4" | 125 | No | 48 | CN16 | For flange:6"300# | A193 GR.B7/A194 GR.BH |  | 1.7184 | 82.4825 | 11685156
78 | StudBolt&nuts | In Production Unit4 | - | 7/8" | 140 | No | 96 | CN16 | For flange:8"300# | A193 GR.B7/A194 GR.BH |  | 2.5837 | 248.0382 | 35910406
79 | StudBolt&nuts | In Production Unit4 | - | 1" | 160 | No | 256 | CN16 | For flange:10"300# | A193 GR.B7/A194 GR.BH |  | 3.7813 | 968.0051 | 202713831
80 | StudBolt&nuts | In Production Unit4 | - | 1 1/8" | 175 | No | 160 | CN16 | For flange:12"300# | A193 GR.B7/A194 GR.BH |  | 5.4135 | 866.1651 | 220755940
81 | StudBolt&nuts | In Production Unit4 | - | 1 1/8" | 180 | No | 80 | CN16 | For flange:14"300# | A193 GR.B7/A194 GR.BH |  | 5.4135 | 433.0825 | 107770253
82 | StudBolt&nuts | In Production Unit4 | - | 1 1/4" | 205 | No | 264 | CN16 | For flange:20"300# | A193 GR.B7/A194 GR.BH |  | 7.5871 | 2003.0067 | 311379055
83 | Fitting | In Production Unit4 | 90deg.Elbow | 2 | - | No | 4 | AN01 | SCH.STD | ASTM A234 |  | 2.8161 | 11.2645 | 1082063
84 | Fitting | In Production Unit4 | 90deg.Elbow | 2 | - | No | 2 | AN06 | SCH.160 | ASTM A234 |  | 2.8161 | 5.6323 | 516209
85 | Fitting | In Production Unit4 | 90deg.Elbow | 6 | - | No | 4 | AN06 | SCH.80 | ASTM A234 |  | 34.7232 | 138.8926 | 16482272
86 | Fitting | In Production Unit4 | 90deg.Elbow | 12 | - | No | 2 | AN16 | SCH.STD | ASTM A234 | NACE | 134.8735 | 269.747 | 38368255
87 | Fitting | In Production Unit4 | 90deg.Elbow | 16 | - | No | 2 | AN16 | SCH.40 | ASTM A234 | NACE | 206.2884 | 412.5767 | 60184495
88 | Fitting | In Production Unit4 | 90deg.Elbow | 20 | - | No | 3 | AN16 | SCH.30 | ASTM A234 | NACE | 260.4237 | 781.271 | 58384368
89 | Fitting | In Production Unit4 | 90deg.Elbow | 6 | - | No | 2 | CN16 | SCH.80 | ASTM A234 | NACE | 34.7232 | 69.4463 | 5370470
90 | Fitting | In Production Unit4 | 90deg.Elbow | 8 | - | No | 4 | CN16 | SCH.80 | ASTM A234 | NACE | 54.6685 | 218.6739 | 25369978
91 | Fitting | In Production Unit4 | 90deg.Elbow | 10 | - | No | 2 | CN16 | SCH.60 | ASTM A234 | NACE | 85.9466 | 171.8933 | 21389604
92 | Fitting | In Production Unit4 | 90deg.Elbow | 12 | - | No | 2 | CN16 | SCH.60 | ASTM A234 | NACE | 156.1859 | 312.3717 | 40026190
93 | Fitting | In Production Unit4 | 90deg.Elbow | 14 | - | No | 2 | CN16 | SCH.60 | ASTM A234 | NACE | 180.4511 | 360.9021 | 48284369
94 | Fitting | In Production Unit4 | 90deg.Elbow | 20 | - | No | 3 | CN16 | SCH.SCH.60 | ASTM A234 | NACE | 281.613 | 844.839 | 90293528
95 | Fitting | In Production Unit4 | Cap | 6 | - | No | 1 | AN06 | SCH.80 |  |  | 10.7177 | 10.7177 | 1138508
96 | Fitting | In Production Unit4 | Pipe Nipple | 1 | - | No | 16 | AN06 | SCH.XXS | API5L-GR.B |  | 1.3671 | 21.8729 | 3429503
97 | Fitting | In Production Unit4 | Pipe Nipple | 1 | - | No | 25 | AN16 | SCH.XXS | API5L-GR.B | NACE | 1.3671 | 34.1763 | 4005140
98 | Fitting | In Production Unit4 | Pipe Nipple | 1 | - | No | 17 | CN16 | SCH.XXS | API5L-GR.B | NACE | 1.3671 | 23.2399 | 2064236
99 | Fitting | In Production Unit4 | Reducer | 12 | 10 | No | 2 | AN16 | SCH.STD | ASTM A234 | NACE | 45.2768 | 90.5536 | 9025184
100 | Fitting | In Production Unit4 | Reducer | 16 | 12 | No | 2 | AN16 | SCH.40 | ASTM A234 | NACE | 60.3691 | 120.7382 | 18441557
101 | Fitting | In Production Unit4 | Reducer | 8 | 6 | No | 2 | CN16 | SCH.80 | ASTM A234 | NACE | 21.6951 | 43.3903 | 3410991
102 | Fitting | In Production Unit4 | Reducer | 10 | 8 | No | 2 | CN16 | SCH.60 | ASTM A234 | NACE | 37.7443 | 75.4887 | 7718777
103 | Fitting | In Production Unit4 | Reducer | 12 | 10 | No | 6 | CN16 | SCH.60 | ASTM A234 | NACE | 45.2768 | 271.6609 | 24195380
104 | Fitting | In Production Unit4 | Reducer | 20 | 14 | No | 2 | CN16 | SCH.SCH.60 | ASTM A234 | NACE | 75.4613 | 150.9227 | 12951881
105 | Fitting | In Production Unit4 | Sockolet | 2 | 1 | No | 8 | AN06 |  | ASTM A105 |  | 9.1729 | 73.3834 | 6599908
106 | Fitting | In Production Unit4 | Sockolet | 6 | 1 | No | 8 | AN06 |  | ASTM A105 |  | 9.7608 | 78.0861 | 5620166
107 | Fitting | In Production Unit4 | Sockolet | 12 | 1 | No | 12 | AN16 |  | ASTM A105 | NACE | 5.1128 | 61.3534 | 9432887
108 | Fitting | In Production Unit4 | Sockolet | 16 | 1 | No | 12 | AN16 |  | ASTM A105 | NACE | 7.0677 | 84.812 | 6370394
109 | Fitting | In Production Unit4 | Sockolet | 20 | 1 | No | 1 | AN16 |  | ASTM A105 | NACE | 7.0677 | 7.0677 | 573758
110 | Fitting | In Production Unit4 | Sockolet | 10 | 1 | No | 8 | CN16 |  | ASTM A105 | NACE | 3.9781 | 31.825 | 2228149
111 | Fitting | In Production Unit4 | Sockolet | 12 | 1 | No | 8 | CN16 |  | ASTM A105 | NACE | 5.1128 | 40.9022 | 4920493
112 | Fitting | In Production Unit4 | Sockolet | 20 | 1 | No | 1 | CN16 |  | ASTM A105 | NACE | 7.0677 | 7.0677 | 573758
113 | Fitting | In Production Unit4 | Tee | 2 | 2 | No | 1 | AN01 | SCH.STD | ASTM A234 |  | 3.8141 | 3.8141 | 519426
114 | Fitting | In Production Unit4 | Tee | 6 | 2 | No | 1 | AN06 | SCH.80 | ASTM A234 |  | 129.1865 | 129.1865 | 19365119
115 | Fitting | In Production Unit4 | Tee | 6 | 6 | No | 1 | AN06 | SCH.80 | ASTM A234 |  | 129.1865 | 129.1865 | 19365119
116 | Fitting | In Production Unit4 | Tee | 20 | 10 | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 1134.545 | 84704728
117 | Fitting | In Production Unit4 | Tee | 20 | 16 | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 1134.545 | 84704728
118 | Fitting | In Production Unit4 | Tee | 20 | 20 | No | 1 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 567.2725 | 40920851
119 | Fitting | In Production Unit4 | Tee | 8 | 6 | No | 2 | CN16 | SCH.80 | ASTM A234 | NACE | 73.8482 | 147.6965 | 11200832
120 | Fitting | In Production Unit4 | Tee | 20 | 10 | No | 2 | CN16 | SCH.SCH.60 | ASTM A234 | NACE | 567.2725 | 1134.545 | 84704728
121 | Fitting | In Production Unit4 | Tee | 20 | 12 | No | 2 | CN16 | SCH.SCH.60 | ASTM A234 | NACE | 567.2725 | 1134.545 | 84704728
122 | Fitting | In Production Unit4 | Tee | 20 | 14 | No | 2 | CN16 | SCH.SCH.60 | ASTM A234 | NACE | 567.2725 | 1134.545 | 84704728
123 | Fitting | In Production Unit4 | Weldolet | 12 | 11/2" | No | 2 | AN16 | SCH.STD |  | NACE | 13.6979 | 27.3958 | 2267434
124 | Fitting | In Production Unit4 | Weldolet | 16 | 11/2" | No | 2 | AN16 | SCH.40 |  | NACE | 13.6979 | 27.3958 | 2267434
125 | Fitting | In Production Unit4 | Weldolet | 20 | 2 | No | 1 | AN16 | SCH.30 |  | NACE | 19.8906 | 19.8906 | 1396233
126 | Fitting | In Production Unit4 | Weldolet | 20 | 11/2" | No | 1 | AN16 | SCH.30 |  | NACE | 13.6979 | 13.6979 | 1844956
127 | Fitting | In Production Unit4 | Weldolet | 10 | 11/2" | No | 4 | CN16 | SCH.60 |  | NACE | 13.6979 | 54.7915 | 4978248
128 | Fitting | In Production Unit4 | Weldolet | 12 | 11/2" | No | 4 | CN16 | SCH.60 |  | NACE | 13.6979 | 54.7915 | 4978248
129 | Fitting | In Production Unit4 | Weldolet | 20 | 8 | No | 1 | CN16 | SCH.SCH.60 |  | NACE | 62.2009 | 62.2009 | 7493442
130 | Flange | In Production Unit4 | Flange | 2 | - | No | 1 | AN01 | SCH.STD | ASTM A105 |  | 12.7683 | 12.7683 | 1590596
131 | Flange | In Production Unit4 | Flange | 2 | - | No | 6 | AN06 | SCH.160 | ASTM A105 |  | 16.7327 | 100.3964 | 8436371
132 | Flange | In Production Unit4 | Flange | 2 | - | No | 1 | AN16 | SCH.160 | ASTM A105 | NACE | 25.0991 | 25.0991 | 2377416
133 | Flange | In Production Unit4 | Flange | 10 | - | No | 2 | AN16 | SCH.STD | ASTM A105 | NACE | 183.0348 | 366.0696 | 49765563
134 | Flange | In Production Unit4 | Flange | 12 | - | No | 10 | AN16 | SCH.STD | ASTM A105 | NACE | 200.9569 | 2009.5686 | 273626171
135 | Flange | In Production Unit4 | Flange | 16 | - | No | 8 | AN16 | SCH.40 | ASTM A105 | NACE | 302.1188 | 2416.9505 | 287777452
136 | Flange | In Production Unit4 | Flange | 20 | - | No | 6 | AN16 | SCH.30 | ASTM A105 | NACE | 508.5439 | 3051.2633 | 383267570
137 | Flange | In Production Unit4 | Flange | 11/2" | - | No | 5 | AN16 | SCH.160 | ASTM A105 | NACE | 16.6644 | 83.3219 | 7788669
138 | Flange | In Production Unit4 | Flange | 6 | - | No | 4 | CN16 | SCH.80 | ASTM A105 | NACE | 52.1804 | 208.7217 | 29808500
139 | Flange | In Production Unit4 | Flange | 8 | - | No | 8 | CN16 | SCH.80 | ASTM A105 | NACE | 186.22 | 1489.7602 | 149903528
140 | Flange | In Production Unit4 | Flange | 10 | - | No | 14 | CN16 | SCH.60 | ASTM A105 | NACE | 183.0348 | 2562.487 | 257604712
141 | Flange | In Production Unit4 | Flange | 12 | - | No | 8 | CN16 | SCH.60 | ASTM A105 | NACE | 328.0928 | 2624.7426 | 183523363
142 | Flange | In Production Unit4 | Flange | 14 | - | No | 4 | CN16 | SCH.60 | ASTM A105 | NACE | 218.7286 | 874.9142 | 128352288
143 | Flange | In Production Unit4 | Flange | 20 | - | No | 9 | CN16 | SCH.SCH.60 | ASTM A105 | NACE | 369.1044 | 3321.9399 | 439372881
144 | Flange | In Production Unit4 | Flange | 11/2" | - | No | 8 | CN16 | SCH.XXS | ASTM A105 | NACE | 11.1141 | 88.9132 | 13718675
145 | Flange | In Production Unit4 | Spectace | 2 | - | No | 1 | AN06 |  | ASTM A516 |  | 22.9255 | 22.9255 | 3121852
146 | Flange | In Production Unit4 | Spectace | 12 | - | No | 2 | AN16 |  | ASTM A516 | NACE | 917.7577 | 1835.5153 | 224986387
147 | Flange | In Production Unit4 | Spectace | 16 | - | No | 2 | AN16 |  | ASTM A516 | NACE | 1455.4334 | 2910.8669 | 447164945
148 | Flange | In Production Unit4 | Spectace | 20 | - | No | 1 | AN16 |  | ASTM A516 | NACE | 2187.2855 | 2187.2855 | 252520444
149 | Flange | In Production Unit4 | Spectace | 10 | - | No | 2 | CN16 |  | ASTM A516 | NACE | 356.6642 | 713.3285 | 53489833
150 | Flange | In Production Unit4 | Spectace | 12 | - | No | 2 | CN16 |  | ASTM A516 | NACE | 917.7577 | 1835.5153 | 224986387
151 | Flange | In Production Unit4 | Spectace | 20 | - | No | 1 | CN16 |  | ASTM A516 | NACE | 3417.6336 | 3417.6336 | 424846915
152 | Gasket | In Production Unit4 | - | 2 | - | No | 1 | AN01 |  | FLAT |  | 1.4081 | 1.4081 | 172163
153 | Gasket | In Production Unit4 | - | 2 | - | No | 5 | AN06 |  | FLAT |  | 1.4081 | 7.0403 | 1082063
154 | Gasket | In Production Unit4 | - | 2 | - | No | 1 | AN16 |  | FLAT | NACE | 1.4081 | 1.4081 | 172163
155 | Gasket | In Production Unit4 | - | 10 | - | No | 2 | AN16 |  | FLAT | NACE | 30.2939 | 60.5878 | 12944789
156 | Gasket | In Production Unit4 | - | 12 | - | No | 12 | AN16 |  | FLAT | NACE | 41.4764 | 497.7168 | 59985689
157 | Gasket | In Production Unit4 | - | 16 | - | No | 10 | AN16 |  | FLAT | NACE | 68.216 | 682.1597 | 148761751
158 | Gasket | In Production Unit4 | - | 20 | - | No | 7 | AN16 |  | FLAT | NACE | 267.9425 | 1875.5973 | 405844215
159 | Gasket | In Production Unit4 | - | 6 | - | No | 4 | CN16 |  | SPIRAL WOUND | NACE | 13.3288 | 53.3151 | 6202970
160 | Gasket | In Production Unit4 | - | 8 | - | No | 8 | CN16 |  | SPIRAL WOUND | NACE | 17.7854 | 142.2829 | 32454447
161 | Gasket | In Production Unit4 | - | 10 | - | No | 20 | CN16 |  | SPIRAL WOUND | NACE | 21.7772 | 435.5432 | 78468358
162 | Gasket | In Production Unit4 | - | 12 | - | No | 14 | CN16 |  | SPIRAL WOUND | NACE | 34.1763 | 478.4687 | 100791546
163 | Gasket | In Production Unit4 | - | 14 | - | No | 4 | CN16 |  | SPIRAL WOUND | NACE | 41.0116 | 164.0464 | 30117187
164 | Gasket | In Production Unit4 | - | 20 | - | No | 13 | CN16 |  | SPIRAL WOUND | NACE | 82.0232 | 1066.3017 | 206413784
165 | Pipe | In Production Unit4 | - | 2 | - | m | 22 | AN01 | SCH.STD | API5L-GR.B |  | 10.3349 | 227.3683 | 18073143
166 | Pipe | In Production Unit4 | - | 2 | - | m | 48 | AN06 | SCH.160 | API5L-GR.B |  | 10.3349 | 496.0764 | 40230754
167 | Pipe | In Production Unit4 | - | 6 | - | m | 50 | AN06 | SCH.80 | API5L-GR.B |  | 111.0321 | 5551.604 | 511752451
168 | Pipe | In Production Unit4 | - | 12 | - | m | 10 | AN16 | SCH.STD | API5L-GR.B | NACE | 244.2514 | 2442.5144 | 227284845
169 | Pipe | In Production Unit4 | - | 16 | - | m | 10 | AN16 | SCH.40 | API5L-GR.B | NACE | 254.9008 | 2549.0078 | 128270657
170 | Pipe | In Production Unit4 | - | 20 | - | m | 32 | AN16 | SCH.30 | API5L-GR.B | NACE | 300.7518 | 9624.0562 | 554134698
171 | Pipe | In Production Unit4 | - | 8 | - | m | 250 | CN16 | SCH.80 | API5L-GR.B | NACE | 175.393 | 34776 | 3139781138
172 | Pipe | In Production Unit4 | - | 10 | - | m | 10 | CN16 | SCH.60 | API5L-GR.B | NACE | 138.4142 | 1384.1416 | 76871489
173 | Pipe | In Production Unit4 | - | 12 | - | m | 10 | CN16 | SCH.60 | API5L-GR.B | NACE | 244.2514 | 2442.5144 | 227284845
174 | Pipe | In Production Unit4 | - | 20 | - | m | 105 | CN16 | SCH.SCH.60 | API5L-GR.B | NACE | 341.7634 | 47669 | 5960987527
175 | Special | In Production Unit4 | Filter | 12 | - | No | 2 | AN16 |  | ASTM A216-GR.WCB | NACE | 1244.0186 | 2488.0373 | 353538325
176 | Special | In Production Unit4 | Filter | 16 | - | No | 2 | AN16 |  | ASTM A216-GR.WCB | NACE | 1804.5105 | 3609.0211 | 294793494
177 | Special | In Production Unit4 | Orifice Flange | 10 | - | No | 4 | CN16 | SCH.60 | ASTM A105 | NACE | 183.0348 | 732.1391 | 74145142
178 | Special | In Production Unit4 | Orifice Flange | 12 | - | No | 4 | CN16 | SCH.60 | ASTM A105 | NACE | 328.0928 | 1312.3713 | 192824349
179 | Special | In Production Unit4 | Orifice Flange | 20 | - | No | 2 | CN16 | SCH.SCH.60 | ASTM A105 | NACE | 369.1044 | 738.2089 | 107980950
180 | Valve | In Production Unit4 | Check | 2 | - | No | 1 | AN06 | - | ASTM A216-GR.WCB |  | 102.529 | 102.529 | 4566088
181 | Valve | In Production Unit4 | Check | 10 | - | No | 2 | CN16 | - | ASTM A216-GR.WCB | NACE | 1640.4641 | 3280.9283 | 196201623
182 | Valve | In Production Unit4 | Check | 12 | - | No | 2 | CN16 | - | ASTM A216-GR.WCB | NACE | 2460.6962 | 4921.3924 | 237181993
183 | Valve | In Production Unit4 | Gate | 1 | - | No | 16 | AN06 |  | ASTM A105 |  | 54.6821 | 874.9142 | 83032426
184 | Valve | In Production Unit4 | Gate | 2 | - | No | 1 | AN06 | - | ASTM A216-GR.WCB |  | 159.2617 | 159.2617 | 12705958
185 | Valve | In Production Unit4 | Gate | 1 | - | No | 25 | AN16 |  | ASTM A105 | NACE | 54.6821 | 1367.0534 | 96451224
186 | Valve | In Production Unit4 | Gate | 2 | - | No | 1 | AN16 | - | ASTM A216-GR.WCB | NACE | 195.4886 | 195.4886 | 10807482
187 | Valve | In Production Unit4 | Gate | 12 | - | No | 2 | AN16 | - | ASTM A216-GR.WCB | NACE | 1864.6609 | 3729.3218 | 321483305
188 | Valve | In Production Unit4 | Gate | 16 | - | No | 2 | AN16 | - | ASTM A216-GR.WCB | NACE | 7518.7939 | 9472 | 1105109373
189 | Valve | In Production Unit4 | Gate | 20 | - | No | 3 | AN16 | - | ASTM A216-GR.WCB | NACE | 7450 | 40808 | 2228596675
190 | Valve | In Production Unit4 | Gate | 1 | - | No | 17 | CN16 |  | ASTM A105 | NACE | 54.6821 | 929.5963 | 75371237
191 | Valve | In Production Unit4 | Gate | 10 | - | No | 2 | CN16 | - | ASTM A216-GR.WCB | NACE | 2050.5802 | 4101.1603 | 287474464
192 | Valve | In Production Unit4 | Gate | 12 | - | No | 2 | CN16 | - | ASTM A216-GR.WCB | NACE | 2460.6962 | 4921.3924 | 237181993
193 | Valve | In Production Unit4 | Gate | 14 | - | No | 1 | CN16 | - | ASTM A216-GR.WCB | NACE | 6151.7405 | 6151.7405 | 493998085
194 | Valve | In Production Unit4 | Gate | 20 | - | No | 4 | CN16 | - | ASTM A216-GR.WCB | NACE | 14605 | 54492 | 5907392096
195 | Valve | In Production Unit4 | Globe | 6 | - | No | 1 | CN16 | - | ASTM A216-GR.WCB | NACE | 2734.1069 | 2734.1069 | 235005917
196 | StudBolt&nuts | In Desalting Plant 4 | - | 1/2" | 65 | No | 8 | AN01 | For flange:1"150# | A193 GR.B7/A194 GR.BH |  | 0.47573 | 3.8059 | 618476
197 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 85 | No | 224 | AN01 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 203.9425 | 40886155
198 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 360 | AN01 | For flange:3"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 327.7647 | 71756467
199 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 496 | AN01 | For flange:4"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 451.587 | 62491723
200 | StudBolt&nuts | In Desalting Plant 4 | - | 3/4" | 105 | No | 96 | AN01 | For flange:6"150# | A193 GR.B7/A194 GR.BH |  | 1.5625 | 150.004 | 17538735
201 | StudBolt&nuts | In Desalting Plant 4 | - | 1/2" | 70 | No | 32 | AN01 | For flange:11/2"150# | A193 GR.B7/A194 GR.BH |  | 0.47573 | 15.2235 | 2311536
202 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 8 | AN01 | For flange:21/2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 7.2837 | 1502212
203 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 85 | No | 408 | AN06 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 371.4667 | 94595174
204 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 336 | AN06 | For flange:3"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 305.9138 | 63368125
205 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 368 | AN06 | For flange:4"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 335.0484 | 45153948
206 | StudBolt&nuts | In Desalting Plant 4 | - | 3/4" | 105 | No | 168 | AN06 | For flange:6"150# | A193 GR.B7/A194 GR.BH |  | 1.5625 | 262.5071 | 35162685
207 | StudBolt&nuts | In Desalting Plant 4 | - | 3/4" | 110 | No | 80 | AN06 | For flange:8"150# | A193 GR.B7/A194 GR.BH |  | 1.5625 | 125.0034 | 20164355
208 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 85 | No | 372 | AN16 | For flange:2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 338.6902 | 56638743
209 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 352 | AN16 | For flange:3"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 320.4811 | 67107429
210 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 272 | AN16 | For flange:4"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 247.6445 | 49195364
211 | StudBolt&nuts | In Desalting Plant 4 | - | 3/4" | 105 | No | 392 | AN16 | For flange:6"150# | A193 GR.B7/A194 GR.BH |  | 1.5625 | 612.5165 | 142982224
212 | StudBolt&nuts | In Desalting Plant 4 | - | 3/4" | 110 | No | 528 | AN16 | For flange:8"150# | A193 GR.B7/A194 GR.BH |  | 1.5625 | 825.0222 | 146024261
213 | StudBolt&nuts | In Desalting Plant 4 | - | 7/8" | 115 | No | 1428 | AN16 | For flange:10"150# | A193 GR.B7/A194 GR.BH |  | 2.3705 | 3385.0321 | 843980885
214 | StudBolt&nuts | In Desalting Plant 4 | - | 7/8" | 125 | No | 96 | AN16 | For flange:12"150# | A193 GR.B7/A194 GR.BH |  | 2.4771 | 237.8017 | 39437717
215 | StudBolt&nuts | In Desalting Plant 4 | - | 7/8" | 125 | No | 1224 | AN16 | For flange:12"150# | A193 GR.B7/A194 GR.BH |  | 2.4771 | 3031.9714 | 398048667
216 | StudBolt&nuts | In Desalting Plant 4 | - | 1" | 135 | No | 192 | AN16 | For flange:16"150# | A193 GR.B7/A194 GR.BH |  | 3.5024 | 672.4591 | 76593095
217 | StudBolt&nuts | In Desalting Plant 4 | - | 1 1/8" | 150 | No | 64 | AN16 | For flange:18"150# | A193 GR.B7/A194 GR.BH |  | 4.8804 | 312.3444 | 49430891
218 | StudBolt&nuts | In Desalting Plant 4 | - | 1 1/8" | 160 | No | 340 | AN16 | For flange:20"150# | A193 GR.B7/A194 GR.BH |  | 5.0444 | 1715.1052 | 274879210
219 | StudBolt&nuts | In Desalting Plant 4 | - | 1 1/4" | 230 | No | 24 | AN16 | For flange:26"150# | A193 GR.B7/A194 GR.BH |  | 8.0383 | 192.9186 | 47308338
220 | StudBolt&nuts | In Desalting Plant 4 | - | 1/2" | 70 | No | 72 | AN16 | For flange:11/2"150# | A193 GR.B7/A194 GR.BH |  | 0.47573 | 34.2529 | 6284484
221 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 16 | AN16 | For flange:21/2"150# | A193 GR.B7/A194 GR.BH |  | 0.91046 | 14.5673 | 2824348
222 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 85 | No | 56 | AZ00 | For flange:2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 67.9808 | 7982385
223 | StudBolt&nuts | In Desalting Plant 4 | - | 5/8" | 90 | No | 40 | AZ00 | For flange:3"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 48.5577 | 12255058
224 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 1 | - | No | 2 | AN01 | SCH.80 | ASTM A234 |  | 5.8783 | 11.7567 | 1057969
225 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 2 | - | No | 62 | AN01 | SCH.STD | ASTM A234 |  | 2.8161 | 174.6001 | 12544853
226 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 3 | - | No | 59 | AN01 | SCH.STD | ASTM A234 |  | 7.013 | 413.7661 | 45161058
227 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 4 | - | No | 42 | AN01 | SCH.STD | ASTM A234 |  | 13.2331 | 555.7892 | 52107766
228 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 6 | - | No | 9 | AN01 | SCH.STD | ASTM A234 |  | 34.7232 | 312.5084 | 45474833
229 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 2 | 3 | No | 2 | AN06 | SCH.160 | ASTM A234 |  | 2.8161 | 5.6323 | 516209
230 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 2 | - | No | 89 | AN06 | SCH.160 | ASTM A234 |  | 2.8161 | 250.6356 | 27822438
231 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 3 | - | No | 77 | AN06 | SCH.80 | ASTM A234 |  | 7.013 | 539.9998 | 51814884
232 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 4 | - | No | 43 | AN06 | SCH.80 | ASTM A234 |  | 13.2331 | 569.0223 | 47018721
233 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 6 | - | No | 40 | AN06 | SCH.80 | ASTM A234 |  | 34.7232 | 1388.9263 | 145769675
234 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 8 | - | No | 13 | AN06 | SCH.60 | ASTM A234 |  | 54.6685 | 710.6901 | 111687528
235 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 2 | - | No | 118 | AN16 | SCH.160 | ASTM A234 | NACE | 2.8161 | 332.3033 | 45965109
236 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 3 | - | No | 52 | AN16 | SCH.80 | ASTM A234 | NACE | 7.013 | 364.6752 | 25532511
237 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 4 | - | No | 19 | AN16 | SCH.80 | ASTM A234 | NACE | 13.2331 | 251.4285 | 23204756
238 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 6 | - | No | 51 | AN16 | SCH.80 | ASTM A234 | NACE | 34.7232 | 1770.881 | 165099586
239 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 8 | - | No | 23 | AN16 | SCH.60 | ASTM A234 | NACE | 54.6685 | 1257.3747 | 105318086
240 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 10 | - | No | 41 | AN16 | SCH.STD | ASTM A234 | NACE | 85.9466 | 3523.8126 | 435838952
241 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 12 | - | No | 76 | AN16 | SCH.STD | ASTM A234 | NACE | 134.8735 | 10095 | 1231440738
242 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 16 | - | No | 11 | AN16 | SCH.40 | ASTM A234 | NACE | 206.2884 | 2269.172 | 321810325
243 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 18 | - | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 246.8899 | 493.7797 | 48805584
244 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 20 | - | No | 5 | AN16 | SCH.30 | ASTM A234 | NACE | 260.4237 | 1302.1184 | 201518839
245 | Fitting | In Desalting Plant 4 | 90deg.Elbow | 2 | - | No | 18 | AZ00 | SCH.40 | ASTM A234 | GALVD | 2.8161 | 50.6903 | 3941156
246 | Fitting | In Desalting Plant 4 | Cap | 2 | - | No | 5 | AN06 | SCH.160 |  |  | 2.7614 | 13.8072 | 1429354
247 | Fitting | In Desalting Plant 4 | Cap | 3 | - | No | 1 | AN06 | SCH.80 |  |  | 3.5817 | 3.5817 | 422153
248 | Fitting | In Desalting Plant 4 | Cap | 2 | - | No | 1 | AN16 | SCH.160 |  | NACE | 2.7614 | 2.7614 | 363569
249 | Fitting | In Desalting Plant 4 | Cap | 8 | - | No | 1 | AN16 | SCH.60 |  | NACE | 12.0848 | 12.0848 | 1766801
250 | Fitting | In Desalting Plant 4 | Cap | 12 | - | No | 2 | AN16 | SCH.STD |  | NACE | 14.19 | 28.38 | 3593590
251 | Fitting | In Desalting Plant 4 | Cap | 16 | - | No | 1 | AN16 | SCH.40 |  | NACE | 22.4197 | 22.4197 | 2988756
252 | Fitting | In Desalting Plant 4 | Cap | 3 | - | No | 1 | AZ00 | SCH.40 |  | GALVD | 3.5817 | 3.5817 | 422153
253 | Fitting | In Desalting Plant 4 | Pipe Nipple | 1 | - | No | 66 | AN01 | SCH.80 | API5L-GR.B |  | 1.3671 | 90.2255 | 8073276
254 | Fitting | In Desalting Plant 4 | Pipe Nipple | 3/4" | - | No | 11 | AN01 | SCH.80 | API5L-GR.B |  | 1.3671 | 15.0376 | 1967279
255 | Fitting | In Desalting Plant 4 | Pipe Nipple | 1 | - | No | 42 | AN06 | SCH.XXS | API5L-GR.B |  | 1.3671 | 57.4162 | 6482618
256 | Fitting | In Desalting Plant 4 | Pipe Nipple | 3/4" | - | No | 16 | AN06 | SCH.XXS | API5L-GR.B |  | 1.3671 | 21.8729 | 3429503
257 | Fitting | In Desalting Plant 4 | Pipe Nipple | 1 | - | No | 140 | AN16 | SCH.XXS | API5L-GR.B | NACE | 1.3671 | 191.3875 | 16448280
258 | Fitting | In Desalting Plant 4 | Pipe Nipple | 1 | - | No | 2 | AZ00 | SCH.80 | API5L-GR.B | GALVD | 1.3671 | 2.7341 | 253752
259 | Fitting | In Desalting Plant 4 | Pipe Nipple | 11/2" | - | No | 1 | AZ00 | SCH.80 | API5L-GR.B | GALVD | 1.3671 | 1.3671 | 179977
260 | Fitting | In Desalting Plant 4 | Plug | 3/4" | - | No | 3 | AN01 |  | ASTM A105 |  | 2.1189 | 6.3568 | 653128
261 | Fitting | In Desalting Plant 4 | Plug | 3/4" | - | No | 16 | AN06 |  | ASTM A105 |  | 2.1189 | 33.9029 | 3774974
262 | Fitting | In Desalting Plant 4 | Plug | 1 | - | No | 10 | AN16 |  | ASTM A105 | NACE | 2.1189 | 21.1893 | 2158001
263 | Fitting | In Desalting Plant 4 | Reducer | 2 | 11/2" | No | 8 | AN01 | SCH.STD | ASTM A234 |  | 25.4135 | 203.3082 | 17699224
264 | Fitting | In Desalting Plant 4 | Reducer | 3 | 2 | No | 3 | AN01 | SCH.STD | ASTM A234 |  | 53.0417 | 159.125 | 17331009
265 | Fitting | In Desalting Plant 4 | Reducer | 3 | 4 | No | 4 | AN01 | SCH.STD | ASTM A234 |  | 53.0417 | 212.1667 | 19052584
266 | Fitting | In Desalting Plant 4 | Reducer | 3 | 21/2" | No | 2 | AN01 | SCH.STD | ASTM A234 |  | 53.0417 | 106.0833 | 7825294
267 | Fitting | In Desalting Plant 4 | Reducer | 4 | 3 | No | 13 | AN01 | SCH.STD | ASTM A234 |  | 5.7143 | 74.2857 | 9968140
268 | Fitting | In Desalting Plant 4 | Reducer | 6 | 4 | No | 3 | AN01 | SCH.STD | ASTM A234 |  | 12.4812 | 37.4436 | 4875821
269 | Fitting | In Desalting Plant 4 | Reducer | 3 | 2 | No | 6 | AN06 | SCH.80 | ASTM A234 |  | 53.0417 | 318.25 | 36101010
270 | Fitting | In Desalting Plant 4 | Reducer | 4 | 3 | No | 6 | AN06 | SCH.80 | ASTM A234 |  | 5.7143 | 34.2857 | 4934595
271 | Fitting | In Desalting Plant 4 | Reducer | 6 | 4 | No | 1 | AN06 | SCH.80 | ASTM A234 |  | 12.4812 | 12.4812 | 1795249
272 | Fitting | In Desalting Plant 4 | Reducer | 2 | 11/2" | No | 10 | AN16 | SCH.160 | ASTM A234 | NACE | 25.4135 | 254.1352 | 38269477
273 | Fitting | In Desalting Plant 4 | Reducer | 3 | 2 | No | 18 | AN16 | SCH.80 | ASTM A234 | NACE | 53.0417 | 954.7501 | 123311899
274 | Fitting | In Desalting Plant 4 | Reducer | 3 | 21/2" | No | 4 | AN16 | SCH.80 | ASTM A234 | NACE | 53.0417 | 212.1667 | 19052584
275 | Fitting | In Desalting Plant 4 | Reducer | 4 | 3 | No | 2 | AN16 | SCH.80 | ASTM A234 | NACE | 5.7143 | 11.4286 | 1280222
276 | Fitting | In Desalting Plant 4 | Reducer | 6 | 3 | No | 2 | AN16 | SCH.80 | ASTM A234 | NACE | 12.4812 | 24.9624 | 3895520
277 | Fitting | In Desalting Plant 4 | Reducer | 6 | 4 | No | 4 | AN16 | SCH.80 | ASTM A234 | NACE | 12.4812 | 49.9248 | 4028361
278 | Fitting | In Desalting Plant 4 | Reducer | 8 | 6 | No | 4 | AN16 | SCH.60 | ASTM A234 | NACE | 21.6951 | 86.7806 | 9148143
279 | Fitting | In Desalting Plant 4 | Reducer | 10 | 8 | No | 14 | AN16 | SCH.STD | ASTM A234 | NACE | 37.7443 | 528.4208 | 56384635
280 | Fitting | In Desalting Plant 4 | Reducer | 12 | 10 | No | 4 | AN16 | SCH.STD | ASTM A234 | NACE | 45.2768 | 181.1072 | 24154367
281 | Fitting | In Desalting Plant 4 | Reducer | 20 | 12 | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 75.4613 | 150.9227 | 12951881
282 | Fitting | In Desalting Plant 4 | Reducer | 20 | 18 | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 75.4613 | 150.9227 | 12951881
283 | Fitting | In Desalting Plant 4 | Reducer | 26 | 16 | No | 1 | AN16 | SCH.30 | ASTM A234 | NACE | 98.0998 | 98.0998 | 7154359
284 | Fitting | In Desalting Plant 4 | Reducer | 3 | 2 | No | 2 | AZ00 | SCH.40 | ASTM A234 | GALVD | 53.0417 | 106.0833 | 7825294
285 | Fitting | In Desalting Plant 4 | Reducer | 4 | 3 | No | 2 | AZ00 | SCH.40 | ASTM A234 | GALVD | 5.7143 | 11.4286 | 1280222
286 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 1 | No | 7 | AN01 |  | ASTM A105 |  | 9.1729 | 64.2105 | 7436782
287 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 3/4" | No | 4 | AN01 |  | ASTM A105 |  | 9.1729 | 36.6917 | 5073645
288 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 1 | No | 30 | AN01 |  | ASTM A105 |  | 3.9781 | 119.3438 | 13268120
289 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 11/2" | No | 2 | AN01 |  | ASTM A105 |  | 3.9781 | 7.9563 | 681731
290 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 3/4" | No | 2 | AN01 |  | ASTM A105 |  | 3.9781 | 7.9563 | 681731
291 | Fitting | In Desalting Plant 4 | Sockolet | 4 | 1 | No | 38 | AN01 |  | ASTM A105 |  | 7.0677 | 268.5713 | 31079424
292 | Fitting | In Desalting Plant 4 | Sockolet | 4 | 3/4" | No | 1 | AN01 |  | ASTM A105 |  | 7.0677 | 7.0677 | 573758
293 | Fitting | In Desalting Plant 4 | Sockolet | 6 | 1 | No | 10 | AN01 |  | ASTM A105 |  | 9.7608 | 97.6076 | 10389597
294 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 1 | No | 60 | AN06 |  | ASTM A105 |  | 9.1729 | 550.3757 | 46734744
295 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 2 | No | 5 | AN06 |  | ASTM A105 |  | 9.1729 | 45.8646 | 4923949
296 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 3/4" | No | 10 | AN06 |  | ASTM A105 |  | 9.1729 | 91.7293 | 11193466
297 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 1 | No | 23 | AN06 |  | ASTM A105 |  | 3.9781 | 91.4969 | 13538780
298 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 3/4" | No | 4 | AN06 |  | ASTM A105 |  | 3.9781 | 15.9125 | 2111723
299 | Fitting | In Desalting Plant 4 | Sockolet | 4 | 1 | No | 18 | AN06 |  | ASTM A105 |  | 7.0677 | 127.218 | 9836497
300 | Fitting | In Desalting Plant 4 | Sockolet | 4 | 3/4" | No | 4 | AN06 |  | ASTM A105 |  | 7.0677 | 28.2707 | 2123080
301 | Fitting | In Desalting Plant 4 | Sockolet | 6 | 1 | No | 24 | AN06 |  | ASTM A105 |  | 9.7608 | 234.2583 | 34359975
302 | Fitting | In Desalting Plant 4 | Sockolet | 6 | 3/4" | No | 8 | AN06 |  | ASTM A105 |  | 9.7608 | 78.0861 | 5620166
303 | Fitting | In Desalting Plant 4 | Sockolet | 8 | 1 | No | 11 | AN06 |  | ASTM A105 |  | 7.0677 | 77.7443 | 8330235
304 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 1 | No | 17 | AN16 |  | ASTM A105 | NACE | 9.1729 | 155.9398 | 22022097
305 | Fitting | In Desalting Plant 4 | Sockolet | 2 | 11/2" | No | 4 | AN16 |  | ASTM A105 | NACE | 9.1729 | 36.6917 | 5073645
306 | Fitting | In Desalting Plant 4 | Sockolet | 3 | 1 | No | 28 | AN16 |  | ASTM A105 | NACE | 3.9781 | 111.3875 | 10502272
307 | Fitting | In Desalting Plant 4 | Sockolet | 4 | 1 | No | 11 | AN16 |  | ASTM A105 | NACE | 7.0677 | 77.7443 | 8330235
308 | Fitting | In Desalting Plant 4 | Sockolet | 6 | 1 | No | 5 | AN16 |  | ASTM A105 | NACE | 9.7608 | 48.8038 | 7492033
309 | Fitting | In Desalting Plant 4 | Sockolet | 8 | 1 | No | 20 | AN16 |  | ASTM A105 | NACE | 7.0677 | 141.3533 | 21527049
310 | Fitting | In Desalting Plant 4 | Sockolet | 10 | 1 | No | 45 | AN16 |  | ASTM A105 | NACE | 3.9781 | 179.0156 | 13435184
311 | Fitting | In Desalting Plant 4 | Sockolet | 12 | 1 | No | 38 | AN16 |  | ASTM A105 | NACE | 5.1128 | 194.2856 | 29352102
312 | Fitting | In Desalting Plant 4 | Sockolet | 20 | 1 | No | 9 | AN16 |  | ASTM A105 | NACE | 7.0677 | 63.609 | 4851335
313 | Fitting | In Desalting Plant 4 | Sockolet | 20 | 3/4" | No | 1 | AN16 |  | ASTM A105 | NACE | 7.0677 | 7.0677 | 573758
314 | Fitting | In Desalting Plant 4 | Tee | 2 | 1 | No | 4 | AN01 | SCH.STD | ASTM A234 |  | 3.8141 | 15.2563 | 2008893
315 | Fitting | In Desalting Plant 4 | Tee | 2 | 2 | No | 9 | AN01 | SCH.STD | ASTM A234 |  | 3.8141 | 34.3267 | 4365260
316 | Fitting | In Desalting Plant 4 | Tee | 2 | 3/4" | No | 3 | AN01 | SCH.STD | ASTM A234 |  | 3.8141 | 11.4422 | 1779234
317 | Fitting | In Desalting Plant 4 | Tee | 3 | 1 | No | 3 | AN01 | SCH.STD | ASTM A234 |  | 10.3896 | 31.1688 | 3195350
318 | Fitting | In Desalting Plant 4 | Tee | 3 | 2 | No | 6 | AN01 | SCH.STD | ASTM A234 |  | 10.3896 | 62.3376 | 4441844
319 | Fitting | In Desalting Plant 4 | Tee | 3 | 3 | No | 15 | AN01 | SCH.STD | ASTM A234 |  | 10.3896 | 155.8441 | 24675540
320 | Fitting | In Desalting Plant 4 | Tee | 4 | 3 | No | 7 | AN01 | SCH.STD | ASTM A234 |  | 17.758 | 124.3062 | 11381857
321 | Fitting | In Desalting Plant 4 | Tee | 4 | 4 | No | 8 | AN01 | SCH.STD | ASTM A234 |  | 17.758 | 142.0642 | 18000758
322 | Fitting | In Desalting Plant 4 | Tee | 6 | 4 | No | 2 | AN01 | SCH.STD | ASTM A234 |  | 129.1865 | 258.3731 | 19843837
323 | Fitting | In Desalting Plant 4 | Tee | 6 | 6 | No | 2 | AN01 | SCH.STD | ASTM A234 |  | 129.1865 | 258.3731 | 19843837
324 | Fitting | In Desalting Plant 4 | Tee | 2 | 2 | No | 10 | AN06 | SCH.160 | ASTM A234 |  | 3.8141 | 38.1408 | 3474435
325 | Fitting | In Desalting Plant 4 | Tee | 3 | 3 | No | 21 | AN06 | SCH.80 | ASTM A234 |  | 10.3896 | 218.1817 | 17309459
326 | Fitting | In Desalting Plant 4 | Tee | 4 | 2 | No | 4 | AN06 | SCH.80 | ASTM A234 |  | 17.758 | 71.0321 | 7062709
327 | Fitting | In Desalting Plant 4 | Tee | 4 | 3 | No | 2 | AN06 | SCH.80 | ASTM A234 |  | 17.758 | 35.516 | 4431299
328 | Fitting | In Desalting Plant 4 | Tee | 4 | 4 | No | 7 | AN06 | SCH.80 | ASTM A234 |  | 17.758 | 124.3062 | 11381857
329 | Fitting | In Desalting Plant 4 | Tee | 6 | 4 | No | 4 | AN06 | SCH.80 | ASTM A234 |  | 129.1865 | 516.7462 | 53518407
330 | Fitting | In Desalting Plant 4 | Tee | 6 | 6 | No | 10 | AN06 | SCH.80 | ASTM A234 |  | 129.1865 | 1291.8655 | 123093743
331 | Fitting | In Desalting Plant 4 | Tee | 8 | 4 | No | 2 | AN06 | SCH.60 | ASTM A234 |  | 73.8482 | 147.6965 | 11200832
332 | Fitting | In Desalting Plant 4 | Tee | 8 | 6 | No | 3 | AN06 | SCH.60 | ASTM A234 |  | 73.8482 | 221.5447 | 26339431
333 | Fitting | In Desalting Plant 4 | Tee | 8 | 8 | No | 5 | AN06 | SCH.60 | ASTM A234 |  | 73.8482 | 369.2411 | 26029671
334 | Fitting | In Desalting Plant 4 | Tee | 2 | 2 | No | 7 | AN16 | SCH.160 | ASTM A234 | NACE | 3.8141 | 26.6986 | 3312663
335 | Fitting | In Desalting Plant 4 | Tee | 3 | 2 | No | 4 | AN16 | SCH.80 | ASTM A234 | NACE | 10.3896 | 41.5584 | 3217263
336 | Fitting | In Desalting Plant 4 | Tee | 3 | 3 | No | 9 | AN16 | SCH.80 | ASTM A234 | NACE | 10.3896 | 93.5065 | 8223455
337 | Fitting | In Desalting Plant 4 | Tee | 4 | 4 | No | 6 | AN16 | SCH.80 | ASTM A234 | NACE | 17.758 | 106.5481 | 14929261
338 | Fitting | In Desalting Plant 4 | Tee | 6 | 3 | No | 2 | AN16 | SCH.80 | ASTM A234 | NACE | 129.1865 | 258.3731 | 19843837
339 | Fitting | In Desalting Plant 4 | Tee | 6 | 4 | No | 6 | AN16 | SCH.80 | ASTM A234 | NACE | 129.1865 | 775.1193 | 111368344
340 | Fitting | In Desalting Plant 4 | Tee | 6 | 6 | No | 2 | AN16 | SCH.80 | ASTM A234 | NACE | 129.1865 | 258.3731 | 19843837
341 | Fitting | In Desalting Plant 4 | Tee | 8 | 8 | No | 2 | AN16 | SCH.60 | ASTM A234 | NACE | 73.8482 | 147.6965 | 11200832
342 | Fitting | In Desalting Plant 4 | Tee | 10 | 6 | No | 4 | AN16 | SCH.STD | ASTM A234 | NACE | 107.2864 | 429.1454 | 56486561
343 | Fitting | In Desalting Plant 4 | Tee | 10 | 8 | No | 12 | AN16 | SCH.STD | ASTM A234 | NACE | 107.2864 | 1287.4362 | 152985448
344 | Fitting | In Desalting Plant 4 | Tee | 10 | 10 | No | 12 | AN16 | SCH.STD | ASTM A234 | NACE | 107.2864 | 1287.4362 | 152985448
345 | Fitting | In Desalting Plant 4 | Tee | 12 | 10 | No | 10 | AN16 | SCH.STD | ASTM A234 | NACE | 157.4299 | 1574.2987 | 211190508
346 | Fitting | In Desalting Plant 4 | Tee | 12 | 12 | No | 24 | AN16 | SCH.STD | ASTM A234 | NACE | 157.4299 | 3778.317 | 282091648
347 | Fitting | In Desalting Plant 4 | Tee | 16 | 16 | No | 2 | AN16 | SCH.40 | ASTM A234 | NACE | 453.8207 | 907.6415 | 69926711
348 | Fitting | In Desalting Plant 4 | Tee | 20 | 12 | No | 3 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 1701.8175 | 138651205
349 | Fitting | In Desalting Plant 4 | Tee | 20 | 18 | No | 2 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 1134.545 | 84704728
350 | Fitting | In Desalting Plant 4 | Tee | 20 | 20 | No | 1 | AN16 | SCH.30 | ASTM A234 | NACE | 567.2725 | 567.2725 | 40920851
351 | Fitting | In Desalting Plant 4 | Tee | 3 | 1 | No | 11 | AZ00 | SCH.40 | ASTM A234 | GALVD | 10.3896 | 114.2857 | 10996202
352 | Fitting | In Desalting Plant 4 | Tee | 3 | 2 | No | 4 | AZ00 | SCH.40 | ASTM A234 | GALVD | 10.3896 | 41.5584 | 3217263
353 | Fitting | In Desalting Plant 4 | Tee | 3 | 3 | No | 1 | AZ00 | SCH.40 | ASTM A234 | GALVD | 10.3896 | 10.3896 | 1615074
354 | Fitting | In Desalting Plant 4 | Tee | 3 | 3/4" | No | 1 | AZ00 | SCH.40 | ASTM A234 | GALVD | 10.3896 | 10.3896 | 1615074
355 | Fitting | In Desalting Plant 4 | Tee | 4 | 11/2" | No | 1 | AZ00 | SCH.40 | ASTM A234 | GALVD | 17.758 | 17.758 | 1528398
356 | Fitting | In Desalting Plant 4 | Weldolet | 3 | 2 | No | 2 | AN01 | SCH.STD |  |  | 19.8906 | 39.7813 | 3087600
357 | Fitting | In Desalting Plant 4 | Weldolet | 3 | 11/2" | No | 4 | AN01 | SCH.STD |  |  | 19.8906 | 79.5625 | 9006072
358 | Fitting | In Desalting Plant 4 | Weldolet | 4 | 2 | No | 1 | AN01 | SCH.STD |  |  | 19.8906 | 19.8906 | 1396233
359 | Fitting | In Desalting Plant 4 | Weldolet | 4 | 11/2" | No | 5 | AN01 | SCH.STD |  |  | 19.8906 | 99.4531 | 15121796
360 | Fitting | In Desalting Plant 4 | Weldolet | 6 | 11/2" | No | 1 | AN01 | SCH.STD |  |  | 19.8906 | 19.8906 | 1396233
361 | Fitting | In Desalting Plant 4 | Weldolet | 3 | 11/2" | No | 1 | AN06 | SCH.80 |  |  | 19.8906 | 19.8906 | 1396233
362 | Fitting | In Desalting Plant 4 | Weldolet | 4 | 11/2" | No | 3 | AN06 | SCH.80 |  |  | 19.8906 | 59.6719 | 7516597
363 | Fitting | In Desalting Plant 4 | Weldolet | 6 | 2 | No | 15 | AN06 | SCH.80 |  |  | 19.8906 | 298.3594 | 42180440
364 | Fitting | In Desalting Plant 4 | Weldolet | 6 | 3 | No | 2 | AN06 | SCH.80 |  |  | 30.9364 | 61.8728 | 4423704
365 | Fitting | In Desalting Plant 4 | Weldolet | 8 | 2 | No | 11 | AN06 | SCH.60 |  |  | 19.8906 | 218.7969 | 29932660
366 | Fitting | In Desalting Plant 4 | Weldolet | 8 | 3 | No | 3 | AN06 | SCH.60 |  |  | 30.9364 | 92.8093 | 14669563
367 | Fitting | In Desalting Plant 4 | Weldolet | 8 | 4 | No | 3 | AN06 | SCH.60 |  |  | 19.8906 | 59.6719 | 7516597
368 | Fitting | In Desalting Plant 4 | Weldolet | 10 | 2 | No | 7 | AN16 | SCH.STD |  | NACE | 19.8906 | 139.2344 | 15998711
369 | Fitting | In Desalting Plant 4 | Weldolet | 10 | 3 | No | 5 | AN16 | SCH.STD |  | NACE | 30.9364 | 154.6821 | 19050307
370 | Fitting | In Desalting Plant 4 | Weldolet | 10 | 4 | No | 1 | AN16 | SCH.STD |  | NACE | 50.827 | 50.827 | 4897752
371 | Fitting | In Desalting Plant 4 | Weldolet | 10 | 11/2" | No | 17 | AN16 | SCH.STD |  | NACE | 13.6979 | 232.8639 | 16171786
372 | Fitting | In Desalting Plant 4 | Weldolet | 12 | 2 | No | 6 | AN16 | SCH.STD |  | NACE | 19.8906 | 119.3438 | 13268120
373 | Fitting | In Desalting Plant 4 | Weldolet | 12 | 4 | No | 4 | AN16 | SCH.STD |  | NACE | 50.827 | 203.3082 | 17699224
374 | Fitting | In Desalting Plant 4 | Weldolet | 12 | 6 | No | 8 | AN16 | SCH.STD |  | NACE | 45.7963 | 366.3703 | 50499454
375 | Fitting | In Desalting Plant 4 | Weldolet | 12 | 11/2" | No | 16 | AN16 | SCH.STD |  | NACE | 13.6979 | 219.166 | 34614078
376 | Fitting | In Desalting Plant 4 | Weldolet | 16 | 2 | No | 5 | AN16 | SCH.40 |  | NACE | 19.8906 | 99.4531 | 15121796
377 | Fitting | In Desalting Plant 4 | Weldolet | 16 | 3 | No | 9 | AN16 | SCH.40 |  | NACE | 30.9364 | 278.4278 | 44314676
378 | Fitting | In Desalting Plant 4 | Weldolet | 16 | 6 | No | 3 | AN16 | SCH.40 |  | NACE | 45.7963 | 137.3889 | 11001070
379 | Fitting | In Desalting Plant 4 | Weldolet | 16 | 11/2" | No | 1 | AN16 | SCH.40 |  | NACE | 13.6979 | 13.6979 | 1844956
380 | Fitting | In Desalting Plant 4 | Weldolet | 20 | 2 | No | 1 | AN16 | SCH.30 |  | NACE | 19.8906 | 19.8906 | 1396233
381 | Fitting | In Desalting Plant 4 | Weldolet | 20 | 3 | No | 1 | AN16 | SCH.30 |  | NACE | 30.9364 | 30.9364 | 3258592
382 | Fitting | In Desalting Plant 4 | Weldolet | 20 | 4 | No | 1 | AN16 | SCH.30 |  | NACE | 50.827 | 50.827 | 4897752
383 | Fitting | In Desalting Plant 4 | Weldolet | 20 | 6 | No | 1 | AN16 | SCH.30 |  | NACE | 45.7963 | 45.7963 | 5360313
384 | Fitting | In Desalting Plant 4 | Weldolet | 20 | 11/2" | No | 2 | AN16 | SCH.30 |  | NACE | 13.6979 | 27.3958 | 2267434
385 | Flange | In Desalting Plant 4 | Flange | 1 | - | No | 2 | AN01 | SCH.80 | ASTM A105 |  | 4.0738 | 8.1476 | 807596
386 | Flange | In Desalting Plant 4 | Flange | 2 | - | No | 55 | AN01 | SCH.STD | ASTM A105 |  | 12.7683 | 702.2554 | 52378609
387 | Flange | In Desalting Plant 4 | Flange | 3 | - | No | 82 | AN01 | SCH.STD | ASTM A105 |  | 22.9392 | 1881.0108 | 150250687
388 | Flange | In Desalting Plant 4 | Flange | 4 | - | No | 48 | AN01 | SCH.STD | ASTM A105 |  | 32.4812 | 1559.0971 | 170672885
389 | Flange | In Desalting Plant 4 | Flange | 6 | - | No | 13 | AN01 | SCH.STD | ASTM A105 |  | 52.1804 | 678.3456 | 47333888
390 | Flange | In Desalting Plant 4 | Flange | 11/2" | - | No | 17 | AN01 | SCH.80 | ASTM A105 |  | 11.1141 | 188.9405 | 23770435
391 | Flange | In Desalting Plant 4 | Flange | 21/2" | - | No | 2 | AN01 | SCH.STD | ASTM A105 |  | 19.8223 | 39.6445 | 3916341
392 | Flange | In Desalting Plant 4 | Flange | 2 | - | No | 106 | AN06 | SCH.160 | ASTM A105 |  | 16.7327 | 1773.6698 | 254002260
393 | Flange | In Desalting Plant 4 | Flange | 3 | - | No | 72 | AN06 | SCH.80 | ASTM A105 |  | 22.9392 | 1651.6193 | 245772010
394 | Flange | In Desalting Plant 4 | Flange | 4 | - | No | 44 | AN06 | SCH.80 | ASTM A105 |  | 32.4812 | 1429.1723 | 227653204
395 | Flange | In Desalting Plant 4 | Flange | 6 | - | No | 22 | AN06 | SCH.80 | ASTM A105 |  | 52.1804 | 1147.9695 | 82796247
396 | Flange | In Desalting Plant 4 | Flange | 8 | - | No | 9 | AN06 | SCH.60 | ASTM A105 |  | 77.2932 | 695.6388 | 108497102
397 | Flange | In Desalting Plant 4 | Flange | 11/2" | - | No | 4 | AN06 | SCH.160 | ASTM A105 |  | 11.1141 | 44.4566 | 4422471
398 | Flange | In Desalting Plant 4 | Flange | 2 | - | No | 94 | AN16 | SCH.160 | ASTM A105 | NACE | 25.0991 | 2359.3155 | 370753245
399 | Flange | In Desalting Plant 4 | Flange | 3 | - | No | 90 | AN16 | SCH.80 | ASTM A105 | NACE | 34.4087 | 3096.7862 | 491598667
400 | Flange | In Desalting Plant 4 | Flange | 4 | - | No | 33 | AN16 | SCH.80 | ASTM A105 | NACE | 48.7218 | 1607.8189 | 242357735
401 | Flange | In Desalting Plant 4 | Flange | 6 | - | No | 38 | AN16 | SCH.80 | ASTM A105 | NACE | 78.2638 | 2974.0248 | 378784344
402 | Flange | In Desalting Plant 4 | Flange | 8 | - | No | 59 | AN16 | SCH.60 | ASTM A105 | NACE | 117.3889 | 6925.9438 | 831532254
403 | Flange | In Desalting Plant 4 | Flange | 10 | - | No | 105 | AN16 | SCH.STD | ASTM A105 | NACE | 183.0348 | 15087 | 1313745026
404 | Flange | In Desalting Plant 4 | Flange | 12 | - | No | 4 | AN16 | SCH.STD | ASTM A105 | NACE | 200.9569 | 803.8274 | 117668650
405 | Flange | In Desalting Plant 4 | Flange | 12 | - | No | 92 | AN16 | SCH.STD | ASTM A105 | NACE | 200.9569 | 19577 | 1551135972
406 | Flange | In Desalting Plant 4 | Flange | 16 | - | No | 14 | AN16 | SCH.40 | ASTM A105 | NACE | 302.1188 | 4229.6633 | 544536335
407 | Flange | In Desalting Plant 4 | Flange | 18 | - | No | 4 | AN16 | SCH.30 | ASTM A105 | NACE | 407.3819 | 1629.5277 | 217828322
408 | Flange | In Desalting Plant 4 | Flange | 20 | - | No | 15 | AN16 | SCH.30 | ASTM A105 | NACE | 508.5439 | 7628.1582 | 741191284
409 | Flange | In Desalting Plant 4 | Flange | 26 | - | No | 1 | AN16 | SCH.30 | ASTM A105 | NACE | 594.6682 | 594.6682 | 78429161
410 | Flange | In Desalting Plant 4 | Flange | 11/2" | - | No | 48 | AN16 | SCH.160 | ASTM A105 | NACE | 16.6644 | 799.8903 | 72006210
411 | Flange | In Desalting Plant 4 | Flange | 21/2" | - | No | 4 | AN16 | SCH.160 | ASTM A105 | NACE | 31.784 | 127.136 | 17186057
412 | Flange | In Desalting Plant 4 | Flange | 2 | - | No | 14 | AZ00 | SCH.40 | ASTM A105 | GALVD | 15.311 | 214.354 | 27203176
413 | Flange | In Desalting Plant 4 | Flange | 3 | - | No | 9 | AZ00 | SCH.40 | ASTM A105 | GALVD | 27.5188 | 247.6691 | 17662122
414 | Flange | In Desalting Plant 4 | Flange | 11/2" | - | No | 1 | AZ00 | SCH.80 | ASTM A105 | GALVD | 13.3288 | 13.3288 | 1219039
415 | Flange | In Desalting Plant 4 | Spectace | 1 | - | No | 2 | AN01 |  | ASTM A516 |  | 5.1675 | 10.3349 | 1494146
416 | Flange | In Desalting Plant 4 | Spectace | 2 | - | No | 1 | AN01 |  | ASTM A516 |  | 22.9255 | 22.9255 | 3121852
417 | Flange | In Desalting Plant 4 | Spectace | 3 | - | No | 8 | AN01 |  | ASTM A516 |  | 34.3814 | 275.0512 | 40730606
418 | Flange | In Desalting Plant 4 | Spectace | 4 | - | No | 10 | AN01 |  | ASTM A516 |  | 57.3069 | 573.0688 | 47603477
419 | Flange | In Desalting Plant 4 | Spectace | 6 | - | No | 2 | AN01 |  | ASTM A516 |  | 114.6001 | 229.2002 | 32018647
420 | Flange | In Desalting Plant 4 | Spectace | 2 | - | No | 11 | AN06 |  | ASTM A516 |  | 22.9255 | 252.1803 | 21281302
421 | Flange | In Desalting Plant 4 | Spectace | 3 | - | No | 9 | AN06 |  | ASTM A516 |  | 34.3814 | 309.4325 | 36943066
422 | Flange | In Desalting Plant 4 | Spectace | 4 | - | No | 11 | AN06 |  | ASTM A516 |  | 57.3069 | 630.3757 | 92663674
423 | Flange | In Desalting Plant 4 | Spectace | 6 | - | No | 3 | AN06 |  | ASTM A516 |  | 114.6001 | 343.8003 | 48700497
424 | Flange | In Desalting Plant 4 | Spectace | 8 | - | No | 1 | AN06 |  | ASTM A516 |  | 296.0491 | 296.0491 | 37994747
425 | Flange | In Desalting Plant 4 | Spectace | 2 | - | No | 9 | AN16 |  | ASTM A516 | NACE | 27.5461 | 247.9151 | 30140339
426 | Flange | In Desalting Plant 4 | Spectace | 3 | - | No | 8 | AN16 |  | ASTM A516 | NACE | 41.2577 | 330.0614 | 24475953
427 | Flange | In Desalting Plant 4 | Spectace | 4 | - | No | 1 | AN16 |  | ASTM A516 | NACE | 68.7628 | 68.7628 | 10409906
428 | Flange | In Desalting Plant 4 | Spectace | 6 | - | No | 6 | AN16 |  | ASTM A516 | NACE | 137.5256 | 825.1535 | 67236298
429 | Flange | In Desalting Plant 4 | Spectace | 8 | - | No | 6 | AN16 |  | ASTM A516 | NACE | 355.2562 | 2131.5371 | 208289876
430 | Flange | In Desalting Plant 4 | Spectace | 10 | - | No | 19 | AN16 |  | ASTM A516 | NACE | 181.0662 | 3440.2583 | 341859134
431 | Flange | In Desalting Plant 4 | Spectace | 12 | - | No | 14 | AN16 |  | ASTM A516 | NACE | 917.7577 | 14368 | 1796959217
432 | Flange | In Desalting Plant 4 | Spectace | 16 | - | No | 2 | AN16 |  | ASTM A516 | NACE | 1455.4334 | 2910.8669 | 447164945
433 | Flange | In Desalting Plant 4 | Spectace | 20 | - | No | 2 | AN16 |  | ASTM A516 | NACE | 2187.2855 | 4374.571 | 535963003
434 | Gasket | In Desalting Plant 4 | - | 1 | - | No | 2 | AN01 |  | FLAT |  | 0.62884 | 1.2577 | 193301
435 | Gasket | In Desalting Plant 4 | - | 2 | - | No | 59 | AN01 |  | FLAT |  | 1.4081 | 83.0758 | 10478029
436 | Gasket | In Desalting Plant 4 | - | 3 | - | No | 101 | AN01 |  | FLAT |  | 2.0916 | 211.2508 | 29749344
437 | Gasket | In Desalting Plant 4 | - | 4 | - | No | 68 | AN01 |  | FLAT |  | 3.3766 | 229.6103 | 35873398
438 | Gasket | In Desalting Plant 4 | - | 6 | - | No | 14 | AN01 |  | FLAT |  | 4.0328 | 56.4593 | 7890743
439 | Gasket | In Desalting Plant 4 | - | 11/2" | - | No | 8 | AN01 |  | FLAT |  | 0.91593 | 7.3274 | 1635373
440 | Gasket | In Desalting Plant 4 | - | 21/2" | - | No | 2 | AN01 |  | FLAT |  | 1.9139 | 3.8277 | 451193
441 | Gasket | In Desalting Plant 4 | - | 2 | - | No | 112 | AN06 |  | FLAT |  | 1.4081 | 157.7033 | 22421698
442 | Gasket | In Desalting Plant 4 | - | 3 | - | No | 90 | AN06 |  | FLAT |  | 2.0916 | 188.2433 | 38124402
443 | Gasket | In Desalting Plant 4 | - | 4 | - | No | 54 | AN06 |  | FLAT |  | 3.3766 | 182.3376 | 27464782
444 | Gasket | In Desalting Plant 4 | - | 6 | - | No | 24 | AN06 |  | FLAT |  | 4.0328 | 96.7874 | 19601515
445 | Gasket | In Desalting Plant 4 | - | 8 | - | No | 11 | AN06 |  | FLAT |  | 5.728 | 63.0075 | 10421418
446 | Gasket | In Desalting Plant 4 | - | 2 | 1 | No | 21 | AN16 |  | FLAT | NACE | 1.4081 | 29.5694 | 6370110
447 | Gasket | In Desalting Plant 4 | - | 2 | - | No | 82 | AN16 |  | FLAT | NACE | 1.4081 | 115.4613 | 28960310
448 | Gasket | In Desalting Plant 4 | - | 3 | 1 | No | 18 | AN16 |  | FLAT | NACE | 2.0916 | 37.6487 | 4883917
449 | Gasket | In Desalting Plant 4 | - | 3 | - | No | 80 | AN16 |  | FLAT | NACE | 2.0916 | 167.3273 | 32028221
450 | Gasket | In Desalting Plant 4 | - | 4 | - | No | 35 | AN16 |  | FLAT | NACE | 3.3766 | 118.1818 | 26399375
451 | Gasket | In Desalting Plant 4 | - | 6 | - | No | 51 | AN16 |  | FLAT | NACE | 4.0328 | 205.6732 | 43777709
452 | Gasket | In Desalting Plant 4 | - | 8 | - | No | 72 | AN16 |  | FLAT | NACE | 5.728 | 412.4127 | 67876428
453 | Gasket | In Desalting Plant 4 | - | 10 | - | No | 143 | AN16 |  | FLAT | NACE | 30.2939 | 4332.0283 | 709818729
454 | Gasket | In Desalting Plant 4 | - | 12 | 15 | No | 8 | AN16 |  | FLAT | NACE | 41.4764 | 331.8112 | 54304763
455 | Gasket | In Desalting Plant 4 | - | 12 | - | No | 122 | AN16 |  | FLAT | NACE | 41.4764 | 5060.121 | 887659020
456 | Gasket | In Desalting Plant 4 | - | 16 | - | No | 15 | AN16 |  | FLAT | NACE | 68.216 | 1023.2395 | 134820385
457 | Gasket | In Desalting Plant 4 | - | 18 | - | No | 4 | AN16 |  | FLAT | NACE | 257.006 | 1028.0242 | 210146771
458 | Gasket | In Desalting Plant 4 | - | 20 | - | No | 20 | AN16 |  | FLAT | NACE | 267.9425 | 5358.8495 | 923970364
459 | Gasket | In Desalting Plant 4 | - | 26 | - | No | 1 | AN16 |  | FLAT | NACE | 267.9425 | 267.9425 | 45299090
460 | Gasket | In Desalting Plant 4 | - | 11/2" | - | No | 18 | AN16 |  | FLAT | NACE | 0.91593 | 16.4867 | 2754029
461 | Gasket | In Desalting Plant 4 | - | 21/2" | - | No | 4 | AN16 |  | FLAT | NACE | 1.9139 | 7.6555 | 1101655
462 | Gasket | In Desalting Plant 4 | - | 2 | - | No | 14 | AZ00 |  | FLAT | GALVD | 1.4081 | 19.7129 | 3026362
463 | Gasket | In Desalting Plant 4 | - | 3 | - | No | 9 | AZ00 |  | FLAT | GALVD | 2.0916 | 18.8243 | 3107073
464 | Pipe | In Desalting Plant 4 | - | 1 | - | m | 2 | AN01 | SCH.80 | API5L-GR.B |  | 6.1517 | 12.3035 | 800932
465 | Pipe | In Desalting Plant 4 | - | 2 | - | m | 957.5 | AN01 | SCH.STD | API5L-GR.B |  | 10.3349 | 9895.6897 | 421125360
466 | Pipe | In Desalting Plant 4 | - | 3 | - | m | 222.9 | AN01 | SCH.STD | API5L-GR.B |  | 20.3281 | 4531.1301 | 219814498
467 | Pipe | In Desalting Plant 4 | - | 4 | - | m | 439.5 | AN01 | SCH.STD | API5L-GR.B |  | 28.9405 | 16919 | 954440495
468 | Pipe | In Desalting Plant 4 | - | 6 | - | m | 33.5 | AN01 | SCH.STD | API5L-GR.B |  | 111.0321 | 3719.5747 | 198712483
469 | Pipe | In Desalting Plant 4 | - | 2 | - | m | 909.5 | AN06 | SCH.160 | API5L-GR.B |  | 10.3349 | 9399.6134 | 816779993
470 | Pipe | In Desalting Plant 4 | - | 3 | - | m | 1054 | AN06 | SCH.80 | API5L-GR.B |  | 20.3281 | 21504 | 1856655965
471 | Pipe | In Desalting Plant 4 | - | 4 | - | m | 325 | AN06 | SCH.80 | API5L-GR.B |  | 28.9405 | 9405.6694 | 836445932
472 | Pipe | In Desalting Plant 4 | - | 6 | - | m | 980 | AN06 | SCH.80 | API5L-GR.B |  | 111.0321 | 79728 | 6057874986
473 | Pipe | In Desalting Plant 4 | - | 8 | - | m | 336 | AN06 | SCH.60 | API5L-GR.B |  | 167.1906 | 44074 | 2890459161
474 | Pipe | In Desalting Plant 4 | - | 2 | - | m | 2452 | AN16 | SCH.160 | API5L-GR.B | NACE | 11.702 | 33696 | 1640510682
475 | Pipe | In Desalting Plant 4 | - | 3 | - | m | 387 | AN16 | SCH.80 | API5L-GR.B | NACE | 22.5564 | 8729.3197 | 596348596
476 | Pipe | In Desalting Plant 4 | - | 4 | - | m | 171 | AN16 | SCH.80 | API5L-GR.B | NACE | 34.1763 | 5844.1534 | 503790888
477 | Pipe | In Desalting Plant 4 | - | 6 | - | m | 455 | AN16 | SCH.80 | API5L-GR.B | NACE | 124.7026 | 56282 | 2626678109
478 | Pipe | In Desalting Plant 4 | - | 8 | - | m | 243 | AN16 | SCH.60 | API5L-GR.B | NACE | 175.393 | 38883 | 3162475885
479 | Pipe | In Desalting Plant 4 | - | 10 | - | m | 1311 | AN16 | SCH.STD | API5L-GR.B | NACE | 165.4135 | 253660 | 9794938732
480 | Pipe | In Desalting Plant 4 | - | 12 | - | m | 647.5 | AN16 | SCH.STD | API5L-GR.B | NACE | 244.2514 | 137784 | 14391254388
481 | Pipe | In Desalting Plant 4 | - | 16 | - | m | 939 | AN16 | SCH.40 | API5L-GR.B | NACE | 254.9008 | 144275 | 33945591601
482 | Pipe | In Desalting Plant 4 | - | 20 | - | m | 1010 | AN16 | SCH.30 | API5L-GR.B | NACE | 300.7518 | 334464 | 56911080771
483 | Pipe | In Desalting Plant 4 | - | 2 | - | m | 182 | AZ00 | SCH.40 | API5L-GR.B | GALVD | 10.3349 | 1880.9562 | 84452957
484 | Special | In Desalting Plant 4 | Filter | 3 | - | No | 3 | AN01 |  | ASTM A216-GR.WCB |  | 390.9773 | 1172.9318 | 130162599
485 | Special | In Desalting Plant 4 | Filter | 4 | - | No | 9 | AN01 |  | ASTM A216-GR.WCB |  | 527.6826 | 4749.1436 | 361801334
486 | Special | In Desalting Plant 4 | Filter | 6 | - | No | 1 | AN01 |  | ASTM A216-GR.WCB |  | 574.1624 | 574.1624 | 45173672
487 | Special | In Desalting Plant 4 | Filter | 3 | - | No | 2 | AN06 |  | ASTM A216-GR.WCB |  | 390.9773 | 781.9546 | 122073020
488 | Special | In Desalting Plant 4 | Filter | 4 | - | No | 2 | AN06 |  | ASTM A216-GR.WCB |  | 527.6826 | 1055.3653 | 114012355
489 | Special | In Desalting Plant 4 | Filter | 3 | - | No | 2 | AN16 |  | ASTM A216-GR.WCB | NACE | 468.8993 | 937.7987 | 122550812
490 | Special | In Desalting Plant 4 | Filter | 8 | - | No | 2 | AN16 |  | ASTM A216-GR.WCB | NACE | 765.5499 | 1531.0999 | 234510021
491 | Special | In Desalting Plant 4 | Filter | 12 | - | No | 2 | AN16 |  | ASTM A216-GR.WCB | NACE | 1244.0186 | 2488.0373 | 353538325
492 | Special | In Desalting Plant 4 | Footvalve | 3 | - | No | 2 | AN06 |  | ASTM A216-GR.WCB |  | 546.8214 | 1093.6428 | 92345218
493 | Special | In Desalting Plant 4 | Orifice Flange | 3 | - | No | 2 | AN01 |  | ASTM A105 |  | 22.9392 | 45.8783 | 5614659
494 | Special | In Desalting Plant 4 | Orifice Flange | 4 | - | No | 4 | AN01 |  | ASTM A105 |  | 30.4306 | 121.7224 | 14408819
495 | Special | In Desalting Plant 4 | Orifice Flange | 6 | - | No | 2 | AN16 | SCH.80 | ASTM A105 | NACE | 52.1804 | 104.3609 | 8956056
496 | Special | In Desalting Plant 4 | Orifice Flange | 10 | - | No | 10 | AN16 | SCH.STD | ASTM A105 | NACE | 98.0314 | 980.314 | 107892432
497 | Special | In Desalting Plant 4 | Orifice Flange | 12 | - | No | 8 | AN16 | SCH.STD | ASTM A105 | NACE | 191.3875 | 1531.0999 | 234510021
498 | Special | In Desalting Plant 4 | Orifice Flange | 3 | - | No | 2 | AZ00 |  | ASTM A105 | GALVD | 22.9392 | 45.8783 | 5614659
499 | Special | In Desalting Plant 4 | Quick Coupling | 3 | 21/2" | No | 1 | AN01 | - | ASTM A105 |  | 150.3759 | 150.3759 | 18979022
500 | Special | In Desalting Plant 4 | Water Trap | 2 | - | No | 1 | AN01 |  | ASTM A216-GR.WCB |  | 273.4107 | 273.4107 | 28698532
501 | Valve | In Desalting Plant 4 | Ball | 2 | - | No | 4 | AN01 | - | ASTM A216-GR.WCB |  | 117.5666 | 470.2664 | 43875936
502 | Valve | In Desalting Plant 4 | Ball | 3 | - | No | 5 | AN01 | - | ASTM A216-GR.WCB |  | 225.5638 | 1127.8191 | 71538721
503 | Valve | In Desalting Plant 4 | Ball | 8 | - | No | 1 | AN06 | - | ASTM A216-GR.WCB |  | 1861.6534 | 1861.6534 | 82791017
504 | Valve | In Desalting Plant 4 | Ball | 1 | - | No | 10 | AN16 |  | ASTM A105 | NACE | 83.6637 | 836.6367 | 63245485
505 | Valve | In Desalting Plant 4 | Ball | 2 | - | No | 16 | AN16 | - | ASTM A216-GR.WCB | NACE | 123.855 | 1981.6807 | 129636050
506 | Valve | In Desalting Plant 4 | Ball | 3 | - | No | 24 | AN16 | - | ASTM A216-GR.WCB | NACE | 226.2473 | 5429.9363 | 508400555
507 | Valve | In Desalting Plant 4 | Ball | 4 | - | No | 3 | AN16 | - | ASTM A216-GR.WCB | NACE | 287.0812 | 861.2437 | 66432116
508 | Valve | In Desalting Plant 4 | Ball | 6 | - | No | 7 | AN16 | - | ASTM A216-GR.WCB | NACE | 1127.8191 | 7894.7336 | 595703221
509 | Valve | In Desalting Plant 4 | Ball | 8 | - | No | 5 | AN16 | - | ASTM A216-GR.WCB | NACE | 1861.6534 | 9308.2669 | 395459729
510 | Valve | In Desalting Plant 4 | Ball | 10 | - | No | 11 | AN16 | - | ASTM A216-GR.WCB | NACE | 2790.8396 | 30748 | 1667924018
511 | Valve | In Desalting Plant 4 | Ball | 16 | - | No | 5 | AN16 | - | ASTM A216-GR.WCB | NACE | 8947.3647 | 55179 | 4052082403
512 | Valve | In Desalting Plant 4 | Ball | 3 | - | No | 2 | AZ00 | - | ASTM B148 |  | 236.0901 | 472.1803 | 43326240
513 | Valve | In Desalting Plant 4 | Check | 1 | - | No | 1 | AN01 |  | ASTM A105 |  | 50.581 | 50.581 | 2928847
514 | Valve | In Desalting Plant 4 | Check | 3 | - | No | 6 | AN01 | - | ASTM A216-GR.WCB |  | 194.1216 | 1164.7295 | 85853056
515 | Valve | In Desalting Plant 4 | Check | 4 | - | No | 4 | AN01 | - | ASTM A216-GR.WCB |  | 287.0812 | 1148.3249 | 56814417
516 | Valve | In Desalting Plant 4 | Check | 2 | - | No | 13 | AN06 | - | ASTM A216-GR.WCB |  | 102.529 | 1332.8771 | 88813065
517 | Valve | In Desalting Plant 4 | Check | 3 | - | No | 7 | AN06 | - | ASTM A216-GR.WCB |  | 194.1216 | 1358.8511 | 108040748
518 | Valve | In Desalting Plant 4 | Check | 4 | - | No | 5 | AN06 | - | ASTM A216-GR.WCB |  | 287.0812 | 1435.4061 | 130804367
519 | Valve | In Desalting Plant 4 | Check | 6 | - | No | 2 | AN06 | - | ASTM A216-GR.WCB |  | 615.174 | 1230.3481 | 92851154
520 | Valve | In Desalting Plant 4 | Check | 8 | - | No | 1 | AN06 | - | ASTM A216-GR.WCB |  | 710.8678 | 710.8678 | 60376392
521 | Valve | In Desalting Plant 4 | Check | 2 | - | No | 4 | AN16 | - | ASTM A216-GR.WCB | NACE | 135.3383 | 541.3532 | 50158267
522 | Valve | In Desalting Plant 4 | Check | 3 | - | No | 1 | AN16 | - | ASTM A216-GR.WCB | NACE | 231.5789 | 231.5789 | 20362178
523 | Valve | In Desalting Plant 4 | Check | 10 | - | No | 4 | AN16 | - | ASTM A216-GR.WCB | NACE | 1105.2627 | 4421.0508 | 270812998
524 | Valve | In Desalting Plant 4 | Check | 20 | - | No | 1 | AN16 | - | ASTM A216-GR.WCB | NACE | 7450 | 7450 | 1026311784
525 | Valve | In Desalting Plant 4 | Gate | 1 | - | No | 66 | AN01 |  | ASTM A105 |  | 54.6821 | 3609.0211 | 157481983
526 | Valve | In Desalting Plant 4 | Gate | 2 | - | No | 16 | AN01 | - | ASTM A216-GR.WCB |  | 159.2617 | 2548.1876 | 153716146
527 | Valve | In Desalting Plant 4 | Gate | 3 | - | No | 18 | AN01 | - | ASTM A216-GR.WCB |  | 248.1202 | 4466.1636 | 344220272
528 | Valve | In Desalting Plant 4 | Gate | 4 | - | No | 12 | AN01 | - | ASTM A216-GR.WCB |  | 314.4223 | 3773.0675 | 357490534
529 | Valve | In Desalting Plant 4 | Gate | 6 | - | No | 4 | AN01 | - | ASTM A216-GR.WCB |  | 526.3156 | 2105.2623 | 164095367
530 | Valve | In Desalting Plant 4 | Gate | 3/4" | - | No | 11 | AN01 |  | ASTM A105 |  | 36.9104 | 406.0149 | 21460415
531 | Valve | In Desalting Plant 4 | Gate | 1 | - | No | 42 | AN06 |  | ASTM A105 |  | 54.6821 | 2296.6498 | 114438254
532 | Valve | In Desalting Plant 4 | Gate | 2 | - | No | 28 | AN06 | - | ASTM A216-GR.WCB |  | 159.2617 | 4459.3283 | 188142550
533 | Valve | In Desalting Plant 4 | Gate | 3 | - | No | 26 | AN06 | - | ASTM A216-GR.WCB |  | 248.1202 | 6451.1252 | 499310535
534 | Valve | In Desalting Plant 4 | Gate | 4 | - | No | 17 | AN06 | - | ASTM A216-GR.WCB |  | 314.4223 | 5345.1789 | 335235872
535 | Valve | In Desalting Plant 4 | Gate | 6 | - | No | 5 | AN06 | - | ASTM A216-GR.WCB |  | 526.3156 | 2631.5779 | 215442444
536 | Valve | In Desalting Plant 4 | Gate | 8 | - | No | 1 | AN06 | - | ASTM A216-GR.WCB |  | 765.5499 | 765.5499 | 50461035
537 | Valve | In Desalting Plant 4 | Gate | 3/4" | - | No | 16 | AN06 |  | ASTM A105 |  | 36.9104 | 590.5671 | 55924627
538 | Valve | In Desalting Plant 4 | Gate | 1 | - | No | 132 | AN16 |  | ASTM A105 | NACE | 54.6821 | 7218.0422 | 537891487
539 | Valve | In Desalting Plant 4 | Gate | 2 | - | No | 17 | AN16 | - | ASTM A216-GR.WCB | NACE | 195.4886 | 3323.3069 | 149335640
540 | Valve | In Desalting Plant 4 | Gate | 3 | - | No | 6 | AN16 | - | ASTM A216-GR.WCB | NACE | 332.3307 | 1993.9841 | 114714454
541 | Valve | In Desalting Plant 4 | Gate | 4 | - | No | 4 | AN16 | - | ASTM A216-GR.WCB | NACE | 448.1201 | 1792.4805 | 112710069
542 | Valve | In Desalting Plant 4 | Gate | 6 | - | No | 6 | AN16 | - | ASTM A216-GR.WCB | NACE | 604.511 | 3627.0662 | 298992488
543 | Valve | In Desalting Plant 4 | Gate | 8 | - | No | 6 | AN16 | - | ASTM A216-GR.WCB | NACE | 998.4958 | 5990.975 | 412683236
544 | Valve | In Desalting Plant 4 | Gate | 10 | - | No | 28 | AN16 | - | ASTM A216-GR.WCB | NACE | 1410.5257 | 45382 | 3294902277
545 | Valve | In Desalting Plant 4 | Gate | 12 | - | No | 4 | AN16 | - | ASTM A216-GR.WCB | NACE | 1864.6609 | 7458.6436 | 350199392
546 | Valve | In Desalting Plant 4 | Gate | 12 | - | No | 33 | AN16 | - | ASTM A216-GR.WCB | NACE | 1864.6609 | 53241 | 3624803922
547 | Valve | In Desalting Plant 4 | Gate | 20 | - | No | 5 | AN16 | - | ASTM A216-GR.WCB | NACE | 7450 | 61497 | 4633783077
548 | Valve | In Desalting Plant 4 | Gate | 1 | - | No | 2 | AZ00 |  | ASTM B148 |  | 355.4339 | 710.8678 | 60376392
549 | Valve | In Desalting Plant 4 | Gate | 3 | - | No | 2 | AZ00 | - | ASTM B148 |  | 1107.3133 | 2214.6266 | 109850882
550 | Valve | In Desalting Plant 4 | Glob | 4 | - | No | 2 | AN16 | - | ASTM A216-GR.WCB | NACE | 546.8214 | 1093.6428 | 95238847
551 | Valve | In Desalting Plant 4 | Globe | 1 | - | No | 1 | AN01 |  | ASTM A105 |  | 136.7053 | 136.7053 | 10273720
552 | Valve | In Desalting Plant 4 | Globe | 2 | - | No | 2 | AN01 | - | ASTM A216-GR.WCB |  | 159.3984 | 318.7969 | 15945938
553 | Valve | In Desalting Plant 4 | Globe | 4 | - | No | 1 | AN01 | - | ASTM A216-GR.WCB |  | 478.4687 | 478.4687 | 33338987
554 | Valve | In Desalting Plant 4 | Globe | 2 | - | No | 2 | AN16 | - | ASTM A216-GR.WCB | NACE | 136.7053 | 273.4107 | 12597849
555 | Valve | In Desalting Plant 4 | Globe | 3 | - | No | 5 | AN16 | - | ASTM A216-GR.WCB | NACE | 235.1332 | 1175.666 | 73115916
556 | Valve | In Desalting Plant 4 | Globe | 4 | - | No | 4 | AN16 | - | ASTM A216-GR.WCB | NACE | 546.8214 | 2187.2855 | 192824349
557 | Valve | In Desalting Plant 4 | Globe | 8 | - | No | 11 | AN16 | - | ASTM A216-GR.WCB | NACE | 1054.1349 | 8456 | 708478496
558 | Valve | In Desalting Plant 4 | Globe | 18 | - | No | 1 | AN16 | - | ASTM A216-GR.WCB | NACE | 8280 | 8280 | 531533053
559 | Valve | In Desalting Plant 4 | Globe | 11/2" | - | No | 2 | AN16 |  | ASTM A105 | NACE | 90.2255 | 180.4511 | 13834470
560 | Valve | In Desalting Plant 4 | Globe | 2 | - | No | 1 | AZ00 | - | ASTM B148 |  | 833.9026 | 833.9026 | 74571220
561 | StudBolt&nuts | Non Metal In Production Unit4 | - | 5/8" | 85 | No | 36 | AX00 | For flange:2"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 87.4039 | 17978209
562 | StudBolt&nuts | Non Metal In Production Unit4 | - | 5/8" | 90 | No | 12 | AX00 | For flange:3"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 29.1346 | 3275944
563 | StudBolt&nuts | Non Metal In Production Unit4 | - | 5/8" | 90 | No | 128 | AX00 | For flange:4"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 310.7695 | 58513661
564 | StudBolt&nuts | Non Metal In Production Unit4 | - | 1/2" | 70 | No | 8 | AX00 | For flange:11/2"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 1.2686 | 10.149 | 2369711
565 | StudBolt&nuts | Non Metal In Production Unit4 | - | 5/8" | 85 | No | 16 | AX01 | For flange:2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 19.4231 | 2847962
566 | Fitting | Non Metal In Production Unit4 | 90deg.Elbow | 2 | - | No | 6 | AX00 | - | GRE |  | 117.0745 | 702.4467 | 109523881
567 | Fitting | Non Metal In Production Unit4 | 90deg.Elbow | 4 | - | No | 15 | AX00 | - | GRE |  | 230.4852 | 3457.2781 | 239576251
568 | Fitting | Non Metal In Production Unit4 | 90deg.Elbow | 2 | - | No | 8 | AX01 | DR11 | HDPE 100 |  | 10.3896 | 83.1168 | 6056525
569 | Fitting | Non Metal In Production Unit4 | Pipe Nipple | 1 | - | No | 5 | AX00 | - | API5L-GR.B |  | 1.3671 | 6.8353 | 808520
570 | Fitting | Non Metal In Production Unit4 | Reducer | 2 | 11/2" | No | 2 | AX00 | - | GRE |  | 69.2823 | 138.5645 | 18607517
571 | Fitting | Non Metal In Production Unit4 | Reducer | 4 | 3 | No | 3 | AX00 | - | GRE |  | 199.043 | 597.1289 | 64799848
572 | Fitting | Non Metal In Production Unit4 | Olet | 2 | 1 | No | 1 | AX00 | - | GRE |  | 120.6835 | 120.6835 | 9625850
573 | Fitting | Non Metal In Production Unit4 | Olet | 4 | 1 | No | 4 | AX00 | - | GRE |  | 212.9869 | 851.9477 | 66354597
574 | Fitting | Non Metal In Production Unit4 | Tee | 2 | 2 | No | 2 | AX00 | - | GRE |  | 171.9753 | 343.9506 | 42581839
575 | Fitting | Non Metal In Production Unit4 | Tee | 4 | 4 | No | 2 | AX00 | - | GRE |  | 214.7368 | 429.4735 | 34117427
576 | Fitting | Non Metal In Production Unit4 | Tee | 2 | 2 | No | 2 | AX01 | DR11 | HDPE 100 |  | 12.987 | 25.974 | 3608751
577 | Fitting | Non Metal In Production Unit4 | Union | 2 | - | No | 2 | AX01 | DR11 | HDPE 100 |  | 2.7341 | 5.4682 | 498875
578 | Fitting | Non Metal In Production Unit4 | Olet | 4 | 2 | No | 1 | AX00 | - | GRE |  | 212.9869 | 212.9869 | 19494443
579 | Fitting | Non Metal In Production Unit4 | Olet | 4 | 11/2" | No |  | AX00 | - | GRE |  | 212.9869 | 0 | 0
580 | Flange | Non Metal In Production Unit4 | Flange | 2 | - | No | 9 | AX00 | - | ASTM A105 |  | 11.2372 | 101.1346 | 8697603
581 | Flange | Non Metal In Production Unit4 | Flange | 3 | - | No | 3 | AX00 | - | ASTM A105 |  | 22.9392 | 68.8175 | 6069578
582 | Flange | Non Metal In Production Unit4 | Flange | 4 | - | No | 15 | AX00 | - | ASTM A105 |  | 30.4306 | 456.4591 | 51969894
583 | Flange | Non Metal In Production Unit4 | Flange | 11/2" | - | No | 2 | AX00 | - | ASTM A105 |  | 6.0834 | 12.1668 | 1578419
584 | Flange | Non Metal In Production Unit4 | Flange | 2 | - | No | 4 | AX01 | DR11 | ASTM A105 |  | 11.2372 | 44.9487 | 6661388
585 | Flange | Non Metal In Production Unit4 | Spectace | 4 | - | No | 2 | AX00 | - | ASTM A516 |  | 57.3069 | 114.6138 | 10807062
586 | Flange | Non Metal In Production Unit4 | Spectace | 2 | - | No | 1 | AX01 | DR11 | ASTM A516 |  | 22.9255 | 22.9255 | 3121852
587 | Gasket | Non Metal In Production Unit4 | - | 2 | - | No | 9 | AX00 | - | FLAT |  | 1.4081 | 12.6726 | 2453292
588 | Gasket | Non Metal In Production Unit4 | - | 3 | - | No | 3 | AX00 | - | FLAT |  | 2.0916 | 6.2748 | 1497753
589 | Gasket | Non Metal In Production Unit4 | - | 4 | - | No | 19 | AX00 | - | FLAT |  | 3.3766 | 64.1558 | 9610644
590 | Gasket | Non Metal In Production Unit4 | - | 11/2" | - | No | 2 | AX00 | - | FLAT |  | 0.91593 | 1.8319 | 372489
591 | Gasket | Non Metal In Production Unit4 | - | 2 | - | No | 5 | AX01 | DR11 | FLAT |  | 1.4081 | 7.0403 | 1082063
592 | Pipe | Non Metal In Production Unit4 | - | 2 | - | m | 235 | AX00 | - | GRE |  | 36.6917 | 8622.5529 | 417063444
593 | Pipe | Non Metal In Production Unit4 | - | 4 | - | m | 876.5 | AX00 | - | GRE |  | 44.4019 | 34653 | 3053858163
594 | Pipe | Non Metal In Production Unit4 | - | 2 | - | m | 47 | AX01 | SDR11 | HDPE 100 |  | 1.464 | 68.8087 | 3823037
595 | Special | Non Metal In Production Unit4 | Filter | 4 | - | No |  | AX00 | - | ASTM A216-GR.WCB |  | 527.6826 | 0 | 0
596 | Special | Non Metal In Production Unit4 | Orifice Flange | 4 | - | No | 2 | AX00 | - | ASTM A105 |  | 30.4306 | 60.8612 | 7703547
597 | Valve | Non Metal In Production Unit4 | Check | 4 | - | No | 1 | AX00 | - | ASTM B148 |  | 1460.1498 | 1460.1498 | 75369236
598 | Valve | Non Metal In Production Unit4 | Gate | 1 | - | No | 5 | AX00 | - | ASTM B148 |  | 355.4339 | 1777.1695 | 149296774
599 | Valve | Non Metal In Production Unit4 | Gate | 2 | - | No | 3 | AX00 | - | ASTM B148 |  | 697.1973 | 2091.5918 | 188616733
600 | Valve | Non Metal In Production Unit4 | Gate | 4 | - | No | 6 | AX00 | - | ASTM B148 |  | 1435.4061 | 8612.4367 | 562275497
601 | Valve | Non Metal In Production Unit4 | Gate | 2 | - | No | 1 | AX01 | - | ASTM B148 |  | 697.1973 | 697.1973 | 43006384
602 | Valve | Non Metal In Production Unit4 | Globe | 2 | - | No | 1 | AX00 | - | ASTM B148 |  | 833.9026 | 833.9026 | 74571220
603 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 85 | No | 24 | AX00 | For flange:2"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 58.2693 | 13164160
604 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 90 | No | 200 | AX00 | For flange:3"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 485.5774 | 69743386
605 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 90 | No | 560 | AX00 | For flange:4"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 2.4279 | 1359.6167 | 195870111
606 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 3/4" | 105 | No | 144 | AX00 | For flange:6"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 4.1668 | 600.0162 | 68478516
607 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 3/4" | 110 | No | 256 | AX00 | For flange:8"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 4.1668 | 1066.6954 | 137857454
608 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 7/8" | 115 | No | 420 | AX00 | For flange:10"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 6.3213 | 2654.9271 | 519437308
609 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 7/8" | 125 | No | 84 | AX00 | For flange:12"150# | A193 GR.B7/A194 GR.BH | PTFE COATED | 6.6056 | 554.8706 | 85504230
610 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 85 | No | 156 | AX01 | For flange:2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 189.3752 | 36963497
611 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 90 | No | 52 | AX01 | For flange:3"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 63.1251 | 12910293
612 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 90 | No | 40 | AX01 | For flange:4"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 48.5577 | 12255058
613 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 3/4" | 105 | No | 96 | AX01 | For flange:6"150# | A193 GR.B7/A194 GR.BH | GALVD | 2.0834 | 200.0054 | 23013350
614 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 5/8" | 90 | No | 4 | AX01 | For flange:21/2"150# | A193 GR.B7/A194 GR.BH | GALVD | 1.2139 | 4.8558 | 761501
615 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 3/4" | 130 | No | 24 | FX00 | For flange:3"600# | A193 GR.B7/A194 GR.BH | CADMIUM PLATED | 4.5824 | 109.9767 | 20957389
616 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 7/8" | 150 | No | 192 | FX00 | For flange:4"600# | A193 GR.B7/A194 GR.BH | CADMIUM PLATED | 7.1743 | 1377.4649 | 287429648
617 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 1" | 170 | No | 224 | FX00 | For flange:5"600# | A193 GR.B7/A194 GR.BH | CADMIUM PLATED | 10.4552 | 2341.9703 | 415295857
618 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 1" | 175 | No | 252 | FX00 | For flange:6"600# | A193 GR.B7/A194 GR.BH | CADMIUM PLATED | 10.8271 | 2728.4199 | 591800869
619 | StudBolt&nuts | Non Metal Lines In Desalting Plant4 | - | 1 1/8" | 195 | No | 48 | FX00 | For flange:8"600# | A193 GR.B7/A194 GR.BH | CADMIUM PLATED | 15.4204 | 740.1774 | 171760213
620 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 3 | - | No | 25 | AX00 | - | GRE |  | 167.2727 | 4181.8165 | 635778593
621 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 4 | - | No | 64 | AX00 | - | GRE |  | 230.4852 | 15183 | 1415426290
622 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 6 | - | No | 16 | AX00 | - | GRE |  | 262.1462 | 4194.3387 | 538660548
623 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 8 | - | No | 14 | AX00 | - | GRE |  | 295.8304 | 4141.6251 | 439011926
624 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 10 | - | No | 58 | AX00 | - | GRE |  | 354.9964 | 26856 | 2500629058
625 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 12 | - | No | 2 | AX00 | - | GRE |  | 423.7866 | 847.5731 | 95342427
626 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 2 | - | No | 56 | AX01 | DR11 | HDPE 100 |  | 10.3896 | 581.8179 | 47967662
627 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 3 | - | No | 9 | AX01 | DR11 | HDPE 100 |  | 19.9043 | 179.1387 | 25838224
628 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 4 | - | No | 7 | AX01 | DR11 | HDPE 100 |  | 23.3766 | 163.6363 | 12342155
629 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 6 | - | No | 11 | AX01 | DR11 | HDPE 100 |  | 68.38 | 752.1801 | 95812818
630 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 4 | - | No | 15 | FX00 | - | GRE |  | 230.4852 | 3457.2781 | 239576251
631 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 5 | - | No | 8 | FX00 | - | GRE |  | 246.8899 | 1975.1188 | 308668779
632 | Fitting | Non Metal Lines In Desalting Plant4 | 90deg.Elbow | 6 | - | No | 15 | FX00 | - | GRE |  | 262.1462 | 3932.1925 | 478993856
633 | Fitting | Non Metal Lines In Desalting Plant4 | Cap | 4 | - | No | 1 | AX00 | - | GRE |  | 317.7032 | 317.7032 | 23301773
634 | Fitting | Non Metal Lines In Desalting Plant4 | Cap | 2 | - | No | 2 | AX01 | DR11 | HDPE 100 |  | 4.7027 | 9.4053 | 1429285
635 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 1 | No | 8 | AX00 | - | GRE |  | 318.0313 | 2544.2505 | 363395230
636 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 11/2" | No | 4 | AX00 | - | GRE |  | 318.0313 | 1272.1252 | 196780587
637 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 1 | No | 7 | AX00 | - | GRE |  | 381.6376 | 2671.463 | 368632324
638 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 11/2" | No | 1 | AX00 | - | GRE |  | 381.6376 | 381.6376 | 29251514
639 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 1 | No | 2 | FX00 | - | GRE |  | 318.0313 | 636.0626 | 60358003
640 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 11/2" | No | 2 | FX00 | - | GRE |  | 318.0313 | 636.0626 | 60358003
641 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 1 | - | No | 67 | AX00 | - | API5L-GR.B |  | 1.3671 | 91.5926 | 13106319
642 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 11/2" | - | No | 1 | AX00 | - | API5L-GR.B |  | 1.3671 | 1.3671 | 179977
643 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 3/4" | - | No | 8 | AX00 | - | API5L-GR.B |  | 1.3671 | 10.9364 | 1218220
644 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 1 | - | No | 14 | AX01 | DR11 | HDPE 100 |  | 1.3671 | 19.1387 | 2876537
645 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 11/2" | - | No | 2 | AX01 | DR11 | HDPE 100 |  | 1.3671 | 2.7341 | 253752
646 | Fitting | Non Metal Lines In Desalting Plant4 | Pipe Nipple | 1 | - | No | 32 | FX00 | - | GRE |  | 1.3671 | 43.7457 | 4906131
647 | Fitting | Non Metal Lines In Desalting Plant4 | Plug | 3/4" | - | No | 2 | AX00 |  | ASTM A105 |  | 2.1189 | 4.2379 | 337565
648 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 4 | 3 | No | 11 | AX00 | - | GRE |  | 199.043 | 2189.4728 | 152101791
649 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 6 | 4 | No | 3 | AX00 | - | GRE |  | 281.3943 | 844.1828 | 73832201
650 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 10 | 6 | No | 2 | AX00 | - | GRE |  | 519.9724 | 1039.9449 | 157293576
651 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 12 | 8 | No | 2 | AX00 | - | GRE |  | 623.9669 | 1247.9339 | 125988530
652 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 3 | 2 | No | 1 | AX01 | DR11 | HDPE 100 |  | 12.0984 | 12.0984 | 1230024
653 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 3 | 21/2" | No | 1 | AX01 | DR11 | HDPE 100 |  | 12.0984 | 12.0984 | 1230024
654 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 4 | 3 | No | 3 | FX00 | - | GRE |  | 5.7143 | 17.1429 | 2508881
655 | Fitting | Non Metal Lines In Desalting Plant4 | Reducer | 6 | 4 | No | 3 | FX00 | - | GRE |  | 12.4812 | 37.4436 | 4875821
656 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 3 | 1 | No | 2 | AX00 | - | GRE |  | 209.8154 | 419.6307 | 42572222
657 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 3 | 3/4" | No | 4 | AX00 | - | GRE |  | 209.8154 | 839.2614 | 105999177
658 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 4 | 1 | No | 27 | AX00 | - | GRE |  | 212.9869 | 5750.647 | 739153754
659 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 6 | 1 | No | 18 | AX00 | - | GRE |  | 237.4298 | 4273.7371 | 572456293
660 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 1 | No | 8 | AX00 | - | GRE |  | 318.0313 | 2544.2505 | 363395230
661 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 3/4" | No | 4 | AX00 | - | GRE |  | 318.0313 | 1272.1252 | 196780587
662 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 12 | 1 | No | 2 | AX00 | - | GRE |  | 445.2438 | 890.4877 | 126172788
663 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 2 | 1 | No | 5 | AX01 | DR11 | HDPE 100 |  | 36.0902 | 180.4511 | 17720994
664 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 4 | 1 | No | 1 | AX01 | DR11 | HDPE 100 |  | 45.1128 | 45.1128 | 5487445
665 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 4 | 1 | No | 12 | FX00 | - | GRE |  | 212.9869 | 2555.8431 | 280237485
666 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 5 | 1 | No | 6 | FX00 | - | GRE |  | 226.9309 | 1361.5852 | 106230679
667 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 6 | 1 | No | 12 | FX00 | - | GRE |  | 237.4298 | 2849.1581 | 266357793
668 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 3 | 3 | No | 6 | AX00 | - | GRE |  | 191.3875 | 1148.3249 | 115523741
669 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 4 | 3 | No | 4 | AX00 | - | GRE |  | 214.7368 | 858.947 | 125529430
670 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 4 | 4 | No | 6 | AX00 | - | GRE |  | 214.7368 | 1288.4205 | 165756134
671 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 2 | No | 2 | AX00 | - | GRE |  | 318.0313 | 636.0626 | 60358003
672 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 4 | No | 8 | AX00 | - | GRE |  | 453.0415 | 3624.3321 | 258401724
673 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 8 | No | 2 | AX00 | - | GRE |  | 453.0415 | 906.083 | 131798788
674 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 1 | No | 4 | AX00 | - | GRE |  | 381.6376 | 1526.5503 | 126740320
675 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 2 | No | 2 | AX00 | - | GRE |  | 333.9438 | 667.8876 | 48956688
676 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 3 | No | 2 | AX00 | - | GRE |  | 400.7326 | 801.4652 | 121396471
677 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 10 | 4 | No | 8 | AX00 | - | GRE |  | 484.265 | 3874.1201 | 539683100
678 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 10 | 6 | No | 4 | AX00 | - | GRE |  | 484.265 | 1937.06 | 137642671
679 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 10 | 8 | No | 4 | AX00 | - | GRE |  | 484.265 | 1937.06 | 137642671
680 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 10 | 10 | No | 6 | AX00 | - | GRE |  | 484.265 | 2905.5901 | 409689174
681 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 10 | 11/2" | No | 1 | AX00 | - | GRE |  | 381.6376 | 381.6376 | 29251514
682 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 12 | 6 | No | 2 | AX00 | - | GRE |  | 580.7243 | 1161.4486 | 119002513
683 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 12 | 8 | No | 1 | AX00 | - | GRE |  | 580.7243 | 580.7243 | 77125568
684 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 12 | 10 | No | 2 | AX00 | - | GRE |  | 580.7243 | 1161.4486 | 119002513
685 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 2 | 1 | No | 4 | AX01 | DR11 | HDPE 100 |  | 12.987 | 51.948 | 6040449
686 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 2 | 2 | No | 15 | AX01 | DR11 | HDPE 100 |  | 12.987 | 194.8051 | 24312124
687 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 3 | 1 | No | 7 | AX01 | DR11 | HDPE 100 |  | 20.7929 | 145.5502 | 19615963
688 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 3 | 3 | No | 2 | AX01 | DR11 | HDPE 100 |  | 20.7929 | 41.5858 | 5253138
689 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 1 | No | 6 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 488.1201 | 47978766
690 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 2 | No | 2 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 162.7067 | 23019104
691 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 4 | No | 4 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 325.4134 | 43467947
692 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 6 | No | 2 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 162.7067 | 23019104
693 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 11/2" | No | 2 | AX01 | DR11 | HDPE 100 |  | 81.3534 | 162.7067 | 23019104
694 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 4 | 4 | No | 6 | FX00 | - | GRE |  | 17.758 | 106.5481 | 14929261
695 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 6 | 6 | No | 6 | FX00 | - | GRE |  | 129.1865 | 775.1193 | 111368344
696 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 3 | No | 2 | FX00 | - | GRE |  | 73.8482 | 147.6965 | 11200832
697 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 4 | No | 8 | FX00 | - | GRE |  | 73.8482 | 590.7858 | 68261299
698 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 5 | No | 6 | FX00 | - | GRE |  | 73.8482 | 443.0894 | 32521987
699 | Fitting | Non Metal Lines In Desalting Plant4 | Tee | 8 | 6 | No | 6 | FX00 | - | GRE |  | 73.8482 | 443.0894 | 32521987
700 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 4 | 11/2" | No | 3 | AX00 | - | GRE |  | 212.9869 | 638.9608 | 88298854
701 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 6 | 11/2" | No | 3 | AX00 | - | GRE |  | 237.4298 | 712.2895 | 109377599
702 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 8 | 11/2" | No | 2 | AX00 | - | GRE |  | 318.0313 | 636.0626 | 60358003
703 | Fitting | Non Metal Lines In Desalting Plant4 | Olet | 5 | 11/2" | No | 2 | FX00 | - | GRE |  | 226.9309 | 453.8617 | 56623106
704 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 2 | - | No | 8 | AX00 | - | ASTM A105 |  | 11.2372 | 89.8974 | 8693282
705 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 3 | - | No | 50 | AX00 | - | ASTM A105 |  | 22.9392 | 1146.9578 | 126421007
706 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 4 | - | No | 69 | AX00 | - | ASTM A105 |  | 30.4306 | 2099.7121 | 261294310
707 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 6 | - | No | 15 | AX00 | - | ASTM A105 |  | 46.7396 | 701.0934 | 109234070
708 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 8 | - | No | 30 | AX00 | - | ASTM A105 |  | 73.3014 | 2199.0422 | 155402028
709 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 10 | - | No | 35 | AX00 | - | ASTM A105 |  | 98.0314 | 3431.0991 | 402848565
710 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 12 | - | No | 7 | AX00 | - | ASTM A105 |  | 136.7053 | 956.9374 | 129896402
711 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 11/2" | - | No | 14 | AX00 | - | ASTM A105 |  | 6.0834 | 85.1674 | 8279495
712 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 2 | - | No | 36 | AX01 | DR11 | ASTM A105 |  | 11.2372 | 404.5385 | 60958170
713 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 3 | - | No | 10 | AX01 | DR11 | ASTM A105 |  | 22.9392 | 229.3916 | 29475150
714 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 4 | - | No | 5 | AX01 | DR11 | ASTM A105 |  | 30.4306 | 152.153 | 13403925
715 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 6 | - | No | 12 | AX01 | DR11 | ASTM A105 |  | 46.7396 | 560.8747 | 47602768
716 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 11/2" | - | No | 2 | AX01 | DR11 | ASTM A105 |  | 6.0834 | 12.1668 | 1578419
717 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 21/2" | - | No | 1 | AX01 | DR11 | ASTM A105 |  | 19.1387 | 19.1387 | 2876537
718 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 3 | - | No | 3 | FX00 | - | ASTM A105 |  | 40.4374 | 121.3123 | 17510619
719 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 4 | - | No | 21 | FX00 | - | ASTM A105 |  | 205.058 | 4306.2183 | 470259083
720 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 5 | - | No | 32 | FX00 | - | ASTM A105 |  | 410.116 | 11289 | 2048934299
721 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 6 | - | No | 18 | FX00 | - | ASTM A105 |  | 160.9022 | 2896.2394 | 258976245
722 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 8 | - | No | 8 | FX00 | - | ASTM A105 |  | 341.7634 | 2734.1069 | 371373216
723 | Flange | Non Metal Lines In Desalting Plant4 | Flange | 11/2" | - | No | 4 | FX00 | - | ASTM A105 |  | 15.9809 | 63.9234 | 6793084
724 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 3 | - | No | 2 | AX00 | - | ASTM A516 |  | 34.3814 | 68.7628 | 10409906
725 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 4 | - | No | 7 | AX00 | - | ASTM A516 |  | 57.3069 | 401.1482 | 53846166
726 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 6 | - | No | 6 | AX00 | - | ASTM A516 |  | 114.6001 | 687.6005 | 59839279
727 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 8 | - | No | 2 | AX00 | - | ASTM A516 |  | 296.0491 | 592.0982 | 72194091
728 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 10 | - | No | 3 | AX00 | - | ASTM A516 |  | 181.0662 | 543.1987 | 39701538
729 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 12 | - | No | 1 | AX00 | - | ASTM A516 |  | 917.7577 | 917.7577 | 112536971
730 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 6 | - | No | 1 | AX01 | DR11 | ASTM A516 |  | 114.6001 | 114.6001 | 15531705
731 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 4 | - | No | 3 | FX00 | - | ASTM A516 |  | 57.3069 | 171.9206 | 16189308
732 | Flange | Non Metal Lines In Desalting Plant4 | Spectace | 6 | - | No | 3 | FX00 | - | ASTM A516 |  | 328.0928 | 984.2785 | 151336192
733 | Gasket | Non Metal Lines In Desalting Plant4 | - | 2 | - | No | 6 | AX00 | - | FLAT |  | 1.4081 | 8.4484 | 1689483
734 | Gasket | Non Metal Lines In Desalting Plant4 | - | 3 | - | No | 54 | AX00 | - | FLAT |  | 2.0916 | 112.946 | 21973864
735 | Gasket | Non Metal Lines In Desalting Plant4 | - | 4 | - | No | 74 | AX00 | - | FLAT |  | 3.3766 | 249.87 | 40383563
736 | Gasket | Non Metal Lines In Desalting Plant4 | - | 6 | - | No | 21 | AX00 | - | FLAT |  | 4.0328 | 84.689 | 13244218
737 | Gasket | Non Metal Lines In Desalting Plant4 | - | 8 | - | No | 40 | AX00 | - | FLAT |  | 5.728 | 229.1182 | 57144820
738 | Gasket | Non Metal Lines In Desalting Plant4 | - | 10 | - | No | 38 | AX00 | - | FLAT |  | 30.2939 | 1151.1684 | 160281582
739 | Gasket | Non Metal Lines In Desalting Plant4 | - | 12 | - | No | 8 | AX00 | - | FLAT |  | 41.4764 | 331.8112 | 54304763
740 | Gasket | Non Metal Lines In Desalting Plant4 | - | 2 | - | No | 35 | AX01 | DR11 | FLAT |  | 1.4081 | 49.2823 | 9442549
741 | Gasket | Non Metal Lines In Desalting Plant4 | - | 3 | - | No | 17 | AX01 | DR11 | FLAT |  | 2.0916 | 35.5571 | 5598508
742 | Gasket | Non Metal Lines In Desalting Plant4 | - | 4 | - | No | 5 | AX01 | DR11 | FLAT |  | 3.3766 | 16.8831 | 3129181
743 | Gasket | Non Metal Lines In Desalting Plant4 | - | 6 | - | No | 14 | AX01 | DR11 | FLAT |  | 4.0328 | 56.4593 | 7890743
744 | Gasket | Non Metal Lines In Desalting Plant4 | - | 21/2" | - | No | 1 | AX01 | DR11 | FLAT |  | 1.9139 | 1.9139 | 460321
745 | Gasket | Non Metal Lines In Desalting Plant4 | - | 3 | - | No | 3 | FX00 | - | SPIRAL WOUND |  | 11.4286 | 34.2857 | 5515703
746 | Gasket | Non Metal Lines In Desalting Plant4 | - | 4 | - | No | 27 | FX00 | - | SPIRAL WOUND |  | 11.4286 | 308.5713 | 78310962
747 | Gasket | Non Metal Lines In Desalting Plant4 | - | 5 | - | No | 20 | FX00 | - | SPIRAL WOUND |  | 26.9856 | 539.7127 | 62035334
748 | Gasket | Non Metal Lines In Desalting Plant4 | - | 6 | - | No | 24 | FX00 | - | SPIRAL WOUND |  | 18.6876 | 448.5029 | 55950355
749 | Gasket | Non Metal Lines In Desalting Plant4 | - | 8 | - | No | 6 | FX00 | - | SPIRAL WOUND |  | 26.9856 | 161.9138 | 18704928
750 | Pipe | Non Metal Lines In Desalting Plant4 | - | 3 | - | m | 263 | AX00 | - | GRE |  | 42.0506 | 7185 | 522484969
751 | Pipe | Non Metal Lines In Desalting Plant4 | - | 4 | - | m | 1439 | AX00 | - | GRE |  | 44.4019 | 88680 | 5892012488
752 | Pipe | Non Metal Lines In Desalting Plant4 | - | 6 | - | m | 98 | AX00 | - | GRE |  | 46.8626 | 4592.534 | 274084729
753 | Pipe | Non Metal Lines In Desalting Plant4 | - | 8 | - | m | 56.9 | AX00 | - | GRE |  | 53.8072 | 3061.631 | 133397470
754 | Pipe | Non Metal Lines In Desalting Plant4 | - | 10 | - | m | 1444 | AX00 | - | GRE |  | 64.5687 | 105073 | 4712815406
755 | Pipe | Non Metal Lines In Desalting Plant4 | - | 12 | - | m | 9 | AX00 | - | GRE |  | 77.4299 | 696.8692 | 63048691
756 | Pipe | Non Metal Lines In Desalting Plant4 | - | 2 | - | m | 1241.5 | AX01 | SDR11 | HDPE 100 |  | 1.464 | 1817.5756 | 135716432
757 | Pipe | Non Metal Lines In Desalting Plant4 | - | 3 | - | m | 35 | AX01 | SDR11 | HDPE 100 |  | 4.6602 | 163.1081 | 7029752
758 | Pipe | Non Metal Lines In Desalting Plant4 | - | 4 | - | m | 55 | AX01 | SDR11 | HDPE 100 |  | 6.9024 | 379.6329 | 23489055
759 | Pipe | Non Metal Lines In Desalting Plant4 | - | 6 | - | m | 83.5 | AX01 | SDR11 | HDPE 100 |  | 14.6621 | 1224.2887 | 105758000
760 | Pipe | Non Metal Lines In Desalting Plant4 | - | 4 | - | m | 36 | FX00 | - | GRE |  | 44.4019 | 1598.4682 | 150919926
761 | Pipe | Non Metal Lines In Desalting Plant4 | - | 5 | - | m | 430 | FX00 | - | GRE |  | 45.933 | 14536 | 1872282250
762 | Pipe | Non Metal Lines In Desalting Plant4 | - | 6 | - | m | 36 | FX00 | - | GRE |  | 46.8626 | 1687.0533 | 160679752
763 | Pipe | Non Metal Lines In Desalting Plant4 | - | 8 | - | m | 54 | FX00 | - | GRE |  | 53.8072 | 2905.5901 | 258851115
764 | Special | Non Metal Lines In Desalting Plant4 | Filter | 4 | - | No | 5 | AX00 | - | ASTM A216-GR.WCB |  | 527.6826 | 2638.4131 | 286517217
765 | Special | Non Metal Lines In Desalting Plant4 | Filter | 6 | - | No | 3 | AX00 | - | ASTM A216-GR.WCB |  | 574.1624 | 1722.4873 | 223763051
766 | Special | Non Metal Lines In Desalting Plant4 | Filter | 3 | - | No | 1 | AX01 | - | ASTM A216-GR.WCB |  | 390.9773 | 390.9773 | 34738593
767 | Special | Non Metal Lines In Desalting Plant4 | Orifice Flange | 8 | - | No | 4 | AX00 | - | ASTM A105 |  | 73.3014 | 293.2056 | 44445523
768 | Special | Non Metal Lines In Desalting Plant4 | Orifice Flange | 6 | - | No | 2 | AX01 | DR11 | ASTM A105 |  | 46.7396 | 93.4791 | 6511469
769 | Special | Non Metal Lines In Desalting Plant4 | Orifice Flange | 4 | - | No | 6 | FX00 | - | ASTM A105 |  | 205.058 | 1230.3481 | 172539482
770 | Special | Non Metal Lines In Desalting Plant4 | Orifice Flange | 5 | - | No | 4 | FX00 | - | ASTM A105 |  | 410.116 | 1640.4641 | 235005917
771 | Special | Non Metal Lines In Desalting Plant4 | Orifice Flange | 6 | - | No | 6 | FX00 | - | ASTM A105 |  | 160.9022 | 965.4131 | 149866287
772 | Special | Non Metal Lines In Desalting Plant4 | Quick Coupling | 3 | 21/2" | No | 1 | AX01 | DR11 | ASTM A105 |  | 150.3759 | 150.3759 | 18979022
773 | Valve | Non Metal Lines In Desalting Plant4 | Check | 1 | - | No | 5 | AX00 | - | ASTM B148 |  | 205.058 | 1025.2901 | 44118800
774 | Valve | Non Metal Lines In Desalting Plant4 | Check | 3 | - | No | 1 | AX00 | - | ASTM B148 |  | 1063.5676 | 1063.5676 | 96905830
775 | Valve | Non Metal Lines In Desalting Plant4 | Check | 4 | - | No | 5 | AX00 | - | ASTM B148 |  | 1460.1498 | 7300.7489 | 619819143
776 | Valve | Non Metal Lines In Desalting Plant4 | Check | 10 | - | No | 1 | AX00 | - | ASTM B148 |  | 4101.1603 | 4101.1603 | 287474464
777 | Valve | Non Metal Lines In Desalting Plant4 | Check | 3 | - | No | 2 | AX01 | - | ASTM B148 |  | 1063.5676 | 2127.1351 | 115739695
778 | Valve | Non Metal Lines In Desalting Plant4 | Check | 4 | - | No | 3 | FX00 | - | ASTM B148 |  | 628.8446 | 1886.5337 | 125836712
779 | Valve | Non Metal Lines In Desalting Plant4 | Check | 6 | - | No | 3 | FX00 | - | ASTM B148 |  | 3417.6336 | 6963 | 559331944
780 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 1 | - | No | 67 | AX00 | - | ASTM B148 |  | 355.4339 | 15002 | 1101659118
781 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 2 | - | No | 2 | AX00 | - | ASTM B148 |  | 697.1973 | 1394.3945 | 76777480
782 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 3 | - | No | 6 | AX00 | - | ASTM B148 |  | 1107.3133 | 6643.8797 | 319907682
783 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 4 | - | No | 16 | AX00 | - | ASTM B148 |  | 1435.4061 | 22920 | 1164850372
784 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 6 | - | No | 6 | AX00 | - | ASTM B148 |  | 2050.5802 | 7450 | 1026311784
785 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 8 | - | No | 7 | AX00 | - | ASTM B148 |  | 2187.2855 | 16854 | 922834432
786 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 10 | - | No | 1 | AX00 | - | ASTM B148 |  | 3896.1023 | 3896.1023 | 341476208
787 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 10 | - | No | 6 | AX00 | - | ASTM B148 |  | 3896.1023 | 26583 | 1501827402
788 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 12 | - | No | 3 | AX00 | - | ASTM B148 |  | 5276.8263 | 11696 | 836902917
789 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 3/4" | - | No | 8 | AX00 | - | ASTM B148 |  | 247.4367 | 1979.4934 | 132309412
790 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 1 | - | No | 14 | AX01 | - | ASTM B148 |  | 355.4339 | 4976.0745 | 474724817
791 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 2 | - | No | 14 | AX01 | - | ASTM B148 |  | 697.1973 | 9760.7615 | 766288083
792 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 3 | - | No | 5 | AX01 | - | ASTM B148 |  | 1107.3133 | 5536.5664 | 232690651
793 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 4 | - | No | 2 | AX01 | - | ASTM B148 |  | 1435.4061 | 2870.8122 | 148933848
794 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 6 | - | No | 4 | AX01 | - | ASTM B148 |  | 2050.5802 | 8202.3206 | 750422989
795 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 1 | - | No | 32 | FX00 | - | ASTM B148 |  | 54.6821 | 1749.8284 | 130664584
796 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 4 | - | No | 3 | FX00 | - | ASTM B148 |  | 738.2089 | 2214.6266 | 109850882
797 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 5 | - | No | 10 | FX00 | - | ASTM B148 |  | 2050.5802 | 21405 | 1422087502
798 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 6 | - | No | 3 | FX00 | - | ASTM B148 |  | 1503.7588 | 4511.2763 | 211173809
799 | Valve | Non Metal Lines In Desalting Plant4 | Gate | 8 | - | No | 2 | FX00 | - | ASTM B148 |  | 2460.6962 | 4921.3924 | 237181993
800 | Valve | Non Metal Lines In Desalting Plant4 | Globe | 3 | - | No | 6 | AX00 | - | ASTM B148 |  | 1401.2298 | 8407.3786 | 603764224
801 | Valve | Non Metal Lines In Desalting Plant4 | Globe | 6 | - | No | 1 | AX00 | - | ASTM B148 |  | 3150.3746 | 3150.3746 | 248763655
802 | Valve | Non Metal Lines In Desalting Plant4 | Globe | 6 | - | No | 1 | AX01 | - | ASTM B148 |  | 3150.3746 | 3150.3746 | 248763655
803 | Valve | Non Metal Lines In Desalting Plant4 | Globe | 5 | - | No | 2 | FX00 | - | ASTM B148 |  | 2460.6962 | 4921.3924 | 237181993
804 |  | خرید پایپینگ مربوط به تفکیک نفت نمکی یک قلم |  |  |  | Lot | 1 |  |  |  |  | 473346 | 473346 | 49080202014
805 | pipe, fitting | Draining material |  |  |  | Lot | 1 |  |  |  |  | 132030 | 132030
806 | pipe, valves,fitting | اتصال توربين شماره 3 به خط هدر 30 اينچ نفت خروجي واحد بهره‌برداري نمونه4 |  |  |  | Lot | 1 |  |  |  |  | 766478 | 766478 | 42048791743
807 | Pipe | Replacement of Existing Lines | - | 4 | - | m | 500 | AN16 | SCH.80 | API5L-GR.B | NACE | 34.1763 | 20681 | 881135894
808 |  | لوازم یدکی شیر الات معادل 5% قیمت خرید شیرآلات | [10 empty] | 153997
809 |  | حمل زمینی اقلام پایپینگ در حدود 190 کفی | [11 empty] | 39808446075
[8 empty] | 153997 | 4646681 | 39808446075 | 453455966742
[8 empty] | Euro | Euro |  | Rls
[8 empty] | لوازم یدکی |  | حمل | جنبي
هزینه کل بدون ضریب
[15 empty] | اجرای پایپینگ بر اساس dia-in |  | 30804 | ریال
[15 empty] | هزینه حمل زمینی یک کانتینر |  | 6,500,000 ~ 8,000,000 | ریال
[15 empty] | حق گمرک و ترخیص لوله اتصالات فلزی |  | 0.2
[15 empty] | نرخ ازاد یورو | اتاق ارز
[15 empty] | 18.576 | 393219

## P.PL
ITEM | DESCRIPTION |  | QUANTITY |  | MATERIAL | هزینه واحد خرید بدون ضریب | هزینه کل بدون ضریب
[7 empty] | خرید | ترخیص | حمل
| PIPELINE | SIZE(in) | LENGTH(M) | unit |  | Euro | Euro | Rls | Rls
1 | احداث خط لوله انتقال نفت نمکی از واحد بهره برداری نمونه 4 به واحد نمک زدایی نمونه 4 ب | 20" | 400 | m | API 5L GR.X52/SCH.30/NACE | 300.7518 | 116808 | 16513703443 | 2204077501
2 | احداث خط لوله انتقال نفت نمک زدایی شده 20 اینچ روزمینی با جنس API 5L GR.X52/SCH.30/NACE از واحد نمک زدایی نمونه 4 به واحد بهره برداری نمونه 4 به طول تقریبی 1500 متر. | 20" | 400 | m | API 5L GR.X52/SCH.30/NACE | 300.7518 | 116808 | 16513703443 | 2204077501
| ساپورت فلزی و فونداسیون (بر اساس تناژ) |  | 2500 | kg | C.S. |  |  |  | 1127054396
3 | تعویض خط لوله انتقال نفت از واحد بهره برداری پازنان 2 به واحد بهره برداری نمونه 2 با سایز 12 اینچ | 12" | 19647 | m | API 5L GR.X52/SCH.40 | 211.8933 | 3531709 | 210058885830 | 20598883111
| ساپورت فلزی و فونداسیون(61000/کیلو) |  | 8000 | kg |  |  |  | 0 | 2661726699
4 | جابجایی خط فشار بالای گاز موجود در سمت شرق سایت و احداث مجدد آن در فاصله حداقل 200 متر از حصار تسهیلات بیرون واحد | 4" | 1900 | m | API5L GR.X52/SCH.80/NACE | 31.4422 | 66950 | 3340545781 | 666301589
5 | احداث خط لوله انتقال گاز 6 اینچ فلزی با جنس API5L GR.X52/SCH.80/NACE به صورت روزمینی از واحد بهره برداری نمونه 4 به واحد نمک زدایی نمونه 4 | 6" | 500 | m | API5L GR.X52/SCH.80/NACE | 71.0868 | 47765 | 2444473200 | 1256522295
6 | ·احداث خط انتقال آب 6 اینچ فلزی با جنس API 5L0 به صورت رو زمینی از تصفیه خانه خیر آباد به واحدنمکزدایی نمونه-4 | 6" | 2000 | m | API 5L GR.X52/SCH.STD | 71.0868 | 109686 | 5908771681 | 2204077501
7 | احداث خط لوله انتقال آب ازاد غیر فلزی با جنس RTP زیر زمینی از واحد بهره برداری نمونه-4 به واحدنمکزدایی نمونه-4 | 4" | 500 |  | RTP | 133.9712 | 41446 | 4986320488 | 879127129
| ساپورت فلزی و فونداسیون(61000/کیلو) |  | 1500 | kg | RTP |  |  | 0 | 2661726699
8 | احداث دو خط لوله انتقال پساب غیر فلزی با جنس RTP زیر زمینی از واحدنمکزدایی نمونه-4 به چاههای تزریق در فاصله تقریبی 3 کیلومتر برای هر خط لوله. | 5" | 6000 | m | RTP | 150.3759 | 2391491 | 147791665052 | 21615995735
| کندن کانال |  | 6000 | m |  |  | 0
9 | خط لوله آب "6 از چاههای لیشتر با جنس PE-100 | 6" | 8500 | m | PE-100 | 14.6685 | 130329 |  | 2204077501
10 | خط لوله "12 آب آتش نشانی اتصال بین دو واحد با جنس PE-100 | 12" | 500 | m | PE-100 | 35.6117 | 17563 |  | 2204077501
|  | 7468679 | 370404571176 | 47049182817
|  | Euro | Rls | Rls
|  | خرید | ترخیص | حمل
|  | هزینه حمل دریایی یک کانتینر |  | 1500$
|  | حق گمرک و ترخیص لوله فلزی |  | 0.2
|  | حق گمرک و ترخیص لوله غیر فلزی |  | 0.05

## P.LAB
|  |  | هزینه واحد بدون ضریب |  | هزینه کل بدون ضریب
|  |  | خرید |  | خرید
| DESCRIPTION | Qty. | Rls | Euro | Rls | Euro
1 | Microwave Digestion System | 1 |  | 48403 |  | 48403
2 | Ion Meter | 1 |  | 24224 |  | 24224
3 | Oxygen Meter | 2 |  | 1722.4873 |  | 3444.9747
4 | Barometer | 2 |  | 3909.7728 |  | 7819.5457
5 | Oil Test Centrifuge | 2 |  | 37584 |  | 63130
6 | Dual Extraction Apparatus | 5 |  | 33215 |  | 106555
7 | Evaporator Mantless (500 cc) | 2 |  | 1640.4641 |  | 3280.9283
8 | Water Still For Douuble Distillation | 4 |  | 9159.258 |  | 44299
9 | Ph Meter | 2 |  | 3417.6336 |  | 6835.2672
10 | Balance | 2 |  | 8885.8473 |  | 14605
11 | R.V.P Automatic | 2 |  | 55567 |  | 107720
12 | Thermostatic Water Baths | 2 |  | 7382.0886 |  | 9342
13 | Density/Visco Meter | 2 |  | 60177 |  | 171569
14 | Oxygen Meter | 2 |  | 1722.4873 |  | 3444.9747
15 | Baro Meter | 2 |  | 3909.7728 |  | 7819.5457
16 | Salt In Crude Analyzer | 2 |  | 26144 |  | 95414
17 | H2S Analyzer For The Determination Of H2S in Fuel Oil | 2 |  | 41446 |  | 157012
18 | Industrial Hood (complete set with valves , sinks , exhoust , etc) | 1 | 17089246412 |  | 17089246412
19 | Sink (Chemically resistant with attachments) | 10 | یک قلم در ردیف 19 |  | یک قلم در ردیف 19
20 | Industrial cupboards(floor & wall mounted) | 1 | یک قلم در ردیف 19 |  | یک قلم در ردیف 19
21 | Safty shower & eyewash | 4 | یک قلم در ردیف 19 |  | یک قلم در ردیف 19
22 | Exhaust Fan(Wall mounted) | 4 | یک قلم در ردیف 19 |  | یک قلم در ردیف 19
23 | Ice Maker | 4 | یک قلم در ردیف 19 |  | یک قلم در ردیف 19
|  |  | هزینه کل بدون ضریب |  | 17089246412 | 900454
[5 empty] | Rls | Euro
ITEM | DESCRIPTION | Volume (Liters) (S.G.~1) | هرینه واحد (Rial/Kg) | هزینه کل (ریال) | توضیحات
1 | Ethylene Glycol | 66264 | 1388549 | 57310923823
2 | Anti-Scale | 61676 | 334259 | 39550853258
3 | Biocide TYPE A | 28326 | 699147 | 13422438965
4 | Biocide TYPE B | 84991 | 411952 | 59635479912
5 | Corrosion Inhibitor | 30477 | 1037998 | 17573214063
6 | Demulsifier | 291801 | 1086803 | 351220896881
7 | O 2 Scavenger | 174362 | 304736 | 83458731938
8 | Reverse Demulsifier | 45752 | 1037998 | 38492894448
9 | Any other chemical required for operation | 1 | 2773543697 | 2773543697
|  | هزینه کل بدون ضریب |  | 816061251335
Rls

## E.Endorsement
Endorsement
Item | Title | نفر ساعت نقشه کش | نفر ساعت کارشناس | نفر ساعت کارشناس ارشد
1 | Basic Document Endorcement Report
1.1 | Process Document |  |  | 600
1.2 | Safety Document |  |  | 500
1.3 | Civil Document |  |  | 400
1.4 | Structural Document |  |  | 400
1.5 | Architectural Document |  |  | 400
1.6 | Mechanical Document |  |  | 600
1.7 | HVAC Document |  |  | 400
1.8 | Piping & Pipeline Document |  |  | 400
1.9 | Electrical Document |  |  | 500
1.10 | Telecommunication Document |  |  | 350
1,11 | Instrumentation Document |  |  | 400
| Total : |  |  | 4950

## E.Process
Process Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification and Criteria | [24 empty] | 0
1.1 | Environmental Data (Site Condition) |  | 10
1.2 | Process Design Basis | 40 | 20
1.3 | Process Design Criteria | 40 | 20
1.4 | Process Description | 40 | 20
1.5 | Technical Specification For Desalter Package | 20 | 5 | 5 | 2 |  |  |  |  | 5 | 2 | 10 | 3 | 10 | 3
1.6 | Technical specification for waste water treatment package | 20 | 5 | 8 | 4 |  |  |  |  | 5 | 2 | 10 | 3 | 5 | 2
2 | Lists | [24 empty] | 0
2.1 | Equipment List | 40 | 10 | 8 | 3 |  |  | 2 | 1
2.2 | Utility Consumption List | 60 | 15 |  |  |  |  | 1 |  |  |  | 2 | 1 | 2 | 1
2.3 | Chemical List | 40 | 5 | [9 empty] | 1
2.4 | Laboratory Equipment List | 10 | 2
2.5 | Flare Load Summary | 50 | 10
2.6 | Set point & Alarm list | 60 | 20 | [8 empty] | 40 | 20
3 | Calculation | [24 empty] | 0
3.1 | Process Simulation Report | 120 | 40
3.2 | Pump Hydrolic Calculation | 100 | 40 | 20
3.3 | Line Sizing And Hydraulic Calculation | 150 | 30 | [6 empty] | 20 | 2
3.4 | Vessel Sizing Report | 80 | 20 |  | 2
3.5 | Flare Sizing Calculation | 60 | 20
3.6 | Burn Pit Calculation | 30 | 10
3.7 | Pipeline Hydranlic Simulation Report | 150 | 40 | [6 empty] | 20 | 5
3.8 | Nace Calculation Report | 10 | 5 |  | 2 |  |  |  |  | 10 | 2
4 | PFD(s) | [24 empty] | 10
4.1 | Overall Block Flow Diagram | 10 | 5 | [22 empty] | 5
4.2 | PFD - Desalting unit | 80 | 40 | [22 empty] | 5
5 | UFD | [24 empty] | 30
5.1 | UFD - Dilution Water | 40 | 10 | [22 empty] | 5
5.2 | UFD - Waste Water Treatment | 40 | 10 | [22 empty] | 5
10 | UFD - Instrument & Plant Air | 40 | 10 | [22 empty] | 5
11 | UFD - Fuel Gas | 40 | 10 | [22 empty] | 5
4 | UFD-Hydrocarbon Drain System | 40 | 10 | [22 empty] | 5
5 | UFD-Flare System | 40 | 10 | [22 empty] | 5
6 | P&ID(s) | [24 empty] | 255
6.1 | P&ID Legend & Symbols | 5 | 5 | [8 empty] | 5 | [13 empty] | 5
6.2 | P&ID- List Of drawings | 5 | 5 | [22 empty] | 5
6.3 | P&ID-Transfer Pumps | 30 | 5 | [6 empty] | 10 | 3 | 0 | 3 | [12 empty] | 10
6.4 | P&ID-Salty Crude/Desalted Crude heat Exchanger | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.5 | P&ID-Crude Oil Indirect Fired Heater | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.6 | P&ID-Electrostatic Desalters | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.7 | P&ID-Water/Water Heat Exchanger | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.8 | P&ID-Chemical Injection Packages | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.9 | P&ID-Instrument & Plant Air | 40 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 8
6.10 | P&ID-Deaeration Package | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.11 | P&ID-Dilution Water | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.12 | P&ID-Potable Water | 30 | 5 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 8
6.13 | P&ID-Skimmer Tank | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.14 | P&ID-Waste Water Treatment | 60 | 15 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 12
6.15 | P&ID-Disposal Storage tank | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.16 | P&ID-Water Water Injection Pumps | 50 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.17 | P&ID-Oily Water Separator | 40 | 10 | [6 empty] | 20 | 3 | 0 | 3 | [12 empty] | 10
6.18 | P&ID-Fuel Oil System | 20 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
6.19 | P&ID-Hydrocarbon Drain Header & System | 20 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
6.20 | P&ID-Flare Header & System | 20 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
6.21 | P&ID-Fuel Gas K.O.Drum | 40 | 10 | [6 empty] | 10 | 2 | 0 | 2 | [12 empty] | 8
6.22 | P&ID-Fuel Gas Header | 20 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 10
6.23 | P&ID-Burn Pit | 30 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 8
6.24 | P&ID-Oily Water Network | 30 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
6.25 | P&ID-Evaporation Pond | 40 | 10 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
6.26 | P&ID-Off-Spec Tank | 50 | 10 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 10
6.27 | P&ID-Dirty Oil Tank | 40 | 10 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 10
6.28 | P&ID-Free Water K.O. Drum | 40 | 10 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 8
6.29 | P&ID-P.U.4 Instrument Air System | 30 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 8
6.30 | P&ID-PU4 Salty/Desalted Crude oil Separation | 80 | 20 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 10
6.31 | P&ID-Supply Water | 25 | 5 | [6 empty] | 5 | 1 | 0 | 1 | [12 empty] | 5
7 | Process Datasheets
7.1 | Process Data Sheet For Dilution Water Pump (P-103) | 5 | 2 | 1
7.2 | Process Data Sheet For Potable Water Pump (P-104) | 5 | 2 | 1
7.3 | Process Data Sheet For Injection Water Pump (P-201-A/B) | 5 | 2 | 1
7.4 | Process Data Sheet For Clean Water Pump (P-703-A/B) | 5 | 2 | 1
7.5 | Process Data Sheet For Diesel Oil Pump (P-801) | 5 | 2 | 1
7.6 | Process Data Sheet For HC Closed Drain Sump Pump (P-702) | 5 | 2 | 1
7.7 | Process Data Sheet For HC Closed Drain Transfer Pump (P-701-A/B) | 5 | 2 | 1
7.8 | Process Data Sheet For Flare K.O. Drum Liquid Pump (P-601-A/B) | 5 | 2 | 1
7.9 | Process Data Sheet For Dirty Oil Pumps(P-705-A/B) | 5 | 2 | 1
7.10 | Process Data Sheet For Degassing Water Pumps(P-005-A/B) | 5 | 2 | 1
7.11 | Process Data Sheet For Waste Water Injection Pumps (P-206-A/B/C) | 5 | 2 | 1
7.12 | Process Data Sheet For Oily Water Separator Pump(P-750) | 5 | 2 | 1
7.13 | Process Data Sheet For Deaerated Water Pump(P-105) | 5 | 2 | 1
7.14 | Process Data Sheet For Dilution Water Pumps(P-106-A1/A2) | 5 | 2 | 1
7.15 | Process Data Sheet For Recovered Waste Water Pumps(P-706-A/B) | 5 | 2 | 1
7.16 | Process Data Sheet For Salty Crude Transfer Pumps (P-002-A/B) | 5 | 2 | 1
7.17 | Process Data Sheet For Dearated Water Pumps (P-102-A/B) | 5 | 2 | 1
7.18 | Process Data Sheet For Salty Crude Transfer Pump (P-001-A/B) | 5 | 2 | 1
7.19 | Process Data Sheet For Off-Spec Pump (P-003-A/B) | 5 | 2 | 1
7.20 | Process Data Sheet for OWS Water Oil Pump (P-704) | 5 | 2 | 1
7.21 | Process Data Sheet For Firewater Loading Pump P-904 | 5 | 2 | 1
7.22 | Process Data Sheet For Chemical Injection Portable Pump (P-508 A/B/C) | 5 | 2 | 1
7.23 | Process Data Sheet For Salty Crude/Desalted Crude Heat Exchanger (E-001-A/B) | 10 | 5 | 1
7.24 | Process Data Sheet For Crude Oil Indirect Fired Heater (H-001-A1/A2/B1/B2) | 20 | 5 | 1 |  |  |  | 1 | 1
7.25 | Process Data Sheet For Water/Water Heat Exchanger (E-002-A/B) | 10 | 5 | 1
7.26 | Process Data Sheet For Demulsifier Injection Package (PK-501) | 5 | 2 | 1
7.27 | Process Data Sheet For Oxygen Scavenger Injection Package (PK-503) | 5 | 2 | 1
7.28 | Process Data Sheet For Corrosion Inhibitor injection Package (PK-504) | 5 | 2 | 1
7.29 | Process Data Sheet For Reverse Demulsifier Injection Package (PK-505) | 5 | 2 | 1
7.30 | Process Data Sheet For Biocide Injection Package (Type A) (PK-506-A) | 5 | 2 | 1
7.31 | Process Data Sheet For Anti Scalant Injection Package (PK-507) | 5 | 2 | 1
7.32 | Process Data Sheet For Air Receiver (V-401) | 5 | 2 | 1
7.33 | Process Data Sheet For Air Compressor Package & Air Dryer package (PK-401-A/B) & (PK-402) | 10 | 2 | 1
7.34 | Process Data Sheet For Air Compressor Package & Air Dryer package (PK-002-A/B) & (PK-003) | 10 | 2 | 1
7.35 | Process Data Sheet For Vacuum Deaerator Package (PK-101) | 10 | 5 | 1
7.36 | Process Data Sheet For Dilution Water Storage Tank (TK-101) | 10 | 2 | 1
7.37 | Process Data Sheet For Potable Water Tank (TK-102) | 10 | 2 | 1
7.38 | Process Data Sheet For Skimmer Tank (OS-201) | 10 | 2 | 1 |  |  |  | 1
7.39 | Process Data Sheet For Disposal Storage Tank (TK-201) | 10 | 2 | 1
7.40 | Process Data Sheet For Oily Water Separator (SU-701) | 10 | 2 | 1
7.41 | Process Data Sheet For Diesel Oil Storage Tank (V-801) | 5 | 2 | 1
7.42 | Process Data Sheet For HC Closed Drain Drum (V-701) | 5 | 2 | 1
7.43 | Process Data Sheet For Flare K.O.Drum (V-601) | 5 | 2 | 1
7.44 | Process Data Sheet For Flare Package (PK-602) | 5 | 5 | 1
7.45 | Process Data Sheet For Cold Flare Package (PK-603) | 5 | 5 | 1
7.46 | Process Data Sheet For Fuel Gas K.O.Drum (V-301) | 5 | 2 | 1
7.47 | Process Data Sheet For Burn Pit Ignition Package (PK-701) | 5 | 2 | 1
7.48 | Process Data Sheet For Dual Polarity Electrostatic Desalter (PK-001-A/B) | 15 | 10 | 1
7.49 | Process Data Sheet For Off-Spec Tank (TK-003) | 10 | 2 | 1 |  |  | 1
7.50 | Process Data Sheet For Free Water K.O. Drum (V-001-A/B) | 5 | 2 | 1
7.51 | Process Data Sheet For Biocide Injection Package (Type B) (PK-506-B) | 5 | 2 | 1
7.52 | Process Data Sheet For Demulsifier Injection Package (PK-502-A/B) | 5 | 2 | 1
7.53 | Process Data Sheet for Dirty Oil Tank (TK-701) | 5 | 2 | 1
7.54 | Process Data Sheet for IGF Package (PK-201-A/B) | 15 | 5 | 1
7.55 | Process Data Sheet for Nutshell Filter Package (PK-202) | 10 | 5 | 1
7.56 | Process Data Sheet For Water Treatment Package | 5 | 2 | 1
7.57 | Process Data Sheet For Portable Skimmer(X-704) | 5 | 2 | 1
7.58 | Process Data Sheet For Air Receiver ( V-002) | 5 | 2 | 1
7.59 | Process Data Sheet For Supply water pump(P-108A/B) | 8 | 2 | 1
7.60 | Process Data Sheet For Supply water Tank(TK-104) | 5 | 2 | 1
8 | Cause & Effect | [24 empty] | 0
8.1 | Cause & Effect Chart | 40 | 30 | [8 empty] | 10 | 2
8.2 | ESD Cause & Effect Block Diagram | 100 | 20 | [8 empty] | 10 | 2
9 | Control Philosophy | [24 empty] | 0
9.1 | FCS Control Philosophy | 120 | 30 | [8 empty] | 10 | 2
9.2 | DCS Control Philosophy (for PU4) | 30 | 10 | [8 empty] | 5 | 1
9.3 | Relief Philosophy | 50 | 20 | [8 empty] | 5 | 1
9.4 | ESD Control Philosophy | 50 | 20 | [8 empty] | 5 | 1
9.5 | Isolation Philosophy | 10 | 5 | [8 empty] | 5 | 1
9.6 | Sparing Philosophy | 10 | 5 | [8 empty] | 5 | 1
10 | Manual | [24 empty] | 0
10.1 | Commissioning and start-up Manual | 200 | 50 | 30 | 5 | [6 empty] | 20 | 5 | 30 | 5
10.2 | Operating Manual | 200 | 50 | 30 | 5 | [6 empty] | 20 | 5 | 30 | 5
11 | خدمات پس از اجرا
11.1 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | 192.65 | [23 empty] | 29.75
| Total : | 4045.65 | 1109 | 161 | 23 | 0 | 1 | 5 | 2 | 425 | 73 | 162 | 109 | 77 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624.75
|  | 3853 | 1109 | 161 | 23 | 0 | 1 | 5 | 2 | 425 | 73 | 162 | 109 | 77 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595

## E.Mechanic
Mechanical Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification, Criteria, Standard Drawing
1.1 | Mechanical Design Criteria |  |  |  | 10
1.2 | General Requirements for Welded Fabrication |  |  |  | 5
1.3 | Specification for Centrifugal Pumps for General Duty Services |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.4 | Specification for Centrifugal Pumps for Process Services |  |  |  | 8 | [6 empty] | 0.5 |  | 0.5
1.5 | Specification for Fire Water Pumps |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.6 | Specification for Indirect Fired Heaters |  |  |  | 8 | [6 empty] | 1 |  | 1
1.7 | Specification for Instrument Air Compressor Package |  |  |  | 8 | [6 empty] | 0.5 |  | 0.5
1.8 | Specification for Minimum Requirements for Packaged Equipment |  |  |  | 8
1.9 | Specification for Plate & Frame Heat Exchangers |  |  |  | 8 | [6 empty] | 0.5 |  | 0.5
1.10 | Specification for Pressure Vessels |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.11 | Specification for Safeguarding of Machinery |  |  |  | 4
1.12 | Specification for Vertical Cylindrical Storage Tanks |  |  |  | 5
1.13 | Specificaion for Flare |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.14 | Specificaion for Cranes |  |  |  | 5 | [8 empty] | 0.5 | [5 empty] | 5
1.15 | Specification for Chemical Injection Package |  |  |  | 5
1.16 | Specification for Electrostatic Crude Oil Desalting Package |  |  |  | 8 | [6 empty] | 1 |  | 1
1.17 | specification for metering pumps API 675 |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.18 | Specification for Waste Water Treatment Unit |  |  |  | 8 | [6 empty] | 1 |  | 1
1.19 | Specifcation for Rotary Pump |  |  |  | 5 | [6 empty] | 0.5 |  | 0.5
1.20 | specification for Lubrication System |  |  |  | 5
1.21 | Standard Drawing for Storage Tanks |  |  |  | 4 | [20 empty] | 10
1.22 | Standard Drawing for Pressure Vessel |  |  |  | 4 | [20 empty] | 10
2 | Process Packkages and Equipment Datasheet
2.1 | Heat Exchanger Datasheet
2.1.1 | Data Sheet For Salty Crude/Desalted Crude Heat Exchanger(E-001-A/B) | 1 |  |  | 5 | [6 empty] | 1
2.1.2 | Data Sheet For Water/Water Heat Exchanger(E-002-A/B) | 1 |  |  | 5 | [6 empty] | 1
2.2 | Data Sheet For Crude Oil Indirect Fired Heater(H-001-A1/A2/B1/B2) | 2 |  |  | 10 | [6 empty] | 2 |  | 1
2.3 | Air Compressors and Dryer Datasheet | [12 empty] | 0.5
2.3.1 | DATA SHEET FOR AIR COMPRESSOR PKG. (PK-401-A/B) & AIR DRYER PKG. (PK-402) | 2 |  |  | 5 | [6 empty] | 2 |  | 1
2.3.2 | Data Sheet For Air COMPRESSOR PKG. (PK-002-A/B) & AIR DRYER PKG. (PK-003) | 2 |  |  | 5 | [6 empty] | 2 |  | 1
2.4 | Data Sheet For Vacuum Deaerator Package | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.5 | Flares Datasheet
2.5.1 | Data Sheet For HOT FLARE PACKAGE AND IGNITION PACKAGE | 1 |  |  | 5 | [6 empty] | 2 |  | 0.5
2.5.2 | Data Sheet For Cold Flare Package(PK-603) | 1 |  |  | 5 | [6 empty] | 1
2.6 | DATA Sheet For Desalter Package (PK-001A/B) | 3 |  |  | 10 | [6 empty] | 2 |  | 2
2.7 | Waste Water Treatment Packages Datasheet
2.7.1 | Data Sheet For Nutshell Filter Package(PK-202) | 3 |  |  | 5 | [6 empty] | 2 |  | 1
2.7.2 | Data Sheet For IGF Package (PK-201A/B) | 1 |  |  | 8 | [6 empty] | 1 |  | 1
2.8 | Data Sheet For Cranes | 1 |  |  | 16 | [8 empty] | 2
2.9 | Injection Packages Datasheet
2.9.1 | Data Sheet For Demulsifier Injection Package (PK-501) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.2 | Data Sheet For Oxygen Scavenger Injection Package(PK-503) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.3 | Data Sheet For Corrosion Inhibitor injection Package(PK-504) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.4 | Data Sheet For Reverse Demulsifier Injection Package(PK-505) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.5 | Data Sheet For Biocide Injection Package (Type A)(PK-506-A) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.6 | Data Sheet For Anti Scalant Injection Package(PK-507) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.7 | Data Sheet For Biocide Injection Package (Type B)(PK-506-B) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
2.9.8 | Data Sheet For Demulsifier Injection Package (PK-502-A/B) | 1 |  |  | 5 | [6 empty] | 1 |  | 1
3 | Pumps Datasheet
3.1 | Data Sheet For Dilution Water Pump(P-103) | 1 |  |  | 5 | [8 empty] | 0.5
3.2 | Data Sheet For Potable Water Pump(P-104) | 1 |  |  | 5 | [8 empty] | 0.5
3.3 | Data Sheet For Waste Water Injection Pump(P-201-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.4 | Data Sheet For OWS Clean Water Pump(p-703-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.5 | Data Sheet For Diesel Oil Pump(P-801) | 1 |  |  | 5 | [8 empty] | 0.5
3.6 | Data Sheet For HC Closed Drain Sump Pump(P-702) | 1 |  |  | 5 | [8 empty] | 0.5
3.7 | Data Sheet For HC Closed Drain Transfer Pump(P-701-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.8 | Data Sheet For Flare K.O. Drum Liquid Pump(P-601-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.9 | Data Sheet for Dilution Water Pumps(P-106-A1/A2) | 1 |  |  | 5 | [8 empty] | 0.5
3.10 | Data Sheet For Dearated Water Pump(p-102-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.11 | Data Sheet for Dirty Oil Pumps(P-705-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.12 | Data Sheet for Booster Pumps (P-002-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.13 | Data Sheet for Booster Pumps (P-001-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.14 | Data Sheet for Evaporation Pond Pumps(P-706-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.15 | Data Sheet for Free Water Transfer PUMPS (P-005-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.16 | Data Sheet for Dearated Water Pump(p-105) | 1 |  |  | 5 | [8 empty] | 0.5
3.17 | Data Sheet for Ows Oil Pump(P-704-A/B) | 1 |  |  | 5 | [8 empty] | 0.5
3.18 | Data Sheet for Oily Water Separator Pump(P-750) | 1 |  |  | 5 | [8 empty] | 0.5
3.19 | Data Sheet for Waste Water Injection Pump(p-206-A/B/C) | 1 |  |  | 5 | [8 empty] | 0.5
3.20 | Data Sheet For Chemical Injection Portable Pump(P508 A/B/C) | 1 |  |  | 5 | [8 empty] | 0.5
3.21 | Data Sheet For Off-Spec Pump | 1 |  |  | 5 | [8 empty] | 0.5
3.22 | Data Sheet For Firewater Loading Pump P-904 | 1 |  |  | 5 |  |  | 1 | [5 empty] | 0.5
3.23 | Data Sheet For Supply water Pump P-108A/B | 1 |  |  | 5 | [8 empty] | 0.5
4 | Pressure Vessels Datasheet
4.1 | Data Sheet For Air Receiver(v-401) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
4.2 | Data Sheet For Diesel Oil Storage Tank(v-801) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
4.3 | Data Sheet For HC Closed Drain Drum(V-701) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
4.4 | Data Sheet For Flare K.O.Drum(V-601) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
4.5 | Data Sheet For Fuel Gas K.O.Drum(V-301) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
4.6 | Data Sheet For Free Water K.O. Drum(v-001-A/B) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 12
4.7 | Data Sheet For Air Receiver ( V-002) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 8
5 | Storage Tanks Datasheet
5.1 | Data Sheet For Dilution Water Storage Tank(TK-101) | 1 |  |  | 12 | [6 empty] | 1 | [13 empty] | 10
5.2 | Data Sheet For Potable Water Tank(TK-102) | 1 |  |  | 12 |  |  | 1 |  |  |  | 1 | [13 empty] | 10
5.3 | Data Sheet For Skimmer Tank(OS-201) | 1 |  |  | 12 | [6 empty] | 1 | [13 empty] | 20
5.4 | Data Sheet For Disposal Storage Tank(TK-201) | 1 |  |  | 12 | [6 empty] | 1 | [13 empty] | 15
5.5 | Data Sheet For Off-Spec Tank | 1 |  |  | 12 |  |  | 1 |  |  |  | 1 | [13 empty] | 20
5.6 | Data Sheet for Dirty Oil Tank(TK-701) | 1 |  |  | 8 | [6 empty] | 1 | [13 empty] | 10
5.7 | Data Sheet for Fire Water Tank(TK-902-A/B) | 1 |  |  | 15 |  |  | 3 | 1 |  |  | 1 | [13 empty] | 20
5.8 | Data Sheet For Supply Water Storage Tank(TK-104) | 1 |  |  | 12 | [6 empty] | 1 | [13 empty] | 10
6 | M.R., M.T.O. and T.B.E.
6.1 | MR for Process Centrifugal Pumps |  |  | 10 | 5
6.2 | MR for General Services Centrifugal Pumps |  |  | 10 | 5
6.3 | MR for Rotary Pumps |  |  | 10 | 5
6.4 | MR for Desalters |  |  | 10 | 5
6.5 | MR for indirect Heaters |  |  | 10 | 5
6.6 | MR for Air Compressors and Dryers |  |  | 10 | 5
6.7 | MR for Pressure Vessels |  |  | 10 | 5
6.8 | MR for Storage Tanks |  |  | 10 | 5
6.9 | MR for Heat Exchanger |  |  | 10 | 5
"6.10 | MR for Vacuum Deaerator Package |  |  | 10 | 5
6.11 | MR for Injection Packages |  |  | 10 | 5
6.12 | MR for Flares and Ignition Packages |  |  | 10 | 5
6.13 | MR for Waste Water Treatment Packages |  |  | 10 | 5
6.14 | MR for Cranes |  |  | 10 | 5
6.15 | TBE for Process Centrifugal Pumps | 25 | 5 | 70 | 12 | [8 empty] | 5 | 1
6.16 | TBE for General Services Centrifugal Pumps | 20 | 4 | 50 | 8 | [8 empty] | 5 | 1
6.17 | TBE for Rotary Pumps | 5 | 1 | 20 | 4 | [8 empty] | 3 | 1
6.18 | TBE for Desalters | 25 | 5 | 70 | 12 | [6 empty] | 10 | 5 | 8 | 2
6.19 | TBE for indirect Heaters | 25 | 5 | 70 | 12 | [6 empty] | 8 | 5 | 2 | 1
6.20 | TBE for Air Compressors and Dryers | 15 | 5 | 40 | 6 | [6 empty] | 8 | 5 | 5 | 1
6.21 | TBE for Pressure Vessels | 8 | 2 | 50 | 8 | [6 empty] | 3 | 1
6.22 | TBE for Storage Tanks | 8 | 2 | 50 | 8 | [6 empty] | 3 | 1
6.23 | TBE for Heat Exchanger | 8 | 2 | 40 | 8 | [6 empty] | 3 | 1
6.24 | TBE for Vacuum Deaerator Package | 8 | 2 | 50 | 8 | [6 empty] | 5 | 1 | 2 | 1
6.25 | TBE for Injection Packages | 8 | 2 | 50 | 8 | [6 empty] | 8 | 2 | 3 | 1
6.26 | TBE for Flares and Ignition Packages | 8 | 2 | 40 | 8 | [6 empty] | 8 | 2 | 3 | 1
6.27 | TBE for Waste Water Treatment Packages | 8 | 2 | 50 | 8 | [6 empty] | 8 | 2 | 5 | 1
6.28 | TBE for Cranes |  |  | 50 | 8 | [8 empty] | 4 | 1
7 | Review of Suppliers Technical Document
7.1 | Review of technical document of Process Centrifugal Pumps | 40 | 2 | 300 | 12 |  |  |  |  | 5 |  | 1 |  | 0 | 2
7.2 | Review of technical document of General Services Centrifugal Pumps | 16 | 2 | 120 | 8 |  |  |  |  | 5 |  | 1 |  | 0 | 2
7.3 | Review of technical document of Rotary Pumps | 4 | 1 | 30 | 5 |  |  |  |  | 1 |  | 1 |  | 0 | 1
7.4 | Review of technical document of Desalters | 40 | 5 | 300 | 30 |  |  |  |  | 8 |  | 80 | 8 | 50 | 8
7.5 | Review of technical document of indirect Heaters | 36 | 5 | 270 | 30 |  |  |  |  | 8 |  | 80 | 8 | 5 | 1
7.6 | Review of technical document of Air Compressors and Dryers | 16 | 4 | 300 | 25 | [6 empty] | 25 | 4 | 10 | 2
7.7 | Review of technical document of Pressure Vessels | 24 | 1 | 180 | 5 |  |  |  |  | 5 |  | 5
7.8 | Review of technical document of Storage Tanks | 40 | 1 | 300 | 10 |  |  |  |  | 5 |  | 5
7.9 | Review of technical document of Heat Exchanger | 16 | 1 | 120 | 15 |  |  |  |  | 5 |  | 3
7.10 | Review of technical document of Vacuum Deaerator Package | 28 | 3 | 300 | 20 |  |  |  |  | 5 |  | 50 | 8 | 5 | 1
7.11 | Review of technical document of Injection Packages | 36 | 4 | 270 | 30 |  |  |  |  | 8 |  | 80 | 8 | 10 | 2
7.12 | Review of technical document of Flares and Ignition Packages | 40 | 4 | 300 | 30 |  |  |  |  | 2 |  | 40 | 5 | 5 | 1
7.13 | Review of technical document of Waste Water Treatment Packages | 32 | 5 | 240 | 30 |  |  |  |  | 5 |  | 80 | 8 | 10 | 2
7.14 | Review of technical document of Cranes |  |  | 90 | 5 | [8 empty] | 15 | 3 |  |  |  |  | 90 | 5
8 | خدمات مرتبط با اجرا و پس از اجرا
8.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) |  |  | 396 | 96.6 | [20 empty] | 19.5
8.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی |  |  | 198 | [21 empty] | 9.75
8.3 | سیاهه کالا (Material Take-off) پس از اجرا |  |  | 30
8.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا |  |  | 25
8.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها |  |  | 40 | 8
| TOTAL : | 604 | 77 | 4649 | 1070.6 | 0 | 0 | 6 | 1 | 62 | 0 | 562.5 | 74 | 193.5 | 37 | 0 | 0 | 0 | 0 | 95 | 5 | 0 | 0 | 0 | 0 | 224.25
|  | 604 | 77 | 3960 | 966 | 0 | 0 | 6 | 1 | 62 | 0 | 562.5 | 74 | 193.5 | 37 | 0 | 0 | 0 | 0 | 95 | 5 | 0 | 0 | 0 | 0 | 195

## E.HVAC
HVAC Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification
1.1 | Specification for HVAC & Plumbing | [5 empty] | 25
1.2 | Typical Detail For Plumbing & HVAC | [5 empty] | 20
1.3 | Specification for HVAC Equipment | [5 empty] | 40
1.4 | HVAC & Plumbing Abbriviation & Symbol |  |  |  |  | 5
1.5 | HVAC & Plumbing Design Criteria | [5 empty] | 25
1.6 | HVAC & Plumbing Installation Detail | [5 empty] | 20
2 | HVAC Calculation
2.1 | HVAC Calculation for Control &Telecommunication Building |  |  |  |  | 100 | 5
2.2 | HVAC Calculation for Guard House |  |  |  |  | 30 | 5
2.3 | HVAC Calculation for DE4 Substation Building |  |  |  |  | 90 | 5
2.4 | HVAC Calculation Extension For PU4 Switchgear Room |  |  |  |  | 40 | 5
2.5 | HVAC Calculation For PU4 Accommodation Building |  |  |  |  | 50 | 5
2.6 | HVAC Calculation for Laboratory |  |  |  |  | 90 | 5
2.7 | HVAC Calculation for Work Shop |  |  |  |  | 60 | 5
2.8 | HVAC Calculation for 3.3 Switch Gear Building Of PU4 Outdoor Substaion |  |  |  |  | 80 | 5
2.9 | HVAC Calculation for 33 KV Switch Gear Building Of 33 KV Station |  |  |  |  | 80 | 5
2.10 | HVAC Calculation for 33 KV Station Guard House |  |  |  |  | 40 | 5
3 | Buildings HVAC Drawings
3.1 | HVAC Drawings for Control &Telecommunication Building |  |  |  |  | 25 | 2 | [10 empty] | 2 | [7 empty] | 150
3.2 | HVAC Drawings for Guard House |  |  |  |  | 15 | 2 | [10 empty] | 1 | [7 empty] | 60
3.3 | HVAC Drawings for DE4 Substation Building |  |  |  |  | 25 | 2 | [10 empty] | 2 | [7 empty] | 150
3.4 | HVAC Drawings Extension For PU4 Switchgear Room |  |  |  |  | 15 | 2 | [10 empty] | 1 | [7 empty] | 40
3.5 | HVAC Drawings For PU4 Accommodation Building |  |  |  |  | 25 | 2 | [10 empty] | 2 | [7 empty] | 120
3.6 | HVAC Drawings for Laboratory |  |  |  |  | 30 | 2 | [10 empty] | 3 | [7 empty] | 160
3.7 | HVAC Drawings for Work Shop |  |  |  |  | 20 | 2 | [10 empty] | 2 | [7 empty] | 80
3.8 | HVAC Drawings for 3.3 Switch Gear Building Of PU4 Outdoor Substaion |  |  |  |  | 25 | 2 | [10 empty] | 2 | [7 empty] | 120
3.9 | HVAC Drawings for 33 KV Switch Gear Building Of 33 KV Station |  |  |  |  | 25 | 2 | [10 empty] | 2 | [7 empty] | 120
3.10 | HVAC Drawings for 33 KV Station Guard House |  |  |  |  | 15 | 2 | [10 empty] | 2 | [7 empty] | 40
4 | Site Drawings
4.1 | Site Plumbing Network Layout |  |  |  |  | 5 | 2 |  |  | 1 | [5 empty] | 5 | 2 | [8 empty] | 80
4.2 | Site Sewage Network Layout |  |  |  |  | 5 | 2 |  |  | 1 | [5 empty] | 5 | 2 | [8 empty] | 80
5 | Equipment Specification
5.1 | HVAC Main Equipment Data Sheet |  |  |  |  | 150 | 40
5.2 | HVAC Equipment List |  |  |  |  | 30 | 5
6 | MTO. MR & TBE
6.1 | HVAC & Plumbing Material Take Off |  |  |  |  | 10
6.2 | MR For Hvac Equipment |  |  |  |  | 12
6.3 | TBE For Hvac Equipment Suppliers |  |  |  |  | 80 | 5
7 | Review of Suppliers Technical Document
8 | خدمات مرتبط با اجرا و پس از اجرا
8.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) |  |  |  |  | 117.7 | 25.4 | [18 empty] | 120
8.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی |  |  |  |  | 58.85 | [19 empty] | 60
8.3 | سیاهه کالا (Material Take-off) پس از اجرا |  |  |  |  | 50
8.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا |  |  |  |  | 60
8.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها |  |  |  |  | 80 | 8
| TOTAL : | 0 | 0 | 0 | 0 | 1543.55 | 287.4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1380
|  | 0 | 0 | 0 | 0 | 1177 | 254 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200

## E.HSE
Safety Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification and Criteria
1.1 | HSE Design Criteria | [7 empty] | 15
1.2 | Safety Design Criteria | [7 empty] | 15
1.3 | Safety Philosophy | [7 empty] | 15
1.4 | Safety Equipment Specification | [7 empty] | 15
1.5 | Specification for CO2 Total Flooding | [7 empty] | 15
1.6 | specification for hazardous area classification | [7 empty] | 15
1.7 | specification for fire water system | [7 empty] | 15
1.8 | specification for safety signs | [7 empty] | 15
1.9 | Specification for Water Spray System | [7 empty] | 15
1.10 | Specification for Fire Alarm System | [7 empty] | 15
1.11 | Hazard Source List | 2 | [5 empty] | 30 | 25 |  |  |  |  | 4 | 1
1.12 | Specification for Foam System | [7 empty] | 15
1.13 | Specification for Foam Chamber | [7 empty] | 8
1.14 | Waste mangaement Plan | [6 empty] | 20 | 5
1.15 | safety boundary limit | [7 empty] | 15
2 | Calculation
2.1 | CO2 Demand Calculation for DE4 Substation | [6 empty] | 25 | 8
2.2 | CO2 Demand Calculation for 33/3.45 Sample-4 Station | [6 empty] | 25 | 8
2.3 | Fire Water Demand Calculation | [6 empty] | 25 | 8
2.4 | Fire Water Hydrolic Calculations | [6 empty] | 60 | 8
2.5 | Flare Radiation and Disperasion Report | [6 empty] | 30 | 8
3 | P&ID
3.1 | Legend and Abbreviation For Safety & Fire Fighting P&ID | [6 empty] | 5 | [17 empty] | 10
3.2 | P&ID for CO2 total Flooding System | [6 empty] | 15 | 5 | [16 empty] | 10
3.3 | P&ID For Fire Water | 5 | 1 |  |  |  |  | 25 | 5 | [16 empty] | 20
4 | Datasheet
4.1 | Fire Water Tank data Sheet |  |  | 4 |  |  |  | 8 | 8
4.2 | Data Sheet For Fire Water Diesel Pump |  |  | 3 |  |  |  | 8 | 8
4.3 | Data Sheet For Fire Water Electrical Pump |  |  | 3 |  |  |  | 8 | 8 | 4 |  | 8 | 2
4.4 | Fire Water Jocy Pump Data Sheet | [6 empty] | 8 | 8
4.5 | Deludge Valve Datasheets | [6 empty] | 8 | 8
4.6 | Water Spray Nozzle Datasheets | [6 empty] | 12 | 8
4.7 | Hydrant data sheet | [6 empty] | 20 | 8
4.8 | Monitor data sheet | [6 empty] | 20 | 8
4.9 | Portable extinguishers data sheet | [6 empty] | 25 | 8
4.10 | Wheeled extinguishers data sheet | [6 empty] | 25 | 8
4.11 | Safety shower data sheet | [6 empty] | 20 | 8
4.12 | Data sheet for Co2 Automatic extinguishing system | [6 empty] | 30 | 8
4.13 | Data sheet for hose box | [6 empty] | 15 | 8
4.14 | Data sheet for Foam Skid | [6 empty] | 10 | 4
5 | Drawings
5.1 | Fire Water Network Piping Plan for Sample-4 Desalting Unit | [6 empty] | 30 | 10 | [16 empty] | 50
5.2 | Fire Water Network Piping Plan for Sample-4 Production Unit | [6 empty] | 30 | 5 | [16 empty] | 30
5.3 | Safety and Fire Fighting Equipment Layout for Sample-4 Desalting Unit Buildings | [6 empty] | 15 | 5 | [16 empty] | 20
5.4 | Safety and Fire Fighting Equipment Layout for Sample-4 Production Unit Buildings | [6 empty] | 15 | 5 | [16 empty] | 20
5.5 | Safety and Fire Fighting Equipment Layout For 33KV Outdoor Station Sample 3 | [6 empty] | 15 | 5 | [16 empty] | 20
5.6 | Safety and Fire Fighting Equipment Layout For 33/3.45KV Outdoor Station Sample 4 | [6 empty] | 15 | 5 | [16 empty] | 20
5.7 | escape routes and safety sign layout for Sample-4 Desalting Unit Buildings | [6 empty] | 20 | 5 | [16 empty] | 40
5.8 | escape routes and safety sign layout for Sample-4 Desalting Unit Buildings | [6 empty] | 15 | 5 | [16 empty] | 20
5.9 | escape routes and safety sign layout For 33KV Outdoor Station Sample 3 | [6 empty] | 15 | 5 | [16 empty] | 20
5.10 | Fire Alarm Layout | [6 empty] | 20 | 8
5.11 | Emergency Response Plane for Sample-4 Desalting Unit | [6 empty] | 15 | 5 | [16 empty] | 20
5.12 | Emergency Response Plane for Sample-4 Production Unit | [6 empty] | 15 | 5 | [16 empty] | 20
6 | M.R. and T.B.E.
6.1 | Safety/fire fighting system equipment list | [6 empty] | 40 | 10
6.2 | MR for CO2 automatic extinguishing system | [6 empty] | 20 | 5
6.3 | MR for fire fighting/safety system Equipment | [6 empty] | 40 | 5
6.4 | MR for Fire Water Pumps | [6 empty] | 20 | 5
6.5 | TBE for CO2 automatic extinguishing system | [6 empty] | 40 | 5
6.6 | TBE for fire fighting/safety system Equipment | [6 empty] | 50 | 5
6.7 | TBE for Fire Water Pumps | [6 empty] | 40 | 5
7 | Review of Suppliers Technical Document
7.1 | Review of Suppliers Technical Document of for CO2 automatic extinguishing system | [6 empty] | 150 | 30
7.2 | Review of Suppliers Technical Document of for fire fighting/safety system Equipment | [6 empty] | 150 | 30
7.3 | Review of Suppliers Technical Document of for Fire Water Pumps |  |  | 10 |  |  |  | 70 | 20 |  |  |  |  | 3
8 | خدمات مرتبط با اجرا و پس از اجرا
8.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [6 empty] | 131.7 | 56.4 | [16 empty] | 32
8.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [6 empty] | 65.85 | [17 empty] | 16
8.3 | سیاهه کالا (Material Take-off) پس از اجرا | [6 empty] | 30
8.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [6 empty] | 40
8.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [6 empty] | 40 | 8
| Total | 7 | 1 | 20 | 0 | 0 | 0 | 1624.55 | 628.4 | 4 | 0 | 8 | 2 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368
|  | 7 | 1 | 20 | 0 | 0 | 0 | 1317 | 564 | 4 | 0 | 8 | 2 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320

## E.Piping&Pipeline
لیست مدارک مهندسی تفصیلی پروژه احداث واحد نمکردایی نمونه-4 به روش EPC
Piping & Pipeline Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification & Criteria
1.1 | Piping Specification & Criteria | [8 empty] | 135 | 77 | [14 empty] | 0
1.1.1 | Piping Desing Criteria | [8 empty] | 15 | 2
1.1.2 | Piping Standard Drawings | [8 empty] | 20 | 5
1.1.3 | Piping Standard Assembly Drawings | [8 empty] | 20 | 5
1.1.4 | Piping Material Specification | 10 | 5 | [6 empty] | 20 | 5
1.1.5 | Specification For Thermal Insulation (Hot Services) | [8 empty] | 5 | 5
1.1.6 | Specification For Painting, Color Coding & Marking | [8 empty] | 5 | 5
1.1.7 | Specification For Coating Of Under Ground Piping | [8 empty] | 5 | 5
1.1.8 | Specification For Stress Analysis | [8 empty] | 5 | 5
1.1.9 | Specification For Pipe Support | [8 empty] | 5 | 5
1.1.10 | Specification For Valves | [8 empty] | 5 | 5
1.1.11 | Specification For Supply Pipe & Piping Component | [8 empty] | 5 | 5
1.1.12 | Specification For Construction piping Fabrication and Erection | [8 empty] | 5 | 5
1.1.13 | Specification For Welding , heat Treatment and inspection of Piping | [8 empty] | 5 | 5
1.1.14 | Specification For Hydrostatic Pressure Testing Of Piping System | [8 empty] | 5 | 5
1.1.15 | Specification For Cleaning & Flushing Of Piping System | [8 empty] | 5 | 5
1.1.16 | Specification For Non-Metal Pipes and Fittings | [8 empty] | 5 | 5 |  |  |  |  | 2 | 2
1.2 | Pipeline Specification & Criteria
1.2.1 | PipeLine Design Criteria | 5 | 2 | [6 empty] | 10 | 5
1.2.2 | PipeLine Material Specification | [8 empty] | 15 | 8
1.2.3 | Specification of Hydrostatic Testing | [8 empty] | 15 | 8
1.2.4 | Welding Specification For Pipeline | [8 empty] | 20 | 10
1.2.5 | Specification for Construction of Pipeline | [8 empty] | 10 | 5 |  |  |  |  | 10 | 5
2 | 3D Modeling by PDMS Software
2.1 | 3D Modeling for Sample-4 Desalting Unit |  | 2 |  | 2 |  |  |  | 2 | 800 | 300 |  | 1 |  | 2 |  | 2 | [8 empty] | 500
2.2 | 3D Modeling for Sample-4 Production Unit Extension |  | 2 |  | 2 |  |  |  | 2 | 500 | 100 |  | 1 |  | 2 |  | 2 | [8 empty] | 300
2.3 | 3D Modeling for Existing Sample-4 Production Unit | [8 empty] | 1000 | 300 | [14 empty] | 700
2.4 | PIPING ISOMETRICS | [8 empty] | 300 | 100 | [14 empty] | 200
3 | Plot Plan
3.1 | Overal Plot Plan For Desalting Unit |  | 8 |  | 8 |  |  |  | 4 | 80 | 50 |  | 2 |  | 8 | 10 | 5 |  |  |  | 5 |  |  |  |  | 300
3.2 | Overal Plot Plan For gachsaran-4 Production Unit Extension Area |  | 4 |  | 4 |  |  |  | 2 | 80 | 50 |  | 2 |  | 4 | 3 | 3 |  |  |  | 3 |  |  |  |  | 250
3.3 | Overal Plot Plan For Existing area od Sample-4 Production Unit | [8 empty] | 120 | 50 |  |  |  |  | 3 | 3 | [8 empty] | 500
3.4 | Off Site Overal Plot Plan |  | 3 |  | 3 |  |  |  | 3 | 80 | 10 |  |  |  | 2 | 10 | 5 |  |  |  | 1 |  |  |  |  | 200
3.5 | Plan For Flare Area |  | 1 |  | 1 |  |  |  |  | 50 | 10 | [14 empty] | 100
3.6 | Piping Plan For Cold Flare Area |  | 1 |  | 1 |  |  |  |  | 50 | 10 | [14 empty] | 100
3.7 | Plot Plan For Burn pit Area |  | 1 |  | 1 |  |  |  |  | 50 | 10 | [14 empty] | 100
3.8 | Plot Plan For Evaporation Pound Area | [8 empty] | 50 | 10 | [14 empty] | 100
3.9 | Plot Plan For 33KV Outdoor Substation In gachsaran NO.4 Area |  |  |  | 3 |  |  |  | 2 | 50 | 10 |  |  |  | 8 |  | 3 |  |  |  | 1 |  |  |  |  | 100
3.10 | Plot Plan For 33KV Outdoor Substation In gachsaran NO.3 Area |  |  |  | 3 |  |  |  | 2 | 50 | 10 |  |  |  | 8 |  | 3 |  |  |  | 1 |  |  |  |  | 100
4 | Piping Plan
4.1 | overal Piping Plan For Desalting Unit
4.1.1 | Key Plan For Desalting Unit | [8 empty] | 20 | 5 | [14 empty] | 10
4.1.2 | Piping Plan for Area 1 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.3 | Piping Plan for Area 2 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.4 | Piping Plan for Area 3 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.5 | Piping Plan for Area 4 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.6 | Piping Plan for Area 5 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.7 | Piping Plan for Area 6 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.8 | Piping Plan for Area 7 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.9 | Piping Plan for Area 8 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.1.10 | Piping Plan for Area 9 |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2 | Overal Piping Plan For Production Unit |  |  |  | 1
4.2.1 | Key Plan For Production Unit | [8 empty] | 20 | 5 | [14 empty] | 10
4.2.2 | overal Piping Plan For Sample-4 Production Unit Extension Area | [8 empty] | 20 | 5 | [14 empty] | 10
4.2.3 | overal Piping Plan For Existing Sample-4 Production Unit |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.4 | Piping Plan for Salty/Desalted Crude oil Separation |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.5 | Key Plan For Offsite |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.6 | Plan For Flare Area |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.7 | Piping Plan For Cold Flare Area |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.8 | Piping Plan For Burn pit Area |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
4.2.9 | Piping Plan For Evaporation Pound Area |  |  |  | 1 |  |  |  |  | 20 | 5 | [14 empty] | 10
5 | Support Layout and List
5.1 | Support Layout For Desalting Unit | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.2 | Support Layout For gachsaran-4 Production Unit Extension Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.3 | Support Layout For Existing area od Sample-4 Production Unit | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.4 | Support Layout For Flare Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.5 | Support Layout For Cold Flare Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.6 | Support Layout For Burn pit Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.7 | Support Layout For Evaporation Pound Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.8 | Support List For Desalting Unit | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.9 | Support List For gachsaran-4 Production Unit Extension Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.10 | Support List For Existing area od Sample-4 Production Unit | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.11 | Support List For Flare Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.12 | Support List For Cold Flare Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.13 | Support List For Burn pit Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
5.14 | Support List For Evaporation Pound Area | [8 empty] | 20 | 5 |  |  |  |  | 2 | [9 empty] | 10
6 | Calculation
6.1 | Stress Analysis Report for Desalting Unit | [8 empty] | 300 | 300 | [14 empty] | 300
6.2 | Stress Analysis Report for Production Unit | [8 empty] | 100 | 50 | [14 empty] | 50
6.3 | Piping Thickness Calculation | [8 empty] | 20 | 5 | [14 empty] | 10
6.4 | Pipelines Wall thickness calculation | [8 empty] | 20 | 5 | [14 empty] | 10
7 | LIST
7.1 | TIE IN POINT LIST | [8 empty] | 100 | 50 | [14 empty] | 0
7.2 | LINE LIST | 50 | 20 | [6 empty] | 150 | 30
8 | MTO. , M.R. and T.B.E.
8.1 | Piping MTO
8.1.1 | MTO. for Pipes | [8 empty] | 20 | 5
8.1.2 | MTO. for Manual Valve | [8 empty] | 20 | 5
8.1.3 | MTO. for Flange | [8 empty] | 20 | 5
8.1.4 | MTO. for Gasket | [8 empty] | 20 | 5
8.1.5 | MTO. for Fitting | [8 empty] | 20 | 5
8.1.6 | MTO. for Bults & Nuts | [8 empty] | 20 | 5
8.1.7 | MTO. for Supports | [8 empty] | 20 | 5
8.1.8 | MTO. for Non-Metallic piping component | [8 empty] | 20 | 5
8.1.9 | MTO.FOR SPECIAL ITEMS | [8 empty] | 20 | 5
8.1.10 | MTO.FOR ORIFICE FLANGES | [8 empty] | 20 | 5
8.1.11 | MTO.FOR PAINT | [8 empty] | 20 | 5
8.1.12 | MTO.FOR COATING &WRAPPING | [8 empty] | 20 | 5
8.1.13 | MTO.FOR INSULATION | [8 empty] | 20 | 5
8.1.14 | MTO.FOR ELECTRODE | [8 empty] | 20 | 5
8.1.15 | MTO.FOR STRAINER | [8 empty] | 20 | 5
8.2 | Piping M.R.
8.2.1 | M.R. for Pipes | [8 empty] | 20 | 5
8.2.2 | M.R. for Manual Valve | [8 empty] | 20 | 5
8.2.3 | M.R. for Flange | [8 empty] | 20 | 5
8.2.4 | M.R. for Gasket | [8 empty] | 20 | 5
8.2.5 | M.R. for Fitting | [8 empty] | 20 | 5
8.2.6 | M.R. for Bults & Nuts | [8 empty] | 20 | 5
8.2.7 | M.R. for Supports | [8 empty] | 20 | 5
8.2.8 | M.R. for Non-Metallic piping component | [8 empty] | 20 | 5
8.2.9 | M.R.FOR SPECIAL ITEMS | [8 empty] | 20 | 5
8.2.10 | M.R.FOR ORIFICE FLANGES | [8 empty] | 20 | 5
8.2.11 | M.R.FOR PAINT | [8 empty] | 20 | 5
8.2.12 | M.R.FOR COATING &WRAPPING | [8 empty] | 20 | 5
8.2.13 | M.R.FOR INSULATION | [8 empty] | 20 | 5
8.2.14 | M.R.FOR ELECTRODE | [8 empty] | 20 | 5
8.2.15 | M.R.FOR STRAINER | [8 empty] | 20 | 5
8.3 | Piping T.B.E.
8.3.1 | T.B.E. for Pipes | [8 empty] | 20 | 5
8.3.2 | T.B.E. for Manual Valve | [8 empty] | 20 | 5
8.3.3 | T.B.E. for Flange | [8 empty] | 20 | 5
8.3.4 | T.B.E. for Gasket | [8 empty] | 20 | 5
8.3.5 | T.B.E. for Fitting | [8 empty] | 20 | 5
8.3.6 | T.B.E. for Bults & Nuts | [8 empty] | 20 | 5
8.3.7 | T.B.E. for Non-Metallic piping component | [8 empty] | 20 | 5
8.3.8 | T.B.E.FOR SPECIAL ITEMS | [8 empty] | 20 | 5
8.3.9 | T.B.E.FOR ORIFICE FLANGES | [8 empty] | 20 | 5
8.3.10 | T.B.E.FOR INSULATION | [8 empty] | 20 | 5
8.3.11 | T.B.E.FOR STRAINER | [8 empty] | 20 | 5
9 | Pipe Line MTO. , M.R. and T.B.E.
9.1 | Pipe Line MTO
9.1.1 | M.T.O. for Metallic Pipeline and component | [8 empty] | 60 | 3
9.1.2 | M.T.O. for Non-Metallic Pipeline and component | [8 empty] | 40 | 3
9.2 | Pipe Line MR
9.2.1 | M.R. for Metallic Pipeline and component | [8 empty] | 40 | 10
9.2.2 | M.R. for Non-Metallic Pipeline and component | [8 empty] | 30 | 10
9.3 | Pipe Line TBE | [8 empty] | 80 | 20
9.3.1 | T.B.E.. for Metallic Pipeline and component | [8 empty] | 50 | 10
9.3.2 | T.B.E.. for Non-Metallic Pipeline and component | [8 empty] | 30 | 10
10 | خدمات مرتبط با اجرا و پس از اجرا
10.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [8 empty] | 610 | 208.6 | [14 empty] | 425
10.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [8 empty] | 305 | [15 empty] | 212.5
10.3 | سیاهه کالا (Material Take-off) پس از اجرا | [8 empty] | 120
10.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [8 empty] | 150
10.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [8 empty] | 80 | 8
| Total : | 65 | 49 | 0 | 45 | 0 | 0 | 0 | 17 | 7365 | 2302.6 | 0 | 6 | 0 | 34 | 66 | 33 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 4887.5
|  | 65 | 49 | 0 | 45 | 0 | 0 | 0 | 17 | 6100 | 2086 | 0 | 6 | 0 | 34 | 66 | 33 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 4250

## E.Instrument
Instrumentation Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification & Criteria
1.1 | Instrumentaion and Control Design Criteria | [11 empty] | 55
1.2 | Specification for Instrumentation | [11 empty] | 50
1.3 | Specification for FCS Control System | [11 empty] | 55
1.4 | Specification for Emergency Shutdown System | [11 empty] | 55
1.5 | Specification for Fire & Gas Detection and Alarm Systems | [11 empty] | 55
1.6 | Specification for Instrument Cables | [11 empty] | 40
1.8 | Specification for Instrumentation of Packaged Units | [11 empty] | 50
1.7 | specification for CCTV And Intruder detection System | [11 empty] | 8
1.8 | Specification forJB & Bulk Material | [11 empty] | 30
2 | Datasheet
2.1 | Data Sheet for Orifice Plates | 12 | [9 empty] | 40 | 20
2.2 | Data Sheet for Local Flow Indicators | 12 | [9 empty] | 40 | 20
2.3 | Data Sheet for Flow Switches | 12 | [9 empty] | 40 | 20
2.4 | Data Sheet for Flow Transmitters | 12 | [9 empty] | 40 | 20
2.5 | Data sheet for level Gage | 12 | [9 empty] | 40 | 20
2.6 | Data Sheet for Level Switches | 12 | [9 empty] | 40 | 20
2.7 | Data Sheet for Level Transmitters | 12 | [9 empty] | 40 | 20
2.8 | Data Sheet for Pressure Indicators (Gages) | 12 | [9 empty] | 40 | 20
2.9 | Data Sheet for Pressure Switches | 12 | [9 empty] | 40 | 20
2.10 | Data Sheet for Pressure & Diff. Pressure Transmitters | 12 | [9 empty] | 40 | 20
2.11 | Data Sheet for Temperature Indicators (Gages) | 12 | [9 empty] | 40 | 20
2.12 | Data Sheet for Temperature Switches | 12 | [9 empty] | 40 | 20
2.13 | Data Sheet for Temperature Transmitters | 12 | [9 empty] | 40 | 20
2.14 | Data Sheet for Control Valves | 12 | [9 empty] | 45 | 30
2.15 | Data Sheet for Safety & Relief Valve | 12 | [9 empty] | 45 | 30
2.16 | Datasheet for ESD & On/Off Valves | 12 | [9 empty] | 45 | 20
2.17 | Data Sheet for Corrosion Coupon & Corrosion Transmitters | 12 | [9 empty] | 45 | 20
2.18 | Datasheet for Analyzers | 12 | [9 empty] | 15 | 25
2.19 | Data sheet for regulator valve | 12 | [9 empty] | 25 | 20
2.20 | Data Sheet for Laboratory Test Equipments | 12 | [9 empty] | 15 | 40
2.21 | Data sheet for CCTV Equipment | [10 empty] | 100 | 40
2.22 | Datasheet for F&G Instrument | [6 empty] | 8 |  |  |  | 40 | 45
3 | List
3.1 | Instrument Index | 8 | [9 empty] | 90 | 30
3.2 | FCS I/O List | 4 | [9 empty] | 65 | 25
3.3 | ESD I/O List | 4 | [9 empty] | 60 | 25
3.4 | F&G I/O List | 4 | [9 empty] | 40 | 30
3.5 | Alarm & Trip Setpoint List | 4 | 8 | [8 empty] | 40 | 20
3.6 | Power Consumption List | [10 empty] | 25 | 30
3.7 | Instrument Air Consumption List | [10 empty] | 25 | 25
3.8 | Instrument Cable List | [10 empty] | 80 | 30
3.9 | CCTV Cable list | [10 empty] | 30 | 5
4 | Calculation
4.1 | Calculation for Control Valve | [10 empty] | 80 | 50
4.2 | Calculation for Safety & Relief Valve | [10 empty] | 80 | 50
4.3 | Calculation for Orifice Plates | [10 empty] | 80 | 50
4.4 | Calculation for Comp. Air Sup. | [10 empty] | 10 | 5
4.5 | FCS Risk Management Report | [10 empty] | 25 | 20
5 | Philosophy
5.1 | F&G Philosophy |  | 8 | [9 empty] | 80
6 | Layout
6.1 | Sample-4 Desalting Unit Layouts | [24 empty] | 335
6.1.1 | Desalting Unit Control Building arrangement Layout | [10 empty] | 40 | 20 |  |  |  |  | 2 | [7 empty] | 35
6.1.2 | Instrument Cable Routing for Desalting Unit Control Building | [10 empty] | 20 | 15 |  |  | 2 | 2 | [8 empty] | 35
6.1.3 | Instrument Location Layout of Desalting Unit |  | 4 |  | 4 | [6 empty] | 60 | 30 | [12 empty] | 65
6.1.4 | Instrument Main Cable Routing Layout for Desalting Unit | [10 empty] | 60 | 30 |  | 4 | 2 | 2 | [8 empty] | 65
6.1.5 | Instrument Air Layout for Desalting Unit | [9 empty] | 4 | 25 | 20 | [12 empty] | 55
6.1.6 | F&G Detection Layouts for Sample-4 Desalting Unit | [7 empty] | 4 |  |  | 65 | 30 | [12 empty] | 20
6.1.8 | CCTV Cable Rout and Equipment layout Drawing for Desalting Unit | [10 empty] | 40 | 10 |  |  | 1 | 1 | [8 empty] | 60
6.2 | Sample-4 Production Unit Layouts
6.2.1 | Production Unit Control Building arrangement Layout | [10 empty] | 20 | 10 |  |  |  |  | 2 | [7 empty] | 20
6.2.2 | Instrument Cable Routing for Production Unit Control Building | [10 empty] | 15 | 10 |  |  | 2 | 2 | [8 empty] | 20
6.2.3 | Instrument Location Layout of Production Unit |  | 4 |  | 4 | [6 empty] | 25 | 15 | [12 empty] | 30
6.2.4 | Instrument Main Cable Routing Layout for Production Unit | [10 empty] | 25 | 15 |  | 4 | 2 | 2 | [8 empty] | 30
6.2.5 | Instrument Air Layout for Production Unit | [10 empty] | 20 | 10 | [12 empty] | 20
6.3 | PU3 33KV Station Layouts | [24 empty] | 10
6.3.1 | F&G Detection Layouts for Sample-3 33KV Station | [7 empty] | 3 |  |  | 10 | 10 | [12 empty] | 15
6.3.1 | F&G cable Route for Sample-3 33KV Station | [7 empty] | 3 |  |  | 5 | 4 | [12 empty] | 10
7 | Instrument Diagrams
7.1 | Control System Architcture Diagram | [10 empty] | 30 | 45 | [12 empty] | 20
7.2 | F&G Cause & Effect Chart | [10 empty] | 30 | 50
7.4 | Loop Diagram For FCS System | [10 empty] | 80 | 25
7.5 | Loop Diagram For ESD System | [10 empty] | 75 | 25
7.6 | Loop Diagram For F&G System | [10 empty] | 75 | 25
7.7 | Logic Diagram for Instrument | [10 empty] | 80 | 40
7.8 | ESD Logic Block Diagram | 10 | 5 | [8 empty] | 80 | 10
7.9 | Junction Box Wiring Diagram For FCS | [10 empty] | 60 | 30
7.10 | Junction Box Wiring Diagram For ESD | [10 empty] | 55 | 30
7.11 | Junction Box Wiring Diagram For F&G | [10 empty] | 55 | 30
7.12 | Instrument Earthing Diagram | [10 empty] | 40 | 25
7.13 | CCTV system block diagram | [10 empty] | 80 | 30 | [12 empty] | 50
8 | Hook-Up & Mounting Diagrams
8.1 | Hook-Up for Instrument | [10 empty] | 30 | 15 | [12 empty] | 20
8.2 | Instrument Mounting Detail | [10 empty] | 40 | 25 | [12 empty] | 10
8.2 | Hook-Up for Instrument Air System | [10 empty] | 25 | 10 | [12 empty] | 10
9 | M.R., M.T.O. and T.B.E.
9.1 | M.T.O.
9.1.1 | MTO for Instrument Cables | [10 empty] | 40 | 10
9.1.2 | MTO for Instrument Bulk Material | [10 empty] | 40 | 10
9.1.3 | MTO for Junction Box & Glands | [10 empty] | 45 | 10
9.1.4 | MTO for Field Indtrumentation | [10 empty] | 50 | 10
9.1.5 | MTO for FCS System | [10 empty] | 20 | 10
9.1.6 | MTO for ESD System | [10 empty] | 30 | 10
9.1.7 | MTO for F&G System | [10 empty] | 50 | 10
9.1.8 | MTO for CCTV | [10 empty] | 20 | 10
9.1.9 | MTO for Laboratory Testing Equipment | [10 empty] | 20 | 10
9.1.10 | MTO for Packages Instrument | [10 empty] | 50 | 10
9.2 | M.R.
9.2.1 | MR for Orifice Plates | [10 empty] | 15 | 5
9.2.2 | MR for Local Flow Indicators | [10 empty] | 15 | 5
9.2.3 | MR for Flow Switches | [10 empty] | 15 | 5
9.2.4 | MR for Flow Transmitters | [10 empty] | 15 | 5
9.2.5 | MR for Level gauge | [10 empty] | 15 | 5
9.2.6 | MR for Level Switches | [10 empty] | 15 | 5
9.2.7 | MR for Level Transmitters | [10 empty] | 15 | 5
9.2.8 | MR for Pressure Indicators (Gages) | [10 empty] | 15 | 5
9.2.9 | MR for Pressure Switches | [10 empty] | 15 | 5
9.2.10 | MR for Pressure & Diff Pressure Transmitters | [10 empty] | 15 | 5
9.2.11 | MR for Temperature Indicators (Gages) | [10 empty] | 15 | 5
9.2.12 | MR for Temperature Switches | [10 empty] | 15 | 5
9.2.13 | MR for Temperature Transmitters | [10 empty] | 15 | 5
9.2.14 | MR for Control Valves | [10 empty] | 15 | 5
9.2.15 | MR for Safety & Relief Valves | [10 empty] | 15 | 5
9.2.16 | MR for ESD & On/Off Valves | [10 empty] | 15 | 5
9.2.17 | MR for Corrosion Coupon & Corrosion Transmitters | [10 empty] | 15 | 5
9.2.18 | MR for Analyzers | [10 empty] | 15 | 5
9.2.19 | MR for Regulators | [10 empty] | 15 | 5
9.2.20 | MR for FCS System | [10 empty] | 8 | 5
9.2.20 | MR for ESD System | [10 empty] | 8 | 5
9.2.21 | MR for F & G System & Equipment | [10 empty] | 15 | 5
9.2.22 | MR for Instrument Cables | [10 empty] | 15 | 5
9.2.23 | MR for Instrument Bulk Material | [10 empty] | 15 | 5
9.2.24 | MR for Junction Box & Glands | [10 empty] | 15 | 5
9.2.25 | M.R. for CCTV system | [10 empty] | 10 | 10
9.2.26 | MR For Laboratory Test Equipment | [10 empty] | 15 | 5
9.3 | T.B.E.
9.3.1 | TBE for Orifice Plates | [10 empty] | 20 | 40
9.3.2 | TBE for Local Flow Indicators | [10 empty] | 20 | 40
9.3.3 | TBE for Flow Switches | [10 empty] | 20 | 40
9.3.4 | TBE for Flow Transmitters | [10 empty] | 20 | 40
9.3.5 | TBE for Level gauge | [10 empty] | 20 | 40
9.3.6 | TBE for Level Switches | [10 empty] | 20 | 40
9.3.7 | TBE for Level Transmitters | [10 empty] | 20 | 40
9.3.8 | TBE for Pressure Indicators (Gages) | [10 empty] | 20 | 40
9.3.9 | TBE for Pressure Switches | [10 empty] | 20 | 40
9.3.10 | TBE for Pressure & Diff Pressure Transmitters | [10 empty] | 20 | 40
9.3.11 | TBE for Temperature Indicators (Gages) | [10 empty] | 20 | 40
9.3.12 | TBE for Temperature Switches | [10 empty] | 20 | 40
9.3.13 | TBE for Temperature Transmitters | [10 empty] | 20 | 40
9.3.14 | TBE for Control Valves | [10 empty] | 20 | 40
9.3.15 | TBE for Safety & Relief Valves | [10 empty] | 20 | 40
9.3.16 | TBE for ESD & On/Off Valves | [10 empty] | 20 | 40
9.3.17 | TBE for Corrosion Coupon & Corrosion Transmitters | [10 empty] | 20 | 40
9.3.18 | TBE for Analyzers | [10 empty] | 20 | 40
9.3.19 | TBE for Regulators | [10 empty] | 20 | 40
9.3.20 | TBE for FCS System | [10 empty] | 20 | 40
9.3.20 | TBE for ESD System | [10 empty] | 20 | 40
9.3.21 | TBE for F&G Equipment | [10 empty] | 20 | 40
9.3.22 | TBE for Instrument Cables | [10 empty] | 20 | 40
9.3.23 | TBE for Instrument Bulk Material | [10 empty] | 20 | 40
9.3.24 | TBE for Junction Box & Glands | [10 empty] | 20 | 40
9.3.25 | T.B.E. for CCTV system | [10 empty] | 50 | 60
9.3.26 | TBE For Laboratory Test Equipment | [10 empty] | 20 | 40
10 | Review of Suppliers Technical Document
10.1 | Review of technical document for Orifice Plates | 8 | [9 empty] | 60 | 40
10.2 | Review of technical document for Local Flow Indicators | 8 | [9 empty] | 60 | 40
10.3 | Review of technical document for Flow Switches | 8 | [9 empty] | 60 | 40
10.4 | Review of technical document for Flow Transmitters | 8 | [9 empty] | 60 | 40
10.5 | Review of technical document for Level gauge | 8 | [9 empty] | 60 | 40
10.6 | Review of technical document for Level Switches | 8 | [9 empty] | 60 | 40
10.7 | Review of technical document for Level Transmitters | 8 | [9 empty] | 60 | 40
10.8 | Review of technical document for Pressure Indicators (Gages) | 8 | [9 empty] | 60 | 40
10.9 | Review of technical document for Pressure Switches | 8 | [9 empty] | 60 | 40
10.10 | Review of technical document for Pressure & Diff Pressure Transmitters | 8 | [9 empty] | 60 | 40
10.11 | Review of technical document for Temperature Indicators (Gages) | 8 | [9 empty] | 60 | 40
10.12 | Review of technical document for Temperature Switches | 8 | [9 empty] | 60 | 40
10.13 | Review of technical document for Temperature Transmitters | 8 | [9 empty] | 60 | 40
10.14 | Review of technical document for Control Valves | 8 | [9 empty] | 70 | 55
10.15 | Review of technical document for Safety & Relief Valves | 8 | [9 empty] | 70 | 55
10.16 | Review of technical document for ESD & On/Off Valves | 8 | [9 empty] | 70 | 55 | 8
10.17 | Review of technical document for Corrosion Coupon & Corrosion Transmitters | 8 | [9 empty] | 60 | 50
10.18 | Review of technical document for Analyzers | 8 | [9 empty] | 40 | 50
10.19 | Review of technical document for Regulators | 8 | [9 empty] | 40 | 50
10.20 | Review of technical document for FCS & ESD System | 8 | [9 empty] | 60 | 75
10.21 | Review of technical document for F & G System & Equipment | 8 | [5 empty] | 5 |  |  |  | 60 | 75
10.22 | Review of technical document for Instrument Cables | 8 | [9 empty] | 50 | 40
10.23 | Review of technical document for Instrument Bulk Material | 8 | [9 empty] | 45 | 40
10.24 | Review of technical document for Junction Box & Glands | 8 | [9 empty] | 40 | 40
10.25 | Review of technical document of CCTV | [10 empty] | 80 | 15 | [8 empty] | 80 | 15
10.26 | Review of technical document for Laboratory Test Equipment | 10 | [9 empty] | 40 | 60
11 | خدمات مرتبط با اجرا و پس از اجرا
11 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [10 empty] | 571.6 | 456.7 | [12 empty] | 93.5
11.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [10 empty] | 285.8 | [13 empty] | 46.75
11.3 | سیاهه کالا (Material Take-off) پس از اجرا | [10 empty] | 120
11.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [10 empty] | 100
11.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [10 empty] | 40 | 8
| TOTAL : | 476 | 29 | 0 | 8 | 0 | 0 | 13 | 10 | 0 | 4 | 6833.4 | 5031.7 | 8 | 8 | 9 | 9 | 4 | 0 | 0 | 0 | 80 | 15 | 0 | 0 | 1075.25
|  | 476 | 29 | 0 | 8 | 0 | 0 | 13 | 10 | 0 | 4 | 5716 | 4567 | 8 | 8 | 9 | 9 | 4 | 0 | 0 | 0 | 80 | 15 | 0 | 0 | 935

## E.Electrical
Electrical Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification, Criteria, Standard Drawing
1.1 | Electrical Design Criteria & Philosophy | [13 empty] | 20
1.2 | Specification for neutral grounding resistor | [13 empty] | 10
1.3 | Specification for DC System | [13 empty] | 20
1.4 | Specification for Diesel Generator | [13 empty] | 20
1.5 | Specification for Electrical Bulk Material | [13 empty] | 20
1.6 | Specification for Grounding & lightning system | [13 empty] | 10
1.7 | Specification for LV Induction Motors | [13 empty] | 15
1.8 | Specification for LV Switchgears | [13 empty] | 20
1.9 | Specification for MV Induction Motors | [13 empty] | 20
1.10 | Specification for MV Switchgears | [13 empty] | 20
1.11 | Specification for Package Units | [13 empty] | 10
1.12 | Specification for Transformers | [13 empty] | 20
1.13 | Specification for UPS System | [13 empty] | 20
1.14 | Specification for Capacitor Banks | [13 empty] | 10
1.15 | Specification for Transmission Lines | [13 empty] | 20
1.16 | Specification for LV Cables and Wires | [13 empty] | 10
1.17 | Specification for MV Power Cables | [13 empty] | 20
1.18 | Typical Lighting Details Drawing | [12 empty] | 15 | [11 empty] | 10
1.19 | Typical Earthing Details drawing | [12 empty] | 15 | [11 empty] | 10
2 | Electrical Equipment Datasheet
2.1 | Data Sheet for Battery & Battery Charger | [12 empty] | 40 | 10
2.2 | Data Sheet for UPS | [12 empty] | 40 | 10
2.3 | Data Sheet for Transformers | [12 empty] | 40 | 10
2.4 | Data Sheet for Diesel Generator |  |  |  | 4 | [8 empty] | 40 | 10
2.5 | Data Sheet for Transmission Lines | [12 empty] | 40 | 10
2.6 | Data Sheet for Induction Motors (LV ) | [12 empty] | 60 | 10
2.7 | Data Sheet for Induction Motors (MV ) | [12 empty] | 40 | 10
2.8 | Data Sheet For LV Capacitor Bank | [12 empty] | 40 | 10
2.9 | Data Sheet For LV & MV Switchgears | [12 empty] | 40 | 10
2.10 | Data Sheet for Neutral Earthing Resistors | [12 empty] | 40 | 10
2.11 | Datasheet for 33KV for Outdoor Disconnector Switch | [12 empty] | 40 | 10
2.12 | Datasheet for 33KV for Outdoor Line Equipment | [12 empty] | 30 | 8
2.13 | Datasheet for 33KV for Outdoor Circuit Breaker | [12 empty] | 30 | 8
2.14 | Datasheet for 33KV for Earthing Switch | [12 empty] | 30 | 8
2.15 | Datasheet for 33KV for Current Transformer | [12 empty] | 30 | 8
2.16 | Datasheet for 33KV for Capacitor Transformer | [12 empty] | 30 | 8
3 | Electrical List
3.1 | Electrical Load List | 5 |  | 30 | [9 empty] | 120 | 50
3.2 | Power & Control cable List for Sample-4 Desalting Plant |  |  | 3 | [9 empty] | 180 | 40
3.3 | Power & Control cable List for Sample-3 33kv outdoor Station |  |  | 2 | [9 empty] | 150 | 40
3.4 | Power & Control cable List for Sample-4 Production Unit |  |  | 1 | [9 empty] | 80 | 35
3.5 | Power & Control cable List for Sample-4 33kv outdoor Station |  |  | 1 | [9 empty] | 150 | 35
3.6 | Power cable list for 33 kv station |  |  | 1 | [9 empty] | 50 | 15
3.7 | Lighting Cable List | [12 empty] | 150 | 30
4 | Single Line Diagram
4.1 | General Single Line Diagram
4.1.1 | Electrical & Telecom. Symbol List & Legend | [12 empty] | 5 | [11 empty] | 10
4.1.2 | Overal Single Line Diagram for Sample D.E.4 | [12 empty] | 60 | 40 | [10 empty] | 80
4.1.3 | L.V. Single Line Diagram for Sample D.E.4 | [12 empty] | 60 | 30 | [10 empty] | 80
4.1.4 | M.V. Single Line Diagram for Sample D.E.4 | [12 empty] | 40 | 20 | [10 empty] | 50
4.1.5 | Overal Single Line Diagram for Sample-3 33KV outdoor substation | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.6 | Overal Single Line Diagram for Sample-4 33KV outdoor substation | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.7 | SLD for Main MV Switchgear (33 KV) in Sample-3 outdoor substation | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.8 | SLD for Main MV Switchgear (3.3 KV) in Sample-4 outdoor substation | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.9 | Overal Single Line Diagram for Sample P.U.4 | [12 empty] | 50 | 35 | [10 empty] | 80
4.1.10 | L.V. Single Line Diagram for Sample P.U.4 | [12 empty] | 60 | 40 | [10 empty] | 50
4.1.11 | M.V. Single Line Diagram for Sample P.U.4 | [12 empty] | 20 | 20 | [10 empty] | 50
4.1.12 | UPS System Single Line Diagram | [12 empty] | 30 | 20 | [10 empty] | 50
4.1.13 | 110VDC Power Supply Single Line Diagram | [12 empty] | 25 | 10 | [10 empty] | 40
4.1.14 | 24VDC Power Supply Single Line Diagram | [12 empty] | 25 | 10 | [10 empty] | 40
4.1.15 | Area Lighting Panel Single Line Diagram Sample D.E | [12 empty] | 25 | 10 | [10 empty] | 70
4.1.16 | Single line Diagram Main Normal/emergency Lighting Distribution Panel D.E | [12 empty] | 30 | 10 | [10 empty] | 80
4.1.17 | Single line Diagram Main Distribution Panel out door substation | [12 empty] | 10 | 10 | [10 empty] | 30
4.1.18 | Single line Diagram Main Normal/emergency Distribution Panel 33kv station | [12 empty] | 10 | 10 | [10 empty] | 30
4.1.19 | Area Lighting Panel Single Line Diagram for PU3 33kv station | [12 empty] | 10 | 10 | [10 empty] | 30
4.1.20 | Area Lighting Panel Single Line Diagram for PU4 33kv station | [12 empty] | 10 | 10 | [10 empty] | 30
4.1.21 | Control, Protection & Metering Schematic Diagrams for 3.3 & 33 KV Switchgear | [12 empty] | 40 | 10 | [10 empty] | 60
4.1.22 | Control, Protection & Metering Schematic Diagrams for 3.3 MV MCC of DP4 | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.23 | Control, Protection & Metering Schematic Diagrams for 3.3 MV MCC of PU4 | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.24 | Control, Protection & Metering Schematic Diagrams for LV MCC of DP4 | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.25 | Control, Protection & Metering Schematic Diagrams for LV MCC of PU4 | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.26 | Control, Protection & Metering Schematic Diagrams for 33KV Sample-4 33KV Station | [12 empty] | 20 | 10 | [10 empty] | 40
4.1.27 | Logic Diagram For MV Switchgears | [12 empty] | 40 | 10 | [10 empty] | 40
4.1.28 | Logic Diagram For LV Switchgears | [12 empty] | 40 | 10 | [10 empty] | 40
4.2 | Single Line Diagram for Buildings
4.2.1 | SLD for lighting Distribution for Air Compressor Room & Emergency Diesel Generator Building | [12 empty] | 10 | 2 | [10 empty] | 20
4.2.2 | SLD for lighting Distribution for Control &Telecommunication Building | [12 empty] | 20 | 2 | [10 empty] | 40
4.2.3 | SLD for lighting Distribution for Guard House | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.4 | SLD for lighting Distribution for DE4 Substation Building | [12 empty] | 15 | 2 | [10 empty] | 40
4.2.5 | SLD for lighting Distribution for DE4 Chemical storage shelter no.1 | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.6 | SLD for lighting Distribution for DE4 Chemical storage shelter no.2 | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.7 | SLD for lighting Distribution for DE4 Chemical injection package shelter no.1 | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.8 | SLD for lighting Distribution for DE4 Chemical injection package shelter no.2 | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.9 | SLD for lighting Distribution for DE4 Process Pumps shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.10 | SLD for lighting Distribution for DE4 Dilution Water Pumps shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.11 | SLD for lighting Distribution for DE4 Waste Water Pumps shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.12 | SLD for lighting Distribution for DE4 Dearated Water Pumps shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.13 | SLD for lighting Distribution for DE4 Fire Water Pumps shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.14 | SLD for lighting Distribution Extension For PU4 Switchgear Room | [12 empty] | 10 | 2 | [10 empty] | 20
4.2.15 | SLD for lighting Distribution Extension Of Control Building For PU4 | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.16 | SLD for lighting Distribution for PU4 pump shelter | [12 empty] | 10 | 2 | [10 empty] | 15
4.2.17 | SLD for lighting Distribution for PU4 Chemical storage shelter | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.18 | SLD for lighting Distribution for PU4 Chemical injection package shelter | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.19 | SLD for lighting Distribution For PU4 Accommodation Building | [12 empty] | 10 | 2 | [10 empty] | 30
4.2.20 | SLD for lighting Distribution for PU4 Air Compressor Room | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.21 | SLD for lighting Distribution for Laboratory | [12 empty] | 10 | 2 | [10 empty] | 30
4.2.22 | SLD for lighting Distribution for Work Shop | [12 empty] | 10 | 2 | [10 empty] | 20
4.2.23 | SLD for lighting Distribution for 3.3 Switch Gear Building Of PU4 Outdoor Substaion | [12 empty] | 10 | 2 | [10 empty] | 30
4.2.24 | SLD for lighting Distribution for 33 KV Switch Gear Building Of 33 KV Station | [12 empty] | 10 | 2 | [10 empty] | 30
4.2.25 | SLD for lighting Distribution for 33 KV Station Guard House | [12 empty] | 10 | 2 | [10 empty] | 10
4.2.26 | SLD for lighting Distribution for 33 KV Station Diesel Generator Building | [12 empty] | 10 | 2 | [10 empty] | 30
5 | Calculations
5.1 | Lighting Calculation | [12 empty] | 80 | 10
5.2 | Grounding Calculation | [12 empty] | 60 | 10
5.3 | Cable Sizing Calculation | [12 empty] | 90 | 10
5.4 | Relay Setting | [12 empty] | 60 | 10
5.5 | Capacitor Bank Capacity Calculation | [12 empty] | 20 | 10
5.6 | 110 V AC UPS Calculation | [12 empty] | 20 | 10
5.7 | DC UPS Calculation | [12 empty] | 20 | 10
5.8 | Power System Study (Short Circuit, load flow, motor starting) | [12 empty] | 100 | 10
5.9 | Diesel Generator Calculation | [12 empty] | 40 | 10
5.10 | Transmission Line Calculation | [12 empty] | 20 | 5
5.11 | Calculation for 33 & 66 KV String Insulator | [12 empty] | 25 | 5
5.12 | NGR Calculation | [12 empty] | 15 | 5
5.13 | Lightning Calculation in Sample-4 Desalting Unit | [12 empty] | 15 | 5
5.14 | Lightning Arrester Calculation for 33KV Outdorr Switchgear in Sample-4 Station | [12 empty] | 15 | 5
5.15 | Lightning Protection Calculation for 33KV Outdorr Switchgear in Sample-4 Station | [12 empty] | 15 | 5
6 | Drawings & Layouts
6.1 | Cable Routs
6.1.1 | Overal main Cable Route for Sample P.U 4 |  |  | 4 | [5 empty] | 4 |  | 2 |  | 50 | 10 | 4 | [9 empty] | 120
6.1.2 | Overal main Cable Route for Sample D.E.4 |  |  | 3 | [5 empty] | 3 |  | 2 |  | 30 | 5 | 4 | [9 empty] | 60
6.1.3 | Overal main Cable Route for PU3 Sample 33kv station |  |  | 2 | [5 empty] | 2 |  | 1 |  | 10 | 3 | 2 | [9 empty] | 25
6.1.4 | Overal main Cable Route for PU4 outdoor substation |  |  | 2 | [5 empty] | 2 |  | 1 |  | 10 | 3 | 2 | [9 empty] | 25
6.1.5 | Cable Route Between Desalting Unit and PU4 33/3.45KV Station | [12 empty] | 10 | 3 | 4 | [9 empty] | 25
6.1.6 | Cable Route Between NGL-1200 station and PU3 33KV Station | [12 empty] | 10 | 3 | 4 | [9 empty] | 25
6.1.7 | Overal main Cable Route for Offsite Areas | [12 empty] | 20 | 5 | 3 | [9 empty] | 25
6.1.8 | Overal main Cable Route for Diesel Generator Room | [12 empty] | 20 | 5 | 2 | [9 empty] | 25
6.1.9 | Overal main Cable Route for Switchgear Building Sample D.E.4 | [12 empty] | 40 | 8 | 2 | [9 empty] | 30
6.1.10 | Overal main Cable Route for Workshop | [12 empty] | 20 | 3 | 2 | [9 empty] | 25
6.1.11 | Overal main Cable Route for DE4 Telecom Room | [12 empty] | 20 | 3 | 2 | [9 empty] | 25
6.2 | Switchgears Equipment Arrangemenst
6.2.1 | Equipment Equipment Layout for Switchgear Building Sample D.E.4 | [12 empty] | 30 | 5 | [10 empty] | 80
6.2.2 | Equipment Equipment Layout for Switchgear Building Sample P.U.4 | [12 empty] | 10 | 2 | [10 empty] | 30
6.2.3 | Equipment Equipment Layout for Switchgear Building of Sample-4 outdoor Station | [12 empty] | 10 | 2 | [10 empty] | 30
6.2.4 | Equipment Equipment Layout for Switchgear Building of Sample-3 outdoor Station | [12 empty] | 10 | 2 | [10 empty] | 30
6.3 | Area Lighting
6.3.1 | Area Lighting layout for Sample D.E.4 | [12 empty] | 15 | 2 | [10 empty] | 80
6.3.2 | Area Lighting layout for Sample PU4 outdoor substation | [12 empty] | 10 | 2 | [10 empty] | 30
6.3.3 | Area Lighting layout forSample PU3 33kv station | [12 empty] | 10 | 2 | [10 empty] | 30
6.4 | Buildings Lighting Layout
6.4.1 | Lighting layout for Air Compressor Room & Emergency Diesel Generator Building | [12 empty] | 5 | [11 empty] | 10
6.4.2 | Lighting layout for Control &Telecommunication Building | [12 empty] | 5 | [11 empty] | 25
6.4.3 | Lighting layout for Guard House | [12 empty] | 5 | [11 empty] | 15
6.4.4 | Lighting layout for DE4 Substation Building | [12 empty] | 5 | [11 empty] | 25
6.4.5 | Lighting layout for DE4 Chemical storage shelter no.1 | [12 empty] | 3 | [11 empty] | 10
6.4.6 | Lighting layout for DE4 Chemical storage shelter no.2 | [12 empty] | 3 | [11 empty] | 10
6.4.7 | Lighting layout for DE4 Chemical injection package shelter no.1 | [12 empty] | 3 | [11 empty] | 10
6.4.8 | Lighting layout for DE4 Chemical injection package shelter no.2 | [12 empty] | 3 | [11 empty] | 10
6.4.9 | Lighting layout for DE4 Process Pumps shelter | [12 empty] | 3 | [11 empty] | 10
6.4.10 | Lighting layout for DE4 Dilution Water Pumps shelter | [12 empty] | 3 | [11 empty] | 10
6.4.11 | Lighting layout for DE4 Waste Water Pumps shelter | [12 empty] | 3 | [11 empty] | 10
6.4.12 | Lighting layout for DE4 Dearated Water Pumps shelter | [12 empty] | 3 | [11 empty] | 10
6.4.13 | Lighting layout for DE4 Fire Water Pumps shelter | [12 empty] | 3 | [11 empty] | 10
6.4.14 | Lighting layout Extension For PU4 Switchgear Room | [12 empty] | 3 | [11 empty] | 25
6.4.15 | Lighting layout Extension Of Control Building For PU4 | [12 empty] | 2 | [11 empty] | 5
6.4.16 | Lighting layout for PU4 pump shelter | [12 empty] | 3 | [11 empty] | 10
6.4.17 | Lighting layout for PU4 Chemical storage shelter | [12 empty] | 3 | [11 empty] | 10
6.4.18 | Lighting layout for PU4 Chemical injection package shelter | [12 empty] | 3 | [11 empty] | 10
6.4.19 | Lighting layout For PU4 Accommodation Building | [12 empty] | 5 | [11 empty] | 10
6.4.20 | Lighting layout for PU4 Air Compressor Room | [12 empty] | 5 | [11 empty] | 10
6.4.21 | Lighting layout for Laboratory | [12 empty] | 10 | [11 empty] | 25
6.4.22 | Lighting layout for Work Shop | [12 empty] | 5 | [11 empty] | 20
6.4.23 | Lighting layout for 3.3 Switch Gear Building Of PU4 Outdoor Substaion | [12 empty] | 5 | [11 empty] | 20
6.4.24 | Lighting layout for 33 KV Switch Gear Building Of 33 KV Station | [12 empty] | 5 | [11 empty] | 20
6.4.25 | Lighting layout for 33 KV Station Guard House | [12 empty] | 5 | [11 empty] | 10
6.4.26 | Lighting layout for 33 KV Station Diesel Generator Building | [12 empty] | 5 | [11 empty] | 20
6.5 | Area Earthing Layout
6.5.1 | Overal Earthing Layout for Sample D.E. | [12 empty] | 50 | 5 | [10 empty] | 80
6.5.2 | Overal Earthing Layout for Sample PU4 Extension Area | [12 empty] | 10 | 2 | [10 empty] | 40
6.5.3 | Overal Earthing Layout for Sample outdoor substation | [12 empty] | 10 | 2 | [10 empty] | 40
6.5.4 | Overal Earthing Layout for 33kv station | [12 empty] | 10 | 2 | [10 empty] | 40
6.6 | Buildings Earthing Layout
6.6.1 | Earthing Layout for Substations Sample D.E. | [12 empty] | 10 | 2 | [10 empty] | 30
6.6.2 | Earthing Layout for Substations 33kv station | [12 empty] | 10 | 2 | [10 empty] | 30
6.6.3 | Earthing Layout for Substations Sample out door substation | [12 empty] | 5 | 2 | [10 empty] | 20
6.6.4 | Earthing Layout for Control Room | [12 empty] | 10 | 2 | [10 empty] | 40
6.6.5 | Earthing Layout for Chemical Shelter | [12 empty] | 5 | 2 | [10 empty] | 10
6.6.6 | Earthing Layout for Pump Shelter | [12 empty] | 5 | 2 | [10 empty] | 10
6.7 | Hazardous Area Classification
6.7.1 | Hazardous Area Classification for Sample D.E.4 | [12 empty] | 20 | 5 | [10 empty] | 20
6.7.2 | Hazardous Area Classification for Sample P.U.4 | [12 empty] | 20 | 5 | [10 empty] | 20
7 | M.R , M.T.O, and T.B.E.
7.1 | M.T.O.(s)
7.1.1 | M.T.O. for Cables and Bulk | [12 empty] | 80 | 10
7.1.2 | M.T.O for cables | [12 empty] | 120 | 10
7.1.3 | M.T.O for cables of out door substation | [12 empty] | 50 | 10
7.1.4 | M.T.O for cables of 33kv station | [12 empty] | 50 | 10
7.1.5 | M.T.O for Earthing & lightning equipment | [12 empty] | 150 | 25
7.1.6 | MTO for tower &gantry for 33kv transmission line | [12 empty] | 50 | 10
7.1.7 | MTO for Transmission Lines | [12 empty] | 40 | 10
7.1.8 | MTO for NGR | [12 empty] | 20 | 5
7.1.9 | MTO for Capacitor Banks | [12 empty] | 20 | 5
7.2 | M.R.(s)
7.2.1 | M.R. for UPS & DC System | [12 empty] | 25 | 15
7.2.2 | M.R. for Transformer | [12 empty] | 25 | 10
7.2.3 | M.R. for Diesel Generator | [12 empty] | 15 | 10
7.2.4 | M.R. for control & protection panels | [12 empty] | 20 | 15
7.2.5 | M.R. for LV/MV Switchgears | [12 empty] | 25 | 15
7.2.6 | M.R. for Capacitor Bank | [12 empty] | 10 | 5
7.2.7 | M.R. for Cables | [12 empty] | 25 | 20
7.2.8 | M.R. for Lighting Panel | [12 empty] | 20 | 15
7.2.9 | M.R. for Cable Gland & LCS | [12 empty] | 20 | 15
7.2.10 | M.R. for cable tray & ladder | [12 empty] | 30 | 15
7.2.11 | M.R. for Electrical Bulk Material | [12 empty] | 50 | 25
7.2.12 | M.R. for Lighting Material | [12 empty] | 40 | 15
7.2.13 | M.R for Neutral Earthing Resistor | [12 empty] | 30 | 10
7.2.14 | M.R for bus duct | [12 empty] | 20 | 5
7.3 | T.B.E.(s)
7.3.1 | T.B.E. for UPS & battery charger | [12 empty] | 40 | 15
7.3.2 | T.B.E. for Transformer | [12 empty] | 40 | 10
7.3.3 | T.B.E. for Diesel Generator | [12 empty] | 40 | 10
7.3.4 | T.B.E. for Main LV/MV Switchgears | [12 empty] | 80 | 30
7.3.5 | T.B.E. for bus duct | [12 empty] | 30 | 10
7.3.6 | T.B.E. for Cable | [12 empty] | 80 | 40
7.3.7 | T.B.E for Cable Gland & LCS | [12 empty] | 40 | 20
8 | Review of Suppliers Technical Document
8.1 | Review of technical document ups & battery charger | [12 empty] | 300 | 50
8.2 | Review of technical document for transformers | [12 empty] | 250 | 30
8.3 | Review of technical document for diesel generator |  |  | 30 | 4 | [8 empty] | 200 | 30
8.4 | Review of technical document for LV/MV switchgear | [12 empty] | 500 | 150
8.5 | Review of technical document for bus duct | [12 empty] | 100 | 20
8.6 | Review of technical document for cable | [12 empty] | 50 | 15
8.7 | Review of technical document for gland & LCS | [12 empty] | 50 | 15
9 | خدمات مرتبط با اجرا و پس از اجرا
9.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [12 empty] | 65.01 | 208.8 | [10 empty] | 328
9.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [12 empty] | 325.05 | [11 empty] | 164
9.3 | سیاهه کالا (Material Take-off) پس از اجرا | [12 empty] | 120
9.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [12 empty] | 100
9.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [12 empty] | 50 | 8
| TOTAL : | 5 | 0 | 79 | 8 | 0 | 0 | 0 | 0 | 11 | 0 | 6 | 0 | 7161.06 | 2304.8 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3772
|  | 5 | 0 | 79 | 8 | 0 | 0 | 0 | 0 | 11 | 0 | 6 | 0 | 6501 | 2088 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3280

## E.TELECOM
Telecommunication Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification and Criteria
1.1 | Specification for Radio System | [21 empty] | 8
1.2 | specification for telephony and paging system | [21 empty] | 8
1.3 | Telecom typical installation Detail | [20 empty] | 20 | 5 |  |  | 30
2 | Data sheet for Telecom Equipment | [20 empty] | 80 | 40
3 | Paging Calculation | [20 empty] | 70 | 30
4 | Buildings Telecom Block Diagram
4.1 | telephone system block diagram | [20 empty] | 80 | 30 |  |  | 30
4.2 | paging system block diagram | [20 empty] | 60 | 20 |  |  | 30
5 | Buildings Telecom. system Layout
5.1 | Telephone andpaging Layout for Control &Telecommunication Building | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 40
5.2 | Telephone andpaging Layout for DE4 Guard House | [12 empty] | 1 | [7 empty] | 5 |  |  |  | 20
5.3 | Telephone andpaging Layout for DE4 Substation Building | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 30
5.4 | Telephone andpaging Layout Extension For PU4 Switchgear Room | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 40
5.5 | Telephone andpaging Layout For Accommodation Building in PU4 | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 30
5.6 | Telephone andpaging Layout for Laboratory | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 40
5.7 | Telephone andpaging Layout for Work Shop | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 30
5.8 | Telephone andpaging Layout fo33 KV Switch Gear Building Of 33 KV Station | [12 empty] | 1 | [7 empty] | 10 |  |  |  | 40
5.9 | Telephone andpaging Layout fo33 KV Station Guard House | [12 empty] | 1 | [7 empty] | 5 |  |  |  | 20
6 | Site Telecom. system Layout & List
6.1 | Telecom equipment layout drawing for Desalting Unit | [12 empty] | 1 | [7 empty] | 15 | 5 |  |  | 40
6.2 | Telecom equipment layout drawing for Production Unit Extension | [12 empty] | 1 | [7 empty] | 10 | 2 |  |  | 20
6.3 | Telecom system cable routing drawing for Desalting Unit | [12 empty] | 1 | [7 empty] | 25 | 2 |  |  | 60
6.4 | Telecom system cable routing drawing for Production Unit Extension | [12 empty] | 1 | [7 empty] | 10 | 2 |  |  | 20
6.5 | Telecom system Cable list for Desalting Unit | [12 empty] | 1 | [7 empty] | 50 | 5
6.6 | Telecom system Cable list for Production Unit Extension | [12 empty] | 1 | [7 empty] | 20 | 3
7 | MTO
7.1 | M.T.O. for Telephone system | [20 empty] | 10 | 3
7.2 | M.T.O. for Paging System | [20 empty] | 10 | 3
7.3 | M.T.O. for Radio system | [20 empty] | 10 | 3
7.5 | M.T.O. for Telephone Cable | [20 empty] | 20 | 5
8 | M.R. and T.B.E.
8.1 | M.R. for Telephone system | [20 empty] | 10 | 3
8.2 | M.R. for Paging/Intercom | [20 empty] | 10 | 3
8.3 | M.R. for Radio system | [20 empty] | 10 | 3
8.5 | T.B.E. for Telephone system | [20 empty] | 30 | 10
8.6 | T.B.E. for Paging/Intercom | [20 empty] | 30 | 10
8.8 | T.B.E. for Radio system | [20 empty] | 30 | 10
9 | Review of Suppliers Technical Document
9.1 | Review of technical document of Telephone System | [20 empty] | 80 | 15
9.2 | Review of technical document of Paging/Intercom System | [20 empty] | 80 | 15
9.3 | Review of technical document of Radio System | [20 empty] | 60 | 15
10 | خدمات مرتبط با اجرا و پس از اجرا
10.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [20 empty] | 91 | 25.8 |  |  | 52
10.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [20 empty] | 45.5 |  |  |  | 26
1-.3 | سیاهه کالا (Material Take-off) پس از اجرا | [20 empty] | 50
10.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [20 empty] | 60
10.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [20 empty] | 30 | 8
| Total : | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1186.5 | 291.8 | 0 | 0 | 598
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 910 | 258 | 0 | 0 | 520

## E.Civil
Civil Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specifications and Design Criteria
1.1 | Design Criteria for Civil Works | [14 empty] | 20 | 8
1.2 | Specification for Earth Works | [14 empty] | 20 | 8
1.3 | Specification for Grading and slope protection | [14 empty] | 16 | 8
1.4 | Specification for fence and gate | [14 empty] | 16 | 8
1.5 | Specification for Sanitary sewer | [14 empty] | 16 | 8
1.6 | Specification for Sewers, Drainage and Underground Systems | 4 | 2 |  |  |  |  | 2 | 1 | 4 | 2 |  |  |  |  | 16 | 8
1.7 | Specification for paving | [14 empty] | 16 | 8
1.8 | Scope of work for Geotechnic | [14 empty] | 16 | 8
1.9 | Scope Of Surveying Work For EPC Contractor | [14 empty] | 16 | 8
1.10 | مشخصات فني فضاي سبز پروژه | [14 empty] | 16 | 8
1.11 | شرح خدمات فضاي سبز پروژه | [14 empty] | 16 | 8
1.12 | Specification for potable water treatment package |  |  | 4 | 2 | [6 empty] | 2 | 1 | 4 | 2 | 16 | 8
1.13 | Specification for sanitary wastewater treatment package |  |  | 4 | 2 |  |  | 2 | 1 |  |  | 2 | 1 | 4 | 2 | 16 | 8
1.14 | Specification for Fireproofing | [14 empty] | 16 | 8
1.15 | Roeport on civil material selection | [14 empty] | 15 | 5
2 | Typical and standard Drawings
2.1 | Typical Civil Detail Drawing | [14 empty] | 20 | 10 | [8 empty] | 30
2.2 | Typical Evaporation Pond Drawing | [14 empty] | 8 | 2 | [8 empty] | 8
2.3 | Typical Fencing Detail Drawing | [14 empty] | 8 | 2 | [8 empty] | 8
2.4 | Typical Irrigation Ditch Crossing For Pipelines | [14 empty] | 8 | 2 | [8 empty] | 8
2.5 | Typical Detail For Crossing Of Existing Facilities | [14 empty] | 8 | 2 | [8 empty] | 8
2.6 | Typical Details For Watercourse And Minor Stream Crossing | [14 empty] | 8 | 2 | [8 empty] | 8
2.7 | Typical Details For Warning Slab & Bearing Slab | [14 empty] | 8 | 2 | [8 empty] | 8
2.8 | Typical Details For R.O.W. Sections - Single Pipeline | [14 empty] | 8 | 2 | [8 empty] | 8
2.9 | Typical Details For Major And Minor Road Crossing | [14 empty] | 8 | 2 | [8 empty] | 8
2.10 | Typical Pipeline Details For Continuous Concrete Coating | [14 empty] | 8 | 2 | [8 empty] | 8
2.11 | Typical Pipeline Details For Irish Crossing | [14 empty] | 8 | 2 | [8 empty] | 8
2.12 | Typical Pipeline Details For Pipeline Marker | [14 empty] | 8 | 2 | [8 empty] | 8
2.13 | Typical Details For Existing Above Ground Pipelines Crossing | [14 empty] | 8 | 2 | [8 empty] | 8
2.14 | Typical Details For Anchor Block | [14 empty] | 8 | 2 | [8 empty] | 8
2.15 | Typical Pipeline detail for Set on weight | [14 empty] | 8 | 2 | [8 empty] | 8
2.16 | Typical Culvert Details For Pipelines | [14 empty] | 8 | 2 | [8 empty] | 8
2.17 | Typical Detail for Stoppage - Backfill on Slope(Pipeline Hillside Anchor) | [14 empty] | 8 | 2 | [8 empty] | 8
2.18 | Typical Detail for Gabion | [14 empty] | 8 | 2 | [8 empty] | 8
2.19 | Typical Road Cross Section for Access Earth Road | [14 empty] | 8 | 2 | [8 empty] | 8
2.20 | Standard Civil Drawing for U.G. | [14 empty] | 20 | 4
3 | Plan and Profile for Pipeline and Transition line
3.1 | Plan and profile for Production Unit-4 to Desalting Unit-4 Salty/Desalted crude oil | [8 empty] | 5 | [5 empty] | 10 | 5 | [8 empty] | 16
3.2 | Plan and profile for Kheirabad Raw water | [8 empty] | 5 | [5 empty] | 30 | 5 | [8 empty] | 16
3.3 | Plan and profile for Lishter Raw water | [8 empty] | 5 | [5 empty] | 30 | 5 | [8 empty] | 16
3.4 | Plan and profile for Waste Water Lines from DE-4 to inhjection wells | [8 empty] | 5 | [5 empty] | 30 | 5 | [8 empty] | 16
3.5 | Plan and profile for Waste Water Lines from PU4 to DE4 | [8 empty] | 5 | [5 empty] | 8 | 5 | [8 empty] | 16
3.6 | Plan and profile for Sample-2 to Sample-3 Crade Oil Line | [8 empty] | 5 | [5 empty] | 30 | 5 | [8 empty] | 16
3.7 | Plan and profile for power tranmission line | [8 empty] | 5 |  |  |  | 30 | 5 | 30 | 5 | [8 empty] | 16
4 | Civil Document for Sample-4 Desalting Unit
4.1 | Topogeraphical drawing for Desalting unit-4 Area | [14 empty] | 30 | 5 | [8 empty] | 16
4.2 | Topographical drawing for Offsite | [14 empty] | 30 | 5 | [8 empty] | 16
4.3 | Rough Grading Plan for Gachsarn-4 Desalting unit | [14 empty] | 50 | 8 | [8 empty] | 25
4.4 | Rough Grading Plan for cold flare | [14 empty] | 20 | 3 | [8 empty] | 10
4.5 | Rough Grading Plan for flare | [14 empty] | 20 | 3 | [8 empty] | 10
4.6 | Rough Grading Plan for burn pit | [14 empty] | 20 | 3 | [8 empty] | 10
4.7 | Rough Grading Plan for Evaporation pond | [14 empty] | 20 | 3 | [8 empty] | 10
4.8 | Finished Grading Plan for Gachsarn-4 Desalting unit | [8 empty] | 5 | [5 empty] | 75 | 5 | [8 empty] | 50
4.9 | Finished Grading Plan for cold flare | [14 empty] | 8 | 3 | [8 empty] | 10
4.10 | Finished Grading Plan for flare | [8 empty] | 2 | [5 empty] | 8 | 3 | [8 empty] | 10
4.11 | Finished Grading Plan for burn pit | [8 empty] | 2 | [5 empty] | 8 | 3 | [8 empty] | 10
4.12 | Finished Grading Plan for Evaporation pond | [8 empty] | 2 | [5 empty] | 20 | 3 | [8 empty] | 10
4.13 | Horizontal And Vertical Alignment Plan for Gachsarn-4 Desalting unit | [14 empty] | 30 | 5 | [8 empty] | 20
4.14 | Civil details for Gachsarn-4 Desalting unit | [14 empty] | 30 | 2 | [8 empty] | 20
4.15 | Civil details for burn pit | [14 empty] | 24 | 8 | [8 empty] | 10
4.16 | Civil details for Evaporation pond | [14 empty] | 24 | 8 | [8 empty] | 10
4.17 | Civil details for overal area of Gachsarn-4 Deslating unit complex | [14 empty] | 10 | 2 | [8 empty] | 10
4.18 | Typical Drawing for Fence and Gate details | [14 empty] | 20 | 4 | [8 empty] | 30
4.19 | Fence and Gate plan for Gachsarn-4 Desalting unit | [14 empty] | 4 | 1 | [8 empty] | 8
4.20 | Fence and Gate plan for cold flare | [14 empty] | 2 | 1 | [8 empty] | 3
4.21 | Fence and Gate plan for flare | [14 empty] | 2 | 1 | [8 empty] | 3
4.22 | Fence and Gate plan for burn pit | [14 empty] | 2 | 1 | [8 empty] | 3
4.23 | Fence and Gate plan for Evaporation pond | [14 empty] | 4 | 1 | [8 empty] | 5
4.24 | Fence and Gate plan for overal area of Gachsarn-4 Deslating unit complex | [14 empty] | 4 | 2 | [8 empty] | 12
4.25 | Road Section and detail for Gachsarn-4 Desalting unit Roads | [14 empty] | 15 | 2 | [8 empty] | 10
4.26 | Road Section and detail for Gachsarn-4 Desalting unit Access Road | [14 empty] | 15 | 2 | [8 empty] | 10
4.27 | Road Section and detail for Gachsarn-4 Desalting unit Patrol Road | [14 empty] | 15 | 2 | [8 empty] | 10
4.28 | Road Section and detail for cold flare Roads | [14 empty] | 15 | 2 | [8 empty] | 10
4.29 | Road Section and detail for flare Roads | [14 empty] | 15 | 2 | [8 empty] | 10
4.30 | Road Section and detail for Evaporation pond | [14 empty] | 15 | 2 | [8 empty] | 10
4.31 | Road Section and detail for overal area of Gachsarn-4 Deslating unit complex | [14 empty] | 20 | 2 | [8 empty] | 10
4.32 | Roads Longitudinal Profiles for Gachsarn-4 Desalting unit Roads | [14 empty] | 50 | 3 | [8 empty] | 30
4.33 | Roads Longitudinal Profiles for Gachsarn-4 Desalting unit Access Road | [14 empty] | 30 | 3 | [8 empty] | 10
4.34 | Roads Longitudinal Profiles for Gachsarn-4 Desalting unit Patrol Road | [14 empty] | 30 | 3 | [8 empty] | 10
4.35 | Roads Longitudinal Profiles for cold flare Roads | [14 empty] | 30 | 3 | [8 empty] | 10
4.36 | Roads Longitudinal Profiles for flare Roads | [14 empty] | 30 | 3 | [8 empty] | 10
4.37 | Roads Longitudinal Profiles for Evaporation pond | [14 empty] | 30 | 3 | [8 empty] | 10
4.38 | Roads Longitudinal Profiles for overal area of Gachsarn-4 Deslating unit complex | [14 empty] | 30 | 3 | [8 empty] | 10
4.39 | Pipe Sleeper Sections And Details | [14 empty] | 15 | 2 | [8 empty] | 10
4.40 | U.G. Composite and Civil Detail Layout for DE-4 | [8 empty] | 10 | 5 | 10 | 5 | 10 | 5 | 70 | 5 | [8 empty] | 50
4.41 | Sanitary Manhole Section And Details | [14 empty] | 15 | 2 | [8 empty] | 8
4.42 | Stormwater Drainage System Layout for DE-4 | [14 empty] | 50 | 5 | [8 empty] | 25
4.43 | Channel Section and Details | [14 empty] | 10 | 2 | [8 empty] | 8
4.44 | Septic Tank Section And Details | [14 empty] | 16 | 4 | [8 empty] | 16
4.45 | Oily Water Separator Section And Details | [14 empty] | 25 | 5 | [8 empty] | 25
4.46 | Burn pit Section And Details | 2 | 1 | [6 empty] | 2 | 1 |  |  |  |  | 10 | 3 | [8 empty] | 8
4.47 | IGF Pit Section And Details | [8 empty] | 1 | [5 empty] | 16 | 4 | [8 empty] | 16
4.48 | Evaporation Pond Rough Grading Plan | [14 empty] | 10 | 3 | [8 empty] | 8
4.49 | Pipe Way Section And Details | [14 empty] | 20 | 3 | [8 empty] | 10
4.50 | Duct Bank Section And Details | [14 empty] | 10 | 2 | [8 empty] | 5
4.51 | Valve Pit Section And Details | [14 empty] | 10 | 2 | [8 empty] | 5
4.52 | Off-site Storm watewr drainage plan | [14 empty] | 80 | 20 | [8 empty] | 5
4.53 | Paving plan for Desalting Unit | [14 empty] | 15 | 8 | [8 empty] | 25
4.54 | Foundation Location Plan for Desalting Unit | [14 empty] | 30 | 8 | [8 empty] | 80
4.55 | Road crossing detail, plan and section | [14 empty] | 15 | 8 | [8 empty] | 40
4.56 | Drawing for Retainig Structure | [14 empty] | 25 | 10 | [8 empty] | 60
5 | Civil Document for Sample-4 Production Unit Unit
5.1 | Topogeraphical drawing for Production unit-4 (Existing Unit) | [14 empty] | 8 | 2 | [8 empty] | 10
5.2 | Topogeraphical drawing for Production unit-4 (extension Area) | [14 empty] | 8 | 2 | [8 empty] | 10
5.3 | Rough Grading Plan for Sample-4 Production Unit Extension | [14 empty] | 20 | 2 | [8 empty] | 20
5.4 | Finished Grading Plan for Sample-4 Production Unit Extension | [8 empty] | 4 | [5 empty] | 20 | 2 | [8 empty] | 20
5.5 | Horizontal And Vertical Alignment Plan for Sample-4 Production Unit Extension | [14 empty] | 30 | 2 | [8 empty] | 10
5.6 | Civil details for Sample-4 Production Unit Extension | [14 empty] | 10 | 2 | [8 empty] | 10
5.7 | Fence and Gate details for Sample-4 Production Unit Extension | [14 empty] | 15 | 2 | [8 empty] | 10
5.8 | Road Section and detail for Sample-4 Production Unit Extension | [14 empty] | 15 | 2 | [8 empty] | 10
5.9 | Roads Longitudinal Profiles for Sample-4 Production Unit Extension | [14 empty] | 30 | 2 | [8 empty] | 10
5.10 | U.G. Composite and Civil Detail Layout for Sample-4 Production Unit Extension | [8 empty] | 5 | 2 | 5 | 2 | 5 | 2 | 35 | 2 | [8 empty] | 40
5.11 | Stormwater Drainage System Layout for Sample-4 Production Unit Extension | [14 empty] | 20 | 2 | [8 empty] | 8
5.12 | Paving plan for Sample-4 Production Unit Extension | [14 empty] | 10 | 5 | [8 empty] | 20
5.13 | Foundation Location Plan for Sample-4 Production Unit Extension | [14 empty] | 20 | 5 | [8 empty] | 30
6 | Calculation
6.1 | Calculation for Storm Water Network | [14 empty] | 60 | 20
6.2 | Calculation for oily water | [14 empty] | 30 | 10
6.3 | Calculation for Earthwork volumes | [14 empty] | 25 | 5
6.4 | Calculation for Paving Design | [14 empty] | 30 | 5
6.5 | Calculation for Retainig Structure | [14 empty] | 60 | 20
7 | Civil Document for Sample-3 33 Kv Station
7.1 | Rough Grading Plan for Sample-3 33KV Station | [14 empty] | 30 | 8 | [8 empty] | 10
7.2 | Finished Grading Plan for Sample-3 33KV Station | [14 empty] | 30 | 8 | [8 empty] | 10
7.3 | Horizontal And Vertical Alignment Plan for Sample-3 33KV Station | [14 empty] | 30 | 8 | [8 empty] | 10
7.4 | Civil details for Sample-3 33KV Station | [14 empty] | 10 | 2 | [8 empty] | 10
7.5 | Fence and Gate details for Sample-3 33KV Station | [14 empty] | 15 | 2 | [8 empty] | 10
7.6 | Road Section and detail for Sample-3 33KV Station | [14 empty] | 15 | 2 | [8 empty] | 10
7.7 | Roads Longitudinal Profiles for Sample-3 33KV Station | [14 empty] | 30 | 2 | [8 empty] | 10
7.8 | Paving plan for Sample-3 33KV Station | [14 empty] | 10 | 5 | [8 empty] | 20
8 | Civil Document for Sample-4 33/3.45 Kv Station | [24 empty] | 100
8.1 | Topogeraphical drawing for Sample-4 33KV Outdoor Station | [14 empty] | 20 | 8 | [8 empty] | 10
8.2 | Rough Grading Plan for Sample-4 33KV Outdoor Station | [14 empty] | 30 | 8 | [8 empty] | 10
8.3 | Finished Grading Plan for Sample-4 33KV Outdoor Station | [14 empty] | 30 | 8 | [8 empty] | 10
8.4 | Horizontal And Vertical Alignment Plan for Sample-4 33KV Outdoor Station | [14 empty] | 30 | 2 | [8 empty] | 10
8.5 | Civil details for Sample-4 33KV Outdoor Station | [14 empty] | 10 | 2 | [8 empty] | 10
8.6 | Fence and Gate details for Sample-4 33KV Outdoor Station | [14 empty] | 15 | 2 | [8 empty] | 10
8.7 | Road Section and detail for Sample-4 33KV Outdoor Station | [14 empty] | 15 | 2 | [8 empty] | 10
8.8 | Roads Longitudinal Profiles for Sample-4 33KV Outdoor Station | [14 empty] | 30 | 2 | [8 empty] | 10
8.9 | Paving Plan for Sample-4 33KV Outdoor Station | [14 empty] | 10 | 5 | [8 empty] | 20
9 | خدمات مرتبط با اجرا و پس از اجرا
9.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [14 empty] | 265.2 | 58.4 | [8 empty] | 166.9
9.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [14 empty] | 132.6 | [9 empty] | 83.45
9.3 | سیاهه کالا (Material Take-off) پس از اجرا | [14 empty] | 120
9.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [14 empty] | 100
9.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [14 empty] | 100 | 8
| Total : | 6 | 3 | 8 | 4 | 0 | 0 | 4 | 2 | 72 | 10 | 19 | 9 | 53 | 16 | 3369.8 | 650.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.35
|  | 6 | 3 | 8 | 4 | 0 | 0 | 4 | 2 | 72 | 10 | 19 | 9 | 53 | 16 | 2652 | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1669
Calculation for Storm Water Network
Calculation for oily water
Calculation for Earthwork volumes
Calculation for Paving Design
Roeport on civil material selection

## E.Arichitectural
Architectural Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Building Specification | [16 empty] | 16 | 3
2 | General Drawings | [16 empty] | 10 | 3 | [6 empty] | 40
3 | Sample-4 Deadsalting Unit Buildings
3.1 | Architectural drawing-Phase 1
3.1.1 | Architectural drawing-Phase 1 for Air Compressor Room & Emergency Diesel Generator Building | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.2 | Architectural drawing-Phase 1 for Control &Telecommunication Building | [5 empty] | 2 |  | 2 |  |  |  | 2 |  | 2 |  |  | 5 | 2 | [6 empty] | 16
3.1.3 | Architectural drawing-Phase 1 for Guard House | [11 empty] | 1 |  |  |  |  | 5 | 2 | [6 empty] | 10
3.1.4 | Architectural drawing-Phase 1 for DE4 Substation Building | [5 empty] | 2 |  | 2 | [5 empty] | 2 |  |  | 5 | 2 | [6 empty] | 16
3.1.5 | Architectural drawing-Phase 1 for DE4 Parking Shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.6 | Architectural drawing-Phase 1 for DE4 Chemical storage shelter no.1 | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.7 | Architectural drawing-Phase 1 for DE4 Chemical storage shelter no.2 | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.8 | Architectural drawing-Phase 1 for Chemical injection package shelter no.1 | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.9 | Architectural drawing-Phase 1 for Chemical injection package shelter no.2 | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.10 | Architectural drawing-Phase 1 for Process Pumps shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.11 | Architectural drawing-Phase 1 for Dilution Water Pumps shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.12 | Architectural drawing-Phase 1 for Waste Water Pumps shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.13 | Architectural drawing-Phase 1 for Dearated Water Pumps shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.14 | Architectural drawing-Phase 1 for Fire Water Pumps shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.15 | Architectural drawing-Phase 1 for Fire extinguisher shelter | [16 empty] | 5 | 2 | [6 empty] | 10
3.1.16 | Architectural drawing-Phase 1 for Foam Storage Building | [16 empty] | 5 | 2
3.1.17 | Architectural drawing-Phase 1 for Consumable Storage Building | [16 empty] | 5 | 2
3.2 | Architectural drawing-Phase 2
3.2.1 | Architectural drawing-Phase 2 for Air Compressor Room & Emergency Diesel Generator Building |  |  | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 25 | 5 | [6 empty] | 80
3.2.2 | Architectural drawing-Phase 2 for Control &Telecommunication Building |  |  |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 120 | 10 | [6 empty] | 200
3.2.3 | Architectural drawing-Phase 2 for Guard House | [16 empty] | 20 | 5 | [6 empty] | 50
3.2.4 | Architectural drawing-Phase 2 for DE4 Substation Building |  |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 100 | 10 | [6 empty] | 180
3.2.5 | Architectural drawing-Phase 2 for DE4 Parking Shelter | [16 empty] | 15 | 5 | [6 empty] | 40
3.2.6 | Architectural drawing-Phase 2 for DE4 Chemical storage shelter no.1 |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
3.2.7 | Architectural drawing-Phase 2 for DE4 Chemical storage shelter no.2 |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
3.2.8 | Architectural drawing-Phase 2 for Chemical injection package shelter no.1 |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
3.2.9 | Architectural drawing-Phase 2 for Chemical injection package shelter no.2 |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
3.2.10 | Architectural drawing-Phase 2 for Process Pumps shelter |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 100
3.2.11 | Architectural drawing-Phase 2 for Dilution Water Pumps shelter |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 50
3.2.12 | Architectural drawing-Phase 2 for Waste Water Pumps shelter |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 50
3.2.13 | Architectural drawing-Phase 2 for Dearated Water Pumps shelter |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 50
3.2.14 | Architectural drawing-Phase 2 for Fire Water Pumps shelter | [6 empty] | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 80
3.2.15 | Architectural drawing-Phase 2 for Fire extinguisher shelter | [6 empty] | 1 | [9 empty] | 8 | 5 | [6 empty] | 20
3.1.16 | Architectural drawing-Phase 2 for Foam Storage Building | [6 empty] | 1 | [9 empty] | 20 | 5 | [6 empty] | 30
3.1.17 | Architectural drawing-Phase 2 for Consumable Storage Building | [16 empty] | 20 | 5 | [6 empty] | 30
4 | Sample-4Production Unit Buildings
4.1 | Architectural drawing-Phase 1
4.1.1 | Architectural drawing-Phase 1 Extension For PU4 Switchgear Room | [13 empty] | 1 |  |  | 5 | 2 | [6 empty] | 8
4.1.2 | Architectural drawing-Phase 1 Extension Of Control Building For PU4 | [11 empty] | 1 |  | 1 |  |  | 5 | 2 | [6 empty] | 10
4.1.3 | Architectural drawing-Phase 1 for pump shelter in production units | [16 empty] | 5 | 2 | [6 empty] | 10
4.1.4 | Architectural drawing-Phase 1 for Chemical storage shelter in production units | [16 empty] | 5 | 2 | [6 empty] | 10
4.1.5 | Architectural drawing-Phase 1 for Chemical injection package shelter in production units | [16 empty] | 5 | 2 | [6 empty] | 10
4.1.6 | Architectural drawing-Phase 1 For Accommodation Building | [16 empty] | 5 | 2 | [6 empty] | 10
4.1.7 | Architectural drawing-Phase 1 for Air Compressor Room | [16 empty] | 5 | 2 | [6 empty] | 10
4.2 | Architectural drawing-Phase 2
4.2.1 | Architectural drawing-Phase 2 Extension of PU4 Switchgear Room |  |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  | 40 | 10 | [6 empty] | 120
4.2.2 | Architectural drawing-Phase 2 Extension Of Control Building For PU4 |  |  |  |  | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 40 | 10 | [6 empty] | 80
4.2.3 | Architectural drawing-Phase 2 for pump shelter in production units |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 30 | 5 | [6 empty] | 80
4.2.4 | Architectural drawing-Phase 2 for Chemical storage shelter in production units |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
4.2.5 | Architectural drawing-Phase 2 for Chemical injection package shelter in production units |  |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  |  |  | 20 | 5 | [6 empty] | 40
4.2.6 | Architectural drawing-Phase 2 For Accommodation Building |  |  |  |  | 1 |  |  | 1 | [8 empty] | 25 | 5 | [6 empty] | 120
4.2.7 | Architectural drawing-Phase 2 for Air Compressor Room |  |  | 1 | [5 empty] | 1 | [7 empty] | 20 | 5 | [6 empty] | 60
5 | Off-Site Buildings
5.1 | Architectural drawing-Phase 1
5.1.1 | Architectural drawing-Phase 1 for Laboratory |  | 1 | [14 empty] | 5 | 2 | [6 empty] | 10
5.1.2 | Architectural drawing-Phase 1 for Work Shop |  |  |  | 1 | [7 empty] | 1 |  | 1 |  |  | 5 | 2 | [6 empty] | 10
5.1.3 | Architectural drawing-Phase 1 for 3.3 Switch Gear Building Of PU4 Outdoor Substaion | [13 empty] | 1 |  |  | 5 | 2 | [6 empty] | 10
5.1.4 | Architectural drawing-Phase 1 for 33 KV Switch Gear Building Of 33 KV Station | [16 empty] | 5 | 2 | [6 empty] | 10
5.1.5 | Architectural drawing-Phase 1 for 33 KV Station Guard House | [16 empty] | 5 | 2 | [6 empty] | 10
5.1.6 | Architectural drawing-Phase 1 for 33 KV Station Diesel Generator Building | [16 empty] | 5 | 2 | [6 empty] | 10
5.2 | Architectural drawing-Phase 2
5.2.1 | Architectural drawing-Phase 2 for Laboratory | 2 |  |  |  | 2 |  |  | 1 |  |  |  |  | 1 |  |  |  | 70 | 10 | [6 empty] | 180
5.2.2 | Architectural drawing-Phase 2 for Work Shop |  |  | 1 |  | 2 |  |  | 1 |  |  |  |  | 1 |  |  |  | 50 | 10 | [6 empty] | 150
5.2.3 | Architectural drawing-Phase 2 fo3.3 Switch Gear Building Of PU4 Outdoor Substaion |  |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 1 |  |  |  | 50 | 10 | [6 empty] | 150
5.2.4 | Architectural drawing-Phase 2 fo33 KV Switch Gear Building Of PU3 33 KV Station |  |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 1 |  |  |  | 50 | 12 | [6 empty] | 200
5.2.5 | Architectural drawing-Phase 2 for 33 KV Station Guard House |  |  |  |  | 1 | [11 empty] | 15 | 4 | [6 empty] | 40
5.2.6 | Architectural drawing-Phase 2 for 33 KV Station Diesel Generator Building | [12 empty] | 1 |  |  |  | 25 | 5 | [6 empty] | 120
6 | Report onarchitectural material selection | [16 empty] | 20 | 5
7 | خدمات مرتبط با اجرا و پس از اجرا
7.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [16 empty] | 120.9 | 26.2 | [6 empty] | 283
7.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [16 empty] | 60.45 | [7 empty] | 141.5
7.3 | سیاهه کالا (Material Take-off) پس از اجرا | [16 empty] | 120
7.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [16 empty] | 100
7.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [16 empty] | 100 | 8
| Total : | 2 | 1 | 14 | 1 | 12 | 4 | 5 | 13 | 14 | 0 | 14 | 5 | 22 | 8 | 0 | 0 | 1710.35 | 296.2 | 0 | 0 | 0 | 0 | 0 | 0 | 3254.5
|  | 2 | 1 | 14 | 1 | 12 | 4 | 5 | 13 | 14 | 0 | 14 | 5 | 22 | 8 | 0 | 0 | 1209 | 262 | 0 | 0 | 0 | 0 | 0 | 0 | 2830

## E.Structure
Structural & Buildings Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | Specification, Criteria, Standard Drawing
1.1 | Design Criteria for Steel Structure | [18 empty] | 10 | 3
1.2 | Design Criteria for Concrete Structure | [18 empty] | 10 | 3
1.3 | Design Criteria for Loads & Forces | [18 empty] | 10 | 3
1.4 | Specification for Powerline transition structure | [18 empty] | 10 | 4
1.5 | Specification for Grouting | [18 empty] | 8 | 3
1.6 | Specification for Structural Concrete Works | [18 empty] | 10 | 4
1.7 | Specification for Structural Steel Fabrication | [18 empty] | 8 | 3
1.8 | Specification for Structural Steel Erection | [18 empty] | 8 | 3
1.9 | Specification for Anchor bolts | [18 empty] | 10 | 4
1.10 | Testing & Inspection Procedure for Concrete Works | [18 empty] | 8 | 3
1.11 | Testing & Inspection Procedure for Steel Works | [18 empty] | 8 | 3
1.12 | Typical Structural Detail Drawing | [18 empty] | 16 | 5 |  |  |  |  | 50
1.11 | Report on overhead crane bridge design | [18 empty] | 40 | 10
1.13 | Report on structural material selection | [18 empty] | 20 | 5
2 | Foundations Calculation
2.1 | Buildings foundations Calculation | [24 empty] | 0
2.1.1 | Foundation Calculation for DE4 Air Compressor Room & Emergency Diesel Generator Building | [18 empty] | 16 | 3
2.1.2 | Foundation Calculation for Control &Telecommunication Building | [18 empty] | 24 | 3
2.1.3 | Foundation Calculation for DE4 Guard House | [18 empty] | 16 | 3
2.1.4 | Foundation Calculation for DE4 Substation Building | [18 empty] | 24 | 3
2.1.5 | Foundation Calculation for DE4 for Foam Storage Building | [18 empty] | 16 | 3
2.1.6 | Foundation Calculation for DE4 for Consumable Storage Building | [18 empty] | 16 | 3
2.1.7 | Foundation Calculation Extension For PU4 Switchgear Room | [18 empty] | 10 | 3
2.1.8 | Foundation Calculation For Accommodation Building in PU4 | [18 empty] | 16 | 3
2.1.9 | Foundation Calculation for Air Compressor Room in PU4 | [18 empty] | 16 | 3
2.1.10 | Foundation Calculation for Laboratory | [18 empty] | 16 | 3
2.1.11 | Foundation Calculation for Work Shop | [18 empty] | 24 | 3
2.1.12 | Foundation Calculation fo3.3 Switch Gear Building Of PU4 Outdoor Substaion | [18 empty] | 10 | 3
2.1.13 | Foundation Calculation fo33 KV Switch Gear Building Of 33 KV Station | [18 empty] | 16 | 3
2.1.14 | Foundation Calculation fo33 KV Station Guard House | [18 empty] | 16 | 3
2.1.15 | Foundation Calculation fo33 KV Station Diesel Generator Building | [18 empty] | 16 | 3
2.2 | Shelters foundations Calculation | [24 empty] | 0
2.2.1 | Foundation Calculation for DE4 Parking Shelter | [18 empty] | 16 | 2
2.2.2 | Foundation Calculation for DE4 Chemical storage shelter no.1 | [18 empty] | 16 | 2
2.2.3 | Foundation Calculation for DE4 Chemical storage shelter no.2 | [18 empty] | 10 | 2
2.2.4 | Foundation Calculation for DE4 Chemical injection package shelter no.1 | [18 empty] | 16 | 2
2.2.5 | Foundation Calculation for DE4 Chemical injection package shelter no.2 | [18 empty] | 10 | 2
2.2.6 | Foundation Calculation for DE4 Process Pumps shelter | [18 empty] | 16 | 2
2.2.7 | Foundation Calculation for DE4 Dilution Water Pumps shelter | [18 empty] | 16 | 2
2.2.8 | Foundation Calculation for DE4 Waste Water Pumps shelter | [18 empty] | 16 | 2
2.2.9 | Foundation Calculation for DE4 Dearated Water Pumps shelter | [18 empty] | 16 | 2
2.2.10 | Foundation Calculation for DE4 Fire Water Pumps shelter | [18 empty] | 16 | 2
2.2.11 | Foundation Calculation for Fire extinguisher shelter | [18 empty] | 10 | 2
2.2.12 | Foundation Calculation for pump shelter in PU4 | [18 empty] | 16 | 2
2.2.13 | Foundation Calculation for Chemical storage shelter in PU4 | [18 empty] | 16 | 2
2.2.14 | Foundation Calculation for Chemical injection package shelter in PU4 | [18 empty] | 10 | 2
2.3 | Process Packages and Equipment Foundation Calculation
2.3.1 | Heat Exchanger Foundation Calculation | [18 empty] | 32 | 6 |  |  |  |  | 0
2.3.1.1 | Foundation Calculation For Salty Crude/Desalted Crude Heat Exchanger(E-001-A/B) | [18 empty] | 16 | 3
2.3.1.2 | Foundation Calculation For Water/Water Heat Exchanger(E-002-A/B) | [18 empty] | 16 | 3
2.3.2 | Foundation Calculation For Crude Oil Indirect Fired Heater(H-001-A1/A2/B1/B2) | [18 empty] | 32 | 5
2.3.3 | Air Compressors and Dryer Foundation Calculation | [18 empty] | 32 | 6 |  |  |  |  | 0
2.3.3.1 | Foundation Calculation FOR AIR COMPRESSOR PKG. (PK-401-A/B) & AIR DRYER PKG. (PK-402) | [18 empty] | 16 | 3
2.3.3.2 | Foundation Calculation For Air COMPRESSOR PKG. (PK-002-A/B) & AIR DRYER PKG. (PK-003) | [18 empty] | 16 | 3
2.3.4 | Foundation Calculation For Vacuum Deaerator Package | [18 empty] | 24 | 3
2.3.5 | Flares Foundation Calculation | [18 empty] | 74 | 13 |  |  |  |  | 0
2.3.5.1 | Foundation Calculation For HOT FLARE | [18 empty] | 32 | 5
2.3.5.2 | Foundation Calculation For IGNITION PACKAGE | [18 empty] | 10 | 3
2.3.5.3 | Foundation Calculation For Cold Flare | [18 empty] | 32 | 5
2.3.6 | Foundation Calculation For Desalter Package (PK-001A/B) | [18 empty] | 32 | 5
2.3.7 | Waste Water Treatment Packages Foundation Calculation | [18 empty] | 40 | 6 |  |  |  |  | 0
2.3.7.1 | Foundation Calculation For Nutshell Filter Package(PK-202) | [18 empty] | 16 | 3
2.3.7.2 | Foundation Calculation For IGF Package (PK-201A/B) | [18 empty] | 24 | 3
2.3.8 | Injection Packages Foundation Calculation | [18 empty] | 96 | 16 |  |  |  |  | 0
2.3.8.1 | Foundation Calculation For Demulsifier Injection Package (PK-501) | [18 empty] | 12 | 2
2.3.8.2 | Foundation Calculation For Oxygen Scavenger Injection Package(PK-503) | [18 empty] | 12 | 2
2.3.8.3 | Foundation Calculation For Corrosion Inhibitor injection Package(PK-504) | [18 empty] | 12 | 2
2.3.8.4 | Foundation Calculation For Reverse Demulsifier Injection Package(PK-505) | [18 empty] | 12 | 2
2.3.8.5 | Foundation Calculation For Biocide Injection Package (Type A)(PK-506-A) | [18 empty] | 12 | 2
2.3.8.6 | Foundation Calculation For Anti Scalant Injection Package(PK-507) | [18 empty] | 12 | 2
2.3.8.7 | Foundation Calculation For Biocide Injection Package (Type B)(PK-506-B) | [18 empty] | 12 | 2
2.3.8.8 | Foundation Calculation For Demulsifier Injection Package (PK-502-A/B) | [18 empty] | 12 | 2
2.4 | Pumps Foundation Calculation | [24 empty] | 0
2.4.1 | Foundation Calculation For Dilution Water Pump(P-103) | [18 empty] | 30 | 5
2.4.2 | Foundation Calculation For Potable Water Pump(P-104) | [18 empty] | 30 | 5
2.4.3 | Foundation Calculation For Waste Water Injection Pump(P-201-A/B) | [18 empty] | 30 | 5
2.4.4 | Foundation Calculation For OWS Clean Water Pump(p-703-A/B) | [18 empty] | 20 | 4
2.4.5 | Foundation Calculation For Diesel Oil Pump(P-801) | [18 empty] | 20 | 4
2.4.6 | Foundation Calculation For HC Closed Drain Sump Pump(P-702) | [18 empty] | 20 | 4
2.4.7 | Foundation Calculation For HC Closed Drain Transfer Pump(P-701-A/B) | [18 empty] | 20 | 4
2.4.8 | Foundation Calculation For Flare K.O. Drum Liquid Pump(P-601-A/B) | [18 empty] | 20 | 4
2.4.9 | Foundation Calculation for Dilution Water Pumps(P-106-A1/A2) | [18 empty] | 30 | 5
2.4.10 | Foundation Calculation For Dearated Water Pump(p-102-A/B) | [18 empty] | 30 | 5
2.4.11 | Foundation Calculation for Dirty Oil Pumps(P-705-A/B) | [18 empty] | 20 | 4
2.4.12 | Foundation Calculation for Booster Pumps (P-002-A/B) | [18 empty] | 30 | 5
2.4.13 | Foundation Calculation for Booster Pumps (P-001-A/B) | [18 empty] | 30 | 5
2.4.14 | Foundation Calculation for Evaporation Pond Pumps(P-706-A/B) | [18 empty] | 20 | 4
2.4.15 | Foundation Calculation for Free Water Transfer PUMPS (P-005-A/B) | [18 empty] | 30 | 5
2.4.16 | Foundation Calculation for Dearated Water Pump(p-105) | [18 empty] | 30 | 5
2.4.17 | Foundation Calculation for Ows Oil Pump(P-704-A/B) | [18 empty] | 20 | 4
2.4.18 | Foundation Calculation for Oily Water Separator Pump(P-750) | [18 empty] | 20 | 4
2.4.19 | Foundation Calculation for Waste Water Injection Pump(p-206-A/B/C) | [18 empty] | 30 | 5
2.4.20 | Foundation Calculation For Off-Spec Pump | [18 empty] | 20 | 4
2.4.21 | Foundation Calculation For Firewater Loading Pump P-904 | [18 empty] | 20 | 4
2.4.22 | Foundation Calculation For Supply Water Pump P-108A/B | [18 empty] | 30 | 5
2.5 | Pressure Vessels Foundation Calculation | [24 empty] | 0
2.5.1 | Foundation Calculation For Air Receiver(v-401) | [18 empty] | 20 | 3
2.5.2 | Foundation Calculation For Diesel Oil Storage Tank(v-801) | [18 empty] | 20 | 3
2.5.3 | Foundation Calculation For HC Closed Drain Drum(V-701) | [18 empty] | 20 | 3
2.5.4 | Foundation Calculation For Flare K.O.Drum(V-601) | [18 empty] | 20 | 3
2.5.5 | Foundation Calculation For Fuel Gas K.O.Drum(V-301) | [18 empty] | 20 | 3
2.5.6 | Foundation Calculation For Free Water K.O. Drum(v-001-A/B) | [18 empty] | 20 | 3
2.5.7 | Foundation Calculation For Air Receiver ( V-002) | [18 empty] | 20 | 3
2.6 | Storage Tanks Foundation Calculation | [24 empty] | 0
2.6.1 | Foundation Calculation For Dilution Water Storage Tank(TK-101) | [18 empty] | 32 | 5
2.6.2 | Foundation Calculation For Potable Water Tank(TK-102) | [18 empty] | 32 | 5
2.6.3 | Foundation Calculation For Skimmer Tank(OS-201) | [18 empty] | 32 | 5
2.6.4 | Foundation Calculation For Disposal Storage Tank(TK-201) | [18 empty] | 32 | 5
2.6.5 | Foundation Calculation For Off-Spec Tank | [18 empty] | 32 | 5
2.6.6 | Foundation Calculation for Dirty Oil Tank(TK-701) | [18 empty] | 32 | 5
2.6.7 | Foundation Calculation For Supply Water Tank (TK-104) | [18 empty] | 32 | 5
2.6.8 | Foundation Calculation for Fire Water Tank(TK-902-A/B) | [18 empty] | 32 | 5
2.7 | Electrical Foundation Calculation | [24 empty] | 0
2.7.1 | Foundation Calculation ForTransformers | [18 empty] | 24 | 4
2.7.2 | Foundation Calculation ForDeisel Generator | [18 empty] | 30 | 5
2.7.3 | Foundation Calculation For Lighting towers | [18 empty] | 30 | 5
2.7.4 | Foundation Calculation For Lighting Poles | [18 empty] | 20 | 4
3 | Foundations Drawing
3.1 | Buildings foundations Drawing | [24 empty] | 273
3.1.1 | Foundation Drawing for DE4 Air Compressor Room & Emergency Diesel Generator Building | [18 empty] | 4 | 2 |  |  |  |  | 16
3.1.2 | Foundation Drawing for Control &Telecommunication Building | [18 empty] | 4 | 2 |  |  |  |  | 30
3.1.3 | Foundation Drawing for DE4 Guard House | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.4 | Foundation Drawing for DE4 Substation Building | [18 empty] | 4 | 2 |  |  |  |  | 25
3.1.5 | Foundation Drawing for DE4 Foam Storage Building | [18 empty] | 4 | 2 |  |  |  |  | 16
3.1.6 | Foundation Drawing for DE4 Consumable Storage Building | [18 empty] | 4 | 2 |  |  |  |  | 16
3.1.7 | Foundation Drawing Extension For PU4 Switchgear Room | [18 empty] | 2 | [5 empty] | 8
3.1.8 | Foundation Drawing For Accommodation Building in PU4 | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.9 | Foundation Drawing for Air Compressor Room in PU4 | [18 empty] | 4 | 2 |  |  |  |  | 16
3.1.10 | Foundation Drawing for Laboratory | [18 empty] | 4 | 2 |  |  |  |  | 25
3.1.11 | Foundation Drawing for Work Shop | [18 empty] | 4 | 2 |  |  |  |  | 25
3.1.12 | Foundation Drawing fo3.3 Switch Gear Building Of PU4 Outdoor Substaion | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.13 | Foundation Drawing fo33 KV Switch Gear Building Of 33 KV Station | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.14 | Foundation Drawing fo33 KV Station Guard House | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.15 | Foundation Drawing fo33 KV Station Diesel Generator Building | [18 empty] | 3 | 2 |  |  |  |  | 16
3.1.16 | Floor Slab & Detail for DE4 Air Compressor Room & Emergency Diesel Generator Building |  |  |  | 1 | [8 empty] | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.1.17 | Floor Slab & Detail for Control &Telecommunication Building |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.1.18 | Floor Slab & Detail for Air Compressor Room in PU4 |  |  |  | 1 | [8 empty] | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.1.19 | Floor Slab & Detail fo33 KV Station Diesel Generator Building | [12 empty] | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2 | Shelters foundations Drawing | [24 empty] | 251
3.2.1 | Foundation Drawing for DE4 Parking Shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.2 | Foundation Drawing for DE4 Chemical storage shelter no.1 | [18 empty] | 5 | 2 |  |  |  |  | 25
3.2.3 | Foundation Drawing for DE4 Chemical storage shelter no.2 | [18 empty] | 5 | 2 |  |  |  |  | 25
3.2.4 | Foundation Drawing for DE4 Chemical injection package shelter no.1 | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.5 | Foundation Drawing for DE4 Chemical injection package shelter no.2 | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.6 | Foundation Drawing for DE4 Process Pumps shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.7 | Foundation Drawing for DE4 Dilution Water Pumps shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.8 | Foundation Drawing for DE4 Waste Water Pumps shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.9 | Foundation Drawing for DE4 Dearated Water Pumps shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.10 | Foundation Drawing for DE4 Fire Water Pumps shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.11 | Foundation Drawing for Fire extinguisher shelter | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.12 | Foundation Drawing for pump shelter in PU4 | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.13 | Foundation Drawing for Chemical storage shelter in PU4 | [18 empty] | 5 | 2 |  |  |  |  | 25
3.2.14 | Foundation Drawing for Chemical injection package shelter in PU4 | [18 empty] | 3 | 2 |  |  |  |  | 16
3.2.15 | Floor Slab & Detail for DE4 Chemical injection package shelter no.1 |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.16 | Floor Slab & Detail for DE4 Chemical injection package shelter no.2 |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.17 | Floor Slab & Detail for DE4 Process Pumps shelter |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.18 | Floor Slab & Detail for DE4 Dilution Water Pumps shelter |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.19 | Floor Slab & Detail for DE4 Waste Water Pumps shelter |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.20 | Floor Slab & Detail for DE4 Dearated Water Pumps shelter |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.21 | Floor Slab & Detail for DE4 Fire Water Pumps shelter |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.22 | Floor Slab & Detail for pump shelter in PU4 |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.2.23 | Floor Slab & Detail for Chemical injection package shelter in PU4 |  |  |  | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 2 |  |  |  |  | 10
3.3 | Process Packkages and Equipment Foundation Drawing
3.3.1 | Heat Exchanger Foundation Drawing | [24 empty] | 24
3.3.1.1 | Foundation Drawing For Salty Crude/Desalted Crude Heat Exchanger(E-001-A/B) | [18 empty] | 2 | [5 empty] | 12
3.3.1.2 | Foundation Drawing For Water/Water Heat Exchanger(E-002-A/B) | [18 empty] | 2 | [5 empty] | 12
3.3.2 | Foundation Drawing For Crude Oil Indirect Fired Heater(H-001-A1/A2/B1/B2) | [18 empty] | 4 | 2 |  |  |  |  | 25
3.3.3 | Air Compressors and Dryer Foundation Drawing | [18 empty] | 8 | 4 |  |  |  |  | 40
3.3.3.1 | Foundation Drawing FOR AIR COMPRESSOR PKG. (PK-401-A/B) & AIR DRYER PKG. (PK-402) | [18 empty] | 4 | 2 |  |  |  |  | 20
3.3.3.2 | Foundation Drawing For Air COMPRESSOR PKG. (PK-002-A/B) & AIR DRYER PKG. (PK-003) | [18 empty] | 4 | 2 |  |  |  |  | 20
3.3.4 | Foundation Drawing For Vacuum Deaerator Package | [18 empty] | 3 | 2 |  |  |  |  | 16
3.3.5 | Flares Foundation Drawing | [18 empty] | 11 | 4 |  |  |  |  | 50
3.3.5.1 | Foundation Drawing For HOT FLARE | [18 empty] | 4 | 2 |  |  |  |  | 25
3.3.5.2 | Foundation Drawing For IGNITION PACKAGE | [18 empty] | 3 | [5 empty] | 10
3.3.5.3 | Foundation Drawing For Cold Flare | [18 empty] | 4 | 2 |  |  |  |  | 15
3.3.6 | Foundation Drawing For Desalter Package (PK-001A/B) | [18 empty] | 4 | 2 |  |  |  |  | 25
3.3.7 | Waste Water Treatment Packages Foundation Drawing | [18 empty] | 6 | 4 |  |  |  |  | 36
3.3.7.1 | Foundation Drawing For Nutshell Filter Package(PK-202) | [18 empty] | 3 | 2 |  |  |  |  | 16
3.3.7.2 | Foundation Drawing For IGF Package (PK-201A/B) | [18 empty] | 3 | 2 |  |  |  |  | 20
3.3.8 | Injection Packages Foundation Drawing | [18 empty] | 16 | 0 |  |  |  |  | 96
3.3.8.1 | Foundation Drawing For Demulsifier Injection Package (PK-501) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.2 | Foundation Drawing For Oxygen Scavenger Injection Package(PK-503) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.3 | Foundation Drawing For Corrosion Inhibitor injection Package(PK-504) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.4 | Foundation Drawing For Reverse Demulsifier Injection Package(PK-505) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.5 | Foundation Drawing For Biocide Injection Package (Type A)(PK-506-A) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.6 | Foundation Drawing For Anti Scalant Injection Package(PK-507) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.7 | Foundation Drawing For Biocide Injection Package (Type B)(PK-506-B) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.3.8.8 | Foundation Drawing For Demulsifier Injection Package (PK-502-A/B) |  |  | 0.5 | [15 empty] | 2 | [5 empty] | 12
3.4 | Pumps Foundation Drawing
3.4.1 | Foundation Drawing For Dilution Water Pump(P-103) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.2 | Foundation Drawing For Potable Water Pump(P-104) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.3 | Foundation Drawing For Waste Water Injection Pump(P-201-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.4 | Foundation Drawing For OWS Clean Water Pump(p-703-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.5 | Foundation Drawing For Diesel Oil Pump(P-801) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.6 | Foundation Drawing For HC Closed Drain Sump Pump(P-702) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.7 | Foundation Drawing For HC Closed Drain Transfer Pump(P-701-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.8 | Foundation Drawing For Flare K.O. Drum Liquid Pump(P-601-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.9 | Foundation Drawing for Dilution Water Pumps(P-106-A1/A2) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.10 | Foundation Drawing For Dearated Water Pump(p-102-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.11 | Foundation Drawing for Dirty Oil Pumps(P-705-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.12 | Foundation Drawing for Booster Pumps (P-002-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.13 | Foundation Drawing for Booster Pumps (P-001-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.14 | Foundation Drawing for Evaporation Pond Pumps(P-706-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.15 | Foundation Drawing for Free Water Transfer PUMPS (P-005-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.16 | Foundation Drawing for Dearated Water Pump(p-105) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.17 | Foundation Drawing for Ows Oil Pump(P-704-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.18 | Foundation Drawing for Oily Water Separator Pump(P-750) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.19 | Foundation Drawing for Waste Water Injection Pump(p-206-A/B/C) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.20 | Foundation Drawing For Off-Spec Pump |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.21 | Foundation Drawing For Firewater Loading Pump P-904 |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.4.22 | Foundation Drawing For Supply Water Pump P-108A/B |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 10
3.5 | Pressure Vessels Foundation Drawing
3.5.1 | Foundation Drawing For Air Receiver(v-401) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.2 | Foundation Drawing For Diesel Oil Storage Tank(v-801) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.3 | Foundation Drawing For HC Closed Drain Drum(V-701) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.4 | Foundation Drawing For Flare K.O.Drum(V-601) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.5 | Foundation Drawing For Fuel Gas K.O.Drum(V-301) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.6 | Foundation Drawing For Free Water K.O. Drum(v-001-A/B) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.5.7 | Foundation Drawing For Air Receiver ( V-002) |  |  | 0.5 | [15 empty] | 3 | 2 |  |  |  |  | 16
3.6 | Storage Tanks Foundation Drawing
3.6.1 | Foundation Drawing For Dilution Water Storage Tank(TK-101) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.2 | Foundation Drawing For Potable Water Tank(TK-102) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.3 | Foundation Drawing For Skimmer Tank(OS-201) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.4 | Foundation Drawing For Disposal Storage Tank(TK-201) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.5 | Foundation Drawing For Off-Spec Tank |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.6 | Foundation Drawing for Dirty Oil Tank(TK-701) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.7 | Foundation Drawing For Supply Water Tank TK-104 |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.6.8 | Foundation Drawing for Fire Water Tank(TK-902-A/B) |  |  | 0.5 | [15 empty] | 5 | 2 |  |  |  |  | 30
3.7 | Electrical Foundation Drawing
3.7.1 | Foundation Drawing For Transformers | [18 empty] | 4 | 2 |  |  |  |  | 30
3.7.2 | Foundation Drawing For Deisel Generator | [18 empty] | 3 | 2 |  |  |  |  | 16
3.7.3 | Foundation Drawing For Lighting towers | [18 empty] | 3 | 2 |  |  |  |  | 16
3.7.4 | Foundation Drawing For Lighting Poles | [18 empty] | 3 | 2 |  |  |  |  | 16
4 | Structurs Calculation
4.1 | Buildings Structural Calculation
4.1.1 | Structural Calculation for DE4 Air Compressor Room & Emergency Diesel Generator Building | [18 empty] | 30 | 5
4.1.2 | Structural Calculation for Control &Telecommunication Building | [18 empty] | 40 | 8
4.1.3 | Structural Calculation for DE4 Guard House | [18 empty] | 30 | 5
4.1.4 | Structural Calculation for DE4 Substation Building | [18 empty] | 40 | 8
4.1.5 | Structural Calculation for DE4 for Foam Storage Building | [18 empty] | 20 | 5
4.1.6 | Structural Calculation for DE4 for Consumable Storage Building | [18 empty] | 20 | 5
4.1.7 | Structural Calculation Extension For PU4 Switchgear Room | [18 empty] | 30 | 5
4.1.8 | Structural Calculation For Accommodation Building in PU4 | [18 empty] | 30 | 5
4.1.9 | Structural Calculation for Air Compressor Room in PU4 | [18 empty] | 30 | 5
4.1.10 | Structural Calculation for Laboratory | [18 empty] | 30 | 5
4.1.11 | Structural Calculation for Work Shop | [18 empty] | 30 | 5
4.1.12 | Structural Calculation fo3.3 Switch Gear Building Of PU4 Outdoor Substaion | [18 empty] | 30 | 5
4.1.13 | Structural Calculation fo33 KV Switch Gear Building Of 33 KV Station | [18 empty] | 30 | 5
4.1.14 | Structural Calculation fo33 KV Station Guard House | [18 empty] | 30 | 5
4.1.15 | Structural Calculation fo33 KV Station Diesel Generator Building | [18 empty] | 30 | 5
4.2 | Shelters Structural Calculation
4.2.1 | Structural Calculation for DE4 Parking Shelter | [18 empty] | 30 | 5
4.2.2 | Structural Calculation for DE4 Chemical storage shelter no.1 | [18 empty] | 30 | 5
4.2.3 | Structural Calculation for DE4 Chemical storage shelter no.2 | [18 empty] | 30 | 5
4.2.4 | Structural Calculation for DE4 Chemical injection package shelter no.1 | [18 empty] | 30 | 5
4.2.5 | Structural Calculation for DE4 Chemical injection package shelter no.2 | [18 empty] | 30 | 5
4.2.6 | Structural Calculation for DE4 Process Pumps shelter | [18 empty] | 30 | 5
4.2.7 | Structural Calculation for DE4 Dilution Water Pumps shelter | [18 empty] | 30 | 5
4.2.8 | Structural Calculation for DE4 Waste Water Pumps shelter | [18 empty] | 30 | 5
4.2.9 | Structural Calculation for DE4 Dearated Water Pumps shelter | [18 empty] | 30 | 5
4.2.10 | Structural Calculation for DE4 Fire Water Pumps shelter | [18 empty] | 30 | 5
4.2.11 | Structural Calculation for Fire extinguisher shelter | [18 empty] | 30 | 5
4.2.12 | Structural Calculation for pump shelter in PU4 | [18 empty] | 30 | 5
4.2.13 | Structural Calculation for Chemical storage shelter in PU4 | [18 empty] | 30 | 5
4.2.14 | Structural Calculation for Chemical injection package shelter in PU4 | [18 empty] | 30 | 5
4.3 | Others Structural Calculation
4.3.1 | Structural Calculation for Diesel Oil Support Structure | [18 empty] | 20 | 5
4.3.2 | Structural Calculation for Stand Pipes | [18 empty] | 20 | 5
4.3.3 | Structural Calculation for Platforms | [18 empty] | 30 | 5
5 | Structurs Drawings
5.1 | Buildings Structural Drawings
5.1.1 | Structural Drawing for DE4 Air Compressor Room & Emergency Diesel Generator Building | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.2 | Structural Drawing for Control &Telecommunication Building | [16 empty] | 1 |  | 8 | 5 |  |  |  |  | 50
5.1.3 | Structural Drawing for DE4 Guard House | [16 empty] | 1 |  | 3 | 2 |  |  |  |  | 16
5.1.4 | Structural Drawing for DE4 Substation Building | [16 empty] | 1 |  | 8 | 5 |  |  |  |  | 50
5.1.5 | Structural Drawing for DE4 Foam Storage Building | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.6 | Structural Drawing for DE4 Consumable Storage Building | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.7 | Structural Drawing Extension For PU4 Switchgear Room | [16 empty] | 1 |  | 3 | 2 |  |  |  |  | 10
5.1.8 | Structural Drawing For Accommodation Building in PU4 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 20
5.1.9 | Structural Drawing for Air Compressor Room in PU4 | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.10 | Structural Drawing for Laboratory | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.11 | Structural Drawing for Work Shop | [16 empty] | 1 |  | 8 | 4 |  |  |  |  | 40
5.1.12 | Structural Drawing fo3.3 Switch Gear Building Of PU4 Outdoor Substaion | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.13 | Structural Drawing fo33 KV Switch Gear Building Of 33 KV Station | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.1.14 | Structural Drawing fo33 KV Station Guard House | [16 empty] | 1 |  | 3 | 2 |  |  |  |  | 16
5.1.15 | Structural Drawing fo33 KV Station Diesel Generator Building | [16 empty] | 1 |  | 4 | 3 |  |  |  |  | 25
5.2 | Shelters Structural Drawings
5.2.1 | Structural Drawing for DE4 Parking Shelter | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.2 | Structural Drawing for DE4 Chemical storage shelter no.1 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.3 | Structural Drawing for DE4 Chemical storage shelter no.2 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.4 | Structural Drawing for DE4 Chemical injection package shelter no.1 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.5 | Structural Drawing for DE4 Chemical injection package shelter no.2 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.6 | Structural Drawing for DE4 Process Pumps shelter | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.7 | Structural Drawing for DE4 Dilution Water Pumps shelter | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.8 | Structural Drawing for DE4 Waste Water Pumps shelter | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.9 | Structural Drawing for DE4 Dearated Water Pumps shelter | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.10 | Structural Drawing for DE4 Fire Water Pumps shelter | [6 empty] | 4 | [9 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.11 | Structural Drawing for Fire extinguisher shelter | [6 empty] | 4 | [9 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.12 | Structural Drawing for pump shelter in PU4 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.13 | Structural Drawing for Chemical storage shelter in PU4 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.2.14 | Structural Drawing for Chemical injection package shelter in PU4 | [16 empty] | 1 |  | 4 | 2 |  |  |  |  | 25
5.3 | Others Structural Draiwngs
5.3.1 | Structural Drawing for Diesel Oil Support Structure | [16 empty] | 1 |  | 3 | 2 |  |  |  |  | 20
5.3.2 | Structural Drawing for Stand Pipes |  |  | 4 | [7 empty] | 4 | [7 empty] | 3 | 2 |  |  |  |  | 20
5.3.3 | Structural Drawing for Platforms | [8 empty] | 5 | [9 empty] | 3 | 2 |  |  |  |  | 30
6 | Other Structures
6.1 | Calculation
6.1.1 | Structural Calculation for Bridges | [18 empty] | 100 | 10
6.1.2 | Structural Calculation for Tanks Dike wall | [18 empty] | 30 | 5
6.1.3 | Structural Calculation for Transmission Tower | [18 empty] | 40 | 10
6.1.4 | Foundation Calculation for Transmission Tower | [18 empty] | 25 | 5
6.2 | Structural Drawing for Bridges | [24 empty] | 50
6.2.1 | Structural Drawing for Tanks Dike wall | [7 empty] | 2 | [10 empty] | 5 | 2 |  |  |  |  | 20
6.2.2 | Structural Drawing for Transmission Tower | [7 empty] | 2 | [10 empty] | 5 | 2 |  |  |  |  | 40
6.2.3 | Foundation Drawing for Transmission Tower | [18 empty] | 5 | 2 |  |  |  |  | 20
6.2.4 | HC Closed Drain Pit Section And Details | [9 empty] | 5 | [8 empty] | 25 | 5 |  |  |  |  | 16
7 | خدمات مرتبط با اجرا و پس از اجرا
7.1 | انجام مهندسی کارگاهی (معادل 10% نفر ساعت مهندسی تفصیلی) | [18 empty] | 397.3 | 89.5 |  |  |  |  | 340.4
7.2 | تهیه نقشه های عین ساخت (As Built) معادل 5% نفر ساعت مهندسی | [18 empty] | 198.65 | [5 empty] | 170.2
7.3 | سیاهه کالا (Material Take-off) پس از اجرا | [18 empty] | 100
7.4 | صورت مصالح مصرفی (Bill of Material) پس از اجرا | [18 empty] | 120
7.5 | جدول تفکیک نرخ کارهای انجام شده به تفکیک ردیفهای فهرست بها | [18 empty] | 100 | 8
| TOTAL : | 0 | 0 | 26.5 | 12 | 0 | 0 | 8 | 4 | 15 | 15 | 14 | 10 | 13 | 13 | 0 | 0 | 30 | 0 | 4888.95 | 992.5 | 0 | 0 | 0 | 0 | 3914.6
|  | 0 | 0 | 26.5 | 12 | 0 | 0 | 8 | 4 | 15 | 15 | 14 | 10 | 13 | 13 | 0 | 0 | 30 | 0 | 3973 | 895 | 0 | 0 | 0 | 0 | 3404

## E.Project Control
Project Control Document
Item | Title | PR |  | ME |  | HV |  | SF |  | PI |  | IN |  | EL |  | CV |  | AR |  | ST |  | TC |  | PC |  | DRAFT MAN
|  | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr | Jr | Sr
1 | دستورالعمل هماهنگی اجرای پروژه | [22 empty] | 60 | 20
2 | دستورالعمل هماهنگی مهندسی پروژه | [22 empty] | 60 | 20
3 | دستورالعمل هماهنگی خرید پروژه | [22 empty] | 60 | 20
4 | دستورالعمل راه اندازی ، به کار گیری و راهبریسیستم اتوماسیون گردش کار | [22 empty] | 200 | 10
5 | برنامه زمانبندی (Time Schedule) | [22 empty] | 120 | 40
6 | ساختار شکست پروژه (W.B.S & C.B.S) | [22 empty] | 120 | 40
7 | لیست مدارک مهندسی پروژه | [22 empty] | 120 | 40
8 | لیست مدارک مهندسی تامین کنندگان کالا | [22 empty] | 120 | 40
| TOTAL : | [22 empty] | 860 | 230